## Overview
Labour and overhead costs for VNI West project
Overview
About this workbook
This workbook is the supporting model to the 'Labour and Indirect Costs forecast for VNI West' document.
This model substantiates values documented in the report in relation to the ‘Labour cost and Corporate and Network Overhead Capex' for the VNI West project.
Tab colour meanings
Control and reporting sheets
Calculation sheets
Primary input sheets
Secondary input sheets (feed in to primary input sheets). These sheets are ad-hoc, free form calculations
Variance sheets
Cell colour meanings
Fixed cell - should not be changed by user
Input cell - value can be changed by the user
Formulas change at this point - value should not be changed by user
Cell targeted by solver - value should not be changed by user
Assertion/check passes
Assertion/check fails
How to use this workbook
Historical data (actuals) in this workbook range from 2017 to 31 May 2023.
Forecast data in this workbook range from 1 June 2023 to 30 April 2025.
Model structure
Reference to report | Header worksheets | Description of worksheet
| Key assumptions | This tab presents the key assumptions applied to the costs in this model.
| Historical indirect capex | This tab presents the hardcoded values summarising the actual cost data accumulated over the 2017 to 31 May 2023 time period ('cost incurred to date' i.e., 'Actuals') relating to the VNI West project. The historical capex is based on transactions recorded in Ellipse (Transgrid's enterprise resource planning system).
| Data source | This tab presents the forecast FTEs and capex for the VNI West project developed using a bottom-up approach. The tab extracts resource rates from TransGrid's finance system and calculates internal labour costs and non-labour cost. It also presents the outsourced labour cost expected over the course of the project. Note that it does not include labour-related costs i.e., travel expenses, IT costs, recruitment and training.
| Internal_labour_inputs | This tab summarises the inputs used in the calculation tabs relating to the internal labour FTEs and costs. It also includes some calculations pertaining to the external recruitment fee.
| Outsourced_labour_inputs | This tab summarises the inputs used in the calculation tabs relating to the outsourced labour FTEs and costs.
| Non-labour_inputs | This tab summarises the inputs used in the calculation tabs relating to the non-labour quantities and costs.
| Internal_labour_calcs | This tab summarises the internal labour costs and categorises them in accordance with the various cost categories. It also splits up the internal labour costs into direct and indirect costs.
| Outsourced_labour_calcs | This tab summarises the outsourced labour costs and categorises them in accordance with the various cost categories. It also splits up the outsourced labour costs into direct and indirect costs.
| Labour-related_calcs | This tab forecasts the labour-related costs i.e., travel expenses, IT costs, recruitment and training.
| Non-labour_calcs | This tab summarises the non-labour costs and categorises them in accordance with the various cost categories.
| FTE&roles_calcs | This tab summarises the number of FTEs by category and is used in the calculations in other tabs of the workbook.
| VINW Summary Tables | Outputs summary tables for VNI West.
| PEC Summary Tables | Outputs summary tables for PEC Enhancement.
| HL Summary Tables | Outputs summary tables for Humelink Interface.

## Data source
CONFIDENTIAL
[CONFIDENTIAL]

## Key assumptions
Labour and overhead costs for VNI West project
Key assumptions
Notes
This tab presents the key assumptions applied in this model. Outputs in this model will be presented in FY23 prices.
General
VNI West cost allocation model period
| Model period |  |  |  | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026
Inflaiton
Rates
| 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
Actual / Forecast Inflation | 1.934% | 2.078% | 1.593% | -0.3484% | 3.846% | 6.145% | 6.7% | 2.919% | 2.919% | 2.919%
Inflation based to 2023 | 0.82275 | 0.83984 | 0.85322 | 0.85025 | 0.88295 | 0.93721 | 1 | 1.0292 | 1.0592 | 1.0902
Real 2023 to Mid Period | 0.81491 | 0.83125 | 0.84651 | 0.85173 | 0.86645 | 0.90967 | 0.96809 | 1.0145 | 1.0441 | 1.0746
Nominal Deflator to $2023 | 1.2271 | 1.203 | 1.1813 | 1.1741 | 1.1541 | 1.0993 | 1.033 | 0.98572 | 0.95776 | 0.93059
Labour cost assumption
Base salary
| Average total hours worked per month |  |  | hours | 157
Labour - related cost assumptions
Apportioning cost |  |  |  |  | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026
[6 empty] | 100% | 100% | 100% | 100%
Recruitment fees assumptions
| Recruitment fees as % of annual salary |  |  | % | 15%
| Roles recruited using external recruiter |  |  | % | 50%
% of number of FTEs considered as 'new'
[5 empty] | Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026
[5 empty] | VNIW - Project Management |  | 0% | 60.3% | 4.261%
[5 empty] | VNIW - Project Development |  | 0% | 136.8% | 0%
[5 empty] | VNIW - Land and Environment |  | 0% | 12.62% | 0%
[5 empty] | PEC - Project Management |  | 0% | 22% | 0%
[5 empty] | PEC - Project Development |  | 0% | 73% | 29%
[5 empty] | PEC - Land and Environment |  | 0% | 0% | 0%
Training cost assumptions
| Training cost per annum per staff |  |  | $Real, 2022-23 | 1750
[5 empty] | Broader cost category | Total annualised training cost
| Total training cost across all internal staff in one year |  |  | $Real, 2022-23 | VNIW - Project Management | 66500
|  |  |  | $Real, 2022-23 | VNIW - Project Development | 15750
|  |  |  | $Real, 2022-23 | VNIW - Land and Environment | 29750
|  |  |  | $Real, 2022-23 | PEC - Project Management | 22750
|  |  |  | $Real, 2022-23 | PEC - Project Development | 33250
|  |  |  | $Real, 2022-23 | PEC - Land and Environment | 10500
[5 empty] | Broader cost category | Total monthly training cost
| Total adj. training cost per month |  |  | $Real, 2022-23 | VNIW - Project Management | 5541.6667
|  |  |  | $Real, 2022-23 | VNIW - Land and Environment | 1312.5
|  |  |  | $Real, 2022-23 | VNIW - Project Development | 2479.1667
|  |  |  | $Real, 2022-23 | PEC - Project Management | 1895.8333
|  |  |  | $Real, 2022-23 | PEC - Land and Environment | 2770.8333
|  |  |  | $Real, 2022-23 | PEC - Project Development | 875
| Split of training cost across months in which internal labour spent on the project |  |  |  | Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026
[5 empty] | VNIW - Project Management |  | 2.657% | 52.17% | 45.17%
[5 empty] | VNIW - Project Development |  | 2.459% | 64.75% | 32.79%
[5 empty] | VNIW - Transaction Procurement Support |  | 3.797% | 45.57% | 50.63%
[5 empty] | VNIW - Community and Stakeholder Engagement |  | 4.442% | 52.17% | 43.39%
[5 empty] | VNIW - Land and Environment |  | 3.542% | 50.41% | 46.05%
[5 empty] | VNIW - Regulatory Approvals |  | 9.091% | 45.45% | 45.45%
[5 empty] | VNIW - Other Support & Corporate Roles |  | 4.294% | 51.53% | 44.17%
[5 empty] | PEC - Project Management |  | 4.498% | 53.98% | 41.52%
[5 empty] | PEC - Project Development |  | 5.405% | 52.03% | 42.57%
[5 empty] | PEC - Community and Stakeholder Engagement |  | 4.348% | 52.17% | 43.48%
[5 empty] | PEC - Land and Environment |  | 14.29% | 85.71% | 0%
[5 empty] | PEC - Regulatory Approvals |  | 5.263% | 63.16% | 31.58%
IT hardware cost assumptions
| IT hardware cost per annum per employee |  |  | $Real, 2022-23 | 3337
Number of FTEs considered as 'new'
[5 empty] | Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026
[5 empty] | VNIW - Project Management |  | 0 | 16 | 1
[5 empty] | VNIW - Project Development |  | 0 | 6 | 0
[5 empty] | VNIW - Land and Environment |  | 0 | 1 | 0
[5 empty] | PEC - Project Management |  | 0 | 1 | 0
[5 empty] | PEC - Project Development |  | 0 | 3 | 1
[5 empty] | PEC - Land and Environment |  | 0 | 0 | 0
Travel expenses assumptions
Number of trips taken in each year of the modelling period
|  |  |  | Number of Nights per trip | Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026
|  |  |  | 1 | VNIW - Project Management |  | 2 | 24 | 20
|  |  |  | 1 | VNIW - Project Development |  | 2 | 36 | 20
|  |  |  | 2 | VNIW - Community and Stakeholder Engagement |  | 8 | 96 | 80
|  |  |  | 1 | VNIW - Land and Environment |  | 4 | 48 | 40
|  |  |  | 1 | PEC - Project Management |  | 2 | 46 | 34
|  |  |  | 1 | PEC - Project Development |  | 4 | 128 | 88
|  |  |  | 2 | PEC - Community and Stakeholder Engagement |  | 2 | 44 | 32
|  |  |  | 1 | PEC - Land and Environment |  | 2 | 44 | 32
| Number of nights assumed per trip throughout modelling period |  |  | $Real, 2022-23 | 1 | 2
| Cost per trip per staff |  |  | $Real, 2022-23 | 1357.55 | 2305.1
| Cost per return flight to sites |  |  | $Real, 2022-23 | 410 | 410
| ATO rates for Accom & Meals |  |  | $Real, 2022-23 | 327.55 | 327.55
| Car hire per day at site |  |  | $Real, 2022-23 | 95 | 95
| Travel time allowance (assume 3 hours of additional travel time) |  |  | $Real, 2022-23 | 525 | 525
| Number of staff per trip |  |  | $Real, 2022-23 | 1
Direct cost assumptions
| Share of internal labour costs that are direct |  |  | % | 70%
| Share of contracted labour costs that are direct |  |  | % | 70%
| Share of labour-related costs that are direct |  |  | % | 70%
| Share of non-labour costs that are direct |  |  | % | 0%
Broader Cost Categories
Broader Cost Category
VNIW - Project Management
VNIW - Project Development
VNIW - Transaction Procurement Support
VNIW - Community and Stakeholder Engagement
VNIW - Land and Environment
VNIW - Regulatory Approvals
VNIW - Other Support & Corporate Roles
PEC - Project Management
PEC - Project Development
PEC - Transaction Procurement Support
PEC - Community and Stakeholder Engagement
PEC - Land and Environment
PEC - Regulatory Approvals
PEC - Other Support & Corporate Roles

## Historical indirect capex
Labour and overhead costs for VNI West project
Historical data (2017 - 31/5/2023)
Source: VNI West - Labour and Indrect Cost Input (19 Jun 2023)
|  |  | Historical ($Nominal) | [5 empty] | FY2023 (01 July 2022 - 31 May 2023) |  | Historical ($ Real 2022-2023) | [5 empty] | FY2023 (01 July 2022 - 31 May 2023)
|  |  | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | TOTAL | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | TOTAL
Labour (internal and outsourced, direct)
|  | VNIW - Land and Environment | [5 empty] | 36263 | 448710 | 484973 | 0 | 0 | 0 | 0 | 0 | 39863.6877 | 463498.0999 | 503361.7876
|  | VNIW - Project Management | [5 empty] | 1147842 | 2603020 | 3750862 | 0 | 0 | 0 | 0 | 0 | 1261815.4889 | 2688807.5237 | 3950623.0126
|  | VNIW - Project Development |  | 2287 |  | 123793 | 180 | 279582 | -77937 | 327905 | 0 | 2751.2664 | 0 | 145342.1691 | 207.7451 | 307342.7336 | -80505.5635 | 375138.3507
|  | VNIW - Community and Stakeholder Engagement | [5 empty] | 151875 | 951314 | 1103189 | 0 | 0 | 0 | 0 | 0 | 166955.232 | 982666.38 | 1149621.612
|  | VNIW - Other Support & Corporate Roles | [5 empty] | 172495 | 363463 | 535958 | 0 | 0 | 0 | 0 | 0 | 189622.6682 | 375441.6213 | 565064.2895
|  | VNIW - Regulatory Approvals | [6 empty] | 29746 | 29746 | 0 | 0 | 0 | 0 | 0 | 0 | 30726.3366 | 30726.3366
|  | PEC - Land and Environment | [5 empty] | 6066 |  | 6066 | 0 | 0 | 0 | 0 | 0 | 6668.3156 | 0 | 6668.3156
Labour related (direct)
|  | VNIW - Land and Environment | [5 empty] | 13 | 6890 | 6903 | 0 | 0 | 0 | 0 | 0 | 14.2908 | 7117.0732 | 7131.364
|  | VNIW - Project Development | [6 empty] | 2807 | 2807 | 0 | 0 | 0 | 0 | 0 | 0 | 2899.5101 | 2899.5101
|  | VNIW - Project Management | [5 empty] | 9966 | 49584 | 59550 | 0 | 0 | 0 | 0 | 0 | 10955.5611 | 51218.136 | 62173.6971
|  | VNIW - Other Support & Corporate Roles |  |  |  | 339 |  |  | 2260 | 2599 | 0 | 0 | 0 | 398.0112 | 0 | 0 | 2334.4826 | 2732.4938
|  | VNIW - Community and Stakeholder Engagement | [5 empty] | 4549 | 13205 | 17754 | 0 | 0 | 0 | 0 | 0 | 5000.6871 | 13640.1961 | 18640.8832
Indirect
|  | VNIW - Land and Environment | [6 empty] | 391400.09 | 391400.09 | 0 | 0 | 0 | 0 | 0 | 0 | 404299.4317 | 404299.4317
|  | VNIW - Project Development | [5 empty] | 1713958 | 1567111 | 3281069 | 0 | 0 | 0 | 0 | 0 | 1884143.2459 | 1618758.1529 | 3502901.3989
|  | VNIW - Project Management | [5 empty] | 585175 | 319711 | 904886 | 0 | 0 | 0 | 0 | 0 | 643279.1958 | 330247.6901 | 973526.8859
|  | VNIW - Other Support & Corporate Roles | [5 empty] | 1485331 | 3188339 | 4673670 | 0 | 0 | 0 | 0 | 0 | 1632815.0232 | 3293416.8356 | 4926231.8588
|  | VNIW - Community and Stakeholder Engagement | [5 empty] | 212796 | 511441 | 724237 | 0 | 0 | 0 | 0 | 0 | 233925.304 | 528296.5205 | 762221.8245
|  | PEC - Land and Environment | [5 empty] | 176625 |  | 176625 | 0 | 0 | 0 | 0 | 0 | 194162.7513 | 0 | 194162.7513
|  | Total | 0 | 2287 | 0 | 124132 | 180 | 5982536 | 10371064.09 | 16480199.09 | 0 | 2751.2664 | 0 | 145740.1803 | 207.7451 | 6576564.1853 | 10712862.4267 | 17438125.8037
|  | Total VNIW | 0 | 2287 | 0 | 124132 | 180 | 5799845 | 10371064.09 | 16297508.09 | 0 | 2751.2664 | 0 | 145740.1803 | 207.7451 | 6375733.1184 | 10712862.4267 | 17237294.7368
|  | Total PEC | 0 | 0 | 0 | 0 | 0 | 182691 | 0 | 182691 | 0 | 0 | 0 | 0 | 0 | 200831.0669 | 0 | 200831.0669
|  | Total HL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK

## Outsourced labour inputs
CONFIDENTIAL
[CONFIDENTIAL]

## Internal labour inputs
CONFIDENTIAL
[CONFIDENTIAL]

## Non-labour_inputs
CONFIDENTIAL
[CONFIDENTIAL]

## Internal_labour_calcs
Labour and overhead costs for VNI West project
Internal labour cost calculations
Notes
This tab calculates the forecast internal labour capex and categorises the costs by cost category.
Total direct and indirect costs | [6 empty] | Labour costs - Direct costs only | [6 empty] | Labour costs - Indirect costs only
| Real, $FY2023 | [6 empty] | Real, $FY2023 | [6 empty] | Real, $FY2023 | 0 | 0 | 0 | 0
| Historical | Forecast | [5 empty] | Historical | Forecast | [5 empty] | Historical | Forecast
Capex category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex | Capex category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex | Capex category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex
VNIW - Project Management |  | 439226.985 | 9644989.6103 | 8695221.945 | 0 | 18779438.5403 | VNIW - Project Management |  | 307458.8895 | 6751492.7272 | 6086655.3615 | 0 | 13145606.9782 | VNIW - Project Management |  | 131768.0955 | 2893496.8831 | 2608566.5835 | 0 | 5633831.5621
VNIW - Project Development |  | 62909.2328 | 2066187.0013 | 1319261.58 | 0 | 3448357.8141 | VNIW - Project Development |  | 44036.4629 | 1446330.9009 | 923483.106 | 0 | 2413850.4698 | VNIW - Project Development |  | 18872.7698 | 619856.1004 | 395778.474 | 0 | 1034507.3442
VNIW - Transaction Procurement Support |  | 13530.9116 | 162370.9386 | 466869.5655 | 0 | 642771.4156 | VNIW - Transaction Procurement Support |  | 9471.6381 | 113659.657 | 326808.6958 | 0 | 449939.991 | VNIW - Transaction Procurement Support |  | 4059.2735 | 48711.2816 | 140060.8697 | 0 | 192831.4247
VNIW - Community and Stakeholder Engagement |  | 271192.6786 | 3188063.9838 | 2786116.9791 | 0 | 6245373.6415 | VNIW - Community and Stakeholder Engagement |  | 189834.875 | 2231644.7886 | 1950281.8854 | 0 | 4371761.5491 | VNIW - Community and Stakeholder Engagement |  | 81357.8036 | 956419.1951 | 835835.0937 | 0 | 1873612.0925
VNIW - Land and Environment |  | 212706.4984 | 3804609.9446 | 3640469.1611 | 0 | 7657785.6042 | VNIW - Land and Environment |  | 148894.5489 | 2663226.9612 | 2548328.4128 | 0 | 5360449.9229 | VNIW - Land and Environment |  | 63811.9495 | 1141382.9834 | 1092140.7483 | 0 | 2297335.6812
VNIW - Regulatory Approvals |  | 110187.4984 | 220374.9968 | 550937.492 | 0 | 881499.9872 | VNIW - Regulatory Approvals |  | 77131.2489 | 154262.4978 | 385656.2444 | 0 | 617049.991 | VNIW - Regulatory Approvals |  | 33056.2495 | 66112.499 | 165281.2476 | 0 | 264449.9962
VNIW - Other Support & Corporate Roles |  | 33248.9062 | 398986.8742 | 428489.0618 | 0 | 860724.8422 | VNIW - Other Support & Corporate Roles |  | 23274.2343 | 279290.8119 | 299942.3433 | 0 | 602507.3895 | VNIW - Other Support & Corporate Roles |  | 9974.6719 | 119696.0623 | 128546.7185 | 0 | 258217.4527
PEC - Project Management |  | 144548 | 1700086 | 1135826 | 0 | 2980460 | PEC - Project Management |  | 101183.6 | 1190060.2 | 795078.2 | 0 | 2086322 | PEC - Project Management |  | 43364.4 | 510025.8 | 340747.8 | 0 | 894138
PEC - Project Development |  | 154811 | 1665047 | 1356154 | 0 | 3176012 | PEC - Project Development |  | 108367.7 | 1165532.9 | 949307.8 | 0 | 2223208.4 | PEC - Project Development |  | 46443.3 | 499514.1 | 406846.2 | 0 | 952803.6
PEC - Community and Stakeholder Engagement |  | 21694 | 260328 | 216940 | 0 | 498962 | PEC - Community and Stakeholder Engagement |  | 15185.8 | 182229.6 | 151858 | 0 | 349273.4 | PEC - Community and Stakeholder Engagement |  | 6508.2 | 78098.4 | 65082 | 0 | 149688.6
PEC - Land and Environment |  | 16148 | 96888 | 0 | 0 | 113036 | PEC - Land and Environment |  | 11303.6 | 67821.6 | 0 | 0 | 79125.2 | PEC - Land and Environment |  | 4844.4 | 29066.4 | 0 | 0 | 33910.8
PEC - Regulatory Approvals |  | 16606 | 199272 | 99636 | 0 | 315514 | PEC - Regulatory Approvals |  | 11624.2 | 139490.4 | 69745.2 | 0 | 220859.8 | PEC - Regulatory Approvals |  | 4981.8 | 59781.6 | 29890.8 | 0 | 94654.2
HL Gugaa - Project Management |  | 0 | 305030.8098 | 254192.3415 | 0 | 559223.1513 | HL Gugaa - Project Management |  | 0 | 213521.5669 | 177934.639 | 0 | 391456.2059 | HL Gugaa - Project Management |  | 0 | 91509.2429 | 76257.7025 | 0 | 167766.9454
HL Gugaa - Project Development |  | 65683.8702 | 440995.3218 | 367496.1015 | 0 | 874175.2935 | HL Gugaa - Project Development |  | 45978.7091 | 308696.7253 | 257247.2711 | 0 | 611922.7055 | HL Gugaa - Project Development |  | 19705.1611 | 132298.5965 | 110248.8305 | 0 | 262252.5881
HL Gugaa - Community & Stakeholder Engagement |  | 0 | 36855.5616 | 30712.968 | 0 | 67568.5296 | HL Gugaa - Community & Stakeholder Engagement |  | 0 | 25798.8931 | 21499.0776 | 0 | 47297.9707 | HL Gugaa - Community & Stakeholder Engagement |  | 0 | 11056.6685 | 9213.8904 | 0 | 20270.5589
HL Gugaa - Land & Environment |  | 0 | 37004.115 | 30836.7625 | 0 | 67840.8775 | HL Gugaa - Land & Environment |  | 0 | 25902.8805 | 21585.7338 | 0 | 47488.6142 | HL Gugaa - Land & Environment |  | 0 | 11101.2345 | 9251.0288 | 0 | 20352.2633
HL Gugaa - Other Support & Corporate Roles |  | 0 | 104284.4868 | 86903.739 | 0 | 191188.2258 | HL Gugaa - Other Support & Corporate Roles |  | 0 | 72999.1408 | 60832.6173 | 0 | 133831.7581 | HL Gugaa - Other Support & Corporate Roles |  | 0 | 31285.346 | 26071.1217 | 0 | 57356.4677
HL Wagga - Project Development |  | 65683.8702 | 136121.9767 | 113434.9806 | 0 | 315240.8275 | HL Wagga - Project Development |  | 45978.7091 | 95285.3837 | 79404.4864 | 0 | 220668.5793 | HL Wagga - Project Development |  | 19705.1611 | 40836.593 | 34030.4942 | 0 | 94572.2483
0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total |  | 1628177.4513 | 24467496.6213 | 21579498.6777 | 0 | 47675172.7503 | Total |  | 1139724.2159 | 17127247.6349 | 15105649.0744 | 0 | 33372620.9252 | Total |  | 488453.2354 | 7340248.9864 | 6473849.6033 | 0 | 14302551.8251
|  | OK | OK | OK | OK | OK | [9 empty] | OK | OK | OK | OK | OK
Total VNIW |  | 1143002.7109 | 19485583.3496 | 17887365.7846 | 0 | 38515951.8451 | Total VNIW |  | 800101.8977 | 13639908.3447 | 12521156.0492 | 0 | 26961166.2916 | Total VNIW | 0 | 342900.8133 | 5845675.0049 | 5366209.7354 | 0 | 11554785.5535
Total PEC |  | 353807 | 3921621 | 2808556 | 0 | 7083984 | Total PEC |  | 247664.9 | 2745134.7 | 1965989.2 | 0 | 4958788.8 | Total PEC |  | 106142.1 | 1176486.3 | 842566.8 | 0 | 2125195.2
Total HL |  | 131367.7404 | 1060292.2717 | 883576.8931 | 0 | 2075236.9052 | Total HL |  | 91957.4183 | 742204.5902 | 618503.8252 | 0 | 1452665.8337 | Total HL |  | 39410.3221 | 318087.6815 | 265073.0679 | 0 | 622571.0716
|  | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK

## Outsourced_labour_calcs
Labour and overhead costs for VNI West project
Outsourced labour cost calculations
Notes
This tab calculates the forecast outsourced labour capex and categorises the costs by cost category.
| Total direct and indirect costs | [7 empty] | Labour-related costs - Direct costs only | [6 empty] | Labour-related costs - Indirect costs only
|  | Real, $FY2023 | [7 empty] | Real, $FY2023 | [6 empty] | Real, $FY2023
|  | Historical | Forecast | [6 empty] | Historical | Forecast | [5 empty] | Historical | Forecast
| Capex category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex |  | Capex category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex | Capex category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex
| VNIW - Project Management |  | 35688.75 | 519727.5 | 401550 | 0 | 956966.25 |  | VNIW - Project Management |  | 24982.125 | 363809.25 | 281085 | 0 | 669876.375 | VNIW - Project Management |  | 10706.625 | 155918.25 | 120465 | 0 | 287089.875
| VNIW - Project Development |  | 28910.4 | 716141.6 | 20000 | 0 | 765052 |  | VNIW - Project Development |  | 20237.28 | 501299.12 | 14000 | 0 | 535536.4 | VNIW - Project Development |  | 8673.12 | 214842.48 | 6000 | 0 | 229515.6
| VNIW - Community and Stakeholder Engagement |  | 70420 | 2275220 | 1827020 | 0 | 4172660 |  | VNIW - Community and Stakeholder Engagement |  | 49294 | 1592654 | 1278914 | 0 | 2920862 | VNIW - Community and Stakeholder Engagement |  | 21126 | 682566 | 548106 | 0 | 1251798
| VNIW - Other Support & Corporate Roles |  | 0 | 35000 | 35000 | 0 | 70000 |  | VNIW - Other Support & Corporate Roles |  | 0 | 24500 | 24500 | 0 | 49000 | VNIW - Other Support & Corporate Roles |  | 0 | 10500 | 10500 | 0 | 21000
| 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Total |  | 135019.15 | 3546089.1 | 2283570 | 0 | 5964678.25 |  | Total |  | 94513.405 | 2482262.37 | 1598499 | 0 | 4175274.775 | Total |  | 40505.745 | 1063826.73 | 685071 | 0 | 1789403.475
|  |  | OK | OK | OK | OK | OK | [10 empty] | OK | OK | OK | OK | OK
| Total VNIW | 0 | 135019.15 | 3546089.1 | 2283570 | 0 | 5964678.25 |  | Total VNIW | 0 | 94513.405 | 2482262.37 | 1598499 | 0 | 4175274.775 | Total VNIW | 0 | 40505.745 | 1063826.73 | 685071 | 0 | 1789403.475
| Total PEC |  | 0 | 0 | 0 | 0 | 0 |  | Total PEC |  | 0 | 0 | 0 | 0 | 0 | Total PEC |  | 0 | 0 | 0 | 0 | 0
| Total HL |  | 0 | 0 | 0 | 0 | 0 |  | Total HL |  | 0 | 0 | 0 | 0 | 0 | Total HL |  | 0 | 0 | 0 | 0 | 0
|  |  | OK | OK | OK | OK | OK |  |  |  | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK
1 | VNIW - Project Management
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Project Management | Integration Manager |  |  | Integration Manager | 15600 | 468000 | 390000 | 0 | 873600
| VNIW - Project Management | Quality Assurance Consultant |  |  | Quality Assurance Consultant | 4620 | 20790 | 11550 | 0 | 36960
| VNIW - Project Management | Consultant Engineer - Sub |  |  | Consultant Engineer - Sub | 0 | 0 | 0 | 0 | 0
| VNIW - Project Management | Consultant Engineer - TL |  |  | Consultant Engineer - TL | 0 | 0 | 0 | 0 | 0
| VNIW - Project Management | Senior Program Scheduler |  |  | Senior Program Scheduler | 15468.75 | 30937.5 | 0 | 0 | 46406.25
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
956966.25
2 | VNIW - Project Development
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Project Development | Senior Engineer Consultant Support |  |  | Senior Engineer Consultant Support | 28910.4 | 115641.6 | 0 | 0 | 144552
| VNIW - Project Development | Foundation Selection (Design Delivery Team) |  |  | Foundation Selection (Design Delivery Team) | 0 | 52500 | 0 | 0 | 52500
| VNIW - Project Development | Primary Engineer |  |  | Primary Engineer |  | 90000 | 0 | 0 | 90000
| VNIW - Project Development | Equipment Engineering |  |  | Equipment Engineering | 0 | 180000 | 0 | 0 | 180000
| VNIW - Project Development | Secondary Engineer |  |  | Secondary Engineer | 0 | 60000 | 0 | 0 | 60000
| VNIW - Project Development | Structural Engineer - Combine with Civil |  |  | Structural Engineer - Combine with Civil | 0 | 63000 | 0 | 0 | 63000
| VNIW - Project Development | Civil Engineer |  |  | Civil Engineer | 0 | 75000 | 0 | 0 | 75000
| VNIW - Project Development | Preparation of tender documents and responding to queries (Subs - Civil/Structural) |  |  | Preparation of tender documents and responding to queries (Subs - Civil/Structural) | 0 | 10000 | 20000 | 0 | 30000
| VNIW - Project Development | GIS Team (Internal) for Access Tracks |  |  | GIS Team (Internal) for Access Tracks | 0 | 70000 | 0 | 0 | 70000
765052
3 | VNIW - Community and Stakeholder Engagement
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Community and Stakeholder Engagement | Place Manager 1 |  |  | Place Manager 1 | 0 | 462720 | 385600 | 0 | 848320
| VNIW - Community and Stakeholder Engagement | Place Manager 2 |  |  | Place Manager 2 | 0 | 462720 | 385600 | 0 | 848320
| VNIW - Community and Stakeholder Engagement | Place Manager 3 |  |  | Place Manager 3 | 0 | 462720 | 385600 | 0 | 848320
| VNIW - Community and Stakeholder Engagement | Place Manager 4 |  |  | Place Manager 4 | 0 | 462720 | 385600 | 0 | 848320
| VNIW - Community and Stakeholder Engagement | RRG / CCG C&S Relations Advisor |  |  | RRG / CCG C&S Relations Advisor | 28350 | 340200 | 242550 | 0 | 611100
| VNIW - Community and Stakeholder Engagement | Independent Chair |  |  | Independent Chair | 42070 | 84140 | 42070 | 0 | 168280
| VNIW - Community and Stakeholder Engagement | Technical Writer |  |  | Technical Writer | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
4172660
4 | VNIW - Other Support & Corporate Roles
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Other Support & Corporate Roles | Audit (Internal) |  |  | Audit (Internal) | 0 | 35000 | 35000 | 0 | 70000
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
70000

## Non-labour_calcs
Labour and overhead costs for VNI West project
Non-labour cost calculations
Notes
This tab calculates the forecast non-labour capex and categorises the costs by cost category.
| Total direct and indirect costs | [8 empty] | Non-labour costs - Direct costs only | [6 empty] | Non-labour costs - Indirect costs only
|  | Real, $FY2023 | [7 empty] | Real, $FY2023 | [6 empty] | Real, $FY2023
|  | Historical | Forecast | [6 empty] | Historical | Forecast | [5 empty] | Historical | Forecast
| Capex category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex |  | Capex category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex | Capex category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex
| VNIW - Project Management |  | 58620.8333 | 174510 | 125208.3333 | 0 | 358339.1667 |  | VNIW - Project Management |  | 0 | 0 | 0 | 0 | 0 | VNIW - Project Management |  | 58620.8333 | 174510 | 125208.3333 | 0 | 358339.1667
| VNIW - Project Development |  | 64592 | 9012262.0162 | 24827960.2039 | 0 | 33904814.2201 |  | VNIW - Project Development |  | 0 | 0 | 0 | 0 | 0 | VNIW - Project Development |  | 64592 | 9012262.0162 | 24827960.2039 | 0 | 33904814.2201
| VNIW - Transaction Procurement Support |  | 37556 | 1947494 | 20706033 | 0 | 22691083 |  | VNIW - Transaction Procurement Support |  | 0 | 0 | 0 | 0 | 0 | VNIW - Transaction Procurement Support |  | 37556 | 1947494 | 20706033 | 0 | 22691083
| VNIW - Regulatory Approvals |  | 209872 | 397866 | 5846319.6195 | 0 | 6454057.6195 |  | VNIW - Regulatory Approvals |  | 0 | 0 | 0 | 0 | 0 | VNIW - Regulatory Approvals |  | 209872 | 397866 | 5846319.6195 | 0 | 6454057.6195
| VNIW - Community and Stakeholder Engagement |  | 128639.2164 | 4634363.4357 | 1101100.964 | 0 | 5864103.6161 |  | VNIW - Community and Stakeholder Engagement |  | 0 | 0 | 0 | 0 | 0 | VNIW - Community and Stakeholder Engagement |  | 128639.2164 | 4634363.4357 | 1101100.964 | 0 | 5864103.6161
| VNIW - Land and Environment |  | 115521.7391 | 7992596.6696 | 9077483.3718 | 0 | 17185601.7805 |  | VNIW - Land and Environment |  | 0 | 0 | 0 | 0 | 0 | VNIW - Land and Environment |  | 115521.7391 | 7992596.6696 | 9077483.3718 | 0 | 17185601.7805
| VNIW - Other Support & Corporate Roles |  | 2848818.66 | 19164903.4294 | 13990279.4436 | 0 | 36004001.533 |  | VNIW - Other Support & Corporate Roles |  | 0 | 0 | 0 | 0 | 0 | VNIW - Other Support & Corporate Roles |  | 2848818.66 | 19164903.4294 | 13990279.4436 | 0 | 36004001.533
| PEC - Project Management |  | 0 | 880000 | 480000 | 0 | 1360000 |  | PEC - Project Management |  | 0 | 0 | 0 | 0 | 0 | PEC - Project Management |  | 0 | 880000 | 480000 | 0 | 1360000
| HL Gugaa - Project Management |  | 0 | 2300250 | 1916875 | 0 | 4217125 |  | HL Gugaa - Project Management |  | 0 | 0 | 0 | 0 | 0 | HL Gugaa - Project Management |  | 0 | 2300250 | 1916875 | 0 | 4217125
| 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
| Total | 0 | 3463620.4489 | 46504245.551 | 78071259.9361 | 0 | 128039125.9359 |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | Total | 0 | 3463620.4489 | 46504245.551 | 78071259.9361 | 0 | 128039125.9359
| Check |  | OK | OK | OK | OK | OK | [10 empty] | OK | OK | OK | OK | OK
| Total VNIW | 0 | 3463620.4489 | 43323995.551 | 75674384.9361 | 0 | 122462000.9359 |  | Total VNIW | 0 | 0 | 0 | 0 | 0 | 0 | Total VNIW | 0 | 3463620.4489 | 43323995.551 | 75674384.9361 | 0 | 122462000.9359
| Total PEC |  | 0 | 880000 | 480000 | 0 | 1360000 |  | Total PEC |  | 0 | 0 | 0 | 0 | 0 | Total PEC |  | 0 | 880000 | 480000 | 0 | 1360000
| Total HL |  | 0 | 2300250 | 1916875 | 0 | 4217125 |  | Total HL |  | 0 | 0 | 0 | 0 | 0 | Total PEC |  | 0 | 2300250 | 1916875 | 0 | 4217125
|  |  | OK | OK | OK | OK | OK |  |  |  | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK
1 | VNIW - Project Management
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Project Management | Risk Worksop |  |  | Risk Worksop | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Management | Team Development - Accelerated Alignment Program |  |  | Team Development - Accelerated Alignment Program | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Management | c-i-c |  |  | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Management | c-i-c |  |  | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Management | Corporate Site Visits |  |  | Corporate Site Visits | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
[5 empty] | 0 | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
[6 empty] | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
358339.1667
2 | VNIW - Project Development
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Project Development | Planning and Scheduling Support (Specialist Consultant) |  |  | Planning and Scheduling Support (Specialist Consultant) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Planning and Scheduling Support (Consultant) |  |  | Planning and Scheduling Support (Consultant) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | QSRA |  |  | QSRA | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Flood Studies |  |  | Flood Studies | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | LIDAR Flyover |  |  | LIDAR Flyover | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Design Software - PLS-CADD |  |  | Design Software - PLS-CADD | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | PSCAD Modelling |  |  | PSCAD Modelling | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | TL - Conductor & Structure Selection |  |  | TL - Conductor & Structure Selection | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | TL - Concept Design |  |  | TL - Concept Design | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | TL - Route Selection - Technical Support |  |  | TL - Route Selection - Technical Support | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | TL - Risk Assesment Report |  |  | TL - Risk Assesment Report | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Owners Engineer |  |  | Owners Engineer | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Aviation Impact Studies |  |  | Aviation Impact Studies | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Transportation Studies |  |  | Transportation Studies | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Third Party Interfaces (Dial Before You Dig) |  |  | Third Party Interfaces (Dial Before You Dig) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Desktop Geotech Studies |  |  | Desktop Geotech Studies | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Pre-tender site geotech investigation (Substation) |  |  | Pre-tender site geotech investigation (Substation) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Pre-tender site geotech investigation (TL) |  |  | Pre-tender site geotech investigation (TL) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | Access Vegetation Clearing & Repair (Geotech Investigation) |  |  | Access Vegetation Clearing & Repair (Geotech Investigation) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | External Legal Support (Property) |  |  | External Legal Support (Property) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | External Legal Support (Enviro) |  |  | External Legal Support (Enviro) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | External Legal General |  |  | External Legal General | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | External Legal Major Contract Transaction Support |  |  | External Legal Major Contract Transaction Support | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | External Legal Defending Contract Claims |  |  | External Legal Defending Contract Claims | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Project Development | External Legal Interface Agreements |  |  | External Legal Interface Agreements | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
33904814.2201
3 | VNIW - Transaction Procurement Support
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Transaction Procurement Support | Room Hire, Catering & Other |  |  | Room Hire, Catering & Other | 3556 | 42672 | 35560 | 0 | 81788
| VNIW - Transaction Procurement Support | Transaction Team |  |  | Transaction Team | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Transaction Procurement Support | Procurement Phase Commercial Advice |  |  | Procurement Phase Commercial Advice | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Transaction Procurement Support | Data Room |  |  | Data Room | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Transaction Procurement Support | Probity Advisor |  |  | Probity Advisor | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Transaction Procurement Support | Class 3 Detail Cost Estimate |  |  | Class 3 Detail Cost Estimate | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Transaction Procurement Support | Procurement Strategy |  |  | Procurement Strategy | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Transaction Procurement Support | Contractor Bidder Payments |  |  | Contractor Bidder Payments | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
22691083
4 | VNIW - Regulatory Approvals
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Regulatory Approvals | Market Modelling - PACR |  |  | Market Modelling - PACR | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Regulatory Approvals | CPA1 Economic Modelling |  |  | CPA1 Economic Modelling | 30384.5 | 91153.5 | 0 | 0 | 121538
| VNIW - Regulatory Approvals | CPA1 Scope Definition Document |  |  | CPA1 Scope Definition Document | 21487.5 | 64462.5 | 0 | 0 | 85950
| VNIW - Regulatory Approvals | CPA1 Capex Forecasting Methodology |  |  | CPA1 Capex Forecasting Methodology | 51750 | 103500 | 0 | 0 | 155250
| VNIW - Regulatory Approvals | CPA1 Labour & Indirect Costs |  |  | CPA1 Labour & Indirect Costs | 25000 | 75000 | 0 | 0 | 100000
| VNIW - Regulatory Approvals | CPA1 Independent Engineering Assessment of Capex |  |  | CPA1 Independent Engineering Assessment of Capex | 21250 | 63750 | 0 | 0 | 85000
| VNIW - Regulatory Approvals | CPA1 Technical Memo (LLE Items) |  |  | CPA1 Technical Memo (LLE Items) | 10000 | 0 | 0 | 0 | 10000
| VNIW - Regulatory Approvals | CPA2 - Submission |  |  | CPA2 - Submission | 0 | 0 | 4167437.6106 | 0 | 4167437.6106
| VNIW - Regulatory Approvals | CPA2 - CPA Market Modelling |  |  | CPA2 - CPA Market Modelling | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Regulatory Approvals | CPA2 - Meetings & Corp Expenses |  |  | CPA2 - Meetings & Corp Expenses | 0 | 0 | 333395.0088 | 0 | 333395.0088
| VNIW - Regulatory Approvals | CPA2 - Board Approval Meetings |  |  | CPA2 - Board Approval Meetings | 0 | 0 | 23813.9292 | 0 | 23813.9292
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
6454057.6195
5 | VNIW - Community and Stakeholder Engagement
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Community and Stakeholder Engagement | Community & Stakeholder Consultant |  |  | Community & Stakeholder Consultant | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Community and Stakeholder Engagement | Consultation & Relationship Management System |  |  | Consultation & Relationship Management System | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Community and Stakeholder Engagement | Digital Engagement Services (Interactive Mapping Services) |  |  | Digital Engagement Services (Interactive Mapping Services) | 0 | 76000 | 114000 | 0 | 190000
| VNIW - Community and Stakeholder Engagement | Graphic Design |  |  | Graphic Design | 24452.25 | 8150.75 | 0 | 0 | 32603
| VNIW - Community and Stakeholder Engagement | Video Content |  |  | Video Content | 28314.1204 | 84942.3611 | 56628.2407 | 0 | 169884.7222
| VNIW - Community and Stakeholder Engagement | Photography |  |  | Photography | 0 | 12075 | 12075 | 0 | 24150
| VNIW - Community and Stakeholder Engagement | Printing |  |  | Printing | 1725 | 20700 | 12075 | 0 | 34500
| VNIW - Community and Stakeholder Engagement | Stakeholder Management Licences |  |  | Stakeholder Management Licences | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Community and Stakeholder Engagement | Community Engagement - Events, Marketing & Advertising |  |  | Community Engagement - Events, Marketing & Advertising | 0 | 68235.6 | 45490.4 | 0 | 113726
| VNIW - Community and Stakeholder Engagement | Community Giving Program |  |  | Community Giving Program | 51647.846 | 98571.5482 | 95775.5674 | 0 | 245994.9617
| VNIW - Community and Stakeholder Engagement | Community Investments Program |  |  | Community Investments Program | 0 | 4186824.1764 | 718316.7558 | 0 | 4905140.9322 | ◄◄◄◄◄◄◄◄◄ | 3570752 | Regional Telecommunications
| VNIW - Community and Stakeholder Engagement | Community Investments Program |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 362653.3539 | Scholarships
| VNIW - Community and Stakeholder Engagement | Community Investments Program |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 971735.5783 | Regional development support
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
5864103.6161
6 | VNIW - Land and Environment
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Land and Environment | Land Agents (Valuations, Access & Easement Acquisition Services) |  |  | Land Agents (Valuations, Access & Easement Acquisition Services) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Land and Environment | Land Agents (Sundry Expenses) |  |  | Land Agents (Sundry Expenses) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Land and Environment | Land Agents (Vehicle) |  |  | Land Agents (Vehicle) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Land and Environment | Route Visual Overlay |  |  | Route Visual Overlay | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Land and Environment | Route Study |  |  | Route Study | 0 | 0 | 0 | 0 | 0
| VNIW - Land and Environment | Heritage Investigations |  |  | Heritage Investigations | 0 | 0 | 0 | 0 | 0
| VNIW - Land and Environment | Flora & Fauna Investigations (Spring Surveys) |  |  | Flora & Fauna Investigations (Spring Surveys) | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Land and Environment | EIS Development & Documentation |  |  | EIS Development & Documentation | 0 | 5112775.8 | 4268464.2 | 0 | 9381240
| VNIW - Land and Environment | Government Fees EIS - NSW Gov (On Lodgement) |  |  | Government Fees EIS - NSW Gov (On Lodgement) | 0 | 0 | 1788416.213 | 0 | 1788416.213
| VNIW - Land and Environment | Government Fees EIS - C'wealth Gov (On Approval) |  |  | Government Fees EIS - C'wealth Gov (On Approval) | 0 | 0 | 95775.5674 | 0 | 95775.5674
| VNIW - Land and Environment | Public Display |  |  | Public Display | 0 | 0 | 0 | 0 | 0
| VNIW - Land and Environment | Submissions Report |  |  | Submissions Report | 0 | 0 | 0 | 0 | 0
| VNIW - Land and Environment | ISCA Sustainability Strategy Report |  |  | ISCA Sustainability Strategy Report | 0 | 0 | 0 | 0 | 0
17185601.7805
7 | VNIW - Other Support & Corporate Roles
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| VNIW - Other Support & Corporate Roles | Indirect Costs (Labour) FY2023 |  |  | Indirect Costs (Labour) FY2023 | 2121243.02 | 0 | 0 | 0 | 2121243.02
| VNIW - Other Support & Corporate Roles | Indirect Costs (Labour) FY2024 |  |  | Indirect Costs (Labour) FY2024 | 0 | 7594726.4294 | 0 | 0 | 7594726.4294
| VNIW - Other Support & Corporate Roles | Indirect Costs (Labour) FY2025 |  |  | Indirect Costs (Labour) FY2025 | 0 | 0 | 7901257.4714 | 0 | 7901257.4714
| VNIW - Other Support & Corporate Roles | Indirect Costs (Labour) FY2026 |  |  | Indirect Costs (Labour) FY2026 | 0 | 0 | 0 | 0 | 0
| VNIW - Other Support & Corporate Roles | c-i-c |  |  | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | c-i-c |  |  | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Benchmarking |  |  | Benchmarking | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Governance Reviews |  |  | Governance Reviews | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Governance, Benchmarking and Lessons Learnt - additional FTE required |  |  | Governance, Benchmarking and Lessons Learnt - additional FTE required | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Community Engagement Transformation Plan & Social Licence Action Plan |  |  | Community Engagement Transformation Plan & Social Licence Action Plan | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Property Portfolio System costs |  |  | Property Portfolio System costs | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Wagga Training Centre |  |  | Wagga Training Centre | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Wagga Hub |  |  | Wagga Hub | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Political Consultants |  |  | Political Consultants | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Sponsorships |  |  | Sponsorships | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Incurred by PTT function, to set up function, dashboarding and resourcing |  |  | Incurred by PTT function, to set up function, dashboarding and resourcing | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Incurred by Origination function |  |  | Incurred by Origination function | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | c-i-c |  |  | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Non-project specific costs in MP Opex. Such as:travel, training, GM recruitment costs, etc |  |  | Non-project specific costs in MP Opex. Such as:travel, training, GM recruitment costs, etc | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Fleet costs |  |  | Fleet costs | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
| VNIW - Other Support & Corporate Roles | Advisory & Assurance |  |  | Advisory & Assurance | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
36004001.533
8 | PEC - Project Management
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| PEC - Project Management | Insurance |  |  | Insurance | c-i-c | c-i-c | c-i-c | c-i-c | c-i-c
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0
c-i-c
9 | HL Gugaa - Project Management
| Broader category | Item |  |  | Item | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period |  | OK
| HL Gugaa - Project Management | Insurance |  |  | Insurance | 0 | 1260000 | 1050000 | 0 | 2310000
| HL Gugaa - Project Management | Legal Fees |  |  | Legal Fees | 0 | 1000000 | 833333.3333 | 0 | 1833333.3333
| HL Gugaa - Project Management | Employers Rep Role |  |  | Employers Rep Role | 0 | 40250 | 33541.6667 | 0 | 73791.6667
4217125

## Labour-related_calcs
Labour and overhead costs for VNI West project
Labour-related cost calculations
Notes
This tab presents the calculations for the forecast capex for training, travel expenses, recruitment and IT hardware across the different cost categories for the VNI West project.
1 | Training
|  | Historical (Real, $22-23) | Forecast (Real, $22-23)
| Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex
| VNIW - Project Management |  | 2797.9604 | 54928.38 | 47565.3263 | 0 | 105291.6667
| VNIW - Project Development |  | 853.4836 | 22475.0683 | 11379.7814 | 0 | 34708.3333
| VNIW - Transaction Procurement Support |  | N/A | N/A | N/A | N/A | 0
| VNIW - Regulatory Approvals |  | N/A | N/A | N/A | N/A | 0
| VNIW - Community and Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| VNIW - Land and Environment |  | 1022.8202 | 14555.5177 | 13296.6621 | 0 | 28875
| VNIW - Other Support & Corporate Roles |  | N/A | N/A | N/A | N/A | 0
| PEC - Project Management |  | 1961.4331 | 23537.1972 | 18105.5363 | 0 | 43604.1667
| PEC - Project Development |  | 756.7568 | 7283.7838 | 5959.4595 | 0 | 14000
| PEC - Community and Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| PEC - Land and Environment |  | 1583.3333 | 9500 | 0 | 0 | 11083.3333
| PEC - Regulatory Approvals |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Project Management |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Project Development |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Community & Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Land & Environment |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Other Support & Corporate Roles |  | N/A | N/A | N/A | N/A | 0
| HL Wagga - Project Development |  | N/A | N/A | N/A | N/A | 0
| 0 |  | N/A | N/A | N/A | N/A | 0
| Total |  | 8975.7873 | 132279.947 | 96306.7657 | 0 | 237562.5
| Total VNIW | 0 | 4674.2641 | 91958.966 | 72241.7699 | 0 | 168875
| Total PEC |  | 4301.5232 | 40320.981 | 24064.9958 | 0 | 68687.5
| Total HL |  | 0 | 0 | 0 | 0 | 0
|  |  | OK | OK | OK | OK | OK
2 | Recruitment
|  | Historical (Real, $22-23) | Forecast (Real, $22-23)
| Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex
| VNIW - Project Management |  | 0 | 198362.6249 | 14017.8133 | 0 | 212380.4382
| VNIW - Project Development |  | 0 | 83024.0949 | 0 | 0 | 83024.0949
| VNIW - Transaction Procurement Support |  | N/A | N/A | N/A | N/A | 0
| VNIW - Regulatory Approvals |  | N/A | N/A | N/A | N/A | 0
| VNIW - Community and Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| VNIW - Land and Environment |  | 0 | 15183.6383 | 0 | 0 | 15183.6383
| VNIW - Other Support & Corporate Roles |  | N/A | N/A | N/A | N/A | 0
| PEC - Project Management |  | 0 | 12016.5282 | 0 | 0 | 12016.5282
| PEC - Project Development |  | 0 | 2537.4654 | 1008.0342 | 0 | 3545.4996
| PEC - Community and Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| PEC - Land and Environment |  | 0 | 0 | 0 | 0 | 0
| PEC - Regulatory Approvals |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Project Management |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Project Development |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Community & Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Land & Environment |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Other Support & Corporate Roles |  | N/A | N/A | N/A | N/A | 0
| HL Wagga - Project Development |  | N/A | N/A | N/A | N/A | 0
| 0 |  | N/A | N/A | N/A | N/A | 0
0
0
0
| Total |  | 0 | 311124.3517 | 15025.8475 | 0 | 326150.1993
| Total VNIW | 0 | 0 | 296570.3582 | 14017.8133 | 0 | 310588.1715
| Total PEC |  | 0 | 14553.9936 | 1008.0342 | 0 | 15562.0278
| Total HL |  | 0 | 0 | 0 | 0 | 0
|  |  | OK | OK | OK | OK | OK
3 | IT Hardware expenses
|  | Historical (Real, $22-23) | Forecast (Real, $22-23)
| Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex
| VNIW - Project Management |  | 0 | 53392 | 3337 | 0 | 56729
| VNIW - Project Development |  | 0 | 20022 | 0 | 0 | 20022
| VNIW - Transaction Procurement Support |  | N/A | N/A | N/A | N/A | 0
| VNIW - Regulatory Approvals |  | N/A | N/A | N/A | N/A | 0
| VNIW - Community and Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| VNIW - Land and Environment |  | 0 | 3337 | 0 | 0 | 3337
| VNIW - Other Support & Corporate Roles |  | N/A | N/A | N/A | N/A | 0
| PEC - Project Management |  | 0 | 3337 | 0 | 0 | 3337
| PEC - Project Development |  | 0 | 10011 | 3337 | 0 | 13348
| PEC - Community and Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| PEC - Land and Environment |  | 0 | 0 | 0 | 0 | 0
| PEC - Regulatory Approvals |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Project Management |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Project Development |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Community & Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Land & Environment |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Other Support & Corporate Roles |  | N/A | N/A | N/A | N/A | 0
| HL Wagga - Project Development |  | N/A | N/A | N/A | N/A | 0
| 0 |  | N/A | N/A | N/A | N/A | 0
0
0
0
| Total |  | 0 | 90099 | 6674 | 0 | 96773
| Total VNIW | 0 | 0 | 76751 | 3337 | 0 | 80088
| Total PEC |  | 0 | 13348 | 3337 | 0 | 16685
| Total HL |  | 0 | 0 | 0 | 0 | 0
|  |  | OK | OK | OK | OK | OK
4 | Travel expenses for non-works delivery staff
|  | Historical (Real, $22-23) | Forecast (Real, $22-23)
| Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex
| VNIW - Project Management |  | 2715.1 | 32581.2 | 27151 | 0 | 62447.3
| VNIW - Project Development |  | 2715.1 | 48871.8 | 27151 | 0 | 78737.9
| VNIW - Transaction Procurement Support |  | N/A | N/A | N/A | N/A | 0
| VNIW - Regulatory Approvals |  | N/A | N/A | N/A | N/A | 0
| VNIW - Community and Stakeholder Engagement |  | 18440.8 | 221289.6 | 184408 | 0 | 424138.4
| VNIW - Land and Environment |  | 5430.2 | 65162.4 | 54302 | 0 | 124894.6
| VNIW - Other Support & Corporate Roles |  | N/A | N/A | N/A | N/A | 0
| PEC - Project Management |  | 2715.1 | 62447.3 | 46156.7 | 0 | 111319.1
| PEC - Project Development |  | 5430.2 | 173766.4 | 119464.4 | 0 | 298661
| PEC - Community and Stakeholder Engagement |  | 4610.2 | 101424.4 | 73763.2 | 0 | 179797.8
| PEC - Land and Environment |  | 2715.1 | 59732.2 | 43441.6 | 0 | 105888.9
| PEC - Regulatory Approvals |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Project Management |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Project Development |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Community & Stakeholder Engagement |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Land & Environment |  | N/A | N/A | N/A | N/A | 0
| HL Gugaa - Other Support & Corporate Roles |  | N/A | N/A | N/A | N/A | 0
| HL Wagga - Project Development |  | N/A | N/A | N/A | N/A | 0
| 0 |  | N/A | N/A | N/A | N/A | 0
0
0
0
| Total |  | 44771.8 | 765275.3 | 575837.9 | 0 | 1385885
| Total VNIW | 0 | 29301.2 | 367905 | 293012 | 0 | 690218.2
| Total PEC |  | 15470.6 | 397370.3 | 282825.9 | 0 | 695666.8
| Total HL |  | 0 | 0 | 0 | 0 | 0
|  |  | OK | OK | OK | OK | OK
Total labour-related costs - direct
|  | Historical (Real, $22-23) | Forecast (Real, $22-23)
| Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex
| VNIW - Project Management |  | 3859.1423 | 237484.9434 | 64449.7978 | 0 | 305793.8834
| VNIW - Project Development |  | 2498.0085 | 122075.0743 | 26971.547 | 0 | 151544.6298
| VNIW - Transaction Procurement Support |  | 0 | 0 | 0 | 0 | 0
| VNIW - Regulatory Approvals |  | 0 | 0 | 0 | 0 | 0
| VNIW - Community and Stakeholder Engagement |  | 12908.56 | 154902.72 | 129085.6 | 0 | 296896.88
| VNIW - Land and Environment |  | 4517.1141 | 68766.9892 | 47319.0635 | 0 | 120603.1668
| VNIW - Other Support & Corporate Roles |  | 0 | 0 | 0 | 0 | 0
| PEC - Project Management |  | 3273.5732 | 70936.6178 | 44983.5654 | 0 | 119193.7564
| PEC - Project Development |  | 4330.8697 | 135519.0544 | 90838.2256 | 0 | 230688.1497
| PEC - Community and Stakeholder Engagement |  | 3227.14 | 70997.08 | 51634.24 | 0 | 125858.46
| PEC - Land and Environment |  | 3008.9033 | 48462.54 | 30409.12 | 0 | 81880.5633
| PEC - Regulatory Approvals |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Project Management |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Project Development |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Community & Stakeholder Engagement |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Land & Environment |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Other Support & Corporate Roles |  | 0 | 0 | 0 | 0 | 0
| HL Wagga - Project Development |  | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 | 0 | 0 | 0
| Total |  | 37623.3111 | 909145.0191 | 485691.1593 | 0 | 1432459.4895
| Total VNIW | 0 | 23782.8249 | 583229.7269 | 267826.0083 | 0 | 874838.56
| Total PEC |  | 13840.4862 | 325915.2922 | 217865.151 | 0 | 557620.9294
| Total HL |  | 0 | 0 | 0 | 0 | 0
|  |  | OK | OK | OK | OK | OK
Total labour-related costs - indirect
|  | Historical (Real, $22-23) | Forecast (Real, $22-23)
| Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex
| VNIW - Project Management |  | 1653.9181 | 101779.2615 | 27621.3419 | 0 | 131054.5215
| VNIW - Project Development |  | 1070.5751 | 52317.889 | 11559.2344 | 0 | 64947.6985
| VNIW - Transaction Procurement Support |  | 0 | 0 | 0 | 0 | 0
| VNIW - Regulatory Approvals |  | 0 | 0 | 0 | 0 | 0
| VNIW - Community and Stakeholder Engagement |  | 5532.24 | 66386.88 | 55322.4 | 0 | 127241.52
| VNIW - Land and Environment |  | 1935.906 | 29471.5668 | 20279.5986 | 0 | 51687.0715
| VNIW - Other Support & Corporate Roles |  | 0 | 0 | 0 | 0 | 0
| PEC - Project Management |  | 1402.9599 | 30401.4076 | 19278.6709 | 0 | 51083.0385
| PEC - Project Development |  | 1856.087 | 58079.5948 | 38930.6681 | 0 | 98866.3499
| PEC - Community and Stakeholder Engagement |  | 1383.06 | 30427.32 | 22128.96 | 0 | 53939.34
| PEC - Land and Environment |  | 1289.53 | 20769.66 | 13032.48 | 0 | 35091.67
| PEC - Regulatory Approvals |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Project Management |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Project Development |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Community & Stakeholder Engagement |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Land & Environment |  | 0 | 0 | 0 | 0 | 0
| HL Gugaa - Other Support & Corporate Roles |  | 0 | 0 | 0 | 0 | 0
| HL Wagga - Project Development |  | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 | 0 | 0 | 0 | 0
| Total |  | 16124.2762 | 389633.5796 | 208153.354 | 0 | 613911.2098
| Total VNIW | 0 | 10192.6392 | 249955.5972 | 114782.575 | 0 | 374930.8114
| Total PEC |  | 5931.637 | 139677.9824 | 93370.779 | 0 | 238980.3983
| Total HL |  | 0 | 0 | 0 | 0 | 0
|  |  | OK | OK | OK | OK | OK

## FTE&roles_calcs
Labour and overhead costs for VNI West project
FTEs and roles
Notes
| This tab presents the FTE calculations for labour across both historical and forecast capex. |  | check | OK
Number of FTEs (internal and contracted labour)
| Broader cost category | 2023-06-01 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30 | 2028-05-31 | Total | Av forecast FTE per month |  | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026
| VNIW - Project Management | 12.9 | 23.2 | 24.2 | 24.7 | 24.7 | 24.7 | 24.7 | 25.35 | 26.35 | 27.35 | 27.35 | 27.35 | 27.35 | 27.85 | 27.85 | 27.85 | 27.65 | 27.65 | 27.65 | 27.65 | 27.65 | 27.65 | 27.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.4 | 25.9696 | 39.21% |  | 12.9 | 307.3 | 277.1 | 0
| VNIW - Project Development | 2.05 | 2.55 | 7.3186 | 7.7686 | 8.2686 | 8.2686 | 10.2686 | 11.2686 | 3.5 | 3.5 | 3.5 | 3.5 | 4.3 | 4.3 | 4.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.4 | 4.8288 | 4.675% |  | 2.05 | 74.0114 | 35 | 0
| VNIW - Transaction Procurement Support | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6 | 0.88478 | 2.054% |  | 0.45 | 5.4 | 14.5 | 0
| VNIW - Regulatory Approvals | 2.8 | 2.8 | 0.7 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0.97391 | 2.479% |  | 2.8 | 5.6 | 14 | 0
| VNIW - Community and Stakeholder Engagement | 9.416 | 13.166 | 12.566 | 12.566 | 12.566 | 12.566 | 12.816 | 12.566 | 12.566 | 13.266 | 13.266 | 13.266 | 13.516 | 13.266 | 13.266 | 13.266 | 13.266 | 13.266 | 13.516 | 13.266 | 13.266 | 12.866 | 12.366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105.078 | 12.8573 | 18.61% |  | 9.416 | 154.692 | 131.61 | 0
| VNIW - Land and Environment | 6.175 | 9.8 | 9.55 | 9.55 | 9.175 | 9.175 | 9.075 | 9.075 | 10.375 | 9.85 | 9.85 | 9.85 | 10.05 | 10.55 | 11.55 | 11.65 | 11.65 | 11.3 | 11.05 | 10.85 | 10.85 | 10.85 | 10.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89.05 | 10.1174 | 15.77% |  | 6.175 | 115.375 | 111.15 | 0
| VNIW - Other Support & Corporate Roles | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 2.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.8042 | 1.8042 | 1.8042 | 2.8042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.2333 | 1.2303 | 2.166% |  | 1.0042 | 13.05 | 14.2417 | 0
| PEC - Project Management | 4.65 | 4.65 | 4.65 | 4.4 | 4.4 | 4.4 | 4.4 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 2.9 | 2.8 | 2.8 | 2.8 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.9 | 4.1848 | 4.941% |  | 4.65 | 54.5 | 37.1 | 0
| PEC - Project Development | 4.65 | 4.65 | 4.65 | 3.85 | 3.9 | 3.9 | 3.9 | 4 | 4 | 4 | 4 | 4 | 4.8 | 4.75 | 5.05 | 5.05 | 5.05 | 5.05 | 5.05 | 4.65 | 2.65 | 2.35 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.2 | 4.187 | 5.703% |  | 4.65 | 49.65 | 42 | 0
| PEC - Community and Stakeholder Engagement | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2 | 0.65 | 0.9209% |  | 0.65 | 7.8 | 6.5 | 0
| PEC - Land and Environment | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18261 | 0% |  | 0.6 | 3.6 | 0 | 0
| PEC - Regulatory Approvals | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0.33043 | 0.2834% |  | 0.4 | 4.8 | 2.4 | 0
| HL Gugaa - Project Management | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6 | 0.66957 | 0.9917% |  | 0 | 8.4 | 7 | 0
| HL Gugaa - Project Development | 1.65 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.36 | 0.95174 | 1.303% | 5.52 | 1.65 | 11.04 | 9.2 | 0
| HL Gugaa - Community & Stakeholder Engagement | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.047826 | 0.07084% | 0.3 | 0 | 0.6 | 0.5 | 0
| HL Gugaa - Land & Environment | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0.095652 | 0.1417%
| HL Gugaa - Other Support & Corporate Roles | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0.1913 | 0.2834%
| HL Wagga - Project Development | 1.65 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0.33957 | 0.3967% | 1.68 | 1.65 | 3.36 | 2.8 | 0
| 0 | [64 empty] | 0
| Total FTEs per month | 49.0452 | 66.1702 | 68.9887 | 68.8887 | 69.0637 | 69.0637 | 70.5137 | 71.6137 | 66.1452 | 67.3202 | 67.3202 | 67.3202 | 70.3702 | 71.0702 | 72.3702 | 71.4702 | 71.2702 | 70.9202 | 72.0202 | 71.4702 | 69.4702 | 68.7702 | 69.2702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564.6613 | 68.6924 |  | 7.5 | 34.0952 | 437.867 | 393.0017 | 0
| VNI West | 34.7952 | 52.9702 | 55.7887 | 56.7387 | 56.8637 | 56.8637 | 58.3137 | 59.7137 | 54.2452 | 55.4202 | 55.4202 | 55.4202 | 57.6702 | 58.4202 | 59.4202 | 58.5202 | 58.3202 | 57.9702 | 60.7702 | 61.1202 | 61.1202 | 60.7202 | 61.2202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.7613 | 56.862
| PEC | 10.95 | 10.95 | 10.95 | 9.9 | 9.95 | 9.95 | 9.95 | 9.65 | 9.65 | 9.65 | 9.65 | 9.65 | 10.45 | 10.4 | 10.7 | 10.7 | 10.7 | 10.7 | 9 | 8.1 | 6.1 | 5.8 | 5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.9 | 9.5348
| HL | 3.3 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2.2957
Number of FTEs (internal labour only)
| Broader cost category | 2023-06-01 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30 | 2028-05-31 | Total | Av forecast FTE per month |  | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026
| VNIW - Project Management | 11.8 | 21.6 | 22.6 | 23.6 | 23.6 | 23.6 | 23.6 | 24.3 | 25.3 | 26.3 | 26.3 | 26.3 | 26.3 | 26.8 | 26.8 | 26.8 | 26.6 | 26.6 | 26.6 | 26.6 | 26.6 | 26.6 | 26.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 24.8609 |  |  | 11.8 | 293.4 | 266.6 | 0
| VNIW - Project Development | 1.55 | 1.55 | 4.09 | 5.54 | 6.04 | 6.04 | 6.04 | 6.04 | 3.5 | 3.5 | 3.5 | 3.5 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.4 | 3.7909 |  |  | 1.55 | 52.64 | 33 | 0
| VNIW - Transaction Procurement Support | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6 | 0.88478 |  |  | 0.45 | 5.4 | 14.5 | 0
| VNIW - Regulatory Approvals | 2.8 | 2.8 | 0.7 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0.97391 |  |  | 2.8 | 5.6 | 14 | 0
| VNIW - Community and Stakeholder Engagement | 8.266 | 8.266 | 7.666 | 7.666 | 7.666 | 7.666 | 7.666 | 7.666 | 7.666 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 8.366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.928 | 8.1443 |  |  | 8.266 | 95.392 | 83.66 | 0
| VNIW - Land and Environment | 6.175 | 9.8 | 9.55 | 9.55 | 9.175 | 9.175 | 9.075 | 9.075 | 10.375 | 9.85 | 9.85 | 9.85 | 10.05 | 10.55 | 11.55 | 11.65 | 11.65 | 11.3 | 11.05 | 10.85 | 10.85 | 10.85 | 10.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89.05 | 10.1174 |  |  | 6.175 | 115.375 | 111.15 | 0
| VNIW - Other Support & Corporate Roles | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.0042 | 1.8042 | 1.8042 | 1.8042 | 1.8042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2333 | 1.1433 |  |  | 1.0042 | 12.05 | 13.2417 | 0
| PEC - Project Management | 4.65 | 4.65 | 4.65 | 4.4 | 4.4 | 4.4 | 4.4 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 2.9 | 2.8 | 2.8 | 2.8 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.9 | 4.1848 |  |  | 4.65 | 54.5 | 37.1 | 0
| PEC - Project Development | 4.65 | 4.65 | 4.65 | 3.85 | 3.9 | 3.9 | 3.9 | 4 | 4 | 4 | 4 | 4 | 4.8 | 4.75 | 5.05 | 5.05 | 5.05 | 5.05 | 5.05 | 4.65 | 2.65 | 2.35 | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.2 | 4.187 |  |  | 4.65 | 49.65 | 42 | 0
| PEC - Community and Stakeholder Engagement | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2 | 0.65 |  |  | 0.65 | 7.8 | 6.5 | 0
| PEC - Land and Environment | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18261 |  |  | 0.6 | 3.6 | 0 | 0
| PEC - Regulatory Approvals | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0.33043 |  |  | 0.4 | 4.8 | 2.4 | 0
| HL Gugaa - Project Management | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6 | 0.66957 |  |  | 0 | 8.4 | 7 | 0
| HL Gugaa - Project Development | 1.65 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.36 | 0.95174 |  |  | 1.65 | 11.04 | 9.2 | 0
| HL Gugaa - Community & Stakeholder Engagement | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.047826
| HL Gugaa - Land & Environment | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0.095652
| HL Gugaa - Other Support & Corporate Roles | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0.1913
| HL Wagga - Project Development | 1.65 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0.33957
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Total FTEs per month | 46.2952 | 58.6702 | 59.2602 | 60.6602 | 60.8352 | 60.8352 | 60.0352 | 60.4352 | 60.1952 | 61.3702 | 61.3702 | 61.3702 | 62.1702 | 64.1202 | 65.4202 | 65.5202 | 65.3202 | 64.9702 | 65.8202 | 65.5202 | 63.5202 | 63.2202 | 63.2202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517.1113 | 61.7458 |  | 0 | 44.6452 | 719.647 | 640.3517 | 0
| VNI West | 32.0452 | 45.4702 | 46.0602 | 48.5102 | 48.6352 | 48.6352 | 47.8352 | 48.5352 | 48.2952 | 49.4702 | 49.4702 | 49.4702 | 49.4702 | 51.4702 | 52.4702 | 52.5702 | 52.3702 | 52.0202 | 54.5702 | 55.1702 | 55.1702 | 55.1702 | 55.1702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432.2113 | 49.9154
| PEC | 10.95 | 10.95 | 10.95 | 9.9 | 9.95 | 9.95 | 9.95 | 9.65 | 9.65 | 9.65 | 9.65 | 9.65 | 10.45 | 10.4 | 10.7 | 10.7 | 10.7 | 10.7 | 9 | 8.1 | 6.1 | 5.8 | 5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.9 | 9.5348
| HL | 3.3 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2.2957
| Broader cost category | No. of internal roles over entire project | No. of outsourced roles over entire project | Total roles | Average number of months working on VNI West project
| VNIW - Project Management | 38 | 5 | 43 | 19
| VNIW - Project Development | 9 | 9 | 18 | 14
| VNIW - Transaction Procurement Support | 4 | 0 | 4 | 20
| VNIW - Regulatory Approvals | 6 | 0 | 6 | 8
| VNIW - Community and Stakeholder Engagement | 47 | 7 | 54 | 21
| VNIW - Land and Environment | 17 | 0 | 17 | 22
| VNIW - Other Support & Corporate Roles | 15 | 1 | 16 | 22
| PEC - Project Management | 13 | 0 | 13 | 23
| PEC - Project Development | 19 | 0 | 19 | 16
| PEC - Community and Stakeholder Engagement | 4 | 0 | 4 | 23
| PEC - Land and Environment | 6 | 0 | 6 | 4
| PEC - Regulatory Approvals | 4 | 0 | 4 | 19
| HL Gugaa - Project Management | 14 | 0 | 14 | 22
| HL Gugaa - Project Development | 20 | 0 | 20 | 16
| HL Gugaa - Community & Stakeholder Engagement | 1 | 0 | 1 | 22
| HL Gugaa - Land & Environment | 2 | 0 | 2 | 22
| HL Gugaa - Other Support & Corporate Roles | 4 | 0 | 4 | 22
| HL Wagga - Project Development | 20 | 0 | 20 | 16
0
| Total | 243 | 22 | 265 | 0
Number of months working on VNI West
| Broader cost category | FY2017 to FY2023 (1 June 2016 - 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total over forecast period
| VNIW - Project Management | 0 | 19 | 373 | 323 | 0 | 715
| VNIW - Project Development | 0 | 3 | 79 | 40 | 0 | 122
| VNIW - Transaction Procurement Support | 0 | 3 | 36 | 40 | 0 | 79
| VNIW - Regulatory Approvals | 0 | 4 | 20 | 20 | 0 | 44
| VNIW - Community and Stakeholder Engagement | 0 | 43 | 505 | 420 | 0 | 968
| VNIW - Land and Environment | 0 | 13 | 185 | 169 | 0 | 367
| VNIW - Other Support & Corporate Roles | 0 | 14 | 168 | 144 | 0 | 326
| PEC - Project Management | 0 | 13 | 156 | 120 | 0 | 289
| PEC - Project Development | 0 | 16 | 154 | 126 | 0 | 296
| PEC - Community and Stakeholder Engagement | 0 | 4 | 48 | 40 | 0 | 92
| PEC - Land and Environment | 0 | 3 | 18 | 0 | 0 | 21
| PEC - Regulatory Approvals | 0 | 4 | 48 | 24 | 0 | 76
| HL Gugaa - Project Management | 0 | 0 | 168 | 140 | 0 | 308
| HL Gugaa - Project Development | 0 | 6 | 168 | 140 | 0 | 314
| HL Gugaa - Community & Stakeholder Engagement | 0 | 0 | 12 | 10 | 0 | 22
| HL Gugaa - Land & Environment | 0 | 0 | 24 | 20 | 0 | 44
| HL Gugaa - Other Support & Corporate Roles | 0 | 0 | 48 | 40 | 0 | 88
| HL Wagga - Project Development | 0 | 6 | 168 | 140 | 0 | 314
| 0 | 0 | 0 | 0 | 0 | 0 | 0

## VNIW Summary Tables
Labour and overhead costs for VNI West project
VNI West summary tables
Notes
This tab outputs actual and forecast expenditure (in FY23 prices).
Total costs across entire period
|  |  | Historical ($ Real 2022-2023) | [6 empty] | Forecast ($ Real 2022-2023)
|  | Capex category | FY2017 | FY2018 | FY2019 | FY2020 | FY2021 | FY2022 | FY2023 (From 1 July 2022 to 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex (incl. historical data) | Total capex (excl. historical data)
Labour (internal and outsourced, direct)
|  | VNIW - Project Management | 0 | 0 | 0 | 0 | 0 | 1261815.4889 | 2688807.5237 | 332441.0145 | 7115301.9772 | 6367740.3615 | 0 | 17766106.3658 | 13815483.3532 | OK
|  | VNIW - Project Development | 0 | 2751.2664 | 0 | 145342.1691 | 207.7451 | 307342.7336 | -80505.5635 | 64273.7429 | 1947630.0209 | 937483.106 | 0 | 3324525.2205 | 2949386.8698 | OK
|  | VNIW - Transaction Procurement Support | 0 | [6 empty] | 9471.6381 | 113659.657 | 326808.6958 | 0 | 449939.991 | 449939.991 | OK
|  | VNIW - Community and Stakeholder Engagement | 0 | 0 | 0 | 0 | 0 | 166955.232 | 982666.38 | 239128.875 | 3824298.7886 | 3229195.8854 | 0 | 8442245.1611 | 7292623.5491 | OK
|  | VNIW - Land and Environment | 0 | 0 | 0 | 0 | 0 | 39863.6877 | 463498.0999 | 148894.5489 | 2663226.9612 | 2548328.4128 | 0 | 5863811.7105 | 5360449.9229 | OK
|  | VNIW - Regulatory Approvals | 0 | 0 | 0 | 0 | 0 | 0 | 30726.3366 | 77131.2489 | 154262.4978 | 385656.2444 | 0 | 647776.3276 | 617049.991 | OK
|  | VNIW - Other Support & Corporate Roles | 0 | 0 | 0 | 0 | 0 | 189622.6682 | 375441.6213 | 23274.2343 | 303790.8119 | 324442.3433 | 0 | 1216571.679 | 651507.3895 | OK
OK
|  | TOTAL | 0 | 2751.2664 | 0 | 145342.1691 | 207.7451 | 1965599.8104 | 4460634.3979 | 894615.3027 | 16122170.7147 | 14119655.0492 | 0 | 37710976.4555 | 31136441.0666
Labour-related (direct)
|  | VNIW - Project Management | 0 | 0 | 0 | 0 | 0 | 10955.5611 | 51218.136 | 3859.1423 | 237484.9434 | 64449.7978 | 0 | 367967.5805 | 305793.8834 | OK
|  | VNIW - Project Development | 0 | 0 | 0 | 0 | 0 | 0 | 2899.5101 | 2498.0085 | 122075.0743 | 26971.547 | 0 | 154444.1399 | 151544.6298 | OK
|  | VNIW - Transaction Procurement Support | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
|  | VNIW - Community and Stakeholder Engagement | 0 | 0 | 0 | 0 | 0 | 5000.6871 | 13640.1961 | 12908.56 | 154902.72 | 129085.6 | 0 | 315537.7632 | 296896.88 | OK
|  | VNIW - Land and Environment | 0 | 0 | 0 | 0 | 0 | 14.2908 | 7117.0732 | 4517.1141 | 68766.9892 | 47319.0635 | 0 | 127734.5308 | 120603.1668 | OK
|  | VNIW - Regulatory Approvals | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
|  | VNIW - Other Support & Corporate Roles | 0 | 0 | 0 | 398.0112 | 0 | 0 | 2334.4826 | 0 | 0 | 0 | 0 | 2732.4938 | 0 | OK
OK
|  | TOTAL | 0 | 0 | 0 | 398.0112 | 0 | 15970.539 | 77209.398 | 23782.8249 | 583229.7269 | 267826.0083 | 0 | 968416.5082 | 874838.56
Indirect
|  | Proportion of labour and labour-related costs | [7 empty] | 393599.1975 | 7159457.3321 | 6166063.3103 | 0 | 13719119.84 | 13719119.84 | OK
|  | VNIW - Project Management | 0 | 0 | 0 | 0 | 0 | 643279.1958 | 330247.6901 | 58620.8333 | 174510 | 125208.3333 | 0 | 1331866.0526 | 358339.1667 | OK
|  | VNIW - Project Development | 0 | 0 | 0 | 0 | 0 | 1884143.2459 | 1618758.1529 | 64592 | 9012262.0162 | 24827960.2039 | 0 | 37407715.619 | 33904814.2201 | OK
|  | VNIW - Transaction Procurement Support | 0 | [6 empty] | 37556 | 1947494 | 20706033 | 0 | 22691083 | 22691083 | OK
|  | VNIW - Community and Stakeholder Engagement | 0 | 0 | 0 | 0 | 0 | 233925.304 | 528296.5205 | 128639.2164 | 4634363.4357 | 1101100.964 | 0 | 6626325.4406 | 5864103.6161 | OK
|  | VNIW - Land and Environment | 0 | 0 | 0 | 0 | 0 | 0 | 404299.4317 | 115521.7391 | 7992596.6696 | 9077483.3718 | 0 | 17589901.2122 | 17185601.7805 | OK
|  | VNIW - Regulatory Approvals | 0 | [6 empty] | 209872 | 397866 | 5846319.6195 | 0 | 6454057.6195 | 6454057.6195 | OK
|  | VNIW - Other Support & Corporate Roles | 0 | 0 | 0 | 0 | 0 | 1632815.0232 | 3293416.8356 | 2848818.66 | 19164903.4294 | 13990279.4436 | 0 | 40930233.3918 | 36004001.533 | OK
OK
OK
|  | TOTAL | 0 | 0 | 0 | 0 | 0 | 4394162.769 | 6175018.6308 | 3857219.6464 | 50483452.8831 | 81840448.2464 | 0 | 146750302.1756 | 136181120.7759
|  | Total | 0 | 2751.2664 | 0 | 145740.1803 | 207.7451 | 6375733.1184 | 10712862.4267 | 4775617.7739 | 67188853.3247 | 96227929.3039 | 0 | 185429695.1394 | 168192400.4025
| check 1 | Labour (internal and outsourced, direct) | [7 empty] | OK | OK | OK | OK
| check 2 | Labour-related (direct) | [7 empty] | OK | OK | OK | OK
| check 3 | Proportion of labour and labour-related costs
| check 4 | Indirect non-labour capex | [7 empty] | OK | OK | OK | OK
| check 5 | Total capex | [7 empty] | OK | OK | OK | OK | OK | OK
FTEs
| Broader cost category | Average FTEs - Internal labour only | Average FTEs - Internal and Contracted Labour | Roles - Internal labour only | $ Internal Labour | No. of outsourced roles over entire project | $ Outsourced Labour | Total roles | $ Total
| VNIW - Project Management | 24.8609 | 25.9696 | 38 | 13145606.9782 | 5 | 669876.375 | 43 | 13815483.3532
| VNIW - Project Development | 3.7909 | 4.8288 | 9 | 2413850.4698 | 9 | 535536.4 | 18 | 2949386.8698
| VNIW - Transaction Procurement Support | 0.88478 | 0.88478 | 4 | 449939.991 | 0 | 535536.4 | 4 | 985476.391
| VNIW - Regulatory Approvals | 0.97391 | 0.97391 | 6 | 4371761.5491 | 0 |  | 6 | 4371761.5491
| VNIW - Community and Stakeholder Engagement | 8.1443 | 12.8573 | 47 | 5360449.9229 | 7 | 2920862 | 54 | 8281311.9229
| VNIW - Land and Environment | 10.1174 | 10.1174 | 17 | 617049.991 | 0 |  | 17 | 617049.991
| VNIW - Other Support & Corporate Roles | 1.1433 | 1.2303 | 15 | 602507.3895 | 1 | 49000 | 16 | 651507.3895
| PEC - Project Management | 4.1848 | 4.1848 | 13 | 2086322 | 0 |  | 13 | 2086322
| PEC - Project Development | 4.187 | 4.187 | 19 | 2223208.4 | 0 |  | 19 | 2223208.4
| PEC - Community and Stakeholder Engagement | 0.65 | 0.65 | 4 | 349273.4 | 0 |  | 4 | 349273.4
| PEC - Land and Environment | 0.18261 | 0.18261 | 6 | 79125.2 | 0 |  | 6 | 79125.2
| PEC - Regulatory Approvals | 0.33043 | 0.33043 | 4 | 220859.8 | 0 |  | 4 | 220859.8
| HL Gugaa - Project Management | 0.66957 | 0.66957 | 14 | 391456.2059 | 0 |  | 14 | 391456.2059
| HL Gugaa - Project Development | 0.95174 | 0.95174 | 20 | 611922.7055 | 0 |  | 20 | 611922.7055
| HL Gugaa - Community & Stakeholder Engagement | 0.047826 | 0.047826 | 1 | 47297.9707 | 0 |  | 1 | 47297.9707
| HL Gugaa - Land & Environment | 0.095652 | 0.095652 | 2 | 47488.6142 | 0 |  | 2 | 47488.6142
| HL Gugaa - Other Support & Corporate Roles | 0.1913 | 0.1913 | 4 | 133831.7581 | 0 |  | 4 | 133831.7581
| HL Wagga - Project Development | 0.33957 | 0.33957 | 20 | 220668.5793 | 0 |  | 20 | 220668.5793
0
| Total | 61.7458 | 68.6924 | 243 | 33372620.9252 | 22 | 4710811.175 | 265 | 38083432.1002
| VNI West | 49.9154 | 56.862 | 136 | 26961166.2916 | 22 | 4710811.175 | 158 | 31671977.4666
| PEC | 9.5348 | 9.5348 | 46 | 4958788.8 | 0 | 0 | 46 | 4958788.8
| HL | 2.2957 | 2.2957 | 61 | 1452665.8337 | 0 | 0 | 61 | 1452665.8337

## PEC Summary Tables
Labour and overhead costs for VNI West project
PEC summary tables
Notes
This tab outputs actual and forecast expenditure (in FY23 prices).
Total costs across entire period
|  | Historical ($ Real 2022-2023) | [6 empty] | Forecast ($ Real 2022-2023)
| Capex category | FY2017 | FY2018 | FY2019 | FY2020 | FY2021 | FY2022 | FY2023 (From 1 July 2022 to 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex (incl. historical data) | Total capex (excl. historical data)
Labour (internal and outsourced, direct)
| PEC - Project Management | 0 | [6 empty] | 101183.6 | 1190060.2 | 795078.2 | 0 | 2086322 | 2086322 | OK
| PEC - Project Development | 0 | [6 empty] | 108367.7 | 1165532.9 | 949307.8 | 0 | 2223208.4 | 2223208.4 | OK
| PEC - Community and Stakeholder Engagement | 0 | [6 empty] | 15185.8 | 182229.6 | 151858 | 0 | 349273.4 | 349273.4 | OK
| PEC - Land and Environment | 0 | 0 | 0 | 0 | 0 | 6668.3156 | 0 | 11303.6 | 67821.6 | 0 | 0 | 85793.5156 | 79125.2 | OK
| PEC - Regulatory Approvals | 0 | [6 empty] | 11624.2 | 139490.4 | 69745.2 | 0 | 220859.8 | 220859.8 | OK
OK
OK
OK
| TOTAL | 0 | 0 | 0 | 0 | 0 | 6668.3156 | 0 | 247664.9 | 2745134.7 | 1965989.2 | 0 | 4965457.1156 | 4958788.8
Labour-related (direct)
| PEC - Project Management | 0 | [6 empty] | 3273.5732 | 70936.6178 | 44983.5654 | 0 | 119193.7564 | 119193.7564 | OK
| PEC - Project Development | 0 | [6 empty] | 4330.8697 | 135519.0544 | 90838.2256 | 0 | 230688.1497 | 230688.1497 | OK
| PEC - Community and Stakeholder Engagement | 0 | [6 empty] | 3227.14 | 70997.08 | 51634.24 | 0 | 125858.46 | 125858.46 | OK
| PEC - Land and Environment | 0 | [6 empty] | 3008.9033 | 48462.54 | 30409.12 | 0 | 81880.5633 | 81880.5633 | OK
| PEC - Regulatory Approvals | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
OK
OK
OK
| TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13840.4862 | 325915.2922 | 217865.151 | 0 | 557620.9294 | 557620.9294
Indirect
| Proportion of labour and labour-related costs | [7 empty] | 112073.737 | 1316164.2824 | 935937.579 | 0 | 2364175.5983 | 2364175.5983 | OK
| PEC - Project Management | 0 | [6 empty] | 0 | 880000 | 480000 | 0 | 1360000 | 1360000 | OK
| PEC - Project Development | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| PEC - Community and Stakeholder Engagement | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| PEC - Land and Environment | 0 | 0 | 0 | 0 | 0 | 194162.7513 | 0 | 0 | 0 | 0 | 0 | 194162.7513 | 0 | OK
| PEC - Regulatory Approvals | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
OK
OK
OK
OK
| TOTAL | 0 | 0 | 0 | 0 | 0 | 194162.7513 | 0 | 112073.737 | 2196164.2824 | 1415937.579 | 0 | 3918338.3496 | 3724175.5983
| Total | 0 | 0 | 0 | 0 | 0 | 200831.0669 | 0 | 373579.1232 | 5267214.2746 | 3599791.93 | 0 | 9441416.3947 | 9240585.3278
check 1 | Labour (internal and outsourced, direct) | [7 empty] | OK | OK | OK | OK
check 2 | Labour-related (direct) | [7 empty] | OK | OK | OK | OK
check 3 | Proportion of labour and labour-related costs
check 4 | Indirect non-labour capex | [7 empty] | OK | OK | OK | OK
check 5 | Total capex | [7 empty] | OK | OK | OK | OK | OK | OK

## HL Summary Tables
Labour and overhead costs for VNI West project
Humelink summary tables
Notes
This tab outputs actual and forecast expenditure (in FY23 prices).
Total costs across entire period
|  | Historical ($ Real 2022-2023) | [6 empty] | Forecast ($ Real 2022-2023)
| Capex category | FY2017 | FY2018 | FY2019 | FY2020 | FY2021 | FY2022 | FY2023 (From 1 July 2022 to 31 May 2023) | FY2023 (From 1 June 2023) | FY2024 | FY2025 | FY2026 | Total capex (incl. historical data) | Total capex (excl. historical data)
Labour (internal and outsourced, direct)
| HL Gugaa - Project Management | 0 | [6 empty] | 0 | 213521.5669 | 177934.639 | 0 | 391456.2059 | 391456.2059 | OK
| HL Gugaa - Project Development | 0 | [6 empty] | 45978.7091 | 308696.7253 | 257247.2711 | 0 | 611922.7055 | 611922.7055 | OK
| HL Gugaa - Community & Stakeholder Engagement | 0 | [6 empty] | 0 | 25798.8931 | 21499.0776 | 0 | 47297.9707 | 47297.9707 | OK
| HL Gugaa - Land & Environment | 0 | [6 empty] | 0 | 25902.8805 | 21585.7338 | 0 | 47488.6142 | 47488.6142 | OK
| HL Gugaa - Other Support & Corporate Roles | 0 | [6 empty] | 0 | 72999.1408 | 60832.6173 | 0 | 133831.7581 | 133831.7581 | OK
| HL Wagga - Project Development | [7 empty] | 45978.7091 | 95285.3837 | 79404.4864 | 0 | 220668.5793 | 220668.5793 | OK
OK
OK
| TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91957.4183 | 742204.5902 | 618503.8252 | 0 | 1452665.8337 | 1452665.8337
Labour-related (direct)
| HL Gugaa - Project Management | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| HL Gugaa - Project Development | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| HL Gugaa - Community & Stakeholder Engagement | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| HL Gugaa - Land & Environment | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| HL Gugaa - Other Support & Corporate Roles | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| HL Wagga - Project Development | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
OK
OK
| TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirect
| Proportion of labour and labour-related costs | [7 empty] | 39410.3221 | 318087.6815 | 265073.0679 | 0 | 622571.0716 | 622571.0716 | OK
| HL Gugaa - Project Management | 0 | [6 empty] | 0 | 2300250 | 1916875 | 0 | 4217125 | 4217125 | OK
| HL Gugaa - Project Development | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| HL Gugaa - Community & Stakeholder Engagement | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| HL Gugaa - Land & Environment | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| HL Gugaa - Other Support & Corporate Roles | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| HL Wagga - Project Development | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
OK
OK
OK
| TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39410.3221 | 2618337.6815 | 2181948.0679 | 0 | 4839696.0716 | 4839696.0716
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131367.7404 | 3360542.2717 | 2800451.8931 | 0 | 6292361.9052 | 6292361.9052
check 1 | Labour (internal and outsourced, direct) | [7 empty] | OK | OK | OK | OK
check 2 | Labour-related (direct) | [7 empty] | OK | OK | OK | OK
check 3 | Proportion of labour and labour-related costs
check 4 | Indirect non-labour capex | [7 empty] | OK | OK | OK | OK
check 5 | Total capex | [7 empty] | OK | OK | OK | OK | OK | OK