## $Real Conversion
CPI indexes (nominal to real 2024) |  | June 2022 | June 2023 | June 2024
|  | 1.1433 | 1.0603 | 1.019
$2024
CPA Stream | Classification | 2021-22 | 2022-23 | 2023-24 | Total
Project Management | Labour | 2501617.8191 | 2756628.1543 | 1679620.4004 | 6937866.3738
Project Management | Indirect | 1279074.0907 | 2136796.9924 | 2463342.3389 | 5879213.422
Project Development | Labour | 1125701.3767 | 799080.6731 | 632016.2551 | 2556798.305
Project Development | Indirect | 3520034.9621 | 2681966.2925 | 946891.5757 | 7148892.8303
Procurement and Contracts | Labour | 909561.4596 | 1225329.5919 | 1066023.6707 | 3200914.7222
Procurement and Contracts | Indirect | 500690.982 | 1666330.6827 | 1927968.4106 | 4094990.0752
Community & Stakeholder | Labour | 931076.8906 | 720606.5501 | 733939.4272 | 2385622.8679
Community & Stakeholder | Indirect | 1105342.3209 | 712206.2879 | 226566.2942 | 2044114.903
Land & Property | Labour | 411307.6793 | 799109.4388 | 1179192.914 | 2389610.0321
Land & Property | Indirect | 1962765.3366 | 1584990.5435 | 1172469.9698 | 4720225.8499
Planning & Environment | Labour | 257238.3917 | 436942.7893 | 394001.7507 | 1088182.9317
Planning & Environment | Indirect | 3997383.7808 | 4832477.571 | 1794735.4955 | 10624596.8473
Regulatory Approvals and other support | Labour | 0 | 0 | 0 | 0
Regulatory Approvals and other support | Indirect | 0 | 0 | 301401.909 | 301401.909
|  |  |  | Total | 53372431.0693

## Total Actual (Stream)
|  |  | Actual cost Total |  | 49625039.27 | #REF!
|  | $Nominal |  |  |  |  | Posting Date
[5 empty] | TRUE | [7 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
CPA Stream | Classification | 2021-22 | 2022-23 | 2023-24 | Total |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | TOTAL
Project Management | Labour | 2188010.76 | 2599881.91 | 1648302.65 | 6436195.32 |  | 125547.93 | 101922.49 | 176982.58 | 177703.28 | 107690.99 | 205243.26 | 72908.23 | 145400.44 | 134531.47 | 407798.34 | 253245.9 | 279035.85 | 385847.14 | 77870.78 | 162813.64 | 187998.5 | 283483.5 | 214845.19 | 207413.23 | 97515.77 | 247895.3 | 198801.89 | 287591.37 | 247805.6 | 153688.52 | 266429.89 | 227638.27 | -95301.22 | 177336.02 | 107397.85 | 135251.01 | 93503.54 | 170092.41 | 206879.43 | 85868.67 | 119518.26 | 6436195.32
Project Management | Indirect | 1118727.19 | 2015295.33 | 2417411.52 | 5551434.04 |  | 37998.19 | 197395.01 | 282972.07 | 57565.82 | 45809.93 | 13097.58 | 42525.64 | -14949.8 | 76544.76 | 173404.79 | 98395.11 | 107968.09 | 185104.61 | 265719.29 | 135634.23 | 199819.24 | 102960.68 | 251848.27 | 141307.85 | 182608.36 | 139092.08 | 95641.48 | 190372.76 | 125186.48 | 313335 | 117372.74 | 326701.81 | 371694 | 87210.86 | 148364.83 | 111307.03 | 135736.26 | 200239.8 | 227569.16 | 204632.2 | 173247.83 | 5551434.04
Project Development | Labour | 984581.54 | 753643.68 | 620231.85 | 2358457.07 |  | 15325.29 | 81767.63 | 32247.43 | 57074.84 | 86150.11 | 131557.56 | 81230.06 | 62413.17 | 90821.29 | 81450.49 | 226470.71 | 38072.96 | -48075.58 | 107713.17 | 69063.77 | 69236.18 | 103303.13 | 77041.83 | 46704.41 | 137689.33 | 108551.9 | 34157.86 | 33429.54 | 14828.14 | 31381.72 | 57691.61 | 56196.69 | 38009.91 | 35798.89 | 46523.29 | 58918.99 | 58065.01 | 42797.48 | 50045.59 | 63081.12 | 81721.55 | 2358457.07
Project Development | Indirect | 3078757.4 | 2529465.44 | 929236.09 | 6537458.93 |  | 263177.8 | 211611.02 | 175814.61 | 101299.53 | 82078.35 | 94671.64 | 195999.96 | 160039.65 | 245784.66 | 347748.85 | 538556.95 | 661974.38 | 344342.81 | 267327.14 | 79984.92 | 78972.22 | 245238.58 | 56919.31 | 53944.06 | 150892.9 | 169478.94 | 66705.8 | 701974.85 | 313683.91 | 547765.31 | 178881.67 | 769.41 | 125904.89 | -5526.54 | 4498.49 | 21442.22 | 17321.24 | 33240.16 | -4144.48 | 3490.79 | 5592.93 | 6537458.93
Procurement and Contracts | Labour | 795537.29 | 1155655.41 | 1046146.88 | 2997339.58 |  | 22501.39 | 29924.93 | 57770.04 | 52228.46 | 73751.33 | 61860.31 | 69107.72 | 74506.9 | 86366.19 | 78023.59 | 81385.43 | 108111 | 89850.07 | 106688.27 | 113903.49 | 76796.75 | 98615.23 | 90795.81 | 82083.5 | 99411.95 | 101511.32 | 74961.01 | 92023.74 | 129014.27 | 97513.81 | 89237.17 | 91638.97 | 80125.98 | 85833.1 | 71557.26 | 79411.35 | 82310.18 | 83740.96 | 91150.23 | 109193.01 | 84434.86 | 2997339.58
Procurement and Contracts | Indirect | 437923.51 | 1571580.48 | 1892020.03 | 3901524.02 |  | 22287.82 | 10015.04 | 47227.24 | 38020.43 | 1389.37 | 3687.76 | 23725.49 | 24077.44 | -27961.56 | 4480.53 | 174603.83 | 116370.12 | 291721.56 | 11252.58 | 176863.96 | 325242.34 | 90306.78 | 38481.12 | 28523.28 | 86465.25 | 134380.21 | 113979.99 | 101670.02 | 172693.39 | 121748.78 | 204993.07 | 181874.49 | 172549.49 | 35115.29 | 17510.29 | 31773.15 | 53156.42 | 198543.55 | 109285.28 | 78118.88 | 687351.34 | 3901524.02
Community & Stakeholder | Labour | 814355.51 | 679631.72 | 720254.59 | 2214241.82 |  | 62433.17 | 55346.04 | 67889.9 | 66436.68 | 68382.73 | 59514.03 | 68442.98 | 72668.58 | 66148.89 | 77875.3 | 79184.17 | 70033.04 | 57227.45 | 56752.61 | 48830.11 | 53904.49 | 65058.97 | 56700.08 | 55279.83 | 50851.54 | 61268.07 | 49930.65 | 60268.88 | 63559.04 | 37146.4 | 72330.69 | 23861.14 | 55193.52 | 72309.56 | 60521.56 | 67559.74 | 65239.12 | 67201.04 | 76072.99 | 70136.05 | 52682.78 | 2214241.82
Community & Stakeholder | Indirect | 966774.73 | 671709.11 | 222341.8 | 1860825.64 |  | 47234.42 | 223462.09 | 35503.88 | 80541.49 | 86907.31 | 95877.77 | 9239.98 | 68496 | 94548.08 | 53183.3 | 99528.18 | 72252.23 | 41163.28 | 73082.57 | 72311.81 | 63989.82 | 74818.35 | 69814.6 | 20410.72 | 59716.32 | 70084.85 | 42394.64 | 49167.38 | 34754.77 | 53974.09 | 69529.87 | 19331.65 | -6477.03 | 43202.74 | 11193.91 | -23585.96 | 9012.44 | 27801.15 | 7176.08 | 9621.24 | 1561.62 | 1860825.64
Land & Property | Labour | 359745.45 | 753670.81 | 1157206 | 2270622.26 |  | 0 | 11656.31 | 37703.32 | 25508 | 31464.52 | 26305.33 | 27126.61 | 31952.28 | 35036.92 | 40501.01 | 45965.92 | 46525.23 | 46020.92 | 61777.87 | 58953.66 | 48259.31 | 55070.57 | 39701.56 | 53879.33 | 67609.01 | 65149.66 | 68940.05 | 91654.53 | 96654.34 | 131851.77 | 114539.63 | 123841.46 | 89342.3 | 89558.63 | 76854.95 | 163318 | 17191.77 | 39161.84 | 84820.15 | 74287.76 | 152437.74 | 2270622.26
Land & Property | Indirect | 1716709.74 | 1494865.47 | 1150608.41 | 4362183.62 |  | 218351 | 199016.62 | 323958.67 | 179318.37 | 72616.57 | 106356.13 | 81307.28 | 82688.39 | 66578.02 | 97537.28 | 143920.3 | 145061.11 | 107062.11 | 76162.75 | 423037.82 | 230197.46 | 227771.69 | 144076.8 | 38387.16 | 121917.6 | 72924.73 | 21688.67 | 24167.94 | 7470.74 | 52589.03 | 75468.34 | 13617.48 | 101417.67 | 30552.48 | 66065.63 | 41035.94 | 100417.58 | 48571.15 | 218506.21 | 269037.77 | 133329.13 | 4362183.62
Planning & Environment | Labour | 224990.55 | 412097.53 | 386655.3 | 1023743.38 |  | -1.9895e-13 | -3046.01 | 22401.24 | 22268.34 | 24142.25 | 19601.67 | 29842.08 | 19145.4 | 20942.15 | 21917.84 | 22218.95 | 25556.64 | 26090.1 | 34287.64 | 24604.78 | 19924.01 | 26075.79 | 29771.85 | 36902.97 | 44731.3 | 45086.6 | 44839.06 | 43997.87 | 35785.56 | 60524.54 | 57954.3 | 76044.71 | 56276.36 | 28333.69 | 27795.23 | 24777.81 | 10633.4 | 15580.15 | 23840.25 | -10126.17 | 15021.03 | 1023743.38
Planning & Environment | Indirect | 3496264.96 | 4557695.24 | 1761271.34 | 9815231.54 |  | 322382.77 | 255135.94 | -181076.12 | 268883.17 | 276506.12 | 69972.36 | 415137.47 | 276590.64 | 253797.06 | 662970.71 | 374597.74 | 501367.1 | 481054.78 | 738073.56 | 351918.37 | 316053.29 | 362955 | 409763.59 | 384310.08 | 504082.24 | 306612.35 | 306288.73 | 146944.43 | 249638.82 | 310229.96 | 147309.8 | 222931.27 | 125846.1 | 139194.66 | 135247.98 | 115960.52 | 32901.97 | 179722.33 | -79828.04 | 173913.75 | 257841.04 | 9815231.54
Regulatory Approvals and other support | Labour | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Regulatory Approvals and other support | Indirect | 0 | 0 | 295782.05 | 295782.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32680 | 157523 | 91861.52 | 7128.03 | 1152 | 5437.5 | 295782.05

## SAP Consolidated
Coded WBS Element | Coded WBS Description | Labour vs indirect | Stream | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30
|  | Indirect | Project Management
|  | Labour | Project Management
|  | Indirect | Project Development
|  | Labour | Project Development
|  | Indirect | Project Management
|  | Labour | Project Management
|  | Indirect | Procurement and Contracts
|  | Labour | Procurement and Contracts
|  | Indirect | Procurement and Contracts
|  | Labour | Procurement and Contracts
|  | Indirect | Project Management
|  | Indirect | Project Management
|  | Labour | Project Management
|  | Labour | Project Management
|  | Indirect | Procurement and Contracts
|  | Labour | Procurement and Contracts
|  | Indirect | Planning & Environment
|  | Labour | Planning & Environment
|  | Indirect | Community & Stakeholder
|  | Labour | Community & Stakeholder
|  | Indirect | Land & Property
|  | Labour | Land & Property
|  | Indirect | Land & Property
|  | Labour | Land & Property
|  | Indirect | Land & Property
|  | Indirect | Land & Property
|  | Indirect | Land & Property
|  | Indirect | Land & Property
|  | Indirect | Project Management
|  | Indirect | Procurement and Contracts
|  | Indirect | Procurement and Contracts
|  | Indirect | Procurement and Contracts
|  | Indirect | Regulatory Approvals and other support
|  | Indirect | Procurement and Contracts
|  | Indirect | Planning & Environment
|  | Indirect | Planning & Environment
|  | Indirect | Planning & Environment
|  | Indirect | Planning & Environment
|  | Labour | Planning & Environment
|  | Indirect | Planning & Environment
|  | Indirect | Land & Property
|  | Labour | Land & Property
|  | Indirect | Land & Property
|  | Labour | Land & Property
|  | Indirect | Land & Property
|  | Indirect | Land & Property
|  | Indirect | Land & Property
|  | Indirect | Procurement and Contracts
|  | Labour | Procurement and Contracts
|  | Indirect | Community & Stakeholder
|  | Labour | Community & Stakeholder
|  | Indirect | Project Management
|  | Indirect | Project Management
|  | Labour | Project Management
|  | Indirect | Project Management
|  | Labour | Project Management
|  | Indirect | Project Management
|  | Labour | Project Management
|  | Indirect | Project Management
|  | Labour | Project Management
|  | Indirect | Project Management
|  | Indirect | Project Management
|  | Labour | Project Management
|  | Indirect | Project Development
|  | Labour | Project Development
|  | Indirect | Project Development
|  | Labour | Project Development
|  | Indirect | Project Development
|  | Labour | Project Development