## Total Forecast
All values in $2024
|  | 2023-24 | 2024-25 | 2025-26 | Sub-total | Total
Community and Stakeholder | Labour | 0 | 760037.398 | 475917.6943 | 1235955.0923 | 2293719.0923 | TRUE
| Indirect | 0 | 634658.4 | 423105.6 | 1057764
| Direct | 0 | 0 | 0 | 0
Land & Property | Labour | 0 | 1307753.3112 | 748662.4178 | 2056415.729 | 9542658.159 | TRUE
| Indirect | 0 | 4593280.958 | 2892961.472 | 7486242.43
| Direct | 0 | 0 | 0 | 0
Planning & Enviroment | Labour | 0 | 642084.9095 | 396964.8487 | 1039049.7582 | 3597635.8682 | TRUE
| Indirect | 0 | 2225085.0525 | 333501.0575 | 2558586.11
| Direct | 0 | 0 | 0 | 0
Procurement and Contracts | Labour | 0 | 1561090.2933 | 862617.2624 | 2423707.5557 | 4654450.0557 | TRUE
| Indirect | 0 | 2136144.1 | 94598.4 | 2230742.5
| Direct | 0 | 0 | 0 | 0
Project Developemnt | Labour | 0 | 1277647.6498 | 937412.6998 | 2215060.3496 | 83006739.3159 | 1
| Indirect | 0 | 1499928.398 | 167830.932 | 1667759.33
| Direct | 0 | 41273166.9674 | 37850752.6688 | 79123919.6363
Project Management | Labour | 0 | 3615387.7039 | 2681866.1371 | 6297253.841 | 10214840.2747 | TRUE
| Indirect | 0 | 2622091.1893 | 1295495.2443 | 3917586.4337
| Direct | 0 | 0 | 0 | 0
Regulatory Approvals and other support | Labour | 0 | 0 | 0 | 0 | 628417.95 | TRUE
| Indirect | 0 | 588417.95 | 40000 | 628417.95
| Direct | 0 | 0 | 0 | 0
| Total | 0 | 64736774.281 | 49201686.4347 | 113938460.7157 | 113938460.7157

## Community and Stakeholder
Labour
| Value | Actual spend to June 30 | Nett Forecast | Artefact
Labour | 1235955.09 | 0 | 1235955.09
Total | 1235955.09 | 0 | 1235955.09
Indirect
Supplier | Value | Actual spend to June 30 | Nett Forecast | Artefact
Total | 1057764 | 0 | 1057764

## Land and Property
Labour
| Value | Actual spend to June 30 | Nett Forecast | Artefact
Labour | 2056415.73 | 0 | 2056415.73
Total | 2056415.73 | 0 | 2056415.73
Indirect Costs
Supplier | Value | Actual spend to June 30 | Nett Forecast | Artefact
Total | 7495447.35 | 9204.92 | 7486242.43

## Planning and Environment
Labour
| Value | Actual spend to June 30 | Nett Forecast | Artefact
Labour | 1039049.76 | 0 | 1039049.76
Total | 1039049.76 | 0 | 1039049.76
Indirect
Supplier | Value | Actual spend to June 30 | Nett Forecast | Artefact
Total | 2827075.75 | 268489.64 | 2558586.11

## Procurement and Contracts
Labour
| Value | Actual spend to June 30 | Nett Forecast | Artefact
Labour | 2423707.56 | 0 | 2423707.56
Total | 2423707.56 | 0 | 2423707.56
Indirect Costs
Supplier | Value | Actual spend to June 30 | Nett Forecast | Artefact
Total | 2416026 | 185283.5 | 2230742.5

## Project Development
Labour
| Value | Actual spend to June 30 | Nett Forecast | Artefact
Labour | 2215060.35 | 0 | 2215060.35
Total | 2215060.35 | 0 | 2215060.35
Indirect
Supplier | Value | Actual spend to June 30 | Nett Forecast | Artefact
Total | 1667759.33 | 0 | 1667759.33
Direct
Supplier | Value | Actual spend to June 30 | Nett Forecast | Artefact
Total | 79123919.6363 | 0 | 79123919.64

## Project Management
Labour
| Value | Actual spend to June 30 | Nett Forecast | Artefact
Labour | 6297253.84 | 0 | 6297253.84
Total | 6297253.84 | 0 | 6297253.84
Indirect Costs
Supplier | Value | Actual spend to June 30 | Nett Forecast | Artefact
Total | 3939207.4337 | 21621 | 3917586.43

## Regulatory Approvals
Labour
| Value | Actual spend to June 30 | Nett Forecast | Artefact
Labour | 0 | 0 | 0
Total | 0 | 0 | 0
Indirect
Supplier | Value | Actual spend to June 30 | Nett Forecast | Artefact
Total | 924200 | 295782.05 | 628417.95