## RIN Requirement
Responsible Person | Reference | Requirement | Response / Cross reference to material provided by Energex
| 4.4 | Capital expenditure
Transparency
| 4.4.4 | For total capital expenditure incurred in the current regulatory period, provide:
| 4.4.4(a) | a comparison of the total expenditure, disaggregated by expenditure or driver, to the forecast capex allowed for the current regulatory period;
| 4.4.4(b) | an explanation of the drivers of differences noted in response to section 4.4.4 (a), for example the impact of efficiency gains, major new projects, project deferrals or rescoping, changing regulatory obligations, asset age, or other factors;
| 4.4.4(c) | a list of projects deferred in the current regulatory control period and included in the forecast capex for the forthcoming regulatory control period, and the rationale for the deferral. | New Bells Creek Zone Substation (refer Attachment 5.5.02) was proposed as part of the 2020-2025 regulatory proposal and was deferred by approximately two years. This deferral was the result of a reduction in new housing being constructed at the start of the Covid pandemic, with housing development only recently reaching levels forecast at the time of the last proposal. Despite this deferral, this project commenced in the 2020-2025 regulatory control period. However, part of this project's expenditure will now fall within the 2025-2030 regulatory control period.
| 4.4.5 | For forecast capex for the forthcoming regulatory period, provide:
| 4.4.5(a) | a comparison of the total forecast expenditure by category or driver to the total capital expenditure expected to be incurred in the current regulatory period;
| 4.4.5(b) | an explanation of the drivers of differences noted in response to section 4.4.5 (a), for example the impact of expected efficiency gains, major new projects, project deferrals or rescoping, changing regulatory obligations, asset age, or other factors.

## Summary of Comparison
4.4.4(a) and (b) Comparison of Current Period Capital Expenditure to AER Allowance (2020-25)
$m, real 2024-25 | 2020-25 AER Allowance | 2020-25 Actuals / Forecast | Difference to Allowance |  | Driver of Difference
Replacement | 757.3966 | 921.9859 | 164.5893 | 21.73% | We are projecting to spend greater than the AER’s repex capital forecast for the current regulatory control period by $165 million. The main drivers for our increased spend are as follows: • the identification of a larger than expected number of conductor clearance issues in the last two years of the 2015-20 regulatory control period, resulting in non-critical work being deferred to the current regulatory control period and increased expenditure against forecast for repex in 2020-21 and 2021-22 • an increase in pole-top structure defects and failures, resulting in increased expenditure above our forecasts at the time of the 2020-25 Regulatory Proposal, and • above inflation increases in construction costs, particularly civil construction costs, impacting our repex, particulary in the final two years of this regulatory control period.
Augmentation | 356.1766 | 376.8638 | 20.6872 | 5.808% | We are projecting to spend at the level of the AER’s augex forecast for the current regulatory control period. Early in this period, we were able to maintain an historically low level of expenditure through increasing the utilisation of our existing assets to meet the growth in customers and load. However, we are forecasting an increase in 2024-25 due to two large projects commencing this financial year, namely: • establishing Bells Creek Central zone substation to supply the growing area of Caloundra South, and • establishing Petrie zone substation to meet growing demand in the Moreton Bay area and address network limitations in the Kallangur and Lawnton areas.
Connections (net) | 250.5018 | 284.243 | 33.7412 | 13.47% | We are projecting to spend greater than the AER’s connex forecast for the current regulatory control period by $33.7 million. The main drivers for our increased spend are: • the unanticipated impact of Covid-19 on migration in South East Queensland and the associated increase in new connections, and • our 2020-25 investment proposals were completed on the back of a construction boom (prior to the Covid-19 pandemic) when a slowdown in construction was anticipated for the 2020-25 period. However, the construction sector proved to be more resilient than anticipated.
Non-network ICT | 175.5967 | 352.0739 | 176.4772 | 100.5% | We are projecting to spend greater than the AER's non-network ICT forecast due to: • high costs associated with replacing a significant, interdependent legacy application portfolio, and • unplanned investment in cyber security in response to new compliance obligations and heightened risk of cyber attacks.
Other Non-Network | 220.1322 | 267.1155 | 46.9832 | 21.34% | We are projecting to spend greater than the AER's other non-network forecast due to increased property expenditure driven by increased costs associated with general industry and market conditions as well as the timing of investments due to project phasing and contractor availability.
Capitalised overheads | 672.7921 | 721.8068 | 49.0147 | 7.285% | We are projecting to spend greater than the AER's capitalised overhead forecast due to a higher program of work and higher than forecast inflationary environment.
Total Net Capex | 2432.596 | 2924.0888 | 491.4928 | 20.2%
4.4.5(a) and (b) Comparison of Forecast Period Capital Expenditure (2025-30) to Current Period Capital Expenditure (2020-25)
$m, real 2024-25 | 2020-25 Actuals / Forecast | 2025-30 Forecast | Difference to Current Period |  | Driver of Difference
Replacement | 921.9859 | 912.7932 | -9.1927 | -0.9971% | Our proposed repex is in line with current period spend with a continuation of our program of work to replace or refurbish network assets that are ageing and/or in poor condition.
Augmentation | 376.8638 | 617.8143 | 240.9506 | 63.94% | Our proposed augex is greater than our current period expenditure and the increase is driven by: • strong population and demand growth in South East Queensland • the need to address the obligations outlined in our Distribution Authority pertaining to Safety Net security criteria, Minimum Service Standards and worst performing feeder requirements, and • increased expenditure to integrate distributed energy resources into the network.
Connections (net) | 284.243 | 320.5533 | 36.3103 | 12.77% | Our proposed increase in connections expenditure above our current period expenditure reflects the expected strong population growth in South East Queensland due to greater migration, smaller household sizes, increasing construction expenditure forecasts and a growing economy.
Non-network ICT | 352.0739 | 243.2503 | -108.8236 | -30.91% | Our proposed reduced investment reflects a shift from a major transformation focus to one of on-going maintenance of non-network ICT systems and capability.
Other non-network | 267.1155 | 350.0168 | 82.9013 | 31.04% | Our proposed increase in other non-network expenditure is driven by increased investment in fleet to replace ageing vehicles that were unable to be replaced in the current period due to market supply challenges.
Capitalised overheads | 721.8068 | 720.3081 | -1.4987 | -0.2076% | The forecast for capitalised overheads is in line with our current period spend.
Total Net Capex | 2924.0888 | 3164.736 | 240.6472 | 8.23%