## RIN Requirement
Responsible Person | Reference | Requirement | Response / Cross reference to material provided by Ergon Energy
| 4.4 | Capital expenditure
Transparency
| 4.4.4 | For total capital expenditure incurred in the current regulatory period, provide:
| 4.4.4(a) | a comparison of the total expenditure, disaggregated by expenditure or driver, to the forecast capex allowed for the current regulatory period;
| 4.4.4(b) | an explanation of the drivers of differences noted in response to section 4.4.4 (a), for example the impact of efficiency gains, major new projects, project deferrals or rescoping, changing regulatory obligations, asset age, or other factors;
| 4.4.4(c) | a list of projects deferred in the current regulatory control period and included in the forecast capex for the forthcoming regulatory control period, and the rationale for the deferral. | No major projects were deferred from the current regulatory control period into the forthcoming period. Some minor projects, such as the Cloncurry supply reinforcement, have been moved between periods as a result of project prioritisation across our portfolio of work.
| 4.4.5 | For forecast capex for the forthcoming regulatory period, provide:
| 4.4.5(a) | a comparison of the total forecast expenditure by category or driver to the total capital expenditure expected to be incurred in the current regulatory period;
| 4.4.5(b) | an explanation of the drivers of differences noted in response to section 4.4.5 (a), for example the impact of expected efficiency gains, major new projects, project deferrals or rescoping, changing regulatory obligations, asset age, or other factors.

## Summary of Comparison
4.4.4(a) and (b) Comparison of Current Period Capital Expenditure to AER Allowance (2020-25)
$m, real 2024-25 | 2020-25 AER Allowance | 2020-25 Actuals / Forecast | Difference to Allowance |  | Driver of Difference
Replacement | 1074.4371 | 2550.0687 | 1475.6315 | 137.3% | We are projecting to spend greater than the AER’s repex forecast for the current regulatory control period by $1,476 million. The main drivers for our increased spend over the 2020-25 regulatory control period are: • the identification of a larger than expected number of defective poles requiring replacement due to a change to our pole serviceability calculation in response to an increasing number of in-service pole failures (as required by Queensland’s Electrical Safety Code of Practice 2020 – Works) • a consequential increase in the need to replace transformers, cross-arms, overhead switches, and service cables associated with pole replacements, resulting in most of our distribution line asset categories being above the AER’s forecast (although bundling of these works ensures our program is delivered efficiently and avoids the need to return to the same site to replace assets that fail subsequently), and • an increase in our reconductoring program to address the safety and reliability risks of an increase in unassisted conductor failure, in particular copper conductor.
Augmentation | 254.8072 | 378.6261 | 123.8188 | 48.59% | We are projecting to spend greater than the AER's augex forecast due to increased expenditure on overhead lines clearance to ground and clearance to structure to comply with our legislative obligation under Queensland's Electrical Safety Act 2002.
Connections (net) | 249.6962 | 368.1734 | 118.4773 | 47.45% | We are projecting to spend greater than the AER’s connex forecast for the current regulatory control period by $119 million. The main drivers for our increased spend are: • the unanticipated impact of Covid-19 on migration in regional Queensland and the associated increase in new connections, and • our 2020-25 investment proposals were completed on the back of a construction boom (prior to the Covid-19 pandemic) when a slowdown in construction was anticipated for the 2020-25 period. However, the construction sector proved to be more resilient than anticipated.
Non-network ICT | 195.9624 | 357.1737 | 161.2113 | 82.27% | We are projecting to spend greater than the AER's non-network ICT forecast due to: • high costs associated with replacing a significant, interdependent legacy application portfolio, and • unplanned investment in cyber security in response to new compliance obligations and heightened risk of cyber attacks.
Other Non-Network | 259.9457 | 410.7344 | 150.7887 | 58.01% | We are projecting to spend greater than the AER's other non-network forecast due to increased property expenditure driven by increased costs associated with general industry and market conditions as well as the timing of investments due to project phasing and contractor availability.
Capitalised overheads | 736.36 | 1066.5369 | 330.1769 | 44.84% | We are projecting to spend greater than the AER's capitalised overhead forecast due to a higher program of work and higher than forecast inflationary environment.
Total Net Capex | 2771.2087 | 5131.3131 | 2360.1044 | 85.17%
4.4.5(a) and (b) Comparison of Forecast Period Capital Expenditure (2025-30) to Current Period Capital Expenditure (2020-25)
$m, real 2024-25 | 2020-25 Actuals / Forecast | 2025-30 Forecast | Difference to Current Period |  | Driver of Difference
Replacement | 2550.0687 | 2285.0144 | -265.0543 | -10.39% | Our proposed repex is marginally lower than our current period repex. Repex remains the most signficant part of our investment plans and is a continuation of our existing asset management practices. It represents a balance of condition and risk, and reactive programs to provide a prudent means of achieving the asset management objectives.
Augmentation | 378.6261 | 751.5659 | 372.9398 | 98.5% | Our proposed augex is greater than our current period expenditure. This increase is driven by: • strong population and demand growth in regional Queensland • the need to address the obligations outlined in our Distribution Authority pertaining to Safety Net security criteria, Minimum Service Standards and worst performing feeder requirements, and • increased expenditure to integrate distributed energy resources into the network.
Connections (net) | 368.1734 | 321.2887 | -46.8847 | -12.73% | While we are still forecasting strong population growth, we expect the connections expenditure to be mariginally lower than the last three years of the current regulatory period. The current period spend is higher than forecast due to the construction boom resutling from post-Covid-19 migration and property investment. Consequently, the forecast expenditute for 2025-30 is lower than the current 2020-25 period expenditure.
Non-network ICT | 357.1737 | 261.7287 | -95.4449 | -26.72% | Our proposed reduced investment reflects a shift from a major transformation focus to one of on-going maintenance of non-network ICT systems and capability.
Other non-network | 410.7344 | 424.1198 | 13.3855 | 3.259% | The forecast for other non-network capex is in line with our current period spend.
Capitalised overheads | 1066.5369 | 1009.6775 | -56.8595 | -5.331% | The forecast for capitalised overheads is in line with our current period spend.
Total Net Capex | 5131.3131 | 5053.395 | -77.9181 | -1.518%