## Cover
United Energy
Regulatory proposal 2026-31
#NAME?
Model number: | #NAME?
2025-01-31

## Summary
United Energy
Infrastructure refresh risk
SUMMARY
RESULTS
|  |  |  | PV of total costs | PV of incremental costs | PV of incremental benefits | NPV
| Option |  |  | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-06-30
| Option 1 (base case) | Maintain status quo |  | -15.1093 | 0 | 0 | 0
| Option 2 | Maintain existing infrastructure with more frequent upgrades |  | -26.8129 | -11.7037 | 72.9406 | 61.237
| Option 3 | Criteria-based IT infrastructure refresh |  | -32.6258 | -17.5165 | 88.8741 | 71.3576
| Option 4 | Public cloud infrastructure refresh |  | -38.5374 | -23.4281 | 87.5135 | 64.0854
NPV
| Preferred option: |  | 2026-06-30
| Option 3 | Criteria-based IT infrastructure refresh | 71.3576
PREFERRED OPTION
Preferred Option
Option 3
| Expenditure forecast | 2026-06-30 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 |  | Total
| Capital expenditure |  | 10.7545 | 8.7207 | 7.8626 | 0.99899 | 1.0323 |  | 29.3691
| Operating expenditure |  | 1.3405 | 2.3272 | 2.4789 | 1.7141 | 2.0206 |  | 9.8814
CHART
OPTION DATA
Select category for table:
Incremental Capital expenditure
| Incremental Capital expenditure | 2026-06-30 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 |  | Total
| Option 1 (base case) | Maintain status quo | 8.3408 | 3.0793 | 4.3469 | 2.0086 | 2.0086 |  | 19.7842
| Option 2 | Maintain existing infrastructure with more frequent upgrades | 3.101 | 3.1926 | 4.2796 | 4.4699 | 1.9919 |  | 17.0349
| Option 3 | Criteria-based IT infrastructure refresh | 2.4138 | 5.6414 | 3.5157 | -1.0096 | -0.97634 |  | 9.5849
| Option 4 | Public cloud infrastructure refresh | 1.085 | 1.0664 | -2.5702 | -1.4578 | -1.3687 |  | -3.2453
End |  |  | . | . | . | . | . | . | .

## Assumptions
United Energy
Infrastructure refresh risk
Project
| Business: | select > | United Energy
| Descripton: |  | Infrastructure refresh risk
| Date of cost inputs: | select > | June | 2024
| Option |  | Description
| Option 1 (base case) |  | Maintain status quo
| Option 2 |  | Maintain existing infrastructure with more frequent upgrades
| Option 3 |  | Criteria-based IT infrastructure refresh
| Option 4 |  | Public cloud infrastructure refresh
Timing & WACC
| Input dollars |  |  | 2024-06-30 | [input_dollars]
| Pre-tax real WACC |  |  | 3.5% | [real_disc]
| Model start year |  |  | 2025-26 | [start]
| Analysis period (years) |  |  | 5 | [years]\
| Output dollars |  |  | 2026-06-30 | [output_dollars]
| Other benefits date |  |  | 2024-06-30 | [custval_date]

## Option1 (base case)
United Energy
Infrastructure refresh risk
OPTION 1 (base case)
Count |  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  |  | Units | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | 2037-38 | 2038-39 | 2039-40 | 2040-41 | 2041-42 | 2042-43 | 2043-44 | 2044-45 | 2045-46 | 2046-47 | 2047-48 | 2048-49 | 2049-50 | 2050-51
INVESTMENT & OPERATING COST
| Capex | Asset life (yrs)
| capex | 5 | 2024-06-30 |  | 7782654 | 3079294 | 4346932 | 2008598 | 2008598 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ongoing capex | 5 | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| < Enter description > | 0 | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capital expenditure |  | 2024-06-30 |  | 7782654 | 3079294 | 4346932 | 2008598 | 2008598 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Operating expenditure |  | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RISK ASSUMPTIONS
| Risk escalation | 0%
| Reliability risk |  | 2024-06-30 |  | 2337311.952 | 2337311.952 | 2337311.952 | 2337311.952 | 2337311.952 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Compliance risk |  | 2024-06-30 |  | 772532.9938 | 772532.9938 | 772532.9938 | 772532.9938 | 772532.9938 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bushfire risk |  | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Safety risk |  | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Customer experience risk |  | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Outage risk |  | 2024-06-30 |  | 18575933.1075 | 18575933.1075 | 18575933.1075 | 18575933.1075 | 18575933.1075 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Suitability and system sustainability |  | 2024-06-30 |  | 3152046.4131 | 3152046.4131 | 3152046.4131 | 3152046.4131 | 3152046.4131 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total risk cost |  |  |  | 24837824.4664 | 24837824.4664 | 24837824.4664 | 24837824.4664 | 24837824.4664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BENEFITS
| Total risk reductions |  | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Billing productivity benefits |  | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SAP productivity benefits |  | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Opex reduction |  | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total other benefits |  | 2024-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUMMARY
| Risks mitigated vs base case |  | 2024-06-30
Capital expenditure
| capex |  | 2024-06-30 | 1 2026-27: -7782654; 2 2027-28: -3079294; 3 2028-29: -4346932; 4 2029-30: -2008598; 5 2030-31: -2008598
| ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0
| < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0
Cumulative capex
| capex |  | 2024-06-30 | 1 2026-27: -7782654; 2 2027-28: -10861948; 3 2028-29: -15208880; 4 2029-30: -17217478; 5 2030-31: -19226076
| ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0
| < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0
Annualised capex
| Annualised capex - capex |  | 2024-06-30 | 1 2026-27: -1723712.8947; 2 2027-28: -2405719.1582; 3 2028-29: -3368483.6266; 4 2029-30: -3813350.6698; 5 2030-31: -4258217.7129
| Annualised capex - ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0
| Annualised capex - < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0
| Total annualised capex |  | 2024-06-30 | 1 2026-27: -1723712.8947; 2 2027-28: -2405719.1582; 3 2028-29: -3368483.6266; 4 2029-30: -3813350.6698; 5 2030-31: -4258217.7129
| Annualised capex |  | 2024-06-30 | 1 2026-27: -1723712.8947; 2 2027-28: -2405719.1582; 3 2028-29: -3368483.6266; 4 2029-30: -3813350.6698; 5 2030-31: -4258217.7129
| Operating expenditure |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0
| Risk mitigated |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0
| Other benefits value |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0
| Net benefits |  | 2024-06-30 | 1 2026-27: -1723712.8947; 2 2027-28: -2405719.1582; 3 2028-29: -3368483.6266; 4 2029-30: -3813350.6698; 5 2030-31: -4258217.7129

## Option2
United Energy
Infrastructure refresh risk
OPTION 2 | Maintain existing infrastructure with more frequent upgrades
Count |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  |  | Units | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | 2037-38 | 2038-39 | 2039-40 | 2040-41 | 2041-42 | 2042-43 | 2043-44 | 2044-45 | 2045-46 | 2046-47 | 2047-48 | 2048-49 | 2049-50 | 2050-51
INVESTMENT & OPERATING COST
| Capex | Asset life (yrs)
| capex | 5 | 2024-06-30 | 10676148 | 6058223 | 8340179 | 6179345 | 3867174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ongoing capex | 5 | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| < Enter description > | 0 | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capital expenditure |  | 2024-06-30 | 10676148 | 6058223 | 8340179 | 6179345 | 3867174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Operating expenditure |  | 2024-06-30 | -1367236.95 | -395086.925 | 458269.975 | 1266246.375 | 1698276.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RISKS
| Risk escalation | 0%
| Reliability risk |  | 2024-06-30 | 2337311.952 | 2337311.952 | 2337311.952 | 2337311.952 | 2337311.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Compliance risk |  | 2024-06-30 | 309013.1975 | 309013.1975 | 309013.1975 | 309013.1975 | 309013.1975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bushfire risk |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Safety risk |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Customer experience risk |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Outage risk |  | 2024-06-30 | 6191977.7025 | 6191977.7025 | 6191977.7025 | 6191977.7025 | 6191977.7025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Suitability and system sustainability |  | 2024-06-30 | 1182623.4853 | 1182623.4853 | 1182623.4853 | 1182623.4853 | 1182623.4853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total risk |  | 2024-06-30 | 10020926.3373 | 10020926.3373 | 10020926.3373 | 10020926.3373 | 10020926.3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BENEFITS
| Total risk reductions (vs base case) |  | 2024-06-30 | 14816898.1291 | 14816898.1291 | 14816898.1291 | 14816898.1291 | 14816898.1291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Billing productivity benefits |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SAP productivity benefits |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Opex reduction |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total other benefits |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUMMARY
| Risks mitigated vs base case |  | 2024-06-30 | 1 2026-27: -14816898.1291; 2 2027-28: -14816898.1291; 3 2028-29: -14816898.1291; 4 2029-30: -14816898.1291; 5 2030-31: -14816898.1291; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
Capital expenditure
| Incremental capex |  | 2024-06-30 | 1 2026-27: -2893494; 2 2027-28: -2978929; 3 2028-29: -3993247; 4 2029-30: -4170747; 5 2030-31: -1858576; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
Cumulative capex
| Incremental capex |  | 2024-06-30 | 1 2026-27: -2893494; 2 2027-28: -5872423; 3 2028-29: -9865670; 4 2029-30: -14036417; 5 2030-31: -15894993; 6 2031-32: -13001499; 7 2032-33: -10022570; 8 2033-34: -6029323; 9 2034-35: -1858576; 10 2035-36: 0
| ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
Annualised capex
| Annualised capex - Incremental capex |  | 2024-06-30 | 1 2026-27: -640855.0243; 2 2027-28: -1300632.3098; 3 2028-29: -2185062.1387; 4 2029-30: -3108804.9114; 5 2030-31: -3520444.876; 6 2031-32: -2879589.8516; 7 2032-33: -2219812.5662; 8 2033-34: -1335382.7373; 9 2034-35: -411639.9646; 10 2035-36: 0
| Annualised capex - ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Annualised capex - < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Total annualised capex |  | 2024-06-30 | 1 2026-27: -640855.0243; 2 2027-28: -1300632.3098; 3 2028-29: -2185062.1387; 4 2029-30: -3108804.9114; 5 2030-31: -3520444.876; 6 2031-32: -2879589.8516; 7 2032-33: -2219812.5662; 8 2033-34: -1335382.7373; 9 2034-35: -411639.9646; 10 2035-36: 0
| Annualised Incremental capex |  | 2024-06-30 | 1 2026-27: -640855.0243; 2 2027-28: -1300632.3098; 3 2028-29: -2185062.1387; 4 2029-30: -3108804.9114; 5 2030-31: -3520444.876; 6 2031-32: -2879589.8516; 7 2032-33: -2219812.5662; 8 2033-34: -1335382.7373; 9 2034-35: -411639.9646; 10 2035-36: 0
| Incremental operating expenditure |  | 2024-06-30 | 1 2026-27: 1367236.95; 2 2027-28: 395086.925; 3 2028-29: -458269.975; 4 2029-30: -1266246.375; 5 2030-31: -1698276.875; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Risk mitigated |  | 2024-06-30 | 1 2026-27: 14816898.1291; 2 2027-28: 14816898.1291; 3 2028-29: 14816898.1291; 4 2029-30: 14816898.1291; 5 2030-31: 14816898.1291; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Other benefits value |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Net benefits |  | 2024-06-30 | 1 2026-27: 15543280.0548; 2 2027-28: 13911352.7443; 3 2028-29: 12173566.0154; 4 2029-30: 10441846.8427; 5 2030-31: 9598176.3781; 6 2031-32: -2879589.8516; 7 2032-33: -2219812.5662; 8 2033-34: -1335382.7373; 9 2034-35: -411639.9646; 10 2035-36: 0
| First capex year |  | 1
| First opex year |  | 1
| First year |  | 1

## Option3
United Energy
Infrastructure refresh risk
OPTION 3 | Criteria-based IT infrastructure refresh
Count |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  |  | Units | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | 2037-38 | 2038-39 | 2039-40 | 2040-41 | 2041-42 | 2042-43 | 2043-44 | 2044-45 | 2045-46 | 2046-47 | 2047-48 | 2048-49 | 2049-50 | 2050-51
INVESTMENT & OPERATING COST
| Capex | Asset life (yrs)
| capex | 5 | 2024-06-30 | 10034897 | 8343171 | 7627377 | 1066547 | 1097589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ongoing capex | 5 | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| < Enter description > | 0 | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capital expenditure |  | 2024-06-30 | 10034897 | 8343171 | 7627377 | 1066547 | 1097589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Operating expenditure |  | 2024-06-30 | 1250839.406 | 2171495.3398 | 2312987.5467 | 1599430.303 | 1885397.1746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RISKS
| Risk escalation | 0%
| Reliability risk |  | 2024-06-30 | 467462.3904 | 467462.3904 | 467462.3904 | 467462.3904 | 467462.3904 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Compliance risk |  | 2024-06-30 | 298006.5988 | 298006.5988 | 298006.5988 | 298006.5988 | 298006.5988 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bushfire risk |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Safety risk |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Customer experience risk |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Outage risk |  | 2024-06-30 | 5651977.7025 | 5651977.7025 | 5651977.7025 | 5651977.7025 | 5651977.7025 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Suitability and system sustainability |  | 2024-06-30 | 366809.2826 | 366809.2826 | 366809.2826 | 366809.2826 | 366809.2826 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total risk |  | 2024-06-30 | 6784255.9743 | 6784255.9743 | 6784255.9743 | 6784255.9743 | 6784255.9743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BENEFITS
| Total risk reductions (vs base case) |  | 2024-06-30 | 18053568.4921 | 18053568.4921 | 18053568.4921 | 18053568.4921 | 18053568.4921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Billing productivity benefits |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SAP productivity benefits |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Opex reduction |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total other benefits |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUMMARY
| Risks mitigated vs base case |  | 2024-06-30 | 1 2026-27: -18053568.4921; 2 2027-28: -18053568.4921; 3 2028-29: -18053568.4921; 4 2029-30: -18053568.4921; 5 2030-31: -18053568.4921; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
Capital expenditure
| Incremental capex |  | 2024-06-30 | 1 2026-27: -2252243; 2 2027-28: -5263877; 3 2028-29: -3280445; 4 2029-30: 942051; 5 2030-31: 911009; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
Cumulative capex
| Incremental capex |  | 2024-06-30 | 1 2026-27: -2252243; 2 2027-28: -7516120; 3 2028-29: -10796565; 4 2029-30: -9854514; 5 2030-31: -8943505; 6 2031-32: -6691262; 7 2032-33: -1427385; 8 2033-34: 1853060; 9 2034-35: 911009; 10 2035-36: 0
| ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
Annualised capex
| Annualised capex - Incremental capex |  | 2024-06-30 | 1 2026-27: -498829.8723; 2 2027-28: -1664680.5784; 3 2028-29: -2391238.0416; 4 2029-30: -2182591.2925; 5 2030-31: -1980819.7682; 6 2031-32: -1481989.8959; 7 2032-33: -316139.1898; 8 2033-34: 410418.2733; 9 2034-35: 201771.5243; 10 2035-36: 0
| Annualised capex - ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Annualised capex - < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Total annualised capex |  | 2024-06-30 | 1 2026-27: -498829.8723; 2 2027-28: -1664680.5784; 3 2028-29: -2391238.0416; 4 2029-30: -2182591.2925; 5 2030-31: -1980819.7682; 6 2031-32: -1481989.8959; 7 2032-33: -316139.1898; 8 2033-34: 410418.2733; 9 2034-35: 201771.5243; 10 2035-36: 0
| Annualised Incremental capex |  | 2024-06-30 | 1 2026-27: -498829.8723; 2 2027-28: -1664680.5784; 3 2028-29: -2391238.0416; 4 2029-30: -2182591.2925; 5 2030-31: -1980819.7682; 6 2031-32: -1481989.8959; 7 2032-33: -316139.1898; 8 2033-34: 410418.2733; 9 2034-35: 201771.5243; 10 2035-36: 0
| Incremental operating expenditure |  | 2024-06-30 | 1 2026-27: -1250839.406; 2 2027-28: -2171495.3398; 3 2028-29: -2312987.5467; 4 2029-30: -1599430.303; 5 2030-31: -1885397.1746; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Risk mitigated |  | 2024-06-30 | 1 2026-27: 18053568.4921; 2 2027-28: 18053568.4921; 3 2028-29: 18053568.4921; 4 2029-30: 18053568.4921; 5 2030-31: 18053568.4921; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Other benefits value |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Net benefits |  | 2024-06-30 | 1 2026-27: 16303899.2138; 2 2027-28: 14217392.5739; 3 2028-29: 13349342.9039; 4 2029-30: 14271546.8967; 5 2030-31: 14187351.5493; 6 2031-32: -1481989.8959; 7 2032-33: -316139.1898; 8 2033-34: 410418.2733; 9 2034-35: 201771.5243; 10 2035-36: 0
| First capex year |  | 1
| First opex year |  | 1
| First year |  | 1

## Option4
United Energy
Infrastructure refresh risk
OPTION 4 | Public cloud infrastructure refresh
Count |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  |  | Units | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | 2037-38 | 2038-39 | 2039-40 | 2040-41 | 2041-42 | 2042-43 | 2043-44 | 2044-45 | 2045-46 | 2046-47 | 2047-48 | 2048-49 | 2049-50 | 2050-51
INVESTMENT & OPERATING COST
| Capex | Asset life (yrs)
| capex | 5 | 2024-06-30 | 8795042 | 4074311 | 1948696 | 648390 | 731457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ongoing capex | 5 | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| < Enter description > | 0 | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capital expenditure |  | 2024-06-30 | 8795042 | 4074311 | 1948696 | 648390 | 731457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Operating expenditure |  | 2024-06-30 | 4279381.3525 | 5067170.3783 | 4516979.1135 | 5041550.3218 | 5349647.6883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RISKS
| Risk escalation | 0%
| Reliability risk |  | 2024-06-30 | 1 2026-27: 467462.3904; 2 2027-28: 467462.3904; 3 2028-29: 467462.3904; 4 2029-30: 467462.3904; 5 2030-31: 467462.3904; 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| Compliance risk |  | 2024-06-30 | 1 2026-27: 745016.4969; 2 2027-28: 745016.4969; 3 2028-29: 745016.4969; 4 2029-30: 745016.4969; 5 2030-31: 745016.4969; 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| Bushfire risk |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| Safety risk |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| Customer experience risk |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| Outage risk |  | 2024-06-30 | 1 2026-27: 5651977.7025; 2 2027-28: 5651977.7025; 3 2028-29: 5651977.7025; 4 2029-30: 5651977.7025; 5 2030-31: 5651977.7025; 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| Suitability and system sustainability |  | 2024-06-30 | 1 2026-27: 196184.5856; 2 2027-28: 196184.5856; 3 2028-29: 196184.5856; 4 2029-30: 196184.5856; 5 2030-31: 196184.5856; 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| Total risk |  | 2024-06-30 | 7060641.1754 | 7060641.1754 | 7060641.1754 | 7060641.1754 | 7060641.1754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BENEFITS
| Total risk reductions (vs base case) |  | 2024-06-30 | 17777183.291 | 17777183.291 | 17777183.291 | 17777183.291 | 17777183.291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Billing productivity benefits |  | 2024-06-30 | 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| SAP productivity benefits |  | 2024-06-30 | 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| Opex reduction |  | 2024-06-30 | 21 2046-47: 0; 22 2047-48: 0; 23 2048-49: 0; 24 2049-50: 0; 25 2050-51: 0
| Total other benefits |  | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUMMARY
| Risks mitigated vs base case |  | 2024-06-30 | 1 2026-27: -17777183.291; 2 2027-28: -17777183.291; 3 2028-29: -17777183.291; 4 2029-30: -17777183.291; 5 2030-31: -17777183.291; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
Capital expenditure
| Incremental capex |  | 2024-06-30 | 1 2026-27: -1012388; 2 2027-28: -995017; 3 2028-29: 2398236; 4 2029-30: 1360208; 5 2030-31: 1277141; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
Cumulative capex
| Incremental capex |  | 2024-06-30 | 1 2026-27: -1012388; 2 2027-28: -2007405; 3 2028-29: 390831; 4 2029-30: 1751039; 5 2030-31: 3028180; 6 2031-32: 4040568; 7 2032-33: 5035585; 8 2033-34: 2637349; 9 2034-35: 1277141; 10 2035-36: 0
| ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
Annualised capex
| Annualised capex - Incremental capex |  | 2024-06-30 | 1 2026-27: -224225.0844; 2 2027-28: -444602.8159; 3 2028-29: 86561.7866; 4 2029-30: 387822.5222; 5 2030-31: 670685.4646; 6 2031-32: 894910.549; 7 2032-33: 1115288.2805; 8 2033-34: 584123.678; 9 2034-35: 282862.9424; 10 2035-36: 0
| Annualised capex - ongoing capex |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Annualised capex - < Enter description > |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Total annualised capex |  | 2024-06-30 | 1 2026-27: -224225.0844; 2 2027-28: -444602.8159; 3 2028-29: 86561.7866; 4 2029-30: 387822.5222; 5 2030-31: 670685.4646; 6 2031-32: 894910.549; 7 2032-33: 1115288.2805; 8 2033-34: 584123.678; 9 2034-35: 282862.9424; 10 2035-36: 0
| Annualised Incremental capex |  | 2024-06-30 | 1 2026-27: -224225.0844; 2 2027-28: -444602.8159; 3 2028-29: 86561.7866; 4 2029-30: 387822.5222; 5 2030-31: 670685.4646; 6 2031-32: 894910.549; 7 2032-33: 1115288.2805; 8 2033-34: 584123.678; 9 2034-35: 282862.9424; 10 2035-36: 0
| Incremental operating expenditure |  | 2024-06-30 | 1 2026-27: -4279381.3525; 2 2027-28: -5067170.3783; 3 2028-29: -4516979.1135; 4 2029-30: -5041550.3218; 5 2030-31: -5349647.6883; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Risk mitigated |  | 2024-06-30 | 1 2026-27: 17777183.291; 2 2027-28: 17777183.291; 3 2028-29: 17777183.291; 4 2029-30: 17777183.291; 5 2030-31: 17777183.291; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Other benefits value |  | 2024-06-30 | 1 2026-27: 0; 2 2027-28: 0; 3 2028-29: 0; 4 2029-30: 0; 5 2030-31: 0; 6 2031-32: 0; 7 2032-33: 0; 8 2033-34: 0; 9 2034-35: 0; 10 2035-36: 0
| Net benefits |  | 2024-06-30 | 1 2026-27: 13273576.8541; 2 2027-28: 12265410.0969; 3 2028-29: 13346765.9641; 4 2029-30: 13123455.4914; 5 2030-31: 13098221.0673; 6 2031-32: 894910.549; 7 2032-33: 1115288.2805; 8 2033-34: 584123.678; 9 2034-35: 282862.9424; 10 2035-36: 0
| First capex year |  | 1
| First opex year |  | 1
| First year |  | 1

## Consol
United Energy
Infrastructure refresh risk
CONSOLIDATED
Discount factor |  |  |  |  | 1 | 0.98295 | 0.94971 | 0.91759 | 0.88656 | 0.85658 | 0.82761 | 0.79963 | 0.77259 | 0.74646 | 0.72122 | 0.69683 | 0.67326 | 0.6505 | 0.6285 | 0.60725 | 0.58671 | 0.56687 | 0.5477 | 0.52918 | 0.51129 | 0.494 | 0.47729 | 0.46115 | 0.44556 | 0.43049
Count |  |  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Analysis period |  |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[5 empty] | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | 2037-38 | 2038-39 | 2039-40 | 2040-41 | 2041-42 | 2042-43 | 2043-44 | 2044-45 | 2045-46 | 2046-47 | 2047-48 | 2048-49 | 2049-50 | 2050-51
COSTS |  |  | PV
Option 1 (base case) | Incremental capital expenditure | Option 1 (base case)Incremental capital expenditure | -18612949.9547 | 2026-06-30 |  | -8340787.0316 | -3079294 | -4346932 | -2008598 | -2008598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 1 (base case) | Total risk cost | Option 1 (base case)Total risk cost | 122271666.1584 | 2026-06-30 |  | 26619069.048 | 26619069.048 | 26619069.048 | 26619069.048 | 26619069.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 1 (base case) |  | Option 1 (base case)
Option 1 (base case) | Annualised Incremental capex | Option 1 (base case)Annualised Incremental capex | -15109265.6926 | 2026-06-30 |  | -1847328.965 | -2578245.3076 | -3610054.4299 | -4086825.113 | -4563595.7962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 1 (base case) | Incremental operating expenditure | Option 1 (base case)Incremental operating expenditure | 0 | 2026-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 1 (base case) | Risk mitigated | Option 1 (base case)Risk mitigated | 0 | 2026-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 1 (base case) | Other benefits value | Option 1 (base case)Other benefits value | 0 | 2026-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 1 (base case) | Net benefits | Option 1 (base case)Net benefits |  | 2026-06-30 |  | -1847328.965 | -2578245.3076 | -3610054.4299 | -4086825.113 | -4563595.7962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 1 (base case) | NPV | Option 1 (base case)NPV | -15109265.6926 | 2026-06-30
Option 1 (base case) | PV of incremental costs | Option 1 (base case)PV of incremental costs | -15109265.6926 | 2026-06-30
Option 1 (base case) | PV of incremental benefits | Option 1 (base case)PV of incremental benefits | 0 | 2026-06-30
Option 2 | Incremental capital expenditure | Option 2Incremental capital expenditure | -15676049.4864 | 2026-06-30 |  | -3101000.9222 | -3192562.8932 | -4279622.7086 | -4469852.1211 | -1991863.7778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 | Total risk cost | Option 2Total risk cost | 49331025.8058 | 2026-06-30 |  | 10739577.0696 | 10739577.0696 | 10739577.0696 | 10739577.0696 | 10739577.0696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 |  | Option 2
Option 2 | Annualised Incremental capex | Option 2Annualised Incremental capex | -10333294.702 | 2026-06-30 |  | -686813.9424 | -1393907.1559 | -2341763.87 | -3331752.8556 | -3772913.5803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 | Incremental operating expenditure | Option 2Incremental operating expenditure | -1370384.6309 | 2026-06-30 |  | 1465288.3479 | 423420.5838 | -491134.8063 | -1357055.2338 | -1820068.8011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 | Risk mitigated | Option 2Risk mitigated | 72940640.3526 | 2026-06-30 |  | 15879491.9784 | 15879491.9784 | 15879491.9784 | 15879491.9784 | 15879491.9784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 | Other benefits value | Option 2Other benefits value | 0 | 2026-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 | Net benefits | Option 2Net benefits |  | 2026-06-30 |  | 16657966.3839 | 14909005.4064 | 13046593.3022 | 11190683.8891 | 10286509.5971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 | NPV | Option 2NPV | 61236961.0197 | 2026-06-30
Option 2 | PV of incremental costs | Option 2PV of incremental costs | -11703679.3329 | 2026-06-30
Option 2 | PV of incremental benefits | Option 2PV of incremental benefits | 72940640.3526 | 2026-06-30
Option 3 | Incremental capital expenditure | Option 3Incremental capital expenditure | -9224830.5458 | 2026-06-30 |  | -2413762.6067 | -5641375.9391 | -3515702.1132 | 1009610.1875 | 976342.0104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 3 | Total risk cost | Option 3Total risk cost | 33397541.8315 | 2026-06-30 |  | 7270788.8915 | 7270788.8915 | 7270788.8915 | 7270788.8915 | 7270788.8915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 3
Option 3 | Annualised Incremental capex | Option 3Annualised Incremental capex | -8463540.3654 | 2026-06-30 |  | -534603.4566 | -1784063.1461 | -2562725.6777 | -2339115.8271 | -2122874.2579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 3 | Incremental operating expenditure | Option 3Incremental operating expenditure | -9052944.2752 | 2026-06-30 |  | -1340543.354 | -2327224.1281 | -2478863.4486 | -1714133.4471 | -2020608.433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 3 | Risk mitigated | Option 3Risk mitigated | 88874124.3269 | 2026-06-30 |  | 19348280.1565 | 19348280.1565 | 19348280.1565 | 19348280.1565 | 19348280.1565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 3 | Other benefits value | Option 3Other benefits value | 0 | 2026-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 3 | Net benefits | Option 3Net benefits |  | 2026-06-30 |  | 17473133.3459 | 15236992.8823 | 14306691.0302 | 15295030.8823 | 15204797.4656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 3 | NPV | Option 3NPV | 71357639.6862 | 2026-06-30
Option 3 | PV of incremental costs | Option 3PV of incremental costs | -17516484.6407 | 2026-06-30
Option 3 | PV of incremental benefits | Option 3PV of incremental benefits | 88874124.3269 | 2026-06-30
Option 4 | Incremental capital expenditure | Option 4Incremental capital expenditure | 2744002.773 | 2026-06-30 |  | -1084991.4054 | -1066374.6442 | 2570225.4947 | 1457755.3167 | 1368731.1668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 4 | Total risk cost | Option 4Total risk cost | 34758131.1651 | 2026-06-30 |  | 7566995.0573 | 7566995.0573 | 7566995.0573 | 7566995.0573 | 7566995.0573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 4 |  | Option 4
Option 4 | Annualised Incremental capex | Option 4Annualised Incremental capex | 380576.3784 | 2026-06-30 |  | -240305.3863 | -476487.5068 | 92769.5651 | 415635.2144 | 718783.6727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 4 | Incremental operating expenditure | Option 4Incremental operating expenditure | -23808702.654 | 2026-06-30 |  | -4586277.1862 | -5430562.502 | -4840914.2706 | -5403105.1031 | -5733297.6723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 4 | Risk mitigated | Option 4Risk mitigated | 87513534.9933 | 2026-06-30 |  | 19052073.9908 | 19052073.9908 | 19052073.9908 | 19052073.9908 | 19052073.9908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 4 | Other benefits value | Option 4Other benefits value | 0 | 2026-06-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 4 | Net benefits | Option 4Net benefits |  | 2026-06-30 |  | 14225491.4182 | 13145023.982 | 14303929.2852 | 14064604.102 | 14037559.9911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 4 | NPV | Option 4NPV | 64085408.7177 | 2026-06-30
Option 4 | PV of incremental costs | Option 4PV of incremental costs | -23428126.2756 | 2026-06-30
Option 4 | PV of incremental benefits | Option 4PV of incremental benefits | 87513534.9933 | 2026-06-30
CHART DATA | [5 empty] | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34 | FY35 | FY36 | FY37 | FY38 | FY39 | FY40 | FY41 | FY42 | FY43 | FY44 | FY45 | FY46 | FY47 | FY48 | FY49 | FY50 | FY51
Option 3 | capex | -1 |  |  | Option 3 capex | 2.3819 | 4.3623 | 6.1728 | 6.4259 | 6.6865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 1 (base case) | Total risk cost | 1 |  |  | Option 1 (base case) risk cost | 26.6191 | 26.6191 | 26.6191 | 26.6191 | 26.6191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Cost summary
United Energy
Infrastructure refresh risk
COST SUMMARY
Unitd Energy
CAPEX
|  |  | Total | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31
| Option 1 - Maintain status quo | $ real 2024 | 19226076 | 7782654 | 3079294 | 4346932 | 2008598 | 2008598
| Option 2 - Maintain existing infrastructure with more frequent upgrades | $ real 2024 | 35121069 | 10676148 | 6058223 | 8340179 | 6179345 | 3867174
| Option 3 - Criteria-based IT infrastructure refresh | $ real 2024 | 28169581 | 10034897 | 8343171 | 7627377 | 1066547 | 1097589
| Option 4 - Public cloud infrastructure refresh | $ real 2024 | 16197896 | 8795042 | 4074311 | 1948696 | 648390 | 731457
OPEX
|  |  | Total | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31
| Option 1 - Maintain status quo | $ real 2024 | 0 | 0 | 0 | 0 | 0 | 0
| Option 2 - Maintain existing infrastructure with more frequent upgrades | $ real 2024 | 1660469.35 | -1367236.95 | -395086.925 | 458269.975 | 1266246.375 | 1698276.875
| Option 3 - Criteria-based IT infrastructure refresh | $ real 2024 | 9220149.7701 | 1250839.406 | 2171495.3398 | 2312987.5467 | 1599430.303 | 1885397.1746
| Option 4 - Public cloud infrastructure refresh | $ real 2024 | 24254728.8544 | 4279381.3525 | 5067170.3783 | 4516979.1135 | 5041550.3218 | 5349647.6883

## Risk summary
United Energy
Infrastructure refresh risk
RISK SUMMARY
Annual risks
Total risk
|  | Business risks |  |  | Maintain status quo | Upgrade as is, more often | Infrastructure refresh | Infrastructure refresh (outsourced)
|  | Reliability | BR1 | Customer loss of supply due to cyber attack
|  |  | BR2 | Customer loss of supply due to system failure
|  |  | BR3 | Customer loss of export capability due to system failure | 9488.3671 | 9488.3671 | 1897.6734 | 1897.6734
|  |  | BR4 | Customer loss of export capability due to cyber attack
|  |  | BR5 | Supply restoration time impacted by system failure | 2327823.5849 | 2327823.5849 | 465564.717 | 465564.717
|  |  | BR6 | Supply restoration time impacted by cyber attack
|  | Compliance | BC1 | Delays in publishing key data to the market due to system failure | 772532.9938 | 309013.1975 | 298006.5988 | 745016.4969
|  |  | BC2 | Delays in publishing key data to the market due to cyber attack
|  |  | BC3 | Unauthorised access to employee personal data due to reasons other than a cyber attack
|  |  | BC4 | Unauthorised access to employee personal data due to cyber attack
|  |  | BC5 | Unauthorised access to customer data due to reasons other than a cyber attack
|  |  | BC6 | Unauthorised access to customer data due to cyber attack
|  |  | BC7 | System fault causes failure to notify life-support customers of an outage
|  |  | BC8 | Cyber attack causes failure to notify life-support customers of an outage
|  | Bushfire | BF1 | Systems outage impacts bushfire preparation / mitigation program
|  |  | BF2 | Cyber attack causes systems outage impacting bushfire preparation / mitigation program
|  | Safety | BS1 | Systems outage causes loss of supply to life-support customers
|  |  | BS2 | Cyber attack causes systems outage impacting life-support customers
|  |  | BS3 | Cyber attack prevents correct operation of network protection systems, causing elevated safety risk, e.g. failure to de-energise a downed line or re-energising a line that should be de-energised for maintenance
|  | Customer experience risks | BCX1 | Customers impacted by failure of customer-facing system due to software or hardware fault
|  |  | BCX2 | Customers impacted by failure of customer-facing system due to cyber attack
IT risks
|  | Outage | ITO1 | System failure | 18575933.1075 | 6191977.7025 | 5651977.7025 | 5651977.7025
|  |  | ITO2 | System down due to cyber attack
|  |  | ITO3 | System down due to cyber attack - critical OT systems (ADMS, etc)
|  |  | ITS1 | Increased change management costs
|  | Suitability and system sustainability | ITS2 | Data storage exceeded | 1573598.8851 | 393399.7213 | 51119.777 | 38339.8328
|  |  | ITS3 | Performance degradation | 1578447.528 | 789223.764 | 315689.5056 | 157844.7528
|  |  | ITS4 | Increased maintenance costs
|  |  | ITS4 | Increased maintenance costs
Other benefits
Other benefits
|  |  |  | Annual total risk | 24837824.4664 | 10020926.3373 | 6784255.9743 | 7060641.1754

## General risk inputs
United Energy
Infrastructure refresh risk
General inputs
| Inputs | Unit | Input value | Source/notes
| VCR | $/kWh | 42.86 | We have used a weighted average of the Victorian residential VCR and the VCR for distribution-connected commercial and industrial customers, as published annually by the AER, weighted according to the UE customer mix.
| CECV | $/kWh | 0.022 | The AER publishes the CECV for Victoria annually in the form of a table of 30-minute $/kWh value forecasts for the following 20 years. For risk quantification, use an average of all 30-minute values for the relevant year, multiplied by two to produce an average hourly value.
| Average hourly rate for internal employees | $/hr | 145.78 | Average hourly rate for internal employees
| Civil penalty under Privacy Act | $ | 50000000 | Maximum penalty per s13G of the Privacy Act 1988
| Average customer kWh per hour | kWh/hr | 1.21 | Based on forecast customer numbers and energy consumption
| AEMO penalty | $ | 1435000 | Per section 2AB(b)(ii)(A) of the National Electricity Law.
| Additional AEMO penalty for every day the breach continues | $/day | 71800 | Per section 2AB(b)(ii)(B) of the National Electricity Law.
| IT specialist / vendor hourly rate (restoration) | $/hr | 225 | Based on $1,800 daily rate of external IT specialists
| Average solar customer export kWh per hour | kWh/hr | 0.60502 | Average customer exports of 5,300 kWh, equating to 0.605 kWh per hour.
| Total number of customers | number | 780700 | Total forecast customer numbers in 2031.
| Total number of employees | number | 1289 | Employees = 386 Contractors = 903
| Total number of solar customers | number | 263500 | Solar customer forecast in 2031.
| Likely system downtime (storage) | hours | 12.1448 | Average system downtime based on critical incidents used as a proxy for downtime for storage incidents.
| Likely system downtime (performance degradation) | hours | 2.6667 | Average system downtime based on critical LAN incidents used as a proxy for downtime for performance degradation.
| Increase in supply restoration time if coinciding with system outage | hours | 3 | Based on past experience if system is not working at the same time as outage, this would cost an additional 3 hours of time.
| Customers connected to LV DERMS | number | 111700 | Solar customer connected to DERMS forecast in 2031.
| Average number of outages per hour | number | 0.77287 | See calculation A below.
Calculation A
|  | Unit | Best case | Source
SAIFI
| SAIFI (UE) - Urban | number | 0.69 | As per targets published on website
| SAIFI (UE) - Short rural | number | 1.92
Number of customers
| Number of customers (UE) - Urban | number | 650772.0899 | Scaled to match total customer figures.
| Number of customers (UE) - Short rural | number | 62331.9101 | Provided by Tim via email on 2/7/24
| Number of individual customer interruptions | number | 568710.0094
| Average customers impacted per outage | number | 84 | customer-days offline.
| Number of outages per annum | number | 6770.3573
| Average number of outages per hour | number | 0.77287
General inputs - other
| Inputs | Unit | Best case | Most Likely | Worst Case
| Likely number of customers affected per outage | number | 1 | 84 | 8148
| Likely system downtime (total) | hours | 2.6667 | 12.1448 | 24.9233
Likelihoods
| Likelihood Per Event | Bound | Likelihood | Occurrence
|  | Years | #
| Monthly | 0.083333 | 12 | Risk occurs once per month
| Annual | 1 | 1 | Risk occurs once per year
| Every 2 years | 2 | 0.5 | Risk occurs once every 2 years
| Every 5 years | 5 | 0.2 | Risk occurs once every 5 years
| Every 10 years | 10 | 0.1 | Risk occurs once every 10 years
| Every 20 years | 20 | 0.05 | Risk occurs once every 20 years

## Benefit BR3
United Energy
Infrastructure refresh risk
Customer loss of export capability due to system failure
Option 1 (base case) - Maintain status quo
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Likelihood of system failure | number | 12 |  |  | Based on incident data
| Likelihood of system failure resulting in customer loss of export | number | 0.5 |  |  | A system failure per the incident data may not necessarily result in customer loss of export capability. Based on incident data, 8 'critical' infrastructure incidents occur per year. It is assumed that only 5% of these incidents will relate to customer loss of export capability. This equates to approximately one incident occurring every two years.
| Likely system downtime | hours | 2.6667 | 12.1448 | 24.9233 | General input
| Number of solar customers on DERMS | number | 111700 | 111700 | 111700 | General input
| Average solar customer export kWh per hour | kWh/hr | 0.60502 | 0.60502 | 0.60502 | General input
| CECV | $/kWh | 0.022 | 0.022 | 0.022 | General input
Option 2 - Maintain existing infrastructure with more frequent upgrades
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Likelihood of system failure | number | 12 |  |  | More frequent upgrade of systems is likely to decrease the likelihood of system failure. However, this decrease in likelihood will not be significant. Therefore, the likelihood of Option 2 is the same as Option 1.
| Likelihood of system failure resulting in customer loss of export | number | 0.5
| Likely system downtime | hours | 2.6667 | 12.1448 | 24.9233 | General input
| Number of solar customers on DERMS | number | 111700 | 111700 | 111700 | General input
| Average solar customer export kWh per hour | kWh/hr | 0.60502 | 0.60502 | 0.60502 | General input
| CECV | $/kWh | 0.022 | 0.022 | 0.022 | General input
Option 3 - Criteria-based IT infrastructure refresh
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Likelihood of system failure | number | 0.5 |  |  | Likelihood reduced when compared to Option 1 due to bulk upgrade of hardware.
| Likelihood of system failure resulting in customer loss of export | number | 0.1
| Likely system downtime | hours | 2.6667 | 12.1448 | 24.9233 | General input
| Number of solar customers on DERMS | number | 111700 | 111700 | 111700 | General input
| Average solar customer export kWh per hour | kWh/hr | 0.60502 | 0.60502 | 0.60502 | General input
| CECV | $/kWh | 0.022 | 0.022 | 0.022 | General input
Option 4 - Public cloud infrastructure refresh
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Likelihood of system failure | number | 0.5 |  |  | Likelihood reduced when compared to Option 1 due to upgraded infrastructure. Likelihood remains that same as Option 3 as all OT systems remain on-premises.
| Likelihood of system failure resulting in customer loss of export | number | 0.1
| Likely system downtime | hours | 2.6667 | 12.1448 | 24.9233 | General input
| Number of solar customers on DERMS | number | 111700 | 111700 | 111700 | General input
| Average solar customer export kWh per hour | kWh/hr | 0.60502 | 0.60502 | 0.60502 | General input
| CECV | $/kWh | 0.022 | 0.022 | 0.022 | General input
Summary
Likelihood
| Option | Likelihood value | Likelihood category
| Option 1 | 0.5 | Every 2 years
| Option 2 | 0.5 | Every 2 years
| Option 3 | 0.1 | Every 10 years
| Option 4 | 0.1 | Every 10 years
Consequence
| Option | Class | Best case | Most likely | Worst Case
| Option 1 |  | 3964.7549 | 18056.6711 | 37055.5909
| Option 2 |  | 3964.7549 | 18056.6711 | 37055.5909
| Option 3 |  | 3964.7549 | 18056.6711 | 37055.5909
| Option 4 |  | 3964.7549 | 18056.6711 | 37055.5909
Monetised risk
| Option | Applied consequence (per annum) | Monetised risk
| Option 1 | 18976.7343 | 9488.3671
| Option 2 | 18976.7343 | 9488.3671
| Option 3 | 18976.7343 | 1897.6734
| Option 4 | 18976.7343 | 1897.6734
Risk benefit
| Option | Risk benefit
| Option 1 | n/a
| Option 2 | 0
| Option 3 | 7590.6937
| Option 4 | 7590.6937

## Benefit BR5
United Energy
Infrastructure refresh risk
Supply restoration time impacted by system failure
Option 1 (base case) - Maintain status quo
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Likelihood of system failure | number | 12 |  |  | Based on incident data
| Likelihood of system failure resulting in impacts to supply restoration | number | 0.5 |  |  | A system failure per the incident data may not necessarily result in customer loss of supply. Based on incident data, 8 'critical' infrastructure incidents occur per year. It is assumed that only 5% of these incidents will relate to customer loss of supply. This equates to approximately one incident occurring every two years.
| Increase in supply restoration time | hours | 3 | 3 | 3 | General input
| Likely system downtime | number | 2.6667 | 12.1448 | 24.9233 | Based on incident data
| Average number of outages per hour | number | 0.77287 | 0.77287 | 0.77287 | General input
| Outages occurring during system downtime per incident per annum | number | 2.061 | 9.3864 | 19.2625 | Calculation
| Number of customers impacted in an outage | number | 1 | 84 | 8148 | General input
| Total number of customers impacted in outages occurring during system downtime | number | 2.061 | 788.4549 | 156951.1948 | Calculation
| Average customer kWh per hour | number | 1.21 | 1.21 | 1.21 | General input
| VCR | $/kWh | 42.86 | 42.86 | 42.86 | General input
| Number of solar customers impacted | number | 0.69562 | 266.1174 | 52973.7925 | Proportion of customers impacted applied to solar customers.
| Average solar customer export kWh per hour | kWh/hr | 0.60502 | 0.60502 | 0.60502 | General input
| CECV | $/kWh | 0.022 | 0.022 | 0.022 | General input
Option 2 - Maintain existing infrastructure with more frequent upgrades
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Likelihood of system failure | number | 12 |  |  | Based on incident data
| Likelihood of system failure resulting in impacts to supply restoration | number | 0.5 |  |  | More frequent upgrade of systems is likely to decrease the likelihood of system failure. However, this decrease in likelihood will not be significant. Therefore, the likliehood of Option 2 is the same as Option 1.
| Increase in supply restoration time | hours | 3 | 3 | 3 | General input
| Likely system downtime | number | 2.6667 | 12.1448 | 24.9233 | Based on incident data
| Average number of outages per hour | number | 0.77287 | 0.77287 | 0.77287 | General input
| Outages occurring during system downtime per incident per annum | number | 2.061 | 9.3864 | 19.2625 | Calculation
| Number of customers impacted in an outage | number | 1 | 84 | 8148 | General input
| Total number of customers impacted in outages occurring during system downtime | number | 2.061 | 788.4549 | 156951.1948 | Calculation
| Average customer kWh per hour | number | 1.21 | 1.21 | 1.21 | General input
| VCR | $/kWh | 42.86 | 42.86 | 42.86 | General input
| Number of solar customers impacted | number | 0.69562 | 266.1174 | 52973.7925 | Proportion of customers impacted applied to solar customers.
| Average solar customer export kWh per hour | kWh/hr | 0.60502 | 0.60502 | 0.60502 | General input
| CECV | $/kWh | 0.022 | 0.022 | 0.022 | General input
Option 3 - Criteria-based IT infrastructure refresh
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Likelihood of system failure | number | 1 |  |  | Likelihood reduced when compared to Option 1 due to bulk upgrade of hardware.
| Likelihood of system failure resulting in impacts to supply restoration | number | 0.1
| Increase in supply restoration time | hours | 3 | 3 | 3 | General input
| Likely system downtime | number | 2.6667 | 12.1448 | 24.9233 | Based on incident data
| Average number of outages per hour | number | 0.77287 | 0.77287 | 0.77287 | General input
| Outages occurring during system downtime per incident per annum | number | 2.061 | 9.3864 | 19.2625 | Calculation
| Number of customers impacted in an outage | number | 1 | 84 | 8148 | General input
| Total number of customers impacted in outages occurring during system downtime | number | 2.061 | 788.4549 | 156951.1948 | Calculation
| Average customer kWh per hour | number | 1.21 | 1.21 | 1.21 | General input
| VCR | $/kWh | 42.86 | 42.86 | 42.86 | General input
| Number of solar customers impacted | number | 0.69562 | 266.1174 | 52973.7925 | Proportion of customers impacted applied to solar customers.
| Average solar customer export kWh per hour | kWh/hr | 0.60502 | 0.60502 | 0.60502 | General input
| CECV | $/kWh | 0.022 | 0.022 | 0.022 | General input
Option 4 - Public cloud infrastructure refresh
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Likelihood of system failure | number | 1 |  |  | Likelihood reduced when compared to Option 1 due to upgraded infrastructure. Likelihood remains that same as Option 3 as all OT systems remain on-premises.
| Likelihood of system failure resulting in impacts to supply restoration | number | 0.1
| Increase in supply restoration time | hours | 3 | 3 | 3 | General input
| Likely system downtime | number | 2.6667 | 12.1448 | 24.9233 | Based on incident data
| Average number of outages per hour | number | 0.77287 | 0.77287 | 0.77287 | General input
| Outages occurring during system downtime per incident per annum | number | 2.061 | 9.3864 | 19.2625 | Calculation
| Number of customers impacted in an outage | number | 1 | 84 | 8148 | General input
| Total number of customers impacted in outages occurring during system downtime | number | 2.061 | 788.4549 | 156951.1948 | Calculation
| Average customer kWh per hour | number | 1.21 | 1.21 | 1.21 | General input
| VCR | $/kWh | 42.86 | 42.86 | 42.86 | General input
| Number of solar customers impacted | number | 0.69562 | 266.1174 | 52973.7925 | Proportion of customers impacted applied to solar customers.
| Average solar customer export kWh per hour | kWh/hr | 0.60502 | 0.60502 | 0.60502 | General input
| CECV | $/kWh | 0.022 | 0.022 | 0.022 | General input
Summary
Likelihood
| Option | Likelihood value | Likelihood category
| Option 1 | 0.5 | Every 2 years
| Option 2 | 0.5 | Every 2 years
| Option 3 | 0.1 | Every 10 years
| Option 4 | 0.1 | Every 10 years
Consequence
| Consequence | Class | Best case | Most likely | Worst Case
| Option 1 |  | 320.6806 | 122679.853 | 24420864.7148
| Option 2 |  | 320.6806 | 122679.853 | 24420864.7148
| Option 3 |  | 320.6806 | 122679.853 | 24420864.7148
| Option 4 |  | 320.6806 | 122679.853 | 24420864.7148
Monetised risk
| Consequence | Applied consequence (per annum) | Monetised risk
| Option 1 | 4655647.1697 | 2327823.5849
| Option 2 | 4655647.1697 | 2327823.5849
| Option 3 | 4655647.1697 | 465564.717
| Option 4 | 4655647.1697 | 465564.717
Risk benefit
| Option | Risk benefit
| Option 1 | n/a
| Option 2 | 0
| Option 3 | 1862258.8679
| Option 4 | 1862258.8679

## Benefit BC1
United Energy
Infrastructure refresh risk
Delays in publishing key data to the market due to system failure
Option 1 (base case) - Maintain status quo
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Forecast frequency of software or hardware failure impacting market system | number | 0.5 | 1 | 1 | A system failure per the incident data may not necessarily result in delays in publishing key data to market. There are also alternatives available for publishing this data. Based on incident data, 8 'critical' infrastructure incidents occur per annum. It is assumed that only 5% of these incidents will result in delays. This equates to approximately one incident occurring every two years.
| Base civil penalty | $ | 1435000 | 1435000 | 1435000 | Based on penalties outlined in the NEL.
| Daily civil penalty | $ | 71800 | 71800 | 71800
| Number of additional days breach continues | days | 0 | 1.5181 | 3.1154 | Best case assumes that the breach does not continue for any additional days. The most likely and worst case is modelled based on incident data (taking the average incident duration and max incident duration respectively).
| AEMO expected penalty | $ | 1435000 | 1543999.5052 | 1658686.9167 | Calculation
Option 2 - Maintain existing infrastructure with more frequent upgrades
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Forecast frequency of software or hardware failure impacting market system | number | 0.2 | 1 | 1 | More frequent upgrade of systems is likely to decrease the likelihood of system failure. Therefore, assumed a lower likelihood when compared to Option 1.
| Base civil penalty | $ | 1435000 | 1435000 | 1435000 | Based on penalties outlined in the NEL.
| Daily civil penalty | $ | 71800 | 71800 | 71800
| Number of additional days breach continues | days | 0 | 1.5181 | 3.1154 | Best case assumes that the breach does not continue for any additional days. The most likely and worst case is modelled based on incident data (taking the average incident duration and max incident duration respectively).
| AEMO expected penalty | $ | 1435000 | 1543999.5052 | 1658686.9167 | Calculation
Option 3 - Criteria-based IT infrastructure refresh
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Forecast frequency of software or hardware failure impacting market system | number | 0.2 |  |  | Likelihood reduced when compared to Option 1 due to bulk upgrade of hardware.
| Base civil penalty | $ | 1435000 | 1435000 | 1435000 | Based on penalties outlined in the NEL.
| Daily civil penalty | $ | 71800 | 71800 | 71800
| Number of additional days breach continues | days | 0 | 0.75905 | 1.5577 | Upgrade to more modern technology will result in a a reduction in additional days a breach continues as there is more segmentation and security in new technology. A 50% reduction in additional days breach continues (based on Option 1) has therefore been applied.
| AEMO expected penalty | $ | 1435000 | 1489499.7526 | 1546843.4583 | Calculation
Option 4 - Public cloud infrastructure refresh
Input value
| Inputs | Unit | Best case | Most Likely | Worst Case | Notes
| Forecast frequency of software or hardware failure impacting market system | number | 0.5 |  |  | Likelihood equal to Option 1 as there is lack of control over this process given that all non-OT applications are outsourced.
| Base civil penalty | $ | 1435000 | 1435000 | 1435000 | Based on penalties outlined in the NEL.
| Daily civil penalty | $ | 71800 | 71800 | 71800
| Number of additional days breach continues | days | 0 | 0.75905 | 1.5577 | Upgrade to more modern technology will result in a a reduction in additional days a breach continues as there is more segmentation and security in new technology. A 50% reduction in additional days breach continues (based on Option 1) has therefore been applied.
| AEMO expected penalty | $ | 1435000 | 1489499.7526 | 1546843.4583 | Calculation
Summary
Likelihood
| Option | Likelihood value | Likelihood category
| Option 1 | 0.5 | Every 2 years
| Option 2 | 0.2 | Every 5 years
| Option 3 | 0.2 | Every 5 years
| Option 4 | 0.5 | Every 2 years
Consequence
| Consequence | Class | Best case | Most likely | Worst Case
| Option 1 |  | 1435000 | 1543999.5052 | 1658686.9167
| Option 2 |  | 1435000 | 1543999.5052 | 1658686.9167
| Option 3 |  | 1435000 | 1489499.7526 | 1546843.4583
| Option 4 |  | 1435000 | 1489499.7526 | 1546843.4583
Monetised risk
| Consequence | Applied consequence (per annum) | Monetised risk
| Option 1 | 1545065.9876 | 772532.9938
| Option 2 | 1545065.9876 | 309013.1975
| Option 3 | 1490032.9938 | 298006.5988
| Option 4 | 1490032.9938 | 745016.4969
Risk benefit
| Option | Risk benefit
| Option 1 | n/a
| Option 2 | 463519.7963
| Option 3 | 474526.3951
| Option 4 | 27516.4969

## Benefit ITO1
United Energy
Infrastructure refresh risk
System failure
Option 1 (base case) - Maintain status quo
| Inputs | Unit | Input value | Notes
| Likelihood of system outage | number | 12 | Per incident data.
| Likely system downtime | hours | 12.1448 | Based on average system downtime per incident data.
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | System failure of IT will have widespread impact on employees. To maintain a conservative approach, it has been assumed that 70% of all employees will be impacted.
| Impacted employees requiring immediate access to IT infrastructure | % | 80% | Not all employees will require immediate access to IT applications supported by IT infrastructure. Therefore a further 20% reduction has been applied.
| Number of users affected | number | 721.84 | Calculation
| Average hourly rate for internal employees | $/hr | 145.78 | General input
| Number of IT specialists required to rectify | number | 30 | Based on previous experience, it is estimated that 30 FTE will be required to perform a system refresh.
| Hours to rectify | hours | 40 | Based on previous experience, it is estimated that each IT specialist will require 5 working days to rectify a system issue.
| IT specialist / vendor hourly rate (restoration) | $/hr | 225 | General input
| Rectification fixed costs | $ | 0 | No fixed rectification costs.
Option 2 - Maintain existing infrastructure with more frequent upgrades
| Inputs | Unit | Input value | Notes
| Likelihood of system outage | number | 4 | Lower likelihood of system failure due to more frequent upgrades to the IT infrastructure.
| Likely system downtime | hours | 12.1448 | Based on average system downtime per incident data.
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1.
| Impacted employees requiring immediate access to IT infrastructure | % | 80% | As per explanation in Option 1.
| Number of users affected | number | 721.84 | Calculation
| Average hourly rate for internal employees | $/hr | 145.78 | General input
| Number of IT specialists required to rectify | number | 30 | Based on previous experience, it is estimated that 30 FTE will be required to perform a system refresh.
| Hours to rectify | hours | 40 | Based on previous experience, it is estimated that each IT specialist will require 5 working days to rectify a system issue.
| IT specialist / vendor hourly rate (restoration) | $/hr | 225 | General input
| Rectification fixed costs | $ | 0 | No fixed rectification costs.
Option 3 - Criteria-based IT infrastructure refresh
| Inputs | Unit | Input value | Notes
| Likelihood of system outage | number | 4 | Lower likelihood of system failure due to migration of infrastructure to cloud.
| Likely system downtime | hours | 12.1448 | Based on average system downtime per incident data.
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1.
| Impacted employees requiring immediate access to IT infrastructure | % | 80% | As per explanation in Option 1.
| Number of users affected | number | 721.84 | Calculation
| Average hourly rate for internal employees | $/hr | 145.78 | General input
| Number of IT specialists required to rectify | number | 30 | Based on previous experience, it is estimated that 30 FTE will be required to perform a system refresh.
| Hours to rectify | hours | 20 | Assumed a 50% reduction in the hours required to rectify an IT outage when compared to Option 1 as modern technology infrastructure will require less time to rectify.
| IT specialist / vendor hourly rate (restoration) | $/hr | 225 | General input
| Rectification fixed costs | $ | 0 | No fixed rectification costs.
Option 4 - Public cloud infrastructure refresh
| Inputs | Unit | Input value | Notes
| Likelihood of system outage | number | 4 | Lower likelihood of system failure due to migration of all non-OT infrastructure to cloud.
| Likely system downtime | hours | 12.1448 | Based on average system downtime per incident data.
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1.
| Impacted employees requiring immediate access to IT infrastructure | % | 80% | As per explanation in Option 1.
| Number of users affected | number | 721.84 | Calculation
| Average hourly rate for internal employees | $/hr | 145.78 | General input
| Number of IT specialists required to rectify | number | 30 | Based on previous experience, it is estimated that 30 FTE will be required to perform a system refresh.
| Hours to rectify | hours | 20 | Assumed a 50% reduction in the hours required to rectify an IT outage when compared to Option 1 as modern technology infrastructure will require less time to rectify.
| IT specialist / vendor hourly rate (restoration) | $/hr | 225 | General input
| Rectification fixed costs | $ | 0 | No fixed rectification costs.
Summary
Likelihood
| Option | Likelihood value | Likelihood category
| Option 1 | 12 | Monthly
| Option 2 | 4 | Quarterly
| Option 3 | 4 | Quarterly
| Option 4 | 4 | Quarterly
Consequence
| Consequence | Consequence (per annum)
| Option 1 | 1547994.4256
| Option 2 | 1547994.4256
| Option 3 | 1412994.4256
| Option 4 | 1412994.4256
Monetised risk
| Consequence | Monetised risk
| Option 1 | 18575933.1075
| Option 2 | 6191977.7025
| Option 3 | 5651977.7025
| Option 4 | 5651977.7025
Risk benefit
| Option | Risk benefit
| Option 1 | n/a
| Option 2 | 12383955.405
| Option 3 | 12923955.405
| Option 4 | 12923955.405

## Benefit ITS2
United Energy
Infrastructure refresh risk
Data storage exceeded
Option 1 (base case) - Maintain status quo
| Inputs | Unit | Input value | Notes
| Likelihood that forecast growth in data exceeds available capacity at some point in the 5 year RCP | number | 0.2 | The growing level of data that will come with DSO will likely justify a 1 in 5 year incident.
| Likely system downtime - storage and backup | hours | 12.1448 | Per average system downtime per incident data.
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | Data storage exceeding will have widespread impact on employees. To maintain a conservative approach, it has been assumed that 70% of all employees will be impacted.
| Impacted employees requiring immediate access to data storage | % | 80% | Not all employees will require immediate access to storage. Therefore, it has been assumed that 80% of employees impacted by storage will be immediately impacted.
| Number of users affected | number | 721.84 | Calculation
| Average hourly rate for internal employees - discounted | $/hr | 145.78 | General input
| IT specialist / vendor hourly rate (restoration) | $/hr | 225 | General input
| Number of IT specialists required to rectify | number | 5 | Based on previous experience, it is estimated that 5 FTE will be required to implement new storage requirements.
| Hours to rectify | hours | 80 | Based on previous experience, it is estimated that each IT specialist will require 10 working days to implement new storage requirements.
| Additional data storage capacity cost | $ | 6500000 | Assumes that once VPN/UE run out of storage, as part of the rectification VPN/UE would ensure adequate storage for the rest of the period, which at a minimum would require more than $6.5m per the prior business case.
Option 2 - Maintain existing infrastructure with more frequent upgrades
| Inputs | Unit | Best case | Notes
| Likelihood that forecast growth in data exceeds available capacity at some point in the 5 year RCP | number | 0.05 | It is assumed that the frequent upgrades in Option 2 will ensure that the storage space and systems are right-sized. Therefore, a decreased likelihood is assumed when compared to Option 1.
| Likely system downtime - storage and backup | hours | 12.1448 | Per incident data
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1
| Impacted employees requiring immediate access to data storage | % | 80% | As per explanation in Option 1
| Number of users affected | number | 721.84 | Calculation
| Average hourly rate for internal employees - discounted | $/hr | 145.78 | General input
| IT specialist / vendor hourly rate (restoration) | $/hr | 225 | General input
| Number of IT specialists required to rectify | number | 5 | Based on previous experience, it is estimated that 5 FTE will be required to implement new storage requirements.
| Hours to rectify | hours | 80 | Based on previous experience, it is estimated that each IT specialist will require 10 working days to implement new storage requirements.
| Additional data storage capacity cost | $ | 6500000 | Assumes that once VPN/UE run out of storage, as part of the rectification VPN/UE would ensure adequate storage for the rest of the period, which at a minimum would require more than $6.5m per the prior business case.
Option 3 - Criteria-based IT infrastructure refresh
| Inputs | Unit | Best case | Notes
| Likelihood that forecast growth in data exceeds available capacity at some point in the 5 year RCP | number | 0.05 | Lower likelihood due to bulk upgrade of hardware establishment of scalable IT environments via a hybrid cloud model.
| Likely system downtime - storage and backup | hours | 9.7158 | Lower system downtime as cloud environments are more easily scalable. (20% reduction when compared to Option 1)
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1
| Impacted employees requiring immediate access to data storage | % | 80% | As per explanation in Option 1
| Number of users affected | number | 721.84 | Calculation
| Average hourly rate for internal employees - discounted | $/hr | 145.78 | General input
| IT specialist / vendor hourly rate (restoration) | $/hr | 225 | General input
| Number of IT specialists required to rectify | number | 0 | Assumed that the rectification costs are zero due to scalable IT environment offered through cloud.
| Hours to rectify | hours | 0
| Additional data storage capacity cost | $ | 0
Option 4 - Public cloud infrastructure refresh
| Inputs | Unit | Best case | Notes
| Likelihood that forecast growth in data exceeds available capacity at some point in the 5 year RCP | number | 0.05 | Lower likelihood due to migration of all non-OT applications to public cloud.
| Likely system downtime - storage and backup | hours | 7.2869 | Lowest downtime due to amount of applications on public cloud which will be easily scalable. (40% reduction when compared to Option 1).
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1
| Impacted employees requiring immediate access to data storage | % | 80% | As per explanation in Option 1
| Number of users affected | number | 721.84 | Calculation
| Average hourly rate for internal employees - discounted | $/hr | 145.78 | General input
| IT specialist / vendor hourly rate (restoration) | $/hr | 225 | General input
| Number of IT specialists required to rectify | number | 0 | Assumed that the rectification costs are zero due to scalable IT environment offered through cloud.
| Hours to rectify | hours | 0
| Additional data storage capacity cost | $ | 0
Summary
Likelihood
| Option | Likelihood value | Likelihood category
| Option 1 | 0.2 | Every 5 years
| Option 2 | 0.05 | Every 20 years
| Option 3 | 0.05 | Every 20 years
| Option 4 | 0.05 | Every 20 years
Consequence
| Consequence | Consequence (per annum)
| Option 1 | 7867994.4256
| Option 2 | 7867994.4256
| Option 3 | 1022395.5405
| Option 4 | 766796.6554
Monetised risk
| Consequence | Monetised risk
| Option 1 | 1573598.8851
| Option 2 | 393399.7213
| Option 3 | 51119.777
| Option 4 | 38339.8328
Risk benefit
| Option | Risk benefit
| Option 1 | n/a
| Option 2 | 1180199.1638
| Option 3 | 1522479.1081
| Option 4 | 1535259.0524

## Benefit ITS3
United Energy
Infrastructure refresh risk
Performance degradation
Option 1 (base case) - Maintain status quo
| Inputs | Unit | Input value | Notes
| Likelihood that forecast growth in data, system users, transactions or new applications leads to an overall degradation in performance and responsiveness of business systems | number | 1 | Likelihood of performance degradation decreased when compared to Option 1 due to more frequent upgrades of IT infrastructure.
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1
| Number of users affected | number | 902.3 | Calculation
| Average hourly rate for internal employees discounted | $/hr | 145.78 | General input
| Estimated time increase per employee | hours | 12 | Assumed an increase in 1 hour per month per employee.
Option 2 - Maintain existing infrastructure with more frequent upgrades
| Inputs | Unit | Input value | Notes
| Likelihood that forecast growth in data, system users, transactions or new applications leads to an overall degradation in performance and responsiveness of business systems | number | 0.5 | Likelihood of performance degradation assumed to be lower as some OT applications have been migrated to cloud.
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1
| Number of users affected | number | 902.3 | Calculation
| Average hourly rate for internal employees discounted | $/hr | 145.78 | General input
| Estimated time increase per employee | hours | 12 | Assumed an increase in 1 hour per month per employee.
Option 3 - Criteria-based IT infrastructure refresh
| Inputs | Unit | Input value | Notes
| Likelihood that forecast growth in data, system users, transactions or new applications leads to an overall degradation in performance and responsiveness of business systems | number | 0.2 | Likelihood of performance degradation assumed to be lowest as non-OT applications have all migrated to cloud.
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1
| Number of users affected | number | 902.3 | Calculation
| Average hourly rate for internal employees discounted | $/hr | 145.78 | General input
| Estimated time increase per employee | hours | 12 | Assumed an increase in 1 hour per month per employee.
Option 4 - Public cloud infrastructure refresh
| Inputs | Unit | Input value | Notes
| Likelihood that forecast growth in data, system users, transactions or new applications leads to an overall degradation in performance and responsiveness of business systems | number | 0.1 | Likelihood of performance degradation assumed to be lowest as non-OT applications have all migrated to cloud.
| Total number of employees |  | 1289 | General input
| Employees impacted | % | 70% | As per explanation in Option 1
| Number of users affected | number | 902.3 | Calculation
| Average hourly rate for internal employees discounted | $/hr | 145.78 | General input
| Estimated time increase per employee | hours | 12 | Assumed an increase in 1 hour per month per employee.
Summary
Likelihood
| Option | Likelihood value | Likelihood category
| Option 1 | 1 | Annual
| Option 2 | 0.5 | Every 2 years
| Option 3 | 0.2 | Every 5 years
| Option 4 | 0.1 | Every 10 years
Consequence
| Consequence | Consequence (per annum)
| Option 1 | 1578447.528
| Option 2 | 1578447.528
| Option 3 | 1578447.528
| Option 4 | 1578447.528
Monetised risk
| Consequence | Monetised risk
| Option 1 | 1578447.528
| Option 2 | 789223.764
| Option 3 | 315689.5056
| Option 4 | 157844.7528
Risk benefit
| Option | Risk benefit
| Option 1 | n/a
| Option 2 | 789223.764
| Option 3 | 1262758.0224
| Option 4 | 1420602.7752

## Misc_calcs
United Energy
Infrastructure refresh risk
ESCALATION & OTHER
| Year end |  |  | 2021-06-30 | 2022-06-30 | 2023-06-30 | 2024-06-30 | 2025-06-30 | 2026-06-30
| Actual/forecast CPI (June to June) |  |  | 0% | 0.86% | 3.5% | 7.83% | 4.05% | 3%
| HY ending |  |  | 2021-06-30 | 2021-12-31 | 2022-06-30 | 2022-12-31 | 2023-06-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2025-06-30 | 2025-12-31 | 2026-06-30
| FY ending |  |  | 2021-06-30 | 2022-06-30 | 2022-06-30 | 2023-06-30 | 2023-06-30 | 2024-06-30 | 2024-06-30 | 2025-06-30 | 2025-06-30 | 2026-06-30 | 2026-06-30
| Actual/forecast CPI (June to June) |  |  | 0% | 0.86% | 0.86% | 3.5% | 3.5% | 7.83% | 7.83% | 4.05% | 4.05% | 3% | 3%
| Actual cumulative HY escalation |  |  | 1 | 1.0043 | 1.0086 | 1.0261 | 1.0439 | 1.084 | 1.1256 | 1.1482 | 1.1712 | 1.1887 | 1.2064
| Convert from input dollars | 2024-06-30 | 1.1256
| To output dollars | 2026-06-30 | 1.2064
| Conversion from input dollars to output dollars |  | 1.0717
FIRST YEAR | bar: 2021-06-30 to 2025-06-30
| Option | First year | Option included
| Option 2 | 1 | TRUE
| Option 3 | 1 | TRUE
| Option 4 | 1 | TRUE
| First year | 1
CHECKS | bar: 2021-06-30 to 2025-06-30
| Option 1 (base case) | FALSE | FALSE
FALSE
FALSE
| Option 2 | FALSE | FALSE
FALSE
FALSE
| Option 3 | FALSE | FALSE
FALSE
FALSE
| Option 4 | FALSE | FALSE
FALSE
FALSE
Message | !! Capex asset life required !!
!

## Data
United Energy | [12 empty] | 2023-09-18
Infrastructure refresh risk
DATA
Options
|  | Not used | Text
Option1 | Option 1 (base case) | FALSE |  | Option 1 (base case): Maintain status quo
Option2 | Option 2 | FALSE
Option3 | Option 3 | FALSE
Option4 | Option 4 | FALSE
Legend
Input
| No change to existing practices | [12 empty] | Fixed input
| Not applicable (compliance) | [12 empty] | Calculation
[defined name]
Categories
Short categ
| Incremental Capital expenditure | -1
| Annualised incremental capex | -1 | [11 empty] | June = Calendar year actual spend
| Incremental operating expenditure | -1 | [11 empty] | December = Financial year actual (eg as reported in RIN)
| Risk mitigated | 1
| Other benefits value | 1
| Net benefits | 1
| Total risk cost | 1
Conversions
| thous_conv | 1000
| mill_conv | 1000000
Message
| Message | Enter asset life
Error message |  | Remove inputs prior to start year
Disproportionate factors applied to various bushfire and other risk valuations
| - Select - |  |  |  | 0
| Harm to property from network |  |  |  | 1
| Harm to property from bushfire |  |  |  | 1
| Harm to environment |  |  |  | 1
| Safety - Public trespass |  |  |  | 1
| Safety - Single fatality or serious injury ^ |  |  |  | 3
| Safety from bushfire in HBRA |  |  |  | 3
| Safety - Multiple fatality or serious injury ^ |  |  |  | 6
| Safety from bushfire (REFCL declared areas) |  |  |  | 6
| Safety from bushfire (electric line construction areas) |  |  |  | 10
DROPDOWN LISTS
| Business |  |  | Type |  | Include | Dollar inputs - month |  |  | Not used options | Conversions | Dollar inputs - year
| CitiPower | CP |  | - Select - |  | 0 | June | 6 | CY | Not used |  | 2024
| Powercor | PA |  | Capex |  | 1899-12-31 | December | 12 | FY |  |  | 2023
| United Energy | UE |  | Opex | [7 empty] | 2022
2021
2020