## Slide 1: Asset Replacement Planning Application Note
Workshop, Melbourne, 25 September 2018

## Slide 2: Overview
Welcome and Introductions
Session 1 – Overview and background
Session 2 – The asset retirement or de rating decision
Session 3 – Identifying and considering options
Session 4 – Uncertainty and risk
Review and close

## Slide 3: Welcome and Introductions
Objectives of the workshop are to:
Provide an overview of the rule change
Consider key aspects of the draft Asset Replacement Planning Application Note (published: 7 September 2018)
Facilitate understanding of the new rules and discussion on the draft Asset Replacement Planning Application Note

## Slide 4: Session 1 – Overview and background
Purpose and objectives of the Asset Replacement Planning Application Note
The NER requires disclosure of asset retirement and de-rating information in APRs and RITs
Developed in response to requests on how to apply the replacement expenditure planning rules
Supplements, but doesn’t replace our guidelines (e.g. RIT application guidelines)
Outlines practices according with good asset management, good risk management, and good industry practice
Outlines an approach to meet the NER requirements to demonstrate prudency and efficiency of asset retirement and de rating
Strikes a balance between principles and practices – not prescriptive about methods or practices
Encourages NSPs to develop good practices that are appropriate to their circumstances

## Slide 5: Session 1 – Overview and background
The “repex rule change”:
  proposed to increase transparency of investment decisions for replacing or de-rating assets
  recognised the greater importance of repex investment, greater focus on managing existing assets due to low (and uncertain) demand growth, and technological change enabling viable alternatives
  built on our existing program to improve quality and effectiveness of APRs
The AEMC amended the NER to require greater transparency:
  the NER aligns the information reporting requirements for repex with those of augex
  the NER requires reporting certain information, including:
    planned asset retirements, and de-ratings that result in a constraint or limitation
    the reasons, methodologies and assumptions involved in these decisions
    information about asset management practices; etc.
    timing of the asset retirement or de-rating
  Emphasises reporting based on assets, not projects

## Slide 6: Session 1 – Overview and background
Definitions: set out in section 1.4 of the Application Note.
Principles:
The Application Note references relevant principles:
  alignment with the NEO, NER, and good industry practice
  service requirements vary over time and cannot be known with certainty
  the asset’s service cost varies over time
  technical end-of-life is a trigger for assessing the prudent response
  economic end-of-life should be demonstrated
  the need to de-rate an asset may arise from technical and economic assessments
  options analysis should be comprehensive and robust
  flexibility, small scale actions, and deferral have economic ‘option’ value

## Slide 7: Session 2 – The asset retirement/de rating decision
Asset retirement /de-rating decisions are made within the context of the NEO, NER and good electricity industry practice
The NER:
  require APRs and RITs to provide transparency of investment to enable stakeholder engagement
  do not require a specific planning framework or direct plans or decisions
  require NSPs to demonstrate prudent and efficient decisions that achieve the capital expenditure objectives to maintain the required service level outcomes

## Slide 8: Session 2 – The asset retirement/de rating decision
Network investment must achieve an objective or ‘identified need’
Service levels relate to the capital expenditure objective, the technical requirements (NER S.5.1), a jurisdictional instrument, or consumer expectations of service outcomes
In an asset retirement context, ‘identified need’ is based on assessment of the asset’s ability to efficiently maintain the service level outcomes
There are two parts to the identified need:
  definition of a service level(s) to be maintained
  assessment of the capability to efficiently maintain service level outcomes
Asset Management Plans (AMPs) should define service levels as specific measurable parameters of the service provided by the asset(s)
AMPs link investment decisions to maintaining service level outcomes

## Slide 9: Session 2 – The asset retirement/de rating decision
A prudent asset manager, acting in the long-term interests of the consumer, would consider when it is optimal to:
  retire an asset (or portion of a fleet of assets); and then
  (to the extent required) implement option(s) to provide required service level(s) at the lowest service cost
This involves two distinct but interrelated decisions:
  deciding that an asset(s) can no longer efficiently maintain service level outcomes and may need to be retired, and
  choosing option(s) that maintain the service levels (to the extent required) at a lowest service cost
That is, where an asset is assessed as nearing the end of its technical life, then intervention in the service provision may be required to efficiently maintain service levels

## Slide 10: Session 2 – The asset retirement/de rating decision
Within an economic framework assessment, remaining technical life is not in itself sufficient reason to retire an asset – this requires assessment of whether the asset is nearing its economic end-of-life
Determining an asset’s economic end-of-life requires assessment of the service cost required if the asset remains in service – this is, the ‘business as usual’ (‘BAU’) or base case against which different options are assessed
That is, justification for retiring asset(s) involves demonstrating:
  The need to consider asset retirement (e.g. nearing technical end-of-life)
  The asset(s) is near its economic end-of-life
Economic end-of-life is when the expected service cost of continued operation (i.e. ‘BAU’ or ‘base case’) is greater than the expected service cost of other available options (which may or may not require investment)
Where at least one other option provides the required service levels at a lower long run service cost than the ‘base case’, then the asset is at the end of its economic life and retirement is indicated

## Slide 11: Session 2 – The asset retirement/de rating decision
Having demonstrated asset retirement/de-rating is efficient, this second leg of the decision needs to be further considered - choosing the best option (or combination of options) to provide/maintain the service levels (to the extent required) at a lowest cost
Assuming there is an ongoing need for the service, then options to efficiently maintain the required service levels following asset retirement/de-rating need to be considered
Depending on the approach adopted, the first and second legs of the asset management decision could be combined, assessed iteratively, or in a linear process of increasing detail

## Slide 12: Session 2 – The asset retirement/de rating decision
The Application Note suggests the above approach for asset retirement/de-rating decisions
The approach quantifies (i.e. monetises) service costs across alternative options based on options analysis that:
  Identifies the asset’s purpose (i.e. service levels required) for the foreseeable future
  Quantifies the expected service cost of the asset remaining in service – the ‘business as usual’, base case or counterfactual
  Applies a simplified but robust assessment of risks or uncertainty to quantify all relevant costs
  Identifies options that efficiently maintain the required service level outcomes
  Quantifies the expected service cost of each option (or combination of options)
  Selects the efficient option (or combination of options) that minimises total expected service cost compared to the ‘business as usual’ case
  Determines the expected economically efficient timing of the options of combination of options

## Slide 13: Session 2 – The asset retirement/de rating decision
In the Application Note, options analysis provides the foundation for:
  deciding if asset retirement/de-rating is prudent and efficient
  deciding what is the prudent and efficient option (or combination of options) to pursue subsequent to an asset retirement/de-rating to maintain the service levels
  establishing prudent and efficient timing
In all cases the preferred option(s) is the option that maximises net economic benefit

## Slide 14: Session 2 – The asset retirement/de rating decision
The Application Note also highlights some important considerations:
  changes to service level requirements
  changes in the operating environment
  changes in consumer preferences or requirements
  non-network options and changing technology
  asset condition and modes, and rates of asset deterioration
  opportunities for lower cost solutions (which may occur before an asset reaches its technical end-of-life)

## Slide 15: Session 2 – The asset retirement/de rating decision
Deciding to de-rate an asset:
Deciding to de-rate an asset is similar to an asset retirement decision in that it involves a technical and economic decision
Asset de-rating manages heightened service level risk and hence greater expected service cost
De-rating is an option to efficiently maintain service level outcomes
De-rating may or may not give rise to subsequent investments. Where it leads to subsequent investments, economic analysis is required to determine the best option (or combination of options) to efficiently maintain the required service levels

## Slide 16: Session 3 – Identifying and considering options
Options analysis is the foundation of the asset retirement/de-rating decision and the selection of subsequent action(s) to efficiently maintain service levels
The RIT Application Guidelines provide relevant advice for selecting credible options, in that options should:
  address the identified need
  be commercially and technically feasible
  be able to be implemented in sufficient time to meet the identified need
The RIT Application Guidelines also considers a credible option to include: ‘a decision rule or policy specifying not just an action or decision that will be taken at the present time, but also an action or decision that will be taken in the future if the appropriate market conditions arise.’
Hence real options are contemplated in the RIT Application Guidelines

## Slide 17: Session 3 – Identifying and considering options
Understanding an asset’s purpose is central to defining the ‘identified need’, assessing the ‘BAU’ case, and in identifying options.
An asset’s purpose is to deliver service outcomes over a relevant timeframe. Since an asset’s purpose could change, in considering options we also need to consider:
  If the asset(s) has an ongoing enduring purpose or will its purpose alter?
  If the asset(s) will still be required to provide the same service at the same level?
  If the service levels could change - increase or decrease?
  And be aware that if there is uncertainty about the required service levels, then flexible small scale actions and deferral have economic ‘real option’ value (e.g. increased maintenance, operational controls, refurbishment, or non-network options)

## Slide 18: Session 3 – Identifying and considering options
The BAU service cost is the basis of the asset retirement/de-rating decision
BAU costs might include:
  risk costs – such as supply reliability risks, health and safety risks, environmental risks, etc.
  operations and maintenance (repairs, obsolescence costs, operational costs)
  emergency replacement, disposal costs, spares holdings, etc.
The BAU counterfactual serves as the point of comparison for all other options

## Slide 19: Session 3 – Identifying and considering options
Generally options analysis should identify and evaluate all credible options and combinations of options and consider non-network and demand management options
Economic cost benefit components of options analysis may comprise:
  market benefits
  risk cost reduction or avoidance benefits
  efficiency savings and avoided operational and maintenance costs
  capital cost of implementing the solution
  the value of optionality (real option value)
  capacity stranding costs
The preferred option (or combination of options) is the option(s) that maximises the net economic benefit compared to all other credible options (including the BAU counterfactual) and represents the maximum long run net benefit
The economically prudent and efficient timing for asset retirement is when the annual net benefit of a credible option exceeds the annual net benefit of BAU counterfactual

## Slide 20: Session 3 – Identifying and considering options
The Application Note identifies some relevant credible options:
  life extension via operational strategies or repair/refurbishment to defer asset retirement. E.g.:
    operational/administrative controls to manage consequence or likelihood of the consequence
    increased maintenance or minor refurbishment to reduce the likelihood of failure
    non-network solutions to reduce the cost of consequence
    network configuration, functional capability to reduces the cost of consequence
    de-rating to reduce the likelihood of failure
  asset substitution/supplementation with non-network solutions so assets can be retired and not replaced, de-rated to lower failure likelihood, or retired and replaced with an alternative network solutions that are supplemented with non-network solutions to reduce consequences (e.g. USE)
  asset replacement with different technology or modified functionality e.g. reduced capacity and supported by non-network options
  asset replacement using similar technology/functionality: partial replacement; brownfield, or greenfield
  Combined options, implemented together or staged for option value and reduced service cost

## Slide 21: Session 3 – Identifying and considering options
All costs and benefits in asset retirement/de-rating decisions are inherently uncertain (i.e. they are not precise or known a priori)
The Application Note identifies some of these uncertainties:
  changes to network service requirements
  changes to consumer demand levels and demand patterns (geospatial and temporal)
  changes to generation patterns, including distributed generation
  the implications of energy storage on consumer service levels and asset utilisation
  technology change, including the implications of energy efficiency, communication and controllability
  asset condition deterioration rate and likelihood of in-service failure
  the risk cost associated with asset performance

## Slide 22: Session 3 – Identifying and considering options
To address uncertainty, the Application Note uses risk assessment, scenario and sensitivity analysis in monetising costs and benefits as a good practice approach to retirement/de-rating decisions
Risk analysis is used to understand the value of likely costs and benefits
Scenarios and sensitivity analysis are used to demonstrate that the preferred option(s) are robust for a range of futures and for a variation in key inputs
Scenarios are based on internally consistent possible future states of the world
Sensitivity analysis is used to identify the most determinant inputs (variables) and focus refinement of the analysis and supporting evidence on these inputs
The RIT Application Guidelines also nominate several key input assumptions for the base case and for sensitivity studies

## Slide 23: Session 4 – Uncertainty and risk
The Application Note outlines a simplified method for assessing risk and addressing uncertainty. Within an economic assessment framework, this approach facilitates:
  Evaluation of uncertainty in the identified need
  Evaluation of uncertainty and risk within options analysis and the BAU counterfactual
  Comparison of options on a common monetised basis
  Conditional and joint probability implications
  Alignment with the NER, NEO, and accords with good industry practice
  Support for analysis over time (e.g. time value of money)
  Comprehensive and robust analysis
  Evaluation of real option values and stranding costs

## Slide 24: Session 4 – Uncertainty and risk
The Application Note monetises risk costs associated with adverse service level outcomes
A simple quantitative approach to risk cost assessment is used:
The avoidance of risk cost is recognised as a benefit in economic options analysis
Other methods could also be used (e.g. Monte Carlo)
Consequence cost of failure event (CoC)
Asset units (No)
Asset Risk Cost ($)
Likelihood of consequence of failure event (LoC)
Probability of asset failure (PoF)

## Slide 25: Session 4 – Uncertainty and risk
Any method used should accommodate all typical areas of network asset risk:
  Reliability & security: including consequences such as unserved energy or other customer impacts of a supply failure
  Safety & health: including consequences to workers and/or members of the public
  Environmental: including consequences to the surrounding community, ecology, flora and fauna
  Legal/regulatory compliance: including consequences of enforcement of legal or regulatory requirements
  Financial: including consequences where there is a financial loss or additional cost not normally part of the revenue allowance
Note: Generally, we do not consider reputational risk as a relevant risk for network investment

## Slide 26: Session 4 – Uncertainty and risk
The Application Note also outlines approaches to:
  identifying consequences using failure mode analysis
  assessing failure probability for assets or asset classes
  assessing the cost of consequence including the application of VCR, unserved energy, SFAIRP and ALARP, etc.
  assessing the likelihood of consequence
  accounting for obsolescence
  considering relevant moderating factors (e.g. controls and risk mitigations)
  the application of non-network solutions in deferring asset retirement
  the treatment of joint and conditional probability

## Slide 27: Considering single assets or asset fleets
The Application Note considers the analysis of single assets and asset fleets as almost indistinguishable and provides no specific guidance
Programs associated with high volume low value assets can be considered as a ‘fleet’
Asset fleets may be whole asset classes or asset groups with similar failure modes and consequences, or asset sub-groups or sub-classes (e.g. line sections), but are likely to reflect voltage level grouping
Subpopulations can be characterised with fleet level failure models, failure likelihoods, consequence costs, and likelihood of consequence applied to the fleet or a proportion of the fleet.
The retirement decision, option analysis and risk cost analysis can be undertaken for the subpopulation as it would for any single asset

## Slide 28: Review and close
Review of key messages
Next steps (including ENA work to develop a consistent cost of consequence)
Close
Thank you.
Have a safe trip home.