## Legend
Costs ($2019)
Risk category based on inspection | Remidiation classification | Remediation works | Defect present | Estimated Costs | Comments
Higher risk - requires immidiate action and/or prioritised remediation | Major | Roof Slab | Cracking | 250000 | Full pit lid replacement (includes all other minor defects)
|  |  | Spalling | 250000 | Full pit lid replacement (includes all other minor defects)
|  |  | Corrosion | 250000 | Full pit lid replacement (includes all other minor defects)
|  | Walls | Cracking | N/A | No defects to date
| Medium | Roof Slab | Cracking | 75000 | E.g. additional steel work
|  |  | Spalling | 75000 | E.g. additional steel work
|  |  | Corrosion | 75000 | E.g. additional steel work
|  | Walls | Cracking | N/A | No defects to date
Low risk - does not require immidiate action | Minor | Roof Slab | Cracking | 2000 | Grout injection
|  |  | Spalling | 2000 | Grout injection
|  |  | Corrosion | 2000 | Scrap, clean and re-paint
|  | Walls | Cracking | 2000 | Grout injection
|  |  | Bulging | 75000
|  |  | Loss of Mortar | 2000 | Grout injection
|  |  | Tree Roots | 2000 | Grout injection
|  | Floor | Cracking | 2000 | Grout injection
|  |  | Spalling | N/A | No defects to date
|  |  | Corrosion | N/A | No defects to date
|  | Footings | Cracking | N/A | No defects to date
|  |  | Spalling | N/A | No defects to date
|  | Misc. | Ladder | 3000
|  |  | Pulling Eyes | 25000 | Only applies if ring beam needs to be installed
|  |  | Turrent | 75000 | Repair / replacement will include pit cover repair / replacement
|  |  | Gatic / Pit Cover | 10000
|  |  | Cable Supports | 65000 | Operator isolation costs, temp supports and re-energising costs incl.
|  |  | Water | 5000
|  |  | Space Constraints | 30000 | Clean-up requirements - e.g. removal of out of service assets
|  |  | Mobilisation Cost |  | Inclusions
|  |  | Minor | 7500 | Eng,contractor, UG team, Traffic for 1 day
|  |  | Medium | 15000 | Eng,contractor, UG team, Traffic for 2 days
|  |  | Major | 15000 | Eng,contractor, UG team, Traffic for 2 days
|  |  | None | 0

## Defect data
Defect Types
|  |  | Roof Slab |  |  | Walls |  |  |  | Floor |  |  | Footings |  | Misc.
Program | Pit No. | Propped | Roof Slab Cracking | Roof Slab Spalling | Roof Slab Corrosion | Wall Bulging | Wall Cracking | Wall Loss of Mortar | Wall Tree Roots | Floor Cracking | Floor Spalling | Floor Corrosion | Footing Cracking | FootingSpalling | Ladder | Pulling Eyes | Turret | Gatic / Pit Cover | Cable Supports | Water | Space Constraints | Number of Defects | Mobilisation Category | Estimated Delivery Cost | Mobilisation Costs | Total Cost | Number of Defects
2020 | 71 |  | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Minor | 11000 | 7500 | 18500 | 5
2020 | 75 |  | 0 | 1 | 1 | [9 empty] | 1 | [6 empty] | 3 | Minor | 7000 | 7500 | 14500 | 3
2020 | 78 | y | 0 | 1 | 2 | [9 empty] | 1 |  |  |  | 1 | 1 | 1 | 7 | Medium | 250000 | 15000 | 265000 | 7
2020 | 81 |  | 2 | 1 | 2 | [9 empty] | 1 | [6 empty] | 6 | Minor | 13000 | 7500 | 20500 | 6
2020 | 85 |  | 0 | [11 empty] | 1 |  |  |  |  | 1 |  | 2 | Minor | 8000 | 7500 | 15500 | 2
2020 | 97 |  | 0 | [11 empty] | 1 |  |  | 1 |  | 1 |  | 3 | Minor | 18000 | 7500 | 25500 | 3
2020 | 129 |  | 0 | [11 empty] | 1 | [6 empty] | 1 | Minor | 3000 | 7500 | 10500 | 1
2020 | 145 | y | 0 |  | 1 | [9 empty] | 1 |  |  |  |  | 1 |  | 3 | Medium | 83000 | 15000 | 98000 | 3
2020 | 158 | y | 0 | 1 | 1 |  | 3 | [7 empty] | 1 |  |  |  |  | 1 |  | 7 | Major | 250000 | 15000 | 265000 | 7
2020 | 160 | y | 0 | 2 | 1 | [9 empty] | 1 | [6 empty] | 4 | Major | 250000 | 15000 | 265000 | 4
2020 | 190 | n | 1 |  | 1 | [9 empty] | 1 |  |  |  | 1 |  |  | 4 | Minor | 72000 | 7500 | 79500 | 4
2020 | 205 |  | 1 | 1 | 1 |  |  |  | 1 | [5 empty] | 1 |  |  |  |  | 1 |  | 6 | Minor | 16000 | 7500 | 23500 | 6
2020 | 206 |  | 0 | [11 empty] | 1 |  |  |  |  | 1 |  | 2 | Minor | 8000 | 7500 | 15500 | 2
2020 | 214 |  | 0 | 1 | 1 | [14 empty] | 1 |  | 3 | Minor | 9000 | 7500 | 16500 | 3
2020 | 215 |  | 0 |  | 2 | [14 empty] | 1 |  | 3 | Minor | 9000 | 7500 | 16500 | 3
2020 | 253 | n | 0 |  |  |  | 1 | [7 empty] | 1 |  |  |  | 1 |  |  | 3 | Minor | 70000 | 7500 | 77500 | 3
2019 | 260 |  | 0 | 1 |  |  | 1 | [7 empty] | 1 |  |  |  |  | 1 |  | 4 | Minor | 12000 | 7500 | 19500 | 4
2019 | 264 |  | 0 | 2 | [10 empty] | 1 |  |  |  |  | 1 |  | 4 | Minor | 12000 | 7500 | 19500 | 4
2019 | 271 |  | 0 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 |  | 3 | Minor | 10000 | 7500 | 17500 | 3
2020 | 275 |  | 1 | [11 empty] | 1 |  |  |  |  | 1 | 1 | 4 | Minor | 40000 | 7500 | 47500 | 4
2020 | 276 | y | 0 |  | 1 | [9 empty] | 1 | [6 empty] | 2 | Major | 250000 | 15000 | 265000 | 2
2019 | 329 |  | 0 | [11 empty] | 1 |  |  |  |  | 1 |  | 2 | Minor | 8000 | 7500 | 15500 | 2
2020 | 345 | y | 1 | 2 | 2 |  | 1 | [7 empty] | 1 |  |  |  |  | 1 |  | 8 | Medium | 250000 | 15000 | 265000 | 8
2020 | 346 | n | 0 | [5 empty] | 1 | [5 empty] | 1 |  |  |  | 1 | 1 |  | 4 | Minor | 75000 | 7500 | 82500 | 4
2020 | 350 | n | 0 |  | 2 | [9 empty] | 1 |  |  |  | 1 | 1 |  | 5 | Medium | 223000 | 15000 | 238000 | 5
2019 | 354 | y | 0 |  | 2 | [9 empty] | 1 |  |  |  |  | 1 |  | 4 | Medium | 158000 | 15000 | 173000 | 4
2020 | 360 | n | 0 |  | 2 |  | 1 | 1 | [9 empty] | 1 | 1 | 1 |  | 7 | Medium | 234000 | 15000 | 249000 | 7
2020 | 366 | n | 1 |  | 1 | [9 empty] | 1 | [5 empty] | 1 | 4 | Major | 250000 | 15000 | 265000 | 4
2020 | 378 | n | 2 |  | 2 | [9 empty] | 1 |  |  |  | 1 |  |  | 6 | Minor | 76000 | 7500 | 83500 | 6
2020 | 383 |  | 0 | [11 empty] | 1 |  |  | 1 |  | 1 |  | 3 | Minor | 18000 | 7500 | 25500 | 3
2020 | 400 | n | 0 | [11 empty] | 1 |  |  |  | 1 | 1 |  | 3 | Minor | 73000 | 7500 | 80500 | 3
2020 | 401 | y | 0 | 1 | 1 | [9 empty] | 1 |  | 1 |  |  | 1 |  | 5 | Major | 250000 | 15000 | 265000 | 5
2019 | 402 | Y | 0 | 1 |  |  | 3 | [7 empty] | 1 | [6 empty] | 5 | Major | 250000 | 15000 | 265000 | 5
2020 | 406 | y | 0 |  | 3 | [9 empty] | 1 | [6 empty] | 4 | Medium | 228000 | 15000 | 243000 | 4
2020 | 417 | n | 0 | 1 | [10 empty] | 1 |  |  |  | 1 | 1 |  | 4 | Minor | 75000 | 7500 | 82500 | 4
2019 | 425 |  | 4 |  | 1 |  |  |  | 1 | [5 empty] | 1 |  |  |  |  | 1 |  | 8 | Minor | 20000 | 7500 | 27500 | 8
2020 | 426 |  | 3 | [11 empty] | 1 |  |  |  |  | 1 |  | 5 | Minor | 14000 | 7500 | 21500 | 5
2020 | 427 |  | 0 | 2 | 1 | [9 empty] | 1 |  |  |  |  | 1 |  | 5 | Minor | 14000 | 7500 | 21500 | 5
2020 | 429 |  | 1 | 1 | 2 | [9 empty] | 1 | [6 empty] | 5 | Minor | 11000 | 7500 | 18500 | 5
2020 | 442 |  | 2 | [5 empty] | 1 | 1 |  |  |  |  | 1 | [6 empty] | 5 | Minor | 11000 | 7500 | 18500 | 5
2019 | 448 |  | 0 | 2 |  |  | 2 | [7 empty] | 1 |  |  |  |  | 1 |  | 6 | Minor | 16000 | 7500 | 23500 | 6
2020 | 450 |  | 0 | [11 empty] | 1 | [6 empty] | 1 | Minor | 3000 | 7500 | 10500 | 1
2020 | 453 |  | 1 |  | 1 |  | 1 | [7 empty] | 1 | 1 | [5 empty] | 5 | Minor | 34000 | 7500 | 41500 | 5
2020 | 454 | n | 0 |  |  |  | 3 | [7 empty] | 1 |  |  |  | 1 |  |  | 5 | Minor | 74000 | 7500 | 81500 | 5
2020 | 458 |  | 0 | [11 empty] | 1 |  |  |  |  | 1 |  | 2 | Minor | 8000 | 7500 | 15500 | 2
2020 | 514 |  | 0 | [11 empty] | 1 |  |  |  |  | 1 |  | 2 | Minor | 8000 | 7500 | 15500 | 2
2020 | 526 |  | 0 | [11 empty] | 1 | [6 empty] | 1 | Minor | 3000 | 7500 | 10500 | 1
2019 | 530 |  | 0 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 |  | 3 | Minor | 10000 | 7500 | 17500 | 3
2019 | 534 | n | 0 |  | 2 |  | 3 | [7 empty] | 1 |  |  |  |  | 1 |  | 7 | Medium | 164000 | 15000 | 179000 | 7
2019 | 546 | n | 0 | 1 | 2 |  |  |  | 1 | [5 empty] | 1 | [6 empty] | 5 | Medium | 230000 | 15000 | 245000 | 5
2020 | 640 |  | 0 | 1 | 1 | [9 empty] | 1 | [6 empty] | 3 | Minor | 7000 | 7500 | 14500 | 3
2020 | 648 | n | 0 | [11 empty] | 1 |  |  |  | 1 | 1 |  | 3 | Minor | 73000 | 7500 | 80500 | 3
2020 | 649 | n | 0 | [11 empty] | 1 |  |  |  | 1 | 1 |  | 3 | Minor | 73000 | 7500 | 80500 | 3
2020 | 663 |  | 0 | [16 empty] | 1 |  | 1 | Minor | 5000 | 7500 | 12500 | 1
2019 | 667 |  | 0 |  | 1 | [9 empty] | 1 |  |  |  |  | 1 |  | 3 | Minor | 10000 | 7500 | 17500 | 3
2019 | 668 |  | 1 |  | 1 | [9 empty] | 1 |  |  |  |  | 1 |  | 4 | Minor | 12000 | 7500 | 19500 | 4
2020 | 677 |  | 0 |  |  |  | 3 | [7 empty] | 1 |  |  |  |  | 1 |  | 5 | Minor | 14000 | 7500 | 21500 | 5
2020 | 681 |  | 0 | [11 empty] | 1 | [6 empty] | 1 | Minor | 3000 | 7500 | 10500 | 1
2020 | 684 |  | 0 |  | 1 | [16 empty] | 1 | Minor | 2000 | 7500 | 9500 | 1
2019 | 689 |  | 0 |  |  |  | 1 | [7 empty] | 1 |  |  |  |  | 1 |  | 3 | Minor | 10000 | 7500 | 17500 | 3
2020 | 706 | y | 0 |  | 1 | [16 empty] | 1 | Medium | 75000 | 15000 | 90000 | 1
2020 | 711 |  | 0 | [11 empty] | 1 | [6 empty] | 1 | Minor | 3000 | 7500 | 10500 | 1
2019 | 728 |  | 0 | 1 |  |  |  |  | 1 | [5 empty] | 1 |  |  |  |  | 1 |  | 4 | Minor | 12000 | 7500 | 19500 | 4
2019 | 729 |  | 3 | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 |  | 6 | Minor | 16000 | 7500 | 23500 | 6
2019 | 731 |  | 0 | 1 | [10 empty] | 1 |  |  |  |  | 1 |  | 3 | Minor | 10000 | 7500 | 17500 | 3
2019 | 744 |  | 0 | [18 empty] | 0 | None | 0 | 0 | 0 | 0
2019 | 745 |  | 0 | 3 | [15 empty] | 1 |  | 4 | Minor | 11000 | 7500 | 18500 | 4
2020 | 778 |  | 0 | [11 empty] | 1 |  |  |  |  | 1 |  | 2 | Minor | 8000 | 7500 | 15500 | 2
2020 | 836 |  | 0 | [18 empty] | 0 | None | 0 | 0 | 0 | 0
2020 | 837 |  | 0 | [18 empty] | 0 | None | 0 | 0 | 0 | 0
2020 | 848 |  | 0 | [18 empty] | 0 | None | 0 | 0 | 0 | 0
2020 | 849 |  | 0 | [18 empty] | 0 | None | 0 | 0 | 0 | 0
2020 | 860 |  | 0 | [16 empty] | 1 |  | 1 | Minor | 5000 | 7500 | 12500 | 1
2020 | 861 |  | 0 | [16 empty] | 1 |  | 1 | Minor | 5000 | 7500 | 12500 | 1
2020 | 864 |  | 0 | [18 empty] | 0 | None | 0 | 0 | 0 | 0
2020 | 865 |  | 0 |  |  |  | 3 | [14 empty] | 3 | Minor | 6000 | 7500 | 13500 | 3
2020 | 877 |  | 0 | [18 empty] | 0 | None | 0 | 0 | 0 | 0
2020 | 878 |  | 0 | [18 empty] | 0 | None | 0 | 0 | 0 | 0
2020 | 966 | n | 1 | 1 | [10 empty] | 1 |  |  |  |  | 1 |  | 4 | Minor | 12000 | 7500 | 19500 | 4
2020 | 967 |  | 0 | [11 empty] | 1 |  |  |  |  | 1 |  | 2 | Minor | 8000 | 7500 | 15500 | 2
2020 | 1214 | y | 1 | [11 empty] | 1 |  |  | 1 |  | 1 |  | 4 | Minor | 20000 | 7500 | 27500 | 4
2020 | 1265 | n | 0 | 1 | 1 | [9 empty] | 1 |  |  | 1 | 1 | 1 |  | 6 | Major | 250000 | 15000 | 265000 | 6
2020 | 1329 |  | 0 | [16 empty] | 1 |  | 1 | Minor | 5000 | 7500 | 12500 | 1
2020 | 262-2 | n | 0 |  | 1 |  | 3 | [7 empty] | 1 |  |  | 1 | 1 | 1 |  | 8 | Medium | 164000 | 15000 | 179000 | 8
2020 | 436-2 | y | 1 | 1 | 1 | [9 empty] | 1 |  |  |  |  | 1 |  | 5 | Major | 250000 | 15000 | 265000 | 5
|  |  | 28 | 33 | 47 | 0 | 29 | 1 | 9 | 1 | 0 | 0 | 0 | 0 | 66 | 1 | 1 | 6 | 14 | 52 | 3 | 291 |  | 5258000 | 720000 | 5978000 | 291

## Options analysis
Costs ($2019)
Pit inspection program volumes
Year | Pits to inspect
2018 | 9
2019/2020 | 85
2021 | 56
2022 | 56
2023 | 56
2024 | 56
2025 | 56
2026 | 56
2027 | 57
2028 | 0
2029 | 0
2030 | 0
Data for Scenario Analysis
2019/20 inspection data | [5 empty] | 2021-26 Repair and remediation forecast
Risk | Remediation | Average of Total Cost | Count of Pit No. | % Defects split |  | Forecast defect distribution | Repair Costing (2021 H2 to 2026 H1) | Defect jobs per year
Higher risk | Major | 265000 | 8 | 9.412% |  | 26.3529 | 6983529.4118 | 5
Higher risk | Medium | 202181.8182 | 11 | 12.94% |  | 36.2353 | 7326117.6471 | 7
Low risk | Minor | 28172.4138 | 58 | 68.24% |  | 191.0588 | 5382588.2353 | 38
NA | None | 0 | 8 | 9.412% |  | 26.3529 | 0 | 5
| Total |  | 85 | 100% |  | 280 | 19692235.2941 | 55
Defect volume
Risk | Remediation | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2021-26 Total
Higher risk | Major | 5 | 5 | 5 | 5 | 5 | 25
Higher risk | Medium | 7 | 7 | 7 | 7 | 7 | 35
Low risk | Minor | 38 | 38 | 38 | 38 | 38 | 190
Cost
Risk | Remediation | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2021-26 Total
Higher risk | Major | 1325000 | 1325000 | 1325000 | 1325000 | 1325000 | 6625000
Higher risk | Medium | 1415272.7273 | 1415272.7273 | 1415272.7273 | 1415272.7273 | 1415272.7273 | 7076363.6364
Low risk | Minor | 1070551.7241 | 1070551.7241 | 1070551.7241 | 1070551.7241 | 1070551.7241 | 5352758.6207
Scenario 1: Repair high risk defects within the AER allocated allowance of $2.9m
Cost
Allowance avaliable for major defects | [5 empty] | 2900000 | 2.9
Allowance avaliable for medium defects | [5 empty] | 0 | 0
Allowance avaliable for minor defects | [5 empty] | 0 | 0
[5 empty] | Total | 2900000 | 2.9
Scenario 2: Repair high risk defects
Cost to repair all major and medium Defects in 2021-26 | [5 empty] | 13701363.6364 | 13.7014
Scenario 3: Repair of all defects
Cost to repair all major, medium and minor defects in 2021-26 | [5 empty] | 19054122.2571 | 19.0541
0