## Plan Lvl
SAMP | Description | FY20 (R) | FY21 (R) | FY22 (R) | FY23 (R) | FY24 (R) | FY25 (R) | FY26 (R) | FY27 (R) | FY28 (R) | FY29 (R) | FY20 (N) | FY21 (N) | FY22 (N) | FY23 (N) | FY24 (N) | FY25 (N) | FY26 (N) | FY27 (N) | FY28 (N) | FY29 (N) | Total (R) | Total (N)
PR | Major projects | 48779978 | 54031929 | 67465040 | 84374940 | 78464500 | 71064851 | 69762154 | 73674650 | 78245200 | 65032400 | 49999477.45 | 56767295.4056 | 72652469.0912 | 93134146.4177 | 88775379.7204 | 82413439.971 | 82925278.605 | 89765407.033 | 97717532.8561 | 83246970.112 | 690895642 | 797397396.6621 | Growth
PRL | Major projects - land | 8848146 | 3000000 | 3500000 | 3000000 | 3000000 | 2800000 | 0 | 5000000 | 0 | 5000000 | 9069349.65 | 3151875 | 3769117.1875 | 3311438.6719 | 3394224.6387 | 3247141.571 | 0 | 6092014.4875 | 0 | 6400422.721 | 34148146 | 38435583.9276 | Growth
AG | Automation growth | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | 384025.3633 | 3000000 | 3445039.8936 | Growth
HV | Distribution works program | 6800844 | 7103063 | 6647368 | 6275047 | 5947097 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6970865.1 | 7462655.5644 | 7158488.2801 | 6926477.7679 | 6728594.3887 | 6958160.5093 | 7132114.522 | 7310417.3851 | 7493177.8197 | 7680507.2652 | 62773419 | 71821458.6022 | Growth
EH | Dist environmental enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Growth
LV | Low voltage development capital | 1830000 | 1830000 | 1830000 | 1830000 | 1830000 | 1830000 | 1830000 | 1830000 | 1830000 | 1830000 | 1875750 | 1922643.75 | 1970709.8437 | 2019977.5898 | 2070477.0296 | 2122238.9553 | 2175294.9292 | 2229677.3024 | 2285419.235 | 2342554.7159 | 18300000 | 21014743.3511 | Growth
AR | Asset relocation | 1623650 | 1563851 | 1542485 | 1535001 | 1533069 | 1533069 | 1533069 | 1533069 | 1533069 | 1533069 | 1664241.25 | 1643020.9569 | 1661087.6357 | 1694353.8909 | 1734526.8575 | 1777890.029 | 1822337.2797 | 1867895.7117 | 1914593.1045 | 1962457.9321 | 15463401 | 17742404.6479 | Growth
DU | Duct installation RMS road works | 2152731 | 2206549 | 2261713 | 2318255 | 2376212 | 2376212 | 2376212 | 2376212 | 2376212 | 2558920 | 2206549.275 | 2318255.5431 | 2435617.5261 | 2558919.7528 | 2688465.7724 | 2755677.4167 | 2824569.3521 | 2895183.5859 | 2967563.1755 | 3275633.9418 | 23379228 | 26926435.3414 | Growth
IC | Industrial & commercial | 7501444 | 5332550 | 4584087 | 4321346 | 4245553 | 4245553 | 4245553 | 4245553 | 4245553 | 4245553 | 7688980.1 | 5602510.3438 | 4936560.3145 | 4769957.4197 | 4803453.5325 | 4923539.8708 | 5046628.3675 | 5172794.0767 | 5302113.9287 | 5434666.7769 | 47212745 | 53681204.7309 | Growth
NU | Non-urban extension | 1019340 | 743122 | 661806 | 631694 | 619417 | 619417 | 619417 | 619417 | 619417 | 619417 | 1044823.5 | 780742.5512 | 712692.677 | 697271.9801 | 700813.481 | 718333.818 | 736292.1635 | 754699.4676 | 773566.9543 | 792906.1281 | 6772464 | 7712142.7208 | Growth
UR | Underground residential | 21659051 | 14600685 | 11758786 | 11056595 | 10803669 | 10803669 | 10803669 | 10803669 | 10803669 | 10803669 | 22200527.275 | 15339844.6781 | 12662926.4048 | 12204412.0874 | 12223359.836 | 12528943.8319 | 12842167.4276 | 13163221.6133 | 13492302.1537 | 13829609.7075 | 123897131 | 140487315.0153 | Growth
RC | Reliability compliance | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 5120338.1768 | 40000000 | 45933865.2482 | Reliability
PQ | Power quality capital | 442400 | 717700 | 973300 | 1047600 | 1464538 | 1399560 | 1529516 | 1529516 | 1269604 | 1269604 | 453460 | 754033.5625 | 1048137.6453 | 1156354.3842 | 1656990.3213 | 1623060.5204 | 1818113.8792 | 1863566.7262 | 1585561.4221 | 1625200.4576 | 11643338 | 13584478.9189 | Reliability
TS | Transmission substation capital (rebuild) | 25994927 | 33488457 | 27401500 | 34141500 | 34393500 | 28941500 | 29570500 | 33070500 | 36055500 | 40757500 | 26644800.175 | 35183810.1356 | 29508418.4609 | 37685827.8053 | 38913088.3701 | 33563267.0632 | 35150032.0788 | 40293193.0221 | 45028378.8129 | 52173045.8101 | 323815384 | 374143861.7341 | Sustainability
TM | Transmission mains capital (refurb) | 10719865 | 12169670 | 12007670 | 9407670 | 10485670 | 23824670 | 30552670 | 34590670 | 39240670 | 44940670 | 10987861.625 | 12785759.5437 | 12930947.2511 | 10384307.4167 | 11863573.1557 | 27629312.9901 | 36317523.5655 | 42145372.5548 | 49006219.6789 | 57527857.0728 | 227939895 | 271578734.8544 | Sustainability
DS | Distribution refurbishment capital | 57383080 | 62236080 | 66694080 | 68130580 | 71674580 | 72149580 | 77429580 | 88024580 | 101364580 | 112764580 | 58817657 | 65386781.55 | 71822229.495 | 75203412.4498 | 81093208.4675 | 83671393.0528 | 92039438.6585 | 107249403.3241 | 126590470.4263 | 144348195.9908 | 777851300 | 906222190.4148 | Sustainability
AU | Automation capital | 3290000 | 3290000 | 4290000 | 4290000 | 3290000 | 3290000 | 3290000 | 4290000 | 4290000 | 3290000 | 3372250 | 3456556.25 | 4619860.7812 | 4735357.3008 | 3722333.0204 | 3815391.3459 | 3910776.1296 | 5226948.4303 | 5357622.1411 | 4211478.1504 | 36900000 | 42428573.5497 | Sustainability
CC | Communications refurbishment | 2175000 | 2035000 | 1865000 | 1645000 | 1445000 | 2130000 | 2620000 | 2290000 | 2560000 | 1870000 | 2229375 | 2138021.875 | 2008401.0156 | 1815772.2051 | 1634884.8676 | 2470146.9808 | 3114356.6746 | 2790142.6353 | 3197089.2031 | 2393758.0976 | 20635000 | 23791948.5547 | Sustainability
PS | Protection systems capital | 8725000 | 6080000 | 5530000 | 5530000 | 5530000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 8943125 | 6387800 | 5955205.1562 | 6104085.2852 | 6256687.4173 | 6703027.9573 | 6870603.6562 | 7042368.7476 | 7218427.9663 | 7398888.6655 | 60295000 | 68880219.8515 | Sustainability
EF | Efficiency | 9085366 | 4116895 | 2092860 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 9312500.15 | 4325312.8094 | 2253781.3134 | 2207625.7812 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | 2560169.0884 | 29295121 | 32553495.6469 | Efficiency
MC | Metering capital | 2537584 | 1797185 | 1736786 | 1646386 | 1635987 | 1550588 | 1535189 | 1449790 | 1434391 | 1348992 | 2601023.6 | 1888167.4906 | 1870328.561 | 1817302.0897 | 1850969.128 | 1798206.698 | 1824857.2935 | 1766428.3368 | 1791357.8043 | 1726823.8094 | 16672878 | 18935464.8114 | Miscellaneous
SL | Streetlighting capital | 4750000 | 4750000 | 4750000 | 4750000 | 4750000 | 4750000 | 4750000 | 4750000 | 4750000 | 4750000 | 4868750 | 4990468.75 | 5115230.4687 | 5243111.2305 | 5374189.0112 | 5508543.7365 | 5646257.3299 | 5787413.7632 | 5932099.1073 | 6080401.5849 | 47500000 | 54546464.9822
SP | Essential spares | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 10000000 | 11483466.3121 | Miscellaneous
SW | Network switching | 6283900.8865 | 6382175.5445 | 6686467.7532 | 6495126.3573 | 6714861.5396 | 7423719.2767 | 7683873.5145 | 7944102.7058 | 8085985.7683 | 8183178.6979 | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | 10475160.5735 | 71883392.0442 | 83109035.6151 | Switching & Overheads
OH | Capitalised overheads | 73106139.0812 | 73273110.1037 | 73775204.5564 | 73462071.757 | 73820942.4206 | 76860996.0999 | 77233408.4879 | 77593252.7624 | 77784338.9426 | 78058962.8601 | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | 99922071.8932 | 754968427.0719 | 868519522.4252 | Switching & Overheads
| Total | 310008445.9677 | 306048021.6482 | 313354153.3096 | 333188812.1143 | 331324595.9602 | 336673384.3766 | 346444811.0024 | 374694981.4683 | 395568189.7109 | 407936515.558 | 317758657.1169 | 321541702.7441 | 337448150.0039 | 367778105.8238 | 374863369.0021 | 390437907.9489 | 411814011.2709 | 456529451.1034 | 494010464.2192 | 522193228.5791 | 3455241911.1161 | 3994375047.8122
| Check | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK

## Program Lvl
Code | ID | Description | FY20 (R) | FY21 (R) | FY22 (R) | FY23 (R) | FY24 (R) | FY25 (R) | FY26 (R) | FY27 (R) | FY28 (R) | FY29 (R) | FY20 (N) | FY21 (N) | FY22 (N) | FY23 (N) | FY24 (N) | FY25 (N) | FY26 (N) | FY27 (N) | FY28 (N) | FY29 (N) | Total (R) | Total (N)
AG | AG | Automation - operational/capacity risk | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | 384025.3633 | 3000000 | 3445039.8936
AR | AR | Asset relocation | 1623650 | 1563851 | 1542485 | 1535001 | 1533069 | 1533069 | 1533069 | 1533069 | 1533069 | 1533069 | 1664241.25 | 1643020.9569 | 1661087.6357 | 1694353.8909 | 1734526.8575 | 1777890.029 | 1822337.2797 | 1867895.7117 | 1914593.1045 | 1962457.9321 | 15463401 | 17742404.6479
AU | AU004 | Substation SCADA RTU replacement | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2234500 | 2290362.5 | 2347621.5625 | 2406312.1016 | 2466469.9041 | 2528131.6517 | 2591334.943 | 2656118.3166 | 2722521.2745 | 2790584.3063 | 21800000 | 25033956.5603
AU | AU013 | SCADA master station development software | 1110000 | 1110000 | 2110000 | 2110000 | 1110000 | 1110000 | 1110000 | 2110000 | 2110000 | 1110000 | 1137750 | 1166193.75 | 2272239.2187 | 2329045.1992 | 1255863.1163 | 1287259.6942 | 1319441.1866 | 2570830.1137 | 2635100.8666 | 1420893.8441 | 15100000 | 17394616.9895
CC | CC002 | Communications development SCADA | 625000 | 525000 | 525000 | 525000 | 525000 | 450000 | 450000 | 450000 | 450000 | 450000 | 640625 | 551578.125 | 565367.5781 | 579501.7676 | 593989.3118 | 521862.0382 | 534908.5892 | 548281.3039 | 561988.3365 | 576038.0449 | 4975000 | 5674140.0951
CC | CC007 | SCADA radio repeaters | 880000 | 840000 | 850000 | 690000 | 640000 | 740000 | 620000 | 610000 | 590000 | 490000 | 902000 | 882525 | 915357.0312 | 761630.8945 | 724101.2562 | 858173.1295 | 736985.1673 | 743225.7675 | 736829.1523 | 627241.4267 | 6950000 | 7888068.8252
CC | CC020 | Microwave refurbishment and extension | 670000 | 670000 | 490000 | 430000 | 280000 | 940000 | 1550000 | 1230000 | 1520000 | 930000 | 686750 | 703918.75 | 527676.4062 | 474639.543 | 316794.2996 | 1090111.8131 | 1842462.9182 | 1498635.5639 | 1898271.7143 | 1190478.6261 | 8710000 | 10229739.6345
DS | DS002 | Pole substation refurbishment | 700000 | 700000 | 700000 | 750000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 717500 | 735437.5 | 753823.4375 | 827859.668 | 905126.5703 | 927754.7346 | 950948.6029 | 974722.318 | 999090.376 | 1024067.6354 | 7650000 | 8816330.8426
DS | DS005 | Distribution pole replacement | 11330000 | 12100000 | 12870000 | 13640000 | 14410000 | 15180000 | 16720000 | 17490000 | 17490000 | 17490000 | 11613250 | 12712562.5 | 13859582.3437 | 15056007.8281 | 16303592.3478 | 17604146.0885 | 19874825.8013 | 21309866.6774 | 21842613.3444 | 22388678.678 | 148720000 | 172565125.6093
DS | DS006 | LV CONSAC cable replacement | 6750000 | 7500000 | 9750000 | 9750000 | 11250000 | 11250000 | 12000000 | 12000000 | 12750000 | 12750000 | 6918750 | 7879687.5 | 10499683.5937 | 10762175.6836 | 12728342.395 | 13046550.9549 | 14264229.044 | 14620834.7701 | 15923002.8668 | 16321077.9385 | 105750000 | 122964334.7467
DS | DS007 | Service wire replacement program | 9200000 | 9300000 | 9300000 | 9450000 | 9800000 | 9800000 | 10300000 | 10300000 | 10800000 | 10800000 | 9430000 | 9770812.5 | 10015082.8125 | 10431031.8164 | 11087800.4863 | 11364995.4985 | 12243463.2628 | 12549549.8444 | 13487720.0754 | 13824913.0773 | 99050000 | 114205369.3736
DS | DS008 | Traffic black spot remediation | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 10000000 | 11483466.3121
DS | DS011 | HV distribution steel mains replacement | 3696000 | 4312000 | 5236000 | 5390000 | 6006000 | 6006000 | 6006000 | 6006000 | 6006000 | 6006000 | 3788400 | 4530295 | 5638599.3125 | 5949551.4805 | 6795237.7266 | 6965118.6698 | 7139246.6365 | 7317727.8024 | 7500670.9975 | 7688187.7724 | 54670000 | 63313035.3983
DS | DS014 | LV cable network renewal | 0 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 0 | 1365812.5 | 1399957.8125 | 1434956.7578 | 1470830.6768 | 1507601.4437 | 1545291.4798 | 1583923.7668 | 1623521.8609 | 1664109.9075 | 11700000 | 13596006.2057
DS | DS301 | Ground substation refurbishment program | 510000 | 510000 | 850000 | 850000 | 1020000 | 1275000 | 1275000 | 1275000 | 1275000 | 1275000 | 522750 | 535818.75 | 915357.0312 | 938240.957 | 1154036.3771 | 1478609.1082 | 1515574.3359 | 1553463.6943 | 1592300.2867 | 1632107.7939 | 10115000 | 11838258.3344
DS | DS302 | Distribution transformer replacement program | 1250000 | 1250000 | 1250000 | 1562500 | 1562500 | 1562500 | 1562500 | 1687500 | 1687500 | 1687500 | 1281250 | 1313281.25 | 1346113.2812 | 1724707.6416 | 1767825.3326 | 1812020.966 | 1857321.4901 | 2056054.8895 | 2107456.2618 | 2160142.6683 | 15062500 | 17426173.7812
DS | DS305 | Compact LV switchgear replacement | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 512500 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | 640042.2721 | 5000000 | 5741733.156
DS | DS307 | Holec MD4 epoxy switchgear replacement | 5950000 | 5600000 | 5950000 | 5950000 | 5950000 | 5950000 | 7700000 | 7700000 | 9450000 | 9450000 | 6098750 | 5883500 | 6407499.2187 | 6567686.6992 | 6731878.8667 | 6900175.8384 | 9152880.3032 | 9381702.3108 | 11801755.066 | 12096798.9427 | 69650000 | 81022627.2458
DS | DS312 | Miscellaneous substation renewal expenditure | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 2000000 | 2000000 | 2500000 | 2500000 | 1537500 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1739540.1273 | 2377371.5073 | 2436805.795 | 3122157.4249 | 3200211.3605 | 18000000 | 20957691.3078
DS | DS315 | Low voltage switchgear replacement | 708000 | 708000 | 708000 | 708000 | 708000 | 708000 | 708000 | 708000 | 708000 | 708000 | 725700 | 743842.5 | 762438.5625 | 781499.5266 | 801037.0147 | 821062.9401 | 841589.5136 | 862629.2514 | 884194.9827 | 906299.8573 | 7080000 | 8130294.1489
DS | DS317 | Future distribution substation renewals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 9300000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5482813.0388 | 11614425.6205 | 19201268.1629 | 28800000 | 36298506.8223
DS | DS318 | Distribution substation earthing refurbishment | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 276750 | 283668.75 | 290760.4687 | 298029.4805 | 305480.2175 | 313117.2229 | 320945.1535 | 328968.7823 | 337193.0019 | 345622.8269 | 2700000 | 3100535.9043
DS | DS405 | Air break switch replacement program | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3731000 | 3824275 | 3919881.875 | 4017878.9219 | 4118325.8949 | 4221284.0423 | 4326816.1434 | 4434986.5469 | 4545861.2106 | 4659507.7409 | 36400000 | 41799817.3759
DS | DS409 | Miscellaneous mains renewal expenditure | 1095000 | 1095000 | 1095000 | 1095000 | 1095000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1122375 | 1150434.375 | 1179195.2344 | 1208675.1152 | 1238891.9931 | 1391632.1019 | 1426422.9044 | 1462083.477 | 1498635.5639 | 1536101.453 | 11475000 | 13214447.218
DS | DS413 | Low mains remediation | 1625000 | 1625000 | 1625000 | 1625000 | 1625000 | 975000 | 975000 | 975000 | 975000 | 975000 | 1665625 | 1707265.625 | 1749947.2656 | 1793695.9473 | 1838538.3459 | 1130701.0828 | 1158968.6098 | 1187942.8251 | 1217641.3957 | 1248082.4306 | 13000000 | 14698408.5278
DS | DS414 | Copper distribution mains replacement | 0 | 960000 | 960000 | 960000 | 960000 | 960000 | 1200000 | 1680000 | 1920000 | 1920000 | 0 | 1008600 | 1033815 | 1059660.375 | 1086151.8844 | 1113305.6815 | 1426422.9044 | 2046916.8678 | 2397816.9023 | 2457762.3249 | 11520000 | 13630451.9402
DS | DS415 | LV mains replacement | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1095000 | 1095000 | 1095000 | 1095000 | 1095000 | 1127500 | 1155687.5 | 1184579.6875 | 1214194.1797 | 1244549.0342 | 1269864.2929 | 1301610.9003 | 1334151.1728 | 1367504.9521 | 1401692.5759 | 10975000 | 12601334.2953
DS | DS416 | Asbestos service fuse replacement | 261000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261000 | 267525
DS | DS417 | Distribution access track reconstruction | 440000 | 1408000 | 1232000 | 1232000 | 1320000 | 1320000 | 1320000 | 1540000 | 1540000 | 1540000 | 451000 | 1479280 | 1326729.25 | 1359897.4812 | 1493458.841 | 1530795.312 | 1569065.1948 | 1876340.4622 | 1923248.9737 | 1971330.1981 | 12892000 | 14981145.7131
DS | DS418 | Pole top structure/hardware refurbishment (LV) | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2674891.25 | 2741763.5312 | 2810307.6195 | 2880565.31 | 2952579.4428 | 3026393.9288 | 3102053.7771 | 3179605.1215 | 3259095.2495 | 3340572.6308 | 26096500 | 29967827.8612
DS | DS420 | Future distribution feeder refurbishment works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 9300000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5482813.0388 | 11614425.6205 | 19201268.1629 | 28800000 | 36298506.8223
DS | DS421 | Pole top structure/hardware refurbishment (HV) | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3329640.75 | 3412881.7687 | 3498203.813 | 3585658.9083 | 3675300.381 | 3767182.8905 | 3861362.4628 | 3957896.5244 | 4056843.9375 | 4158265.0359 | 32484300 | 37303236.4721
DU | DU | Duct installation RMS road works | 2152731 | 2206549 | 2261713 | 2318255 | 2376212 | 2376212 | 2376212 | 2376212 | 2376212 | 2558920 | 2206549.275 | 2318255.5431 | 2435617.5261 | 2558919.7528 | 2688465.7724 | 2755677.4167 | 2824569.3521 | 2895183.5859 | 2967563.1755 | 3275633.9418 | 23379228 | 26926435.3414
EF | EF001 | Distribution management system | 8585366 | 3616895 | 92860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8800000.15 | 3800000.3094 | 100000.0634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12295121 | 12700000.5228
EF | EF002 | Technology pilots | 500000 | 500000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 512500 | 525312.5 | 2153781.25 | 2207625.7812 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | 2560169.0884 | 17000000 | 19853495.1241
HV | HVW | HV development works | 6800844 | 7103063 | 6647368 | 6275047 | 5947097 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6970865.1 | 7462655.5644 | 7158488.2801 | 6926477.7679 | 6728594.3887 | 6958160.5093 | 7132114.522 | 7310417.3851 | 7493177.8197 | 7680507.2652 | 62773419 | 71821458.6022
IC | IC | Industrial & commercial | 7501444 | 5332550 | 4584087 | 4321346 | 4245553 | 4245553 | 4245553 | 4245553 | 4245553 | 4245553 | 7688980.1 | 5602510.3438 | 4936560.3145 | 4769957.4197 | 4803453.5325 | 4923539.8708 | 5046628.3675 | 5172794.0767 | 5302113.9287 | 5434666.7769 | 47212745 | 53681204.7309
LV | LV001 | Overloaded distribution sub uprates | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 82000 | 84050 | 86151.25 | 88305.0312 | 90512.657 | 92775.4735 | 95094.8603 | 97472.2318 | 99909.0376 | 102406.7635 | 800000 | 918677.305
LV | LV002 | Quality of supply reactive projects | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 512500 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | 640042.2721 | 5000000 | 5741733.156
LV | LV003 | LV planning reactive projects | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 10000000 | 11483466.3121
LV | LV005 | Dsub monitoring & LV feeder monitoring for solar PV | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 256250 | 262656.25 | 269222.6562 | 275953.2227 | 282852.0532 | 289923.3546 | 297171.4384 | 304600.7244 | 312215.7425 | 320021.136 | 2500000 | 2870866.578
MC | MC104 | Meters - renewal | 60000 | 60000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 61500 | 63037.5 | 10768.9062 | 11038.1289 | 11314.0821 | 11596.9342 | 11886.8575 | 12184.029 | 12488.6297 | 12800.8454 | 200000 | 218615.9131
MC | MC105 | Relays - renewal | 957584 | 907185 | 856786 | 806386 | 755987 | 705588 | 655189 | 604790 | 554391 | 503992 | 981523.6 | 953111.2406 | 922664.811 | 890099.2616 | 855329.9006 | 818265.7596 | 778813.8303 | 736877.8884 | 692358.3908 | 645152.3696 | 7307878 | 8274197.0525
MC | MC107 | Test equipment | 120000 | 80000 | 120000 | 80000 | 120000 | 85000 | 120000 | 85000 | 120000 | 85000 | 123000 | 84050 | 129226.875 | 88305.0312 | 135768.9855 | 98573.9405 | 142642.2904 | 103564.2463 | 149863.5564 | 108807.1863 | 1015000 | 1163802.1117
MC | MC109 | Demand management technology | 1400000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 1435000 | 787968.75 | 807667.9687 | 827859.668 | 848556.1597 | 869770.0637 | 891514.3153 | 913802.1731 | 936647.2275 | 960063.4081 | 8150000 | 9278849.734
NU | NU | Non urban extension | 1019340 | 743122 | 661806 | 631694 | 619417 | 619417 | 619417 | 619417 | 619417 | 619417 | 1044823.5 | 780742.5512 | 712692.677 | 697271.9801 | 700813.481 | 718333.818 | 736292.1635 | 754699.4676 | 773566.9543 | 792906.1281 | 6772464 | 7712142.7208
PQ | PQ001 | Permanent power quality monitoring | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 102500 | 105062.5 | 107689.0625 | 110381.2891 | 113140.8213 | 115969.3418 | 118868.5754 | 121840.2898 | 124886.297 | 128008.4544 | 1000000 | 1148346.6312
PQ | PQ004 | Power quality monitoring replacement | 342400 | 617700 | 873300 | 947600 | 1364538 | 1299560 | 1429516 | 1429516 | 1169604 | 1169604 | 350960 | 648971.0625 | 940448.5828 | 1045973.0952 | 1543849.5 | 1507091.1786 | 1699245.3038 | 1741726.4364 | 1460675.1251 | 1497192.0032 | 10643338 | 12436132.2877
PR | PR081 | Collimore Park ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4195200 | 12585600 | 11187200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5111443.8356 | 15717689.7946 | 14320561.8128 | 27968000 | 35149695.443
PR | PR110 | Edmondson Park ZS establishment | 1765854 | 5111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810000.35 | 5369.7444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1770965 | 1815370.0944
PR | PR113 | Augment feeder 308 Nepean to Douglas Park | 1313250 | 3939750 | 3502000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346081.25 | 4139199.8437 | 3771270.9687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8755000 | 9256552.0625
PR | PR170 | Holsworthy 33/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4202400 | 8404800 | 8404800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5120216.3365 | 10496443.4898 | 10758854.5771 | 21012000 | 26375514.4034
PR | PR190 | Eschol Park ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 4429200 | 8858400 | 8858400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5264926.9401 | 10793100.2273 | 11062927.733 | 0 | 22146000 | 27120954.9004
PRL | PR248 | Penrith Lakes ZS site acquisition | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347908.0255 | 0 | 0 | 0 | 0 | 300000 | 347908.0255
PR | PR249 | Establish Penrith Lakes 33/11kV Zone Substation | 0 | 0 | 0 | 0 | 0 | 1571001 | 6284004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1821879.5197 | 7469706.0308 | 0 | 0 | 0 | 7855005 | 9291585.5505
PR | PR258 | Menangle Park 66/11kV ZS establishment | 4487188 | 8566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4599367.7 | 8999.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4495754 | 4608367.3537
PR | PR278 | Kemps Creek new BSP associated works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278000 | 1278000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557118.903 | 1596046.8756 | 0 | 2556000 | 3153165.7786
PR | PR292 | South Marsden Park (industrial) 132/11kV ZS establishment | 1215012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245387.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215012 | 1245387.3
PR | PR423 | Maryland ZS establishment | 0 | 4126720 | 8253440 | 8253440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4335635.2 | 8888052.16 | 9110253.464 | 0 | 0 | 0 | 0 | 0 | 0 | 20633600 | 22333940.824
PR | PR425 | Austral ZS establishment (interim initially) | 0 | 3556000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3736022.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3556000 | 3736022.5
PR | PR427 | Leppington North ZS establishment | 1755910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1799807.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1755910 | 1799807.75
PRL | PR430 | North Rossmore ZS site purchase | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3311438.6719 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3311438.6719
PRL | PR432 | Rossmore ZS site purchase | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3394224.6387 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3394224.6387
PR | PR433 | Rossmore ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12800845.442 | 10000000 | 12800845.442
PR | PR435 | Catherine Fields North ZS establishment (interim) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4291200 | 8582400 | 8582400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5228410.5138 | 10718241.5533 | 10986197.5921 | 21456000 | 26932849.6592
PRL | PR436 | Catherine Fields ZS site purchase | 653024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669349.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653024 | 669349.6
PRL | PR438 | North Bringelly ZS site purchase | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769117.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3769117.1875
PR | PR439 | North Bringelly ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 4420000 | 8840000 | 8840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5253991.0312 | 10770681.614 | 11039948.6543 | 0 | 22100000 | 27064621.2995
PR | PR444 | Culburra Beach development (33kV fdr and single transformer ZS) | 0 | 0 | 0 | 0 | 0 | 0 | 3832500 | 1916250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4555638.1509 | 2334764.5524 | 0 | 0 | 5748750 | 6890402.7033
PR | PR499 | Southpipe (Oakdale Estate) ZS 132/11kV establishment | 6347200 | 12694400 | 12694400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6505880 | 13337054 | 13670480.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31736000 | 33513414.35
PRL | PR602 | Riverstone West site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6092014.4875 | 0 | 0 | 5000000 | 6092014.4875
PRL | PR603 | Eschol Park ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400422.721 | 5000000 | 6400422.721
PR | PR620 | West Dapto ZS establishment | 0 | 0 | 4085600 | 8171200 | 4671200 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 4399744.3375 | 9019475.8919 | 5285034.0441 | 4058926.9637 | 0 | 0 | 0 | 0 | 20428000 | 22763181.2372
PR | PR653 | Avondale (South West Dapto) 132/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5943428.7683 | 6092014.4875 | 6244314.8497 | 0 | 15000000 | 18279758.1056
PR | PR656 | Leppington South ZS establishment (permanent) | 13566645 | 3526693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13905811.125 | 3705231.8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17093338 | 17611042.9581
PR | PR657 | Calderwood ZS establishment (interim initially) | 1476500 | 1476500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513412.5 | 1551247.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2953000 | 3064660.3125
PRL | PR659 | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2899233.5455 | 0 | 0 | 0 | 0 | 2500000 | 2899233.5455
PR | PR673 | Liverpool ZS 11kV switchboard extension & distribution works | 292683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292683 | 300000.075
PR | PR677 | South Penrith Zone Substation | 0 | 0 | 0 | 5826000 | 11652000 | 11652000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6430813.9008 | 13183168.4966 | 13512747.709 | 0 | 0 | 0 | 0 | 29130000 | 33126730.1064
PR | PR698 | Marsden Park (residential) 132/11kV ZS - stage 2 | 3064000 | 3064000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3140600 | 3219115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6128000 | 6359715
PR | PR700 | Riverstone east ZS establishment | 0 | 0 | 4085600 | 8171200 | 4671200 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 4399744.3375 | 9019475.8919 | 5285034.0441 | 4058926.9637 | 0 | 0 | 0 | 0 | 20428000 | 22763181.2372
PRL | PR703 | Riverstone East site purchase | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6150000
PRL | PR704 | Oakdale (Southpipe) site purchase | 195122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195122 | 200000.05
PR | PR713 | Box Hill 132/22kV ZS establishment | 7169600 | 14339200 | 14339200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7348840 | 15065122 | 15441750.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35848000 | 37855712.05
PRL | PR717 | Acquire improved site for West Dapto ZS | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2050000
PR | PR722 | Camellia TS connection works for Ausgrid | 274973 | 104989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281847.325 | 110304.0681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379962 | 392151.3931
PR | PR723 | Supply to Luddenham Science Park | 0 | 0 | 0 | 8617000 | 17234000 | 17234000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9511555.6785 | 19498689.141 | 19986156.3695 | 0 | 0 | 0 | 0 | 43085000 | 48996401.189
PR | PR724 | Establish Mt Gilead ZS | 0 | 0 | 4044600 | 8089200 | 4589200 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 4355591.8219 | 8928963.2348 | 5192258.5706 | 4058926.9637 | 0 | 0 | 0 | 0 | 20223000 | 22535740.5911
PR | PR728 | Western Sydney Employment Lands ZS | 0 | 0 | 4517000 | 9034000 | 9034000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4864314.9531 | 9971845.6539 | 10221141.7953 | 0 | 0 | 0 | 0 | 0 | 22585000 | 25057302.4023
PR | PR729 | Cheriton Avenue 3rd transformer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7066066.684 | 5520000 | 7066066.684
PR | PR732 | Feeder 214/215 contraints | 5140000 | 5140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5268500 | 5400212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10280000 | 10668712.5
PR | PR733 | Bringelly ZS augmentation | 0 | 0 | 0 | 0 | 0 | 4264000 | 8528000 | 8528000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4944932.7353 | 10137112.1073 | 10390539.91 | 0 | 0 | 21320000 | 25472584.7525
PR | PR739 | South Gilead (South Campbelltown) | 0 | 0 | 0 | 0 | 0 | 4044600 | 8089200 | 8089200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690495.9993 | 9615516.7986 | 9855904.7185 | 0 | 0 | 20223000 | 24161917.5164
PR | PR740 | AFIC upgrade Minto, Prospect, Kingswood | 311163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318942.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311163 | 318942.075
PR | PR741 | Western Sydney Airport 132kV supply | 0 | 0 | 7860000 | 15720000 | 15720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8464360.3125 | 17351938.6406 | 17785737.1066 | 0 | 0 | 0 | 0 | 0 | 39300000 | 43602036.0598
PR | PR742 | North Bomaderry ZS establishment | 0 | 0 | 3683200 | 7366400 | 3866400 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 3966403.55 | 8131127.2775 | 4374476.7143 | 4058926.9637 | 0 | 0 | 0 | 0 | 18416000 | 20530934.5056
PR | PR744 | Termeil ZS establishment | 0 | 0 | 0 | 0 | 0 | 3980750 | 3980750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4616449.5746 | 4731860.8139 | 0 | 0 | 0 | 7961500 | 9348310.3885
PR | PR745 | Austral Permanent ZS establishment | 0 | 0 | 0 | 0 | 0 | 10518500 | 10518500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12198235.2195 | 12503191.1 | 0 | 0 | 0 | 21037000 | 24701426.3194
PR | PR746 | Sydney University - Western Sydney Employment Lands ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12256000 | 12256000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14932745.9119 | 15306064.5597 | 0 | 24512000 | 30238810.4716
PR | PR748 | Establish permanent Catherine Park ZS | 0 | 0 | 0 | 0 | 1900000 | 3800000 | 3800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2149675.6045 | 4406834.9892 | 4517005.8639 | 0 | 0 | 0 | 9500000 | 11073516.4576
PR | PR749 | Nepean ZS augmentation | 0 | 0 | 0 | 0 | 0 | 0 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4279268.7132 | 0 | 0 | 0 | 3600000 | 4279268.7132
PR | PR751 | Parklea ZS to Bella Vista ZS load transfer | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1050625
PR | PR752 | Kemps Creek 132kV conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8898000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11390192.2743 | 8898000 | 11390192.2743
PR | PR754 | Augment Westmead Zone Substation | 0 | 0 | 0 | 5126500 | 5126500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5658696.7838 | 5800164.2034 | 0 | 0 | 0 | 0 | 0 | 10253000 | 11458860.9872
PR | PR755 | Narellan ZS busbar augmentation | 0 | 0 | 0 | 0 | 0 | 0 | 7280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8653632.2867 | 0 | 0 | 0 | 7280000 | 8653632.2867
PRL | PR761 | Glenfield Zone Substation site acquisition | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3151875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3151875
PR | PR765 | Minto 66kV Reconfiguration | 300000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307500 | 420250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 727750
PR | PR766 | Baulkham Hills 132kV bus section CB | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367718.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 367718.75
PR | PR767 | Mt Terry 132kV bus section CB | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430756.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 430756.25
PR | PR768 | Establish Glenfield 66/11kV Zone Substation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6220000 | 12440000 | 12440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7578466.0225 | 15535855.3461 | 15924251.7298 | 31100000 | 39038573.0985
PR | PR769 | Nepean TS 132kV bus section CB | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307500 | 315187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 622687.5
PS | PS008 | Substation protection relay refurbishment | 4375000 | 4500000 | 4500000 | 4500000 | 4500000 | 4750000 | 4750000 | 4750000 | 4750000 | 4750000 | 4484375 | 4727812.5 | 4846007.8125 | 4967158.0078 | 5091336.958 | 5508543.7365 | 5646257.3299 | 5787413.7632 | 5932099.1073 | 6080401.5849 | 46125000 | 53071405.8001
PS | PS011 | Protection refurbishment (miscellaneous) | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 717500 | 735437.5 | 753823.4375 | 772669.0234 | 791985.749 | 811785.3927 | 832080.0276 | 852882.0283 | 874204.079 | 896059.1809 | 7000000 | 8038426.4184
PS | PS012 | Distribution feeder safety improvement | 3100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3177500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100000 | 3177500
PS | PS013 | Feeder differential relay replacement | 0 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 0 | 346706.25 | 355373.9062 | 364258.2539 | 373364.7103 | 382698.828 | 392266.2987 | 402072.9562 | 412124.7801 | 422427.8996 | 2970000 | 3451293.883
PS | PS014 | Under frequency load shedding | 550000 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563750 | 577843.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 1141593.75
RC | RC | Reliability compliance | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 5120338.1768 | 40000000 | 45933865.2482
SL | SL001 | Streetlighting growth | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1793750 | 1838593.75 | 1884558.5937 | 1931672.5586 | 1979964.3726 | 2029463.4819 | 2080200.0689 | 2132205.0706 | 2185510.1974 | 2240147.9523 | 17500000 | 20096066.0461
SL | SL002 | Streetlighting refurbishment | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3075000 | 3151875 | 3230671.875 | 3311438.6719 | 3394224.6387 | 3479080.2546 | 3566057.261 | 3655208.6925 | 3746588.9098 | 3840253.6326 | 30000000 | 34450398.9362
SP | SP | Essential spares | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 10000000 | 11483466.3121
TM | TM012 | Sub-transmission pole replacement | 3720000 | 3720000 | 3720000 | 3720000 | 4920000 | 5540000 | 5540000 | 5540000 | 5540000 | 5540000 | 3813000 | 3908325 | 4006033.125 | 4106183.9531 | 5566528.4074 | 6424701.5369 | 6585319.0753 | 6749952.0522 | 6918700.8535 | 7091668.3748 | 47500000 | 55170412.3783
TM | TM014 | Renewal of 33kV and 66kV gas and oil filled cables | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 2674542.9458 | 2741406.5194 | 2809941.6824 | 2880190.2244 | 9000000 | 11106081.372
TM | TM015 | Subtransmission tower replacement | 960000 | 960000 | 960000 | 960000 | 960000 | 1920000 | 1920000 | 1920000 | 1920000 | 1920000 | 984000 | 1008600 | 1033815 | 1059660.375 | 1086151.8844 | 2226611.363 | 2282276.647 | 2339333.5632 | 2397816.9023 | 2457762.3249 | 14400000 | 16876028.0598
TM | TM028 | 132kV oil cable replacement | 0 | 0 | 0 | 0 | 0 | 10200000 | 9900000 | 9900000 | 10200000 | 10200000 | 0 | 0 | 0 | 0 | 0 | 11828872.8658 | 11767988.9613 | 12062188.6853 | 12738402.2935 | 13056862.3508 | 50400000 | 61454315.1567
TM | TM030 | Feeder 7028 replacement | 1600000 | 1600000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640000 | 1681000 | 1723025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800000 | 5044025
TM | TM031 | Steel tower asbestos removal | 2812195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2882499.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2812195 | 2882499.875
TM | TM033 | Pole top structure/hardware refurbishment (TR) | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1381361.75 | 1415895.7937 | 1451293.1886 | 1487575.5183 | 1524764.9063 | 1562884.0289 | 1601956.1296 | 1642005.0329 | 1683055.1587 | 1725131.5377 | 13476700 | 15475923.0448
TM | TM132 | Sub-transmission pilot cable renewal program | 0 | 0 | 0 | 0 | 0 | 0 | 1115000 | 1115000 | 1115000 | 1115000 | 0 | 0 | 0 | 0 | 0 | 0 | 1325384.6153 | 1358519.2307 | 1392482.2115 | 1427294.2668 | 4460000 | 5503680.3243
TM | TM134 | Wollongong - Port Kembla pilot cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 1665000 | 1665000 | 1665000 | 1665000 | 0 | 0 | 0 | 0 | 0 | 0 | 1979161.7799 | 2028640.8244 | 2079356.845 | 2131340.7661 | 6660000 | 8218500.2153
TM | TM135 | Optical fibre protection and communication upgrades in the Blue Mountains | 0 | 0 | 0 | 0 | 0 | 0 | 928000 | 928000 | 928000 | 928000 | 0 | 0 | 0 | 0 | 0 | 0 | 1103100.3794 | 1130677.8889 | 1158944.8361 | 1187918.457 | 3712000 | 4580641.5614
TM | TM137 | Optical fibre protection and communication upgrades in the Macarthur area | 0 | 0 | 0 | 0 | 0 | 0 | 908000 | 908000 | 908000 | 908000 | 0 | 0 | 0 | 0 | 0 | 0 | 1079326.6643 | 1106309.8309 | 1133967.5767 | 1162316.7661 | 3632000 | 4481920.8381
TM | TM171 | Replacement of corroded earthwires | 0 | 0 | 0 | 0 | 138000 | 897000 | 897000 | 897000 | 897000 | 897000 | 0 | 0 | 0 | 0 | 156134.3334 | 1040244.9961 | 1066251.121 | 1092907.3991 | 1120230.084 | 1148235.8361 | 4623000 | 5624003.7698
TM | TM172 | Earthwire replacement due to fault rating | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050625 | 1076890.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2127515.625
TM | TM174 | Hardex earthwire replacement | 0 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 9000000 | 10458466.3121
TM | TM302 | Oil filled cable auxiliary equipment refurbishment | 0 | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 75645 | 0 | 0 | 0 | 0 | 85585.3743 | 0 | 0 | 0 | 144000 | 161230.3743
TM | TM303 | Guilford and Camellia 132kV cables oil testing and flushing | 0 | 90000 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 94556.25 | 0 | 0 | 0 | 0 | 106981.7178 | 0 | 0 | 0 | 180000 | 201537.9678
TM | TM419 | Future sub-transmission feeder refurbishment works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 9300000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5482813.0388 | 11614425.6205 | 19201268.1629 | 28800000 | 36298506.8223
TM | TM801 | Steel tower painting program | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 800000 | 800000 | 800000 | 0 | 0 | 0 | 0 | 0 | 927754.7346 | 950948.6029 | 974722.318 | 999090.376 | 1024067.6354 | 4000000 | 4876583.6668
TM | TM803 | Steel tower below ground rectification work | 0 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1200000 | 750000 | 750000 | 0 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1739540.1273 | 1783028.6305 | 1462083.477 | 936647.2275 | 960063.4081 | 11700000 | 13425467.9632
TM | TM805 | Earthing refurbishment of lines 940/941 | 280000 | 280000 | 280000 | 280000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 287000 | 294175 | 301529.375 | 309067.6094 | 22628.1643 | 23193.8684 | 23773.7151 | 24368.058 | 24977.2594 | 25601.6909 | 1240000 | 1336314.7403
TM | TM809 | Subtransmission line earthing refurbishment | 0 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | 630375 | 646134.375 | 662287.7344 | 678844.9277 | 695816.0509 | 713211.4522 | 731041.7385 | 749317.782 | 768050.7265 | 5400000 | 6275079.7872
TS | TS004 | 132kV circuit breaker replacement | 0 | 0 | 0 | 362000 | 362000 | 362000 | 362000 | 362000 | 362000 | 362000 | 0 | 0 | 0 | 399580.2664 | 409569.7731 | 419809.0174 | 430304.2428 | 441061.8489 | 452088.3951 | 463390.605 | 2534000 | 3015804.1487
TS | TS005 | 33kV circuit breaker replacement | 0 | 0 | 0 | 770000 | 770000 | 1184000 | 1184000 | 1184000 | 1184000 | 1184000 | 0 | 0 | 0 | 849935.9258 | 871184.3239 | 1373077.0072 | 1407403.9323 | 1442589.0307 | 1478653.7564 | 1515620.1003 | 7460000 | 8938464.0766
TS | TS007 | 11kV circuit breaker replacement | 0 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367718.75 | 376911.7187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 744630.4688
TS | TS008 | Battery replacement | 520000 | 520000 | 520000 | 520000 | 520000 | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 | 533000 | 546325 | 559983.125 | 573982.7031 | 588332.2707 | 1206081.1549 | 1236233.1838 | 1267139.0134 | 1298817.4887 | 1331287.926 | 7800000 | 9141181.8657
TS | TS009 | Auxiliary switchgear replacement | 0 | 0 | 0 | 282000 | 0 | 282000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311275.2352 | 0 | 327033.5439 | 0 | 0 | 0 | 0 | 564000 | 638308.7791
TS | TS015 | Replacement of surge arrester in zone and sub-transmission substations | 37000 | 118000 | 118000 | 118000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 37925 | 123973.75 | 127073.0937 | 130249.9211 | 56570.4106 | 57984.6709 | 59434.2877 | 60920.1449 | 62443.1485 | 64004.2272 | 691000 | 780578.6547
TS | TS016 | VT and CT replacement | 0 | 0 | 0 | 698000 | 698000 | 698000 | 698000 | 698000 | 698000 | 698000 | 0 | 0 | 0 | 770461.3977 | 789722.9326 | 809466.0059 | 829702.6561 | 850445.2225 | 871706.353 | 893499.0118 | 4886000 | 5815003.5796
TS | TS024 | Building and amenities refurbishment | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 1537500 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | 2560169.0884 | 17500000 | 20273064.2598
TS | TS025 | Asbestos and other hazardous material reporting, management and removal | 89000 | 450000 | 450000 | 518000 | 520000 | 539000 | 450000 | 450000 | 518000 | 520000 | 91225 | 472781.25 | 484600.7812 | 571775.0773 | 588332.2707 | 625074.7524 | 534908.5892 | 548281.3039 | 646911.0184 | 665643.963 | 4504000 | 5229534.0062
TS | TS026 | Noise attenuation in ZS and TS | 0 | 0 | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 1076890.625 | 0 | 1131408.2129 | 0 | 1188685.7537 | 0 | 1248862.9699 | 0 | 4000000 | 4645847.5615
TS | TS027 | Substation switchyard lighting improvement | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 112750 | 115568.75 | 118457.9687 | 121419.418 | 124454.9034 | 127566.276 | 130755.4329 | 134024.3187 | 137374.9267 | 140809.2999 | 1100000 | 1263181.2943
TS | TS031 | Substation safety fence upgrade program | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 102500 | 105062.5 | 107689.0625 | 110381.2891 | 113140.8213 | 115969.3418 | 118868.5754 | 121840.2898 | 124886.297 | 128008.4544 | 1000000 | 1148346.6312
TS | TS032 | Substation security systems | 150000 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153750 | 157593.75 | 161533.5937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 472877.3438
TS | TS033 | Substation fire hydrant installations | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 205000 | 210125 | 215378.125 | 220762.5781 | 226281.6426 | 231938.6836 | 237737.1507 | 243680.5795 | 249772.594 | 256016.9088 | 2000000 | 2296693.2624
TS | TS034 | Substation deluge showers and fire blankets | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 164000 | 168100 | 172302.5 | 176610.0625 | 181025.3141 | 185550.9469 | 190189.7206 | 194944.4636 | 199818.0752 | 204813.5271 | 1600000 | 1837354.6099
TS | TS035 | Substation oil containment program - bund walls | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 71750 | 73543.75 | 75382.3437 | 77266.9023 | 79198.5749 | 81178.5393 | 83208.0028 | 85288.2028 | 87420.4079 | 89605.9181 | 700000 | 803842.6418
TS | TS036 | Substation earthing | 340000 | 408000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348500 | 428655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748000 | 777155
TS | TS049 | Tunnelboard refurbishment | 0 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 49671.5801 | 50913.3696 | 0 | 0 | 0 | 56198.8336 | 57603.8045 | 180000 | 214387.5878
TS | TS055 | 66kV circuit breaker replacement | 258000 | 258000 | 0 | 0 | 0 | 258000 | 258000 | 258000 | 258000 | 258000 | 264450 | 271061.25 | 0 | 0 | 0 | 299200.9019 | 306680.9244 | 314347.9476 | 322206.6462 | 330261.8124 | 1806000 | 2108209.4826
TS | TS086 | Busbar support and isolator replacement | 0 | 94500 | 94500 | 94500 | 94500 | 94500 | 94500 | 94500 | 94500 | 94500 | 0 | 99284.0625 | 101766.1641 | 104310.3182 | 106918.0761 | 109591.028 | 112330.8037 | 115139.0738 | 118017.5507 | 120967.9894 | 850500 | 988325.0665
TS | TS116 | Roof refurbishment for control and switch rooms | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1537500 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1739540.1273 | 1783028.6305 | 1827604.3463 | 1873294.4549 | 1920126.8163 | 15000000 | 17225199.4681
TS | TS144 | Substation fire stopping measures | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 67650 | 69341.25 | 71074.7812 | 72851.6508 | 74672.9421 | 76539.7656 | 78453.2597 | 80414.5912 | 82424.956 | 84485.5799 | 660000 | 757908.7766
TS | TS146 | Marayong Zone Substation renewal | 8204878 | 1829077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8409999.95 | 1921674.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10033955 | 10331673.9731
TS | TS155 | Sussex Inlet Zone Substation - stage 2 renewal | 1678556 | 37345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1720519.9 | 39235.5906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1715901 | 1759755.4906
TS | TS167 | Carlingford Transmission Substation control building replacement | 0 | 4500000 | 4500000 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4727812.5 | 4846007.8125 | 4967158.0078 | 0 | 0 | 0 | 0 | 0 | 0 | 13500000 | 14540978.3203
TS | TS173 | 11kV switchboard truck replacement program | 3648000 | 3648000 | 3648000 | 2928000 | 2928000 | 2928000 | 2928000 | 2928000 | 0 | 0 | 3739200 | 3832680 | 3928497 | 3231964.1437 | 3312763.2473 | 3395582.3285 | 3480471.8867 | 3567483.6839 | 0 | 0 | 25584000 | 28488642.2903
TS | TS177 | Substation battery duplication | 0 | 918000 | 765000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964473.75 | 823821.3281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683000 | 1788295.0781
TS | TS180 | Transformer fire wall installation | 0 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | 630375 | 646134.375 | 662287.7344 | 678844.9277 | 695816.0509 | 713211.4522 | 731041.7385 | 749317.782 | 768050.7265 | 5400000 | 6275079.7872
TS | TS199 | Future sub-transmission substation renewal programs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 9300000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5482813.0388 | 11614425.6205 | 19201268.1629 | 28800000 | 36298506.8223
TS | TS600 | Power transformer replacement | 1700000 | 11600000 | 7500000 | 11000000 | 11100000 | 12700000 | 12700000 | 12700000 | 12700000 | 12700000 | 1742500 | 12187250 | 8076679.6875 | 12141941.7969 | 12558631.1631 | 14728106.4113 | 15096309.0716 | 15473716.7984 | 15860559.7183 | 16257073.7113 | 106400000 | 124122768.3584
TS | TS616 | Camellia TS transformer replacement and 33kV busbar rearrangement | 332642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340958.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332642 | 340958.05
TS | TS617 | Prospect ZS transformer replacement | 29268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29999.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29268 | 29999.7
TS | TS618 | Albion Park ZS transformer replacement | 1577261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616692.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1577261 | 1616692.525
TS | TS620 | Minto 66/11kV No 1 transformer replacement | 1080563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1107577.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080563 | 1107577.075
TS | TS700 | 11kV zone substation switchboard replacement | 0 | 4000000 | 4000000 | 8000000 | 12000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0 | 4202500 | 4307562.5 | 8830503.125 | 13576898.5547 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 5120338.1768 | 48000000 | 55300382.5138
TS | TS701 | North Rocks ZS 11kV switchboard replacement | 777546 | 36169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 796984.65 | 38000.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813715 | 834984.7056
TS | TS702 | Kellyville ZS 11kV switchboard replacement | 953171 | 265366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977000.275 | 278800.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218537 | 1255800.4287
TS | TS703 | Horsley Park ZS 11kV switchboard replacement | 424390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434999.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424390 | 434999.75
TS | TS704 | Port Central ZS 11kV switchboard replacement | 488652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500868.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488652 | 500868.3
UR | UR | Underground residential | 21659051 | 14600685 | 11758786 | 11056595 | 10803669 | 10803669 | 10803669 | 10803669 | 10803669 | 10803669 | 22200527.275 | 15339844.6781 | 12662926.4048 | 12204412.0874 | 12223359.836 | 12528943.8319 | 12842167.4276 | 13163221.6133 | 13492302.1537 | 13829609.7075 | 123897131 | 140487315.0153
| SW | Network Switching | 6283900.8865 | 6382175.5445 | 6686467.7532 | 6495126.3573 | 6714861.5396 | 7423719.2767 | 7683873.5145 | 7944102.7058 | 8085985.7683 | 8183178.6979 | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | 10475160.5735 | 71883392.0442 | 83109035.6151
| OH | Capitalised Overheads | 73106139.0812 | 73273110.1037 | 73775204.5564 | 73462071.757 | 73820942.4206 | 76860996.0999 | 77233408.4879 | 77593252.7624 | 77784338.9426 | 78058962.8601 | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | 99922071.8932 | 754968427.0719 | 868519522.4252
|  | Total | 310008445.9677 | 306048021.6482 | 313354153.3096 | 333188812.1143 | 331324595.9602 | 336673384.3766 | 346444811.0024 | 374694981.4683 | 395568189.7109 | 407936515.558 | 317758657.1169 | 321541702.7441 | 337448150.0039 | 367778105.8238 | 374863369.0021 | 390437907.9489 | 411814011.2709 | 456529451.1034 | 494010464.2192 | 522193228.5791 | 3455241911.1161 | 3994375047.8122
|  | Check | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK

## Division Lvl
ID | Description | Division | FY19 (R) | FY20 (R) | FY21 (R) | FY22 (R) | FY23 (R) | FY24 (R) | FY25 (R) | FY26 (R) | FY27 (R) | FY28 (R) | FY29 (R) | FY19 (N) | FY20 (N) | FY21 (N) | FY22 (N) | FY23 (N) | FY24 (N) | FY25 (N) | FY26 (N) | FY27 (N) | FY28 (N) | FY29 (N) | Reg Tot (R) | SAMP Tot (R) | Reg Tot (N) | SAMP Tot (N) | Rank | Wgt Rank | Percentage | Code | Plantname | Category | Type | Classification | RAB Category
AG | Automation - operational/capacity risk | Program - Short Term Need | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0 | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | 384025.3633 | 1500000 | 3000000 | 1616321.0186 | 3445039.8936 | 190 | 2850 | 66.11% | AG | AGs | Augex | Std | Std | Substations
AR | Asset relocation | Program - Short Term Need | 1674562.9105 | 1623650 | 1563851 | 1542485 | 1535001 | 1533069 | 1533069 | 1533069 | 1533069 | 1533069 | 1533069 | 1670000 | 1664241.25 | 1643020.9569 | 1661087.6357 | 1694353.8909 | 1734526.8575 | 1777890.029 | 1822337.2797 | 1867895.7117 | 1914593.1045 | 1962457.9321 | 7798056 | 15463401 | 8397230.591 | 17742404.6479 | 140 | 2100 | 78.28% | AR | ARs | Connections | Std | Std | Distribution lines and cables
AU002 | Transmission substation SCADA upgrade | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | AU | AU002s | Repex | Std | Unallocated | Unallocated
AU004 | Substation SCADA RTU replacement | Program - Short Term Need | 1044144 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 2180000 | 714162 | 2234500 | 2290362.5 | 2347621.5625 | 2406312.1016 | 2466469.9041 | 2528131.6517 | 2591334.943 | 2656118.3166 | 2722521.2745 | 2790584.3063 | 10900000 | 21800000 | 11745266.0682 | 25033956.5603 | 220 | 3300 | 54.32% | AU | AU004s | Repex | Std | Std | Substations
AU008 | Western Sydney Ramtel SCADA upgrades | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | AU | AU008s | Repex | Std | Unallocated | Unallocated
AU013 | SCADA master station development software | Program - Short Term Need | 1000000 | 1110000 | 1110000 | 2110000 | 2110000 | 1110000 | 1110000 | 1110000 | 2110000 | 2110000 | 1110000 | 978004 | 1137750 | 1166193.75 | 2272239.2187 | 2329045.1992 | 1255863.1163 | 1287259.6942 | 1319441.1866 | 2570830.1137 | 2635100.8666 | 1420893.8441 | 7550000 | 15100000 | 8161091.2843 | 17394616.9895 | 310 | 4650 | 21% | AU | AU013s | Repex | Std | Std | Substations
AU014 | SCADA substation refurbishments | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | AU | AU014s | Repex | Std | Unallocated | Unallocated
AU016 | PM121 (MD1000) MD3 to DNP3 conversion | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2250 | 70.85% | AU | AU016s | Repex | Std | Std | Substations
AU017 | AFIC availability and SCADA control | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | AU | AU017s | Repex | Std | Unallocated | Unallocated
CC002 | Communications development SCADA | Program - Short Term Need | 750000 | 625000 | 525000 | 525000 | 525000 | 525000 | 450000 | 450000 | 450000 | 450000 | 450000 | 515765.25 | 640625 | 551578.125 | 565367.5781 | 579501.7676 | 593989.3118 | 521862.0382 | 534908.5892 | 548281.3039 | 561988.3365 | 576038.0449 | 2725000 | 4975000 | 2931061.7825 | 5674140.0951 | 150 | 2250 | 70.85% | CC | CC002s | Repex | Std | Std | Communications
CC007 | SCADA radio repeaters | Program - Short Term Need | 870000 | 880000 | 840000 | 850000 | 690000 | 640000 | 740000 | 620000 | 610000 | 590000 | 490000 | 692279.51 | 902000 | 882525 | 915357.0312 | 761630.8945 | 724101.2562 | 858173.1295 | 736985.1673 | 743225.7675 | 736829.1523 | 627241.4267 | 3900000 | 6950000 | 4185614.182 | 7888068.8252 | 270 | 4050 | 37.22% | CC | CC007s | Repex | Std | Std | Communications
CC020 | Microwave refurbishment and extension | Program - Short Term Need | 550000 | 670000 | 670000 | 490000 | 430000 | 280000 | 940000 | 1550000 | 1230000 | 1520000 | 930000 | 418230.73 | 686750 | 703918.75 | 527676.4062 | 474639.543 | 316794.2996 | 1090111.8131 | 1842462.9182 | 1498635.5639 | 1898271.7143 | 1190478.6261 | 2540000 | 8710000 | 2709778.9988 | 10229739.6345 | 230 | 3450 | 51.29% | CC | CC020s | Repex | Std | Std | Communications
DS002 | Pole substation refurbishment | Program - Short Term Need | 735000 | 700000 | 700000 | 700000 | 750000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 740000 | 717500 | 735437.5 | 753823.4375 | 827859.668 | 905126.5703 | 927754.7346 | 950948.6029 | 974722.318 | 999090.376 | 1024067.6354 | 3650000 | 7650000 | 3939747.1758 | 8816330.8426 | 280 | 4200 | 36.29% | DS | DS002s | Repex | Std | Std | Transformers
DS003 | Distribution substation refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | DS | DS003s | Repex | Std | Std | Substations
DS004 | Distribution mains refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | DS | DS004s | Repex | Std | Std | Distribution lines and cables
DS005 | Distribution pole replacement | Program - Short Term Need | 10800000 | 11330000 | 12100000 | 12870000 | 13640000 | 14410000 | 15180000 | 16720000 | 17490000 | 17490000 | 17490000 | 10800000 | 11613250 | 12712562.5 | 13859582.3437 | 15056007.8281 | 16303592.3478 | 17604146.0885 | 19874825.8013 | 21309866.6774 | 21842613.3444 | 22388678.678 | 64350000 | 148720000 | 69544995.0196 | 172565125.6093 | 310 | 4650 | 21% | DS | DS005s | Repex | Std | Std | Distribution lines and cables
DS006 | LV CONSAC cable replacement | Program - Short Term Need | 6000000 | 6750000 | 7500000 | 9750000 | 9750000 | 11250000 | 11250000 | 11250000 | 11250000 | 11250000 | 11250000 | 6053654 | 6918750 | 7879687.5 | 10499683.5937 | 10762175.6836 | 12728342.395 | 13046550.9549 | 13372714.7288 | 13707032.597 | 14049708.4119 | 14400951.1222 | 45000000 | 101250000 | 48788639.1724 | 117365596.9871 | 230 | 3450 | 51.29% | DS | DS006s | Repex | Std | Std | Distribution lines and cables
DS006 | LV CONSAC cable replacement | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891514.3153 | 913802.1731 | 936647.2275 | 960063.4081 | 0 | 3000000 | 0 | 3702027.124 | 230 | 2300 | 69.74% | DS | DS006m | Repex | Std | Std | Distribution lines and cables
DS006 | LV CONSAC cable replacement | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936647.2275 | 960063.4081 | 0 | 1500000 | 0 | 1896710.6356 | 230 | 1150 | 94.48% | DS | DS006l | Repex | Std | Std | Distribution lines and cables
DS007 | Service wire replacement program | Program - Short Term Need | 9167401 | 9200000 | 9300000 | 9300000 | 9450000 | 9800000 | 9800000 | 9800000 | 9800000 | 9800000 | 9800000 | 4489678.5 | 9430000 | 9770812.5 | 10015082.8125 | 10431031.8164 | 11087800.4863 | 11364995.4985 | 11649120.3859 | 11940348.3956 | 12238857.1055 | 12544828.5331 | 47050000 | 96050000 | 50734727.6152 | 110472877.5339 | 300 | 4500 | 25.55% | DS | DS007s | Repex | Std | Std | Low Voltage lines and cables
DS007 | Service wire replacement program | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594342.8768 | 609201.4488 | 624431.485 | 640042.2721 | 0 | 2000000 | 0 | 2468018.0827 | 300 | 3000 | 58.52% | DS | DS007m | Repex | Std | Std | Low Voltage lines and cables
DS007 | Service wire replacement program | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624431.485 | 640042.2721 | 0 | 1000000 | 0 | 1264473.7571 | 300 | 1500 | 92.18% | DS | DS007l | Repex | Std | Std | Low Voltage lines and cables
DS008 | Traffic black spot remediation | Program - Short Term Need | 1700000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 917955.5 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 5000000 | 10000000 | 5387736.7285 | 11483466.3121 | 150 | 2250 | 70.85% | DS | DS008s | Repex | Std | Std | Distribution lines and cables
DS009 | Reliability focused distribution mains renewal | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | DS | DS009s | Repex | Std | Std | Distribution lines and cables
DS011 | HV distribution steel mains replacement | Program - Short Term Need | 4800000 | 3696000 | 4312000 | 5236000 | 5390000 | 6006000 | 6006000 | 6006000 | 6006000 | 6006000 | 6006000 | 4367566 | 3788400 | 4530295 | 5638599.3125 | 5949551.4805 | 6795237.7266 | 6965118.6698 | 7139246.6365 | 7317727.8024 | 7500670.9975 | 7688187.7724 | 24640000 | 54670000 | 26702083.5196 | 63313035.3983 | 280 | 4200 | 36.29% | DS | DS011s | Repex | Std | Std | Distribution lines and cables
DS012 | HV porcelain expulsion drop-out fuse replacement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3383.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4800 | 12.56% | DS | DS012s | Repex | Std | Std | Distribution lines and cables
DS014 | LV cable network renewal | Program - Short Term Need | 0 | 0 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 213.75 | 0 | 1365812.5 | 1399957.8125 | 1434956.7578 | 1470830.6768 | 1507601.4437 | 1545291.4798 | 1583923.7668 | 1623521.8609 | 1664109.9075 | 5200000 | 11700000 | 5671557.7471 | 13596006.2057 | 230 | 3450 | 51.29% | DS | DS014s | Repex | Std | Std | Low Voltage lines and cables
DS301 | Ground substation refurbishment program | Program - Short Term Need | 510000 | 510000 | 510000 | 510000 | 510000 | 510000 | 510000 | 510000 | 510000 | 510000 | 510000 | 504882.99 | 522750 | 535818.75 | 549214.2187 | 562944.5742 | 577018.1886 | 591443.6433 | 606229.7344 | 621385.4777 | 636920.1147 | 652843.1175 | 2550000 | 5100000 | 2747745.7315 | 5856567.8191 | 240 | 3600 | 42.68% | DS | DS301s | Repex | Std | Std | Substations
DS301 | Ground substation refurbishment program | Program - Medium Term Need |  | 0 | 0 | 340000 | 340000 | 510000 | 510000 | 510000 | 510000 | 510000 | 510000 | 0 | 0 | 0 | 366142.8125 | 375296.3828 | 577018.1886 | 591443.6433 | 606229.7344 | 621385.4777 | 636920.1147 | 652843.1175 | 1190000 | 3740000 | 1318457.3839 | 4427279.4715 | 240 | 2400 | 69.74% | DS | DS301m | Repex | Std | Std | Substations
DS301 | Ground substation refurbishment program | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 255000 | 255000 | 255000 | 255000 | 255000 | 0 | 0 | 0 | 0 | 0 | 0 | 295721.8216 | 303114.8672 | 310692.7389 | 318460.0573 | 326421.5588 | 0 | 1275000 | 0 | 1554411.0438 | 240 | 1200 | 94.48% | DS | DS301l | Repex | Std | Std | Substations
DS302 | Distribution transformer replacement program | Program - Short Term Need | 1170000 | 1125000 | 1125000 | 1125000 | 1437500 | 1437500 | 1437500 | 1437500 | 1437500 | 1437500 | 1437500 | 1169485.63 | 1153125 | 1181953.125 | 1211501.9531 | 1586731.0303 | 1626399.306 | 1667059.2887 | 1708735.7709 | 1751454.1652 | 1795240.5193 | 1840121.5323 | 6250000 | 13437500 | 6759710.4144 | 15522321.6908 | 270 | 4050 | 37.22% | DS | DS302s | Repex | Std | Std | Substations
DS302 | Distribution transformer replacement program | Program - Medium Term Need |  | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 0 | 128125 | 131328.125 | 134611.3281 | 137976.6113 | 141426.0266 | 144961.6773 | 148585.7192 | 152300.3622 | 156107.8712 | 160010.568 | 625000 | 1250000 | 673467.0911 | 1435433.289 | 270 | 2700 | 66.47% | DS | DS302m | Repex | Std | Std | Substations
DS302 | Distribution transformer replacement program | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152300.3622 | 156107.8712 | 160010.568 | 0 | 375000 | 0 | 468418.8015 | 270 | 1350 | 92.18% | DS | DS302l | Repex | Std | Std | Substations
DS305 | Compact LV switchgear replacement | Program - Short Term Need | 508400 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 387187.91 | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | 384025.3633 | 1500000 | 3000000 | 1616321.0186 | 3445039.8936 | 240 | 3600 | 42.68% | DS | DS305s | Repex | Std | Std | Substations
DS305 | Compact LV switchgear replacement | Program - Medium Term Need |  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 0 | 205000 | 210125 | 215378.125 | 220762.5781 | 226281.6426 | 231938.6836 | 237737.1507 | 243680.5795 | 249772.594 | 256016.9088 | 1000000 | 2000000 | 1077547.3457 | 2296693.2624 | 240 | 2400 | 69.74% | DS | DS305m | Repex | Std | Std | Substations
DS307 | Holec MD4 epoxy switchgear replacement | Program - Short Term Need | 4035224.6688 | 5950000 | 5600000 | 5950000 | 5950000 | 5950000 | 5950000 | 5950000 | 5950000 | 5950000 | 5950000 | 2360741.09 | 6098750 | 5883500 | 6407499.2187 | 6567686.6992 | 6731878.8667 | 6900175.8384 | 7072680.2343 | 7249497.2402 | 7430734.6712 | 7616503.038 | 29400000 | 59150000 | 31689314.7847 | 67958905.8067 | 280 | 4200 | 36.29% | DS | DS307s | Repex | Std | Std | Substations
DS307 | Holec MD4 epoxy switchgear replacement | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 1750000 | 1750000 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080200.0689 | 2132205.0706 | 2185510.1974 | 2240147.9523 | 0 | 7000000 | 0 | 8638063.2893 | 280 | 2800 | 66.39% | DS | DS307m | Repex | Std | Std | Substations
DS307 | Holec MD4 epoxy switchgear replacement | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2185510.1974 | 2240147.9523 | 0 | 3500000 | 0 | 4425658.1498 | 280 | 1400 | 92.18% | DS | DS307l | Repex | Std | Std | Substations
DS308 | HV RGB12 switchgear replacement | Program - Short Term Need | 598000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4200 | 36.29% | DS | DS308s | Repex | Std | Std | Substations
DS312 | Miscellaneous substation renewal expenditure | Program - Short Term Need | 750000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 877711.92 | 1537500 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1739540.1273 | 1783028.6305 | 1827604.3463 | 1873294.4549 | 1920126.8163 | 7500000 | 15000000 | 8081605.0928 | 17225199.4681 | 230 | 3450 | 51.29% | DS | DS312s | Repex | Std | Std | Substations
DS312 | Miscellaneous substation renewal expenditure | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594342.8768 | 609201.4488 | 624431.485 | 640042.2721 | 0 | 2000000 | 0 | 2468018.0827 | 230 | 2300 | 69.74% | DS | DS312m | Repex | Std | Std | Substations
DS312 | Miscellaneous substation renewal expenditure | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624431.485 | 640042.2721 | 0 | 1000000 | 0 | 1264473.7571 | 230 | 1150 | 94.48% | DS | DS312l | Repex | Std | Std | Substations
DS313 | Padmount substation fire risk mitigation | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61797.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.32% | DS | DS313s | Repex | Std | Std | Substations
DS315 | Low voltage switchgear replacement | Program - Short Term Need | 354000 | 531000 | 531000 | 531000 | 531000 | 531000 | 531000 | 531000 | 531000 | 531000 | 531000 | 263730.92 | 544275 | 557881.875 | 571828.9219 | 586124.6449 | 600777.761 | 615797.2051 | 631192.1352 | 646971.9386 | 663146.237 | 679724.893 | 2655000 | 5310000 | 2860888.2028 | 6097720.6117 | 280 | 4200 | 36.29% | DS | DS315s | Repex | Std | Std | Substations
DS315 | Low voltage switchgear replacement | Program - Medium Term Need |  | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 177000 | 0 | 181425 | 185960.625 | 190609.6406 | 195374.8816 | 200259.2537 | 205265.735 | 210397.3784 | 215657.3129 | 221048.7457 | 226574.9643 | 885000 | 1770000 | 953629.4009 | 2032573.5372 | 280 | 2800 | 66.39% | DS | DS315m | Repex | Std | Std | Substations
DS316 | HV oil switchgear replacement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17102.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | DS | DS316s | Repex | Std | Std | Substations
DS317 | Future distribution substation renewals | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 7500000 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4264410.1413 | 9366472.2746 | 15361014.5304 | 0 | 23000000 | 0 | 28991896.9462 | 180 | 2700 | 66.47% | DS | DS317s | Repex | Std | Unallocated | Unallocated
DS317 | Future distribution substation renewals | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 900000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609201.4488 | 1123976.673 | 1920126.8163 | 0 | 2900000 | 0 | 3653304.938 | 180 | 1800 | 82.35% | DS | DS317m | Repex | Std | Unallocated | Unallocated
DS317 | Future distribution substation renewals | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 900000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609201.4488 | 1123976.673 | 1920126.8163 | 0 | 2900000 | 0 | 3653304.938 | 180 | 900 | 97.4% | DS | DS317l | Repex | Std | Unallocated | Unallocated
DS318 | Distribution substation earthing refurbishment | Program - Short Term Need | 676000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 180000 | 0 | 184500 | 189112.5 | 193840.3125 | 198686.3203 | 203653.4783 | 208744.8153 | 213963.4357 | 219312.5216 | 224795.3346 | 230415.218 | 900000 | 1800000 | 969792.6111 | 2067023.9362 | 340 | 5100 | 9.283% | DS | DS318s | Repex | Std | Std | Substations
DS318 | Distribution substation earthing refurbishment | Program - Medium Term Need |  | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 0 | 92250 | 94556.25 | 96920.1562 | 99343.1602 | 101826.7392 | 104372.4076 | 106981.7178 | 109656.2608 | 112397.6673 | 115207.609 | 450000 | 900000 | 484896.3056 | 1033511.9681 | 340 | 3400 | 51.32% | DS | DS318m | Repex | Std | Std | Substations
DS404 | Cast iron UGOH replacement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | DS | DS404s | Repex | Std | Std | Distribution lines and cables
DS405 | Air break switch replacement program | Program - Short Term Need | 6146400.5487 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 3640000 | 7304354.42 | 3731000 | 3824275 | 3919881.875 | 4017878.9219 | 4118325.8949 | 4221284.0423 | 4326816.1434 | 4434986.5469 | 4545861.2106 | 4659507.7409 | 18200000 | 36400000 | 19611361.6918 | 41799817.3759 | 280 | 4200 | 36.29% | DS | DS405s | Repex | Std | Std | Distribution lines and cables
DS409 | Miscellaneous mains renewal expenditure | Program - Short Term Need | 750000 | 1095000 | 1095000 | 1095000 | 1095000 | 1095000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 2087412.32 | 1122375 | 1150434.375 | 1179195.2344 | 1208675.1152 | 1238891.9931 | 1391632.1019 | 1426422.9044 | 1462083.477 | 1498635.5639 | 1536101.453 | 5475000 | 11475000 | 5899571.7177 | 13214447.218 | 290 | 4350 | 29.29% | DS | DS409s | Repex | Std | Std | Distribution lines and cables
DS410 | Capital works for compliance to NSW Maritime Waterways - crossing codes | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.32% | DS | DS410s | Repex | Std | Std | Distribution lines and cables
DS411 | Capital works for compliance to NSW Maritime Waterways - signage replacement and drawings update | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.32% | DS | DS411s | Repex | Std | Std | Distribution lines and cables
DS413 | Low mains remediation | Program - Short Term Need | 1800000 | 1625000 | 1625000 | 1625000 | 1625000 | 1625000 | 975000 | 975000 | 975000 | 975000 | 975000 | 2293431.29 | 1665625 | 1707265.625 | 1749947.2656 | 1793695.9473 | 1838538.3459 | 1130701.0828 | 1158968.6098 | 1187942.8251 | 1217641.3957 | 1248082.4306 | 8125000 | 13000000 | 8755072.1838 | 14698408.5278 | 230 | 3450 | 51.29% | DS | DS413s | Repex | Std | Std | Distribution lines and cables
DS414 | Copper distribution mains replacement | Program - Short Term Need | 5600000 | 0 | 960000 | 960000 | 960000 | 960000 | 960000 | 960000 | 960000 | 960000 | 960000 | 4779336 | 0 | 1008600 | 1033815 | 1059660.375 | 1086151.8844 | 1113305.6815 | 1141138.3235 | 1169666.7816 | 1198908.4511 | 1228881.1624 | 3840000 | 8640000 | 4188227.2594 | 10040127.6596 | 260 | 3900 | 38.53% | DS | DS414s | Repex | Std | Std | Distribution lines and cables
DS414 | Copper distribution mains replacement | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 480000 | 480000 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285284.5809 | 584833.3908 | 599454.2256 | 614440.5812 | 0 | 1680000 | 0 | 2084012.7785 | 260 | 2600 | 66.7% | DS | DS414m | Repex | Std | Std | Distribution lines and cables
DS414 | Copper distribution mains replacement | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 480000 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292416.6954 | 599454.2256 | 614440.5812 | 0 | 1200000 | 0 | 1506311.5022 | 260 | 1300 | 92.18% | DS | DS414l | Repex | Std | Std | Distribution lines and cables
DS415 | LV mains replacement | Program - Short Term Need | 550000 | 966000 | 966000 | 966000 | 966000 | 966000 | 960000 | 960000 | 960000 | 960000 | 960000 | 0 | 990150 | 1014903.75 | 1040276.3437 | 1066283.2523 | 1092940.3337 | 1113305.6815 | 1141138.3235 | 1169666.7816 | 1198908.4511 | 1228881.1624 | 4830000 | 9630000 | 5204553.6797 | 11056454.0799 | 190 | 2850 | 66.11% | DS | DS415s | Repex | Std | Std | Distribution lines and cables
DS415 | LV mains replacement | Program - Medium Term Need |  | 134000 | 134000 | 134000 | 134000 | 134000 | 135000 | 135000 | 135000 | 135000 | 135000 | 0 | 137350 | 140783.75 | 144303.3437 | 147910.9273 | 151608.7005 | 156558.6115 | 160472.5767 | 164484.3912 | 168596.5009 | 172811.4135 | 670000 | 1345000 | 721956.7216 | 1544880.2154 | 190 | 1900 | 80.68% | DS | DS415m | Repex | Std | Std | Distribution lines and cables
DS416 | Asbestos service fuse replacement | Program - Short Term Need | 261000 | 261000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86000 | 267525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261000 | 261000 | 267525 | 267525 | 200 | 3000 | 58.52% | DS | DS416s | Repex | Std | Std | Customer metering & load control
DS417 | Distribution access track reconstruction | Program - Short Term Need | 500000 | 440000 | 1408000 | 528000 | 528000 | 616000 | 616000 | 616000 | 616000 | 616000 | 616000 | 500000 | 451000 | 1479280 | 568598.25 | 582813.2062 | 696947.4591 | 714371.1456 | 732230.4243 | 750536.1849 | 769299.5895 | 788532.0792 | 3520000 | 6600000 | 3778638.9154 | 7533608.3388 | 290 | 4350 | 29.29% | DS | DS417s | Repex | Std | Std | Distribution lines and cables
DS417 | Distribution access track reconstruction | Program - Medium Term Need |  | 0 | 0 | 704000 | 704000 | 704000 | 704000 | 704000 | 704000 | 704000 | 704000 | 0 | 0 | 0 | 758131 | 777084.275 | 796511.3819 | 816424.1664 | 836834.7706 | 857755.6398 | 879199.5308 | 901179.5191 | 2112000 | 5632000 | 2331726.6569 | 6623120.2837 | 290 | 2900 | 59.74% | DS | DS417m | Repex | Std | Std | Distribution lines and cables
DS417 | Distribution access track reconstruction | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220000 | 220000 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268048.6375 | 274749.8534 | 281618.5997 | 0 | 660000 | 0 | 824417.0906 | 290 | 1450 | 92.18% | DS | DS417l | Repex | Std | Std | Distribution lines and cables
DS418 | Pole top structure/hardware refurbishment (LV) | Program - Short Term Need | 5000000 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 2609650 | 3923342.5 | 2674891.25 | 2741763.5312 | 2810307.6195 | 2880565.31 | 2952579.4428 | 3026393.9288 | 3102053.7771 | 3179605.1215 | 3259095.2495 | 3340572.6308 | 13048250 | 26096500 | 14060107.1536 | 29967827.8612 | 330 | 4950 | 12.56% | DS | DS418s | Repex | Std | Std | Distribution lines and cables
DS420 | Future distribution feeder refurbishment works | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 7500000 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4264410.1413 | 9366472.2746 | 15361014.5304 | 0 | 23000000 | 0 | 28991896.9462 | 180 | 2700 | 66.47% | DS | DS420s | Repex | Std | Unallocated | Unallocated
DS420 | Future distribution feeder refurbishment works | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 900000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609201.4488 | 1123976.673 | 1920126.8163 | 0 | 2900000 | 0 | 3653304.938 | 180 | 1800 | 82.35% | DS | DS420m | Repex | Std | Unallocated | Unallocated
DS420 | Future distribution feeder refurbishment works | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 900000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609201.4488 | 1123976.673 | 1920126.8163 | 0 | 2900000 | 0 | 3653304.938 | 180 | 900 | 97.4% | DS | DS420l | Repex | Std | Unallocated | Unallocated
DS421 | Pole top structure/hardware refurbishment (HV) | Program - Short Term Need |  | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3248430 | 3793027.469 | 3329640.75 | 3412881.7687 | 3498203.813 | 3585658.9083 | 3675300.381 | 3767182.8905 | 3861362.4628 | 3957896.5244 | 4056843.9375 | 4158265.0359 | 16242150 | 32484300 | 17501685.621 | 37303236.4721 | 330 | 4950 | 12.56% | DS | DS421s | Repex | Std | Std | Distribution lines and cables
DU | Duct installation RMS road works | Program - Short Term Need | 1955226.0176 | 2152731 | 2206549 | 2261713 | 2318255 | 2376212 | 2376212 | 2376212 | 2376212 | 2376212 | 2558920 | 700000 | 2206549.275 | 2318255.5431 | 2435617.5261 | 2558919.7528 | 2688465.7724 | 2755677.4167 | 2824569.3521 | 2895183.5859 | 2967563.1755 | 3275633.9418 | 11315460 | 23379228 | 12207807.8694 | 26926435.3414 | 170 | 2550 | 68.67% | DU | DUs | Connections | Std | Std | Distribution lines and cables
EF001 | Distribution management system | Program - Short Term Need | 12000000 | 8585366 | 3616895 | 92860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11928177.61 | 8800000.15 | 3800000.3094 | 100000.0634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12295121 | 12295121 | 12700000.5228 | 12700000.5228 | 260 | 3900 | 38.53% | EF | EF001s | Other | Std | Std | Communications
EF002 | Technology pilots | Program - Short Term Need | 552599 | 500000 | 500000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 505504.11 | 512500 | 525312.5 | 2153781.25 | 2207625.7812 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | 2560169.0884 | 7000000 | 17000000 | 7662035.957 | 19853495.1241 | 230 | 3450 | 51.29% | EF | EF002s | Other | Std | Std | Distribution lines and cables
EF003 | Battery energy storage system pilot | Program - Short Term Need | 1692215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1639952.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.29% | EF | EF003s | Other | Std | Std | Substations
EH | Dist environmental enhancement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 2850 | 66.11% | EH | EHs | Other | Std | Std | Distribution lines and cables
HVW | HV development works | Program - Short Term Need | 7057544 | 6800844 | 7103063 | 6647368 | 6275047 | 5947097 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 8536573.1465 | 6970865.1 | 7462655.5644 | 7158488.2801 | 6926477.7679 | 6728594.3887 | 6958160.5093 | 7132114.522 | 7310417.3851 | 7493177.8197 | 7680507.2652 | 32773419 | 62773419 | 35247081.101 | 71821458.6022 | 350 | 5250 | 4.71% | HV | HVWs | Augex | Std | Std | Distribution lines and cables
IC | Industrial & commercial | Program - Short Term Need | 10000000 | 7501444 | 5332550 | 4584087 | 4321346 | 4245553 | 4245553 | 4245553 | 4245553 | 4245553 | 4245553 | 10000000 | 7688980.1 | 5602510.3438 | 4936560.3145 | 4769957.4197 | 4803453.5325 | 4923539.8708 | 5046628.3675 | 5172794.0767 | 5302113.9287 | 5434666.7769 | 25984980 | 47212745 | 27801461.7103 | 53681204.7309 | 200 | 3000 | 58.52% | IC | ICs | Connections | Std | Std | Distribution lines and cables
LV001 | Overloaded distribution sub uprates | Program - Short Term Need | 120000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 120000 | 82000 | 84050 | 86151.25 | 88305.0312 | 90512.657 | 92775.4735 | 95094.8603 | 97472.2318 | 99909.0376 | 102406.7635 | 400000 | 800000 | 431018.9383 | 918677.305 | 330 | 4950 | 12.56% | LV | LV001s | Augex | Std | Std | Low Voltage lines and cables
LV002 | Quality of supply reactive projects | Program - Short Term Need | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 499406.74 | 512500 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | 640042.2721 | 2500000 | 5000000 | 2693868.3643 | 5741733.156 | 300 | 4500 | 25.55% | LV | LV002s | Other | Std | Std | Low Voltage lines and cables
LV003 | LV planning reactive projects | Program - Short Term Need | 1000000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 998030.36 | 871250 | 893031.25 | 915357.0312 | 938240.957 | 961696.981 | 985739.4055 | 1010382.8906 | 1035642.4629 | 1061533.5245 | 1088071.8626 | 4250000 | 8500000 | 4579576.2192 | 9760946.3652 | 300 | 4500 | 25.55% | LV | LV003s | Other | Std | Std | Low Voltage lines and cables
LV003 | LV planning reactive projects | Program - Medium Term Need |  | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 998030.36 | 153750 | 157593.75 | 161533.5937 | 165571.9336 | 169711.2319 | 173954.0127 | 178302.8631 | 182760.4346 | 187329.4455 | 192012.6816 | 750000 | 1500000 | 808160.5093 | 1722519.9468 | 300 | 3000 | 58.52% | LV | LV003m | Other | Std | Std | Low Voltage lines and cables
LV004 | Low voltage system augmentations | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2498.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1200 | 94.48% | LV | LV004s | Other | Std | Std | Low Voltage lines and cables
LV005 | Dsub monitoring & LV feeder monitoring for solar PV | Program - Short Term Need | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 232429.45 | 256250 | 262656.25 | 269222.6562 | 275953.2227 | 282852.0532 | 289923.3546 | 297171.4384 | 304600.7244 | 312215.7425 | 320021.136 | 1250000 | 2500000 | 1346934.1821 | 2870866.578 | 250 | 3750 | 38.64% | LV | LV005s | Other | Std | Std | Low Voltage lines and cables
MC101 | Meters - Growth | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1050 | 95.93% | MC | MC101s | Other | Alt | Alt | Metering & Load control
MC102 | Relays - growth | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2847.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1050 | 95.93% | MC | MC102s | Other | Std | Std | Customer metering & load control
MC104 | Meters - renewal | Program - Short Term Need | 25000 | 60000 | 60000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 25000 | 61500 | 63037.5 | 10768.9062 | 11038.1289 | 11314.0821 | 11596.9342 | 11886.8575 | 12184.029 | 12488.6297 | 12800.8454 | 150000 | 200000 | 157658.6173 | 218615.9131 | 50 | 750 | 99.19% | MC | MC104s | Other | Alt | Alt | Metering & Load control
MC105 | Relays - renewal | Program - Short Term Need | 300000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 100000 | 410000 | 420250 | 430756.25 | 441525.1562 | 452563.2852 | 463877.3673 | 475474.3015 | 487361.159 | 499545.188 | 512033.8177 | 2000000 | 4000000 | 2155094.6914 | 4593386.5248 | 100 | 1500 | 92.18% | MC | MC105s | Other | Std | Std | Customer metering & load control
MC105 | Relays - renewal | Program - Medium Term Need |  | 557584 | 507185 | 456786 | 406386 | 355987 | 305588 | 255189 | 204790 | 154391 | 103992 | 100000 | 571523.6 | 532861.2406 | 491908.561 | 448574.1054 | 402766.6155 | 354388.3923 | 303339.5288 | 249516.7294 | 192813.2028 | 133118.5519 | 2283928 | 3307878 | 2447634.1225 | 3680810.5277 | 100 | 1000 | 97.4% | MC | MC105m | Other | Std | Std | Customer metering & load control
MC106 | Labour (meter/relay renewal) | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | MC | MC106s | Other | Alt | Alt | Metering & load control
MC107 | Test equipment | Program - Short Term Need | 80000 | 120000 | 80000 | 120000 | 80000 | 120000 | 85000 | 120000 | 85000 | 120000 | 85000 | 80000 | 123000 | 84050 | 129226.875 | 88305.0312 | 135768.9855 | 98573.9405 | 142642.2904 | 103564.2463 | 149863.5564 | 108807.1863 | 520000 | 1015000 | 560350.8918 | 1163802.1117 | 50 | 750 | 99.19% | MC | MC107s | Other | Alt | Alt | Metering & Load control
MC108 | Smart metering pilot | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | MC | MC108s | Other | Alt | Unallocated | Unallocated
MC109 | Demand management technology | Program - Short Term Need | 500000 | 1400000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 508000 | 1435000 | 787968.75 | 807667.9687 | 827859.668 | 848556.1597 | 869770.0637 | 891514.3153 | 913802.1731 | 936647.2275 | 960063.4081 | 4400000 | 8150000 | 4707052.5464 | 9278849.734 | 80 | 1200 | 94.48% | MC | MC109s | Other | Std | Std | Distribution lines and cables
MC110 | Labour meter renewal | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | MC | MC110s | Other | Alt | Alt | Metering & load control
MC111 | Labour relay renewal | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | MC | MC111s | Other | Std | Unallocated | Unallocated
MC112 | Neutral integrity monitoring | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3600 | 42.68% | MC | MC112s | Other | Std | Std | Customer metering & load control
NU | Non urban extension | Program - Short Term Need | 850000 | 1019340 | 743122 | 661806 | 631694 | 619417 | 619417 | 619417 | 619417 | 619417 | 619417 | 850000 | 1044823.5 | 780742.5512 | 712692.677 | 697271.9801 | 700813.481 | 718333.818 | 736292.1635 | 754699.4676 | 773566.9543 | 792906.1281 | 3675379 | 6772464 | 3936344.1894 | 7712142.7208 | 120 | 1800 | 82.35% | NU | NUs | Connections | Std | Std | Distribution lines and cables
OFP | Overloaded feeders (compliance) | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.32% | OF | OFPs | Augex | Std | Std | Distribution lines and cables
PF | Power factor | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PF | PFs | Other | Std | Unallocated | Unallocated
PQ001 | Permanent power quality monitoring | Program - Short Term Need | 615000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 428055.67 | 102500 | 105062.5 | 107689.0625 | 110381.2891 | 113140.8213 | 115969.3418 | 118868.5754 | 121840.2898 | 124886.297 | 128008.4544 | 500000 | 1000000 | 538773.6729 | 1148346.6312 | 300 | 4500 | 25.55% | PQ | PQ001s | Other | Std | Std | Substations
PQ003 | PQ surveying | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3600 | 42.68% | PQ | PQ003s | Other | Std | Std | Substations
PQ004 | Power quality monitoring replacement | Program - Short Term Need | 400000 | 342400 | 617700 | 873300 | 947600 | 1364538 | 1299560 | 1429516 | 1429516 | 1169604 | 1169604 | 363621.62 | 350960 | 648971.0625 | 940448.5828 | 1045973.0952 | 1543849.5 | 1507091.1786 | 1699245.3038 | 1741726.4364 | 1460675.1251 | 1497192.0032 | 4145538 | 10643338 | 4530202.2405 | 12436132.2877 | 200 | 3000 | 58.52% | PQ | PQ004s | Other | Std | Std | Substations
PR017 | Werrington ZS rebuild to 132kV | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR017 | Augex | Std | Unallocated | Unallocated
PR035 | Baulkham Hills TS 11kV supply | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR035 | Augex | Std | Unallocated | Unallocated
PR044 | West Liverpool ZS (Hoxton Park ZS rebuild) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6450 | 0% | PR | PR044 | Augex | Std | Std | Substations
PR052 | Penrith TS transformer and busbar augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6150 | 0% | PR | PR052 | Augex | Std | Std | Substations
PR054 | Quakers Hill ZS augment (132kV bar + 1st 132/11kV tfr) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR054 | Augex | Std | Std | Sub-transmission lines and cables
PR059 | ELTS 132kV busbar & substation works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR059 | Augex | Std | Std | Substations
PR060 | WLTS-ELTS first 132kV cable links | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR060 | Augex | Std | Std | Sub-transmission lines and cables
PR061 | Russell Vale ZS augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5325 | 1.974% | PR | PR061 | Augex | Std | Std | Substations
PR070 | Caddens ZS establishment and feeders | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR070 | Augex | Std | Std | Substations
PR073 | Campbelltown 66kV busbar & line to Ambarvale | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR073 | Augex | Std | Unallocated | Unallocated
PR081 | Collimore Park ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4195200 | 12585600 | 11187200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5111443.8356 | 15717689.7946 | 14320561.8128 | 0 | 27968000 | 0 | 35149695.443 | 210 | 1050 | 95.93% | PR | PR081 | Augex | Std | Unallocated | Unallocated
PR090 | Doonside 132kV/11kV ZS rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6750 | 0% | PR | PR090 | Augex | Std | Std | Substations
PR091 | West Parramatta CBD 132kV/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5850 | 1.673% | PR | PR091 | Augex | Std | Std | Substations
PR096 | Berry ZS LDC CT's | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR096 | Augex | Std | Unallocated | Unallocated
PR102 | Kemps Creek/Luddenham capacity uprate | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4500 | 25.55% | PR | PR102 | Augex | Std | Std | Sub-transmission lines and cables
PR110 | Edmondson Park ZS establishment | Major Project - Committed Project | 2187000 | 1765854 | 5111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3153918 | 1810000.35 | 5369.7444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1770965 | 1770965 | 1815370.0944 | 1815370.0944 | 170 | 2550 | 68.67% | PR | PR110 | Augex | Std | Std | Substations
PR113 | Augment feeder 308 Nepean to Douglas Park | Major Project - Committed Project | 518000 | 1313250 | 3939750 | 3502000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99996 | 1346081.25 | 4139199.8437 | 3771270.9687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8755000 | 8755000 | 9256552.0625 | 9256552.0625 | 340 | 5100 | 9.283% | PR | PR113 | Augex | Std | Std | Sub-transmission lines and cables
PR123 | Connection works associated with Tomerong/Bamarang BSP | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR123 | Augex | Std | Std | Sub-transmission lines and cables
PR126 | Chipping Norton 33/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR126 | Augex | Std | Std | Substations
PR128 | Nepean ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PR | PR128 | Augex | Std | Std | Substations
PR144 | Sherwood ZS augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR144 | Augex | Std | Std | Substations
PR148 | Dapto ZS 3rd transformer & 33kV bus section CB's | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR148 | Augex | Std | Std | Transformers
PR149 | Gerringong ZS augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR149 | Augex | Std | Std | Substations
PR157 | Richmond ZS rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6450 | 0% | PR | PR157 | Augex | Std | Std | Substations
PR170 | Holsworthy 33/11kV ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4202400 | 8404800 | 8404800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5120216.3365 | 10496443.4898 | 10758854.5771 | 0 | 21012000 | 0 | 26375514.4034 | 40 | 200 | 100% | PR | PR170 | Augex | Std | Std | Substations
PR172 | Parklea ZS 3rd transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR172 | Augex | Std | Std | Transformers
PR176 | Cheriton Av 132/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR176 | Augex | Std | Std | Substations
PR183 | Schofields ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR183 | Augex | Std | Unallocated | Unallocated
PR184 | Box Hill 22kV conversion | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PR | PR184 | Augex | Std | Std | Substations
PR186 | Glenorie ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR186 | Augex | Std | Std | Substations
PR190 | Eschol Park ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4429200 | 8858400 | 8858400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5264926.9401 | 10793100.2273 | 11062927.733 | 0 | 0 | 22146000 | 0 | 27120954.9004 | 80 | 400 | 99.71% | PR | PR190 | Augex | Std | Std | Distribution lines and cables
PR192 | Feeder 7158 augment from Albion Park to Warilla | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR192 | Augex | Std | Unallocated | Unallocated
PR200 | Cordeaux/Figtree 33/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR200 | Augex | Std | Std | Substations
PR204 | Canley Vale subtransmission network upgrade | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5400 | 1.974% | PR | PR204 | Augex | Std | Std | Sub-transmission lines and cables
PR206 | Cawdor 66/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR206 | Augex | Std | Std | Substations
PR208 | Abbotsbury 132/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5700 | 1.673% | PR | PR208 | Augex | Std | Std | Substations
PR244 | Bellavista ZS establishment with two 132kV cable links | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR244 | Augex | Std | Unallocated | Unallocated
PR248 | Penrith Lakes ZS site acquisition | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347908.0255 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 347908.0255 | 140 | 700 | 99.19% | PRL | PR248 | Augex | Std | Std | Land
PR249 | Establish Penrith Lakes 33/11kV Zone Substation | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 1571001 | 6284004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1821879.5197 | 7469706.0308 | 0 | 0 | 0 | 0 | 7855005 | 0 | 9291585.5505 | 140 | 700 | 99.19% | PR | PR249 | Augex | Std | Std | Substations
PR255 | Line works associated with Oran Park | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.32% | PR | PR255 | Augex | Std | Std | Sub-transmission lines and cables
PR257 | Menangle Park 66/11kV ZS site purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3150 | 54.86% | PRL | PR257 | Augex | Std | Std | Land
PR258 | Menangle Park 66/11kV ZS establishment | Major Project - Committed Project | 3800000 | 4487188 | 8566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295852.71 | 4599367.7 | 8999.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4495754 | 4495754 | 4608367.3537 | 4608367.3537 | 170 | 2550 | 68.67% | PR | PR258 | Augex | Std | Std | Substations
PR261 | Huntingwood ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR261 | Augex | Std | Std | Substations
PR278 | Kemps Creek new BSP associated works | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278000 | 1278000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557118.903 | 1596046.8756 | 0 | 0 | 2556000 | 0 | 3153165.7786 | 20 | 100 | 100% | PR | PR278 | Augex | Std | Std | Sub-transmission lines and cables
PR280 | Wilton Park 66/11kV ZS establishment & 66kV line works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR280 | Augex | Std | Std | Substations
PR288 | Holroyd 330/132kV BSP associated works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR288 | Augex | Std | Std | Sub-transmission lines and cables
PR291 | Marsden Park Zone Substation site acquisition | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR291 | Augex | Std | Unallocated | Unallocated
PR292 | South Marsden Park (industrial) 132/11kV ZS establishment | Major Project - Committed Project | 14500000 | 1215012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14082714.11 | 1245387.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215012 | 1215012 | 1245387.3 | 1245387.3 | 210 | 3150 | 54.86% | PR | PR292 | Augex | Std | Std | Substations
PR303 | Mittagong ZS transformer augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR303 | Augex | Std | Std | Transformers
PR308 | Granville ZS & Camellia TS rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3900 | 38.53% | PR | PR308 | Augex | Std | Std | Substations
PR311 | Quakers Hill ZS 2nd 132kV feeder | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR311 | Augex | Std | Unallocated | Unallocated
PR326 | Casula 33/11kV ZS establishment with link to LTS or WLTS | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR326 | Augex | Std | Std | Substations
PR329 | Box Hill site purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PRL | PR329 | Augex | Std | Std | Land
PR339 | North Eastern Creek ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR339 | Augex | Std | Std | Substations
PR342 | Jordan Springs establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.32% | PR | PR342 | Augex | Std | Std | Substations
PR343 | Wetherill Park ZS augmentation | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR343 | Augex | Std | Unallocated | Unallocated
PR353 | Shoalhaven Feeder 7510/7511 Augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR353 | Augex | Std | Std | Sub-transmission lines and cables
PR384 | Glossodia ZS transformer augments | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR384 | Augex | Std | Std | Substations
PR406 | Tomerong ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4350 | 29.29% | PR | PR406 | Augex | Std | Std | Substations
PR408 | Oran Park (permanent) ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.52% | PR | PR408 | Augex | Std | Std | Substations
PR413 | Windsor transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.32% | PR | PR413 | Augex | Std | Std | Transformers
PR423 | Maryland ZS establishment | Major Project - Prior to Approval | 0 | 0 | 4126720 | 8253440 | 8253440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4335635.2 | 8888052.16 | 9110253.464 | 0 | 0 | 0 | 0 | 0 | 0 | 20633600 | 20633600 | 22333940.824 | 22333940.824 | 80 | 800 | 99.13% | PR | PR423 | Augex | Std | Std | Substations
PR424 | Austral ZS site purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1520855.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.32% | PRL | PR424 | Augex | Std | Std | Land
PR425 | Austral ZS establishment (interim initially) | Major Project - Prior to Approval | 0 | 0 | 3556000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3736022.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3556000 | 3556000 | 3736022.5 | 3736022.5 | 160 | 1600 | 91.18% | PR | PR425 | Augex | Std | Std | Substations
PR426 | Leppington North ZS site purchase (strategic) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR426 | Augex | Std | Std | Land
PR427 | Leppington North ZS establishment | Major Project - Committed Project | 10000000 | 1755910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9689043 | 1799807.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1755910 | 1755910 | 1799807.75 | 1799807.75 | 210 | 3150 | 54.86% | PR | PR427 | Augex | Std | Std | Substations
PR429 | Leppington South ZS establishment (interim initially) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3675 | 38.64% | PR | PR429 | Augex | Std | Std | Substations
PR430 | North Rossmore ZS site purchase | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3311438.6719 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000 | 3311438.6719 | 3311438.6719 | 40 | 400 | 99.71% | PRL | PR430 | Augex | Std | Std | Land
PR432 | Rossmore ZS site purchase | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3394224.6387 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000 | 3394224.6387 | 3394224.6387 | 40 | 400 | 99.71% | PRL | PR432 | Augex | Std | Std | Land
PR433 | Rossmore ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12800845.442 | 0 | 10000000 | 0 | 12800845.442 | 160 | 800 | 99.13% | PR | PR433 | Augex | Std | Unallocated | Unallocated
PR434 | Catherine Fields North land purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR434 | Augex | Std | Unallocated | Unallocated
PR435 | Catherine Fields North ZS establishment (interim) | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4291200 | 8582400 | 8582400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5228410.5138 | 10718241.5533 | 10986197.5921 | 0 | 21456000 | 0 | 26932849.6592 | 140 | 700 | 99.19% | PR | PR435 | Augex | Std | Std | Substations
PR436 | Catherine Fields ZS site purchase | Major Project - Committed Project | 0 | 653024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669349.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653024 | 653024 | 669349.6 | 669349.6 | 240 | 3600 | 42.68% | PRL | PR436 | Augex | Std | Std | Land
PR437 | Catherine Fields 11kV feeder works | Major Project - Committed Project | 530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2400 | 69.74% | PR | PR437 | Augex | Std | Std | Substations
PR438 | North Bringelly ZS site purchase | Major Project - Prior to Approval | 0 | 0 | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769117.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3500000 | 3769117.1875 | 3769117.1875 | 20 | 200 | 100% | PRL | PR438 | Augex | Std | Std | Land
PR439 | North Bringelly ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4420000 | 8840000 | 8840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5253991.0312 | 10770681.614 | 11039948.6543 | 0 | 0 | 22100000 | 0 | 27064621.2995 | 40 | 200 | 100% | PR | PR439 | Augex | Std | Unallocated | Unallocated
PR440 | Feeder 443 and 458/1 augmentation and Cattai rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4800 | 12.56% | PR | PR440 | Augex | Std | Std | Sub-transmission lines and cables
PR444 | Culburra Beach development (33kV fdr and single transformer ZS) | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3832500 | 1916250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4555638.1509 | 2334764.5524 | 0 | 0 | 0 | 5748750 | 0 | 6890402.7033 | 110 | 550 | 99.19% | PR | PR444 | Augex | Std | Std | Substations
PR479 | Far South Coast 132kV voltage constraints | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12266.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4800 | 12.56% | PR | PR479 | Augex | Std | Std | Transformers
PR487 | Connection works associated with Macarthur BSP | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14791.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4050 | 37.22% | PR | PR487 | Augex | Std | Std | Sub-transmission lines and cables
PR499 | Southpipe (Oakdale Estate) ZS 132/11kV establishment | Major Project - Committed Project | 0 | 6347200 | 12694400 | 12694400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 6505880 | 13337054 | 13670480.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31736000 | 31736000 | 33513414.35 | 33513414.35 | 140 | 2100 | 78.28% | PR | PR499 | Augex | Std | Std | Substations
PR517 | Installation of OPGW on Feeders 98W and 98F | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3825 | 38.53% | PR | PR517 | Augex | Std | Std | Sub-transmission lines and cables
PR521 | Culburra ZS fdr duplication & provision for rural ZS's | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3150 | 54.86% | PR | PR521 | Augex | Std | Std | Sub-transmission lines and cables
PR559 | Mamre ZS transformer augment and 11kV busbar extension | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PR | PR559 | Augex | Std | Std | Substations
PR563 | Shoalhaven TS 132kV capacitor install | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR563 | Augex | Std | Unallocated | Unallocated
PR595 | The Oaks ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR595 | Augex | Std | Unallocated | Unallocated
PR596 | Marsden Park (residential) 132/11kV ZS establishment - stage 1 | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179571.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4050 | 37.22% | PR | PR596 | Augex | Std | Std | Substations
PR599 | Penrith CBD ZS site purchase | Major Project - Committed Project | 3720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3367600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2100 | 78.28% | PRL | PR599 | Augex | Std | Std | Land
PR602 | Riverstone West site purchase | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6092014.4875 | 0 | 0 | 0 | 5000000 | 0 | 6092014.4875 | 70 | 350 | 99.71% | PRL | PR602 | Augex | Std | Std | Land
PR603 | Eschol Park ZS site purchase | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400422.721 | 0 | 5000000 | 0 | 6400422.721 | 100 | 500 | 99.19% | PRL | PR603 | Augex | Std | Std | Land
PR620 | West Dapto ZS establishment | Major Project - Prior to Approval | 0 | 0 | 0 | 4085600 | 8171200 | 4671200 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4399744.3375 | 9019475.8919 | 5285034.0441 | 4058926.9637 | 0 | 0 | 0 | 0 | 16928000 | 20428000 | 18704254.2734 | 22763181.2372 | 110 | 1100 | 95.93% | PR | PR620 | Augex | Std | Std | Substations
PR632 | Mt Druitt TS automation scheme | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR632 | Augex | Std | Unallocated | Unallocated
PR642 | Auxiliary transformer at Shoalhaven TS | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR642 | Augex | Std | Unallocated | Unallocated
PR643 | Fibre works at Carlingford TS for Ausgrid | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR643 | Augex | Std | Std | Substations
PR652 | Purchase of additional land Lawson TS | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR652 | Augex | Std | Unallocated | Unallocated
PR653 | Avondale (South West Dapto) 132/11kV ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5943428.7683 | 6092014.4875 | 6244314.8497 | 0 | 0 | 15000000 | 0 | 18279758.1056 | 110 | 550 | 99.19% | PR | PR653 | Augex | Std | Unallocated | Unallocated
PR656 | Leppington South ZS establishment (permanent) | Major Project - Committed Project | 10900000 | 13566645 | 3526693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7152455 | 13905811.125 | 3705231.8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17093338 | 17093338 | 17611042.9581 | 17611042.9581 | 230 | 3450 | 51.29% | PR | PR656 | Augex | Std | Std | Substations
PR657 | Calderwood ZS establishment (interim initially) | Major Project - Committed Project | 200000 | 1476500 | 1476500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46912.52 | 1513412.5 | 1551247.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2953000 | 2953000 | 3064660.3125 | 3064660.3125 | 170 | 2550 | 68.67% | PR | PR657 | Augex | Std | Std | Substations
PR659 | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2899233.5455 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 2899233.5455 | 60 | 300 | 99.71% | PRL | PR659 | Augex | Std | Std | Land
PR660 | Install 66kV iso Douglas Pk/Appin/Wcliff | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR660 | Augex | Std | Unallocated | Unallocated
PR673 | Liverpool ZS 11kV switchboard extension & distribution works | Major Project - Committed Project | 950000 | 292683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1625842 | 300000.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292683 | 292683 | 300000.075 | 300000.075 | 360 | 5400 | 1.974% | PR | PR673 | Augex | Std | Std | Substations
PR674 | South Marsden Park (stage 1) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5100 | 9.283% | PR | PR674 | Augex | Std | Std | Substations
PR677 | South Penrith Zone Substation | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 5826000 | 11652000 | 11652000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6430813.9008 | 13183168.4966 | 13512747.709 | 0 | 0 | 0 | 0 | 17478000 | 29130000 | 19613982.3974 | 33126730.1064 | 210 | 2100 | 78.28% | PR | PR677 | Augex | Std | Std | Substations
PR698 | Marsden Park (residential) 132/11kV ZS - stage 2 | Major Project - Prior to Approval | 0 | 3064000 | 3064000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3140600 | 3219115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6128000 | 6128000 | 6359715 | 6359715 | 200 | 2000 | 80.61% | PR | PR698 | Augex | Std | Std | Substations
PR700 | Riverstone east ZS establishment | Major Project - Prior to Approval | 0 | 0 | 0 | 4085600 | 8171200 | 4671200 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4399744.3375 | 9019475.8919 | 5285034.0441 | 4058926.9637 | 0 | 0 | 0 | 0 | 16928000 | 20428000 | 18704254.2734 | 22763181.2372 | 120 | 1200 | 94.48% | PR | PR700 | Augex | Std | Std | Substations
PR701 | Dapto 33kV feeder constraints | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2400 | 69.74% | PR | PR701 | Augex | Std | Std | Sub-transmission lines and cables
PR702 | Penrith ZS 11kV transformer cable constraints | Major Project - Committed Project | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PR | PR702 | Augex | Std | Std | Transformers
PR703 | Riverstone East site purchase | Major Project - Prior to Approval | 0 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 6000000 | 6150000 | 6150000 | 120 | 1200 | 94.48% | PRL | PR703 | Augex | Std | Std | Land
PR704 | Oakdale (Southpipe) site purchase | Major Project - Committed Project | 300000 | 195122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128559 | 200000.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195122 | 195122 | 200000.05 | 200000.05 | 160 | 2400 | 69.74% | PRL | PR704 | Augex | Std | Std | Land
PR707 | 132kV ducts Bringelly Rd | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850291.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2850 | 66.11% | PR | PR707 | Augex | Std | Std | Sub-transmission lines and cables
PR709 | Feeder 230 undergrounding | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.32% | PR | PR709 | Augex | Std | Std | Sub-transmission lines and cables
PR710 | Feeder 868 rebuild & rearrangement South32 | Major Project - Committed Project | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1050 | 95.93% | PR | PR710 | Augex | Std | Std | Sub-transmission lines and cables
PR713 | Box Hill 132/22kV ZS establishment | Major Project - Prior to Approval | 0 | 7169600 | 14339200 | 14339200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7348840 | 15065122 | 15441750.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35848000 | 35848000 | 37855712.05 | 37855712.05 | 170 | 1700 | 88.92% | PR | PR713 | Augex | Std | Std | Substations
PR715 | Nepean TS constraints | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR715 | Augex | Std | Std | Substations
PR716 | Box Hill ZS - 132kV ducts Old Pitt Town | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR716 | Augex | Std | Std | Sub-transmission lines and cables
PR717 | Acquire improved site for West Dapto ZS | Major Project - Committed Project | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 2050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 2050000 | 2050000 | 140 | 2100 | 78.28% | PRL | PR717 | Augex | Std | Std | Land
PR722 | Camellia TS connection works for Ausgrid | Major Project - Committed Project | 187082 | 274973 | 104989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1247859 | 281847.325 | 110304.0681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379962 | 379962 | 392151.3931 | 392151.3931 | 170 | 2550 | 68.67% | PR | PR722 | Augex | Std | Std | Substations
PR723 | Supply to Luddenham Science Park | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 8617000 | 17234000 | 17234000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9511555.6785 | 19498689.141 | 19986156.3695 | 0 | 0 | 0 | 0 | 25851000 | 43085000 | 29010244.8195 | 48996401.189 | 210 | 2100 | 78.28% | PR | PR723 | Augex | Std | Std | Substations
PR724 | Establish Mt Gilead ZS | Major Project - Prior to Approval | 0 | 0 | 0 | 4044600 | 8089200 | 4589200 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4355591.8219 | 8928963.2348 | 5192258.5706 | 4058926.9637 | 0 | 0 | 0 | 0 | 16723000 | 20223000 | 18476813.6273 | 22535740.5911 | 200 | 2000 | 80.61% | PR | PR724 | Augex | Std | Std | Substations
PR727 | Luddenham ZS site purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR727 | Augex | Std | Std | Land
PR728 | Western Sydney Employment Lands ZS | Major Project - Prior to Approval | 0 | 0 | 0 | 4517000 | 9034000 | 9034000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4864314.9531 | 9971845.6539 | 10221141.7953 | 0 | 0 | 0 | 0 | 0 | 22585000 | 22585000 | 25057302.4023 | 25057302.4023 | 160 | 1600 | 91.18% | PR | PR728 | Augex | Std | Std | Substations
PR729 | Cheriton Avenue 3rd transformer | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7066066.684 | 0 | 5520000 | 0 | 7066066.684 | 210 | 1050 | 95.93% | PR | PR729 | Augex | Std | Unallocated | Unallocated
PR732 | Feeder 214/215 contraints | Major Project - Committed Project | 0 | 5140000 | 5140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5268500 | 5400212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10280000 | 10280000 | 10668712.5 | 10668712.5 | 220 | 3300 | 54.32% | PR | PR732 | Augex | Std | Std | Sub-transmission lines and cables
PR733 | Bringelly ZS augmentation | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 4264000 | 8528000 | 8528000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4944932.7353 | 10137112.1073 | 10390539.91 | 0 | 0 | 0 | 21320000 | 0 | 25472584.7525 | 140 | 700 | 99.19% | PR | PR733 | Augex | Std | Unallocated | Unallocated
PR735 | Termeil area distribution works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1131110.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR735 | Augex | Std | Std | Distribution lines and cables
PR739 | South Gilead (South Campbelltown) | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 4044600 | 8089200 | 8089200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690495.9993 | 9615516.7986 | 9855904.7185 | 0 | 0 | 0 | 20223000 | 0 | 24161917.5164 | 110 | 550 | 99.19% | PR | PR739 | Augex | Std | Std | Substations
PR740 | AFIC upgrade Minto, Prospect, Kingswood | Major Project - Committed Project | 1900000 | 311163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2242841 | 318942.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311163 | 311163 | 318942.075 | 318942.075 | 150 | 2250 | 70.85% | PR | PR740 | Augex | Std | Std | Substations
PR741 | Western Sydney Airport 132kV supply | Major Project - Prior to Approval | 0 | 0 | 0 | 7860000 | 15720000 | 15720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8464360.3125 | 17351938.6406 | 17785737.1066 | 0 | 0 | 0 | 0 | 0 | 39300000 | 39300000 | 43602036.0598 | 43602036.0598 | 170 | 1700 | 88.92% | PR | PR741 | Augex | Cont | Std | Sub-transmission lines and cables
PR742 | North Bomaderry ZS establishment | Major Project - Prior to Approval | 0 | 0 | 0 | 3683200 | 7366400 | 3866400 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3966403.55 | 8131127.2775 | 4374476.7143 | 4058926.9637 | 0 | 0 | 0 | 0 | 14916000 | 18416000 | 16472007.5418 | 20530934.5056 | 100 | 1000 | 97.4% | PR | PR742 | Augex | Std | Std | Substations
PR744 | Termeil ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 3980750 | 3980750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4616449.5746 | 4731860.8139 | 0 | 0 | 0 | 0 | 7961500 | 0 | 9348310.3885 | 270 | 1350 | 92.18% | PR | PR744 | Augex | Std | Std | Substations
PR745 | Austral Permanent ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 10518500 | 10518500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12198235.2195 | 12503191.1 | 0 | 0 | 0 | 0 | 21037000 | 0 | 24701426.3194 | 160 | 800 | 99.13% | PR | PR745 | Augex | Std | Unallocated | Unallocated
PR746 | Sydney University - Western Sydney Employment Lands ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12256000 | 12256000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14932745.9119 | 15306064.5597 | 0 | 0 | 24512000 | 0 | 30238810.4716 | 80 | 400 | 99.71% | PR | PR746 | Augex | Std | Unallocated | Unallocated
PR748 | Establish permanent Catherine Park ZS | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 0 | 1900000 | 3800000 | 3800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2149675.6045 | 4406834.9892 | 4517005.8639 | 0 | 0 | 0 | 1900000 | 9500000 | 2149675.6045 | 11073516.4576 | 240 | 2400 | 69.74% | PR | PR748 | Augex | Std | Std | Substations
PR749 | Nepean ZS augmentation | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4279268.7132 | 0 | 0 | 0 | 0 | 3600000 | 0 | 4279268.7132 | 250 | 1250 | 92.18% | PR | PR749 | Augex | Std | Unallocated | Unallocated
PR750 | Feeder 512 augmentation | Major Project - Committed Project | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2300 | 69.74% | PR | PR750 | Augex | Std | Std | Sub-transmission lines and cables
PR751 | Parklea ZS to Bella Vista ZS load transfer | Major Project - Prior to Approval | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 1050625 | 1050625 | 360 | 3600 | 42.68% | PR | PR751 | Augex | Std | Std | Substations
PR752 | Kemps Creek 132kV conversion | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8898000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11390192.2743 | 0 | 8898000 | 0 | 11390192.2743 | 340 | 1700 | 88.92% | PR | PR752 | Augex | Std | Unallocated | Unallocated
PR754 | Augment Westmead Zone Substation | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 5126500 | 5126500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5658696.7838 | 5800164.2034 | 0 | 0 | 0 | 0 | 0 | 10253000 | 10253000 | 11458860.9872 | 11458860.9872 | 360 | 3600 | 42.68% | PR | PR754 | Augex | Std | Std | Substations
PR755 | Narellan ZS busbar augmentation | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8653632.2867 | 0 | 0 | 0 | 0 | 7280000 | 0 | 8653632.2867 | 360 | 1800 | 82.35% | PR | PR755 | Augex | Std | Unallocated | Unallocated
PR761 | Glenfield Zone Substation site acquisition | Major Project - Prior to Approval |  | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3151875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 3000000 | 3151875 | 3151875 | 170 | 1700 | 88.92% | PRL | PR761 | Augex | Std | Std | Substations
PR765 | Minto 66kV Reconfiguration | Major Project - Prior to Approval |  | 300000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307500 | 420250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 700000 | 727750 | 727750 | 180 | 1800 | 82.35% | PR | PR765 | Augex | Std | Std | Substations
PR766 | Baulkham Hills 132kV bus section CB | Major Project - Prior to Approval |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367718.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 367718.75 | 367718.75 | 180 | 1800 | 82.35% | PR | PR766 | Augex | Std | Std | Substations
PR767 | Mt Terry 132kV bus section CB | Major Project - Prior to Approval |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430756.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 430756.25 | 430756.25 | 180 | 1800 | 82.35% | PR | PR767 | Augex | Std | Std | Substations
PR768 | Establish Glenfield 66/11kV Zone Substation | Major Project - Future/Planning Stage |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6220000 | 12440000 | 12440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7578466.0225 | 15535855.3461 | 15924251.7298 | 0 | 31100000 | 0 | 39038573.0985 | 170 | 850 | 97.4% | PR | PR768 | Augex | Std | Unallocated | Unallocated
PR769 | Nepean TS 132kV bus section CB | Major Project - Prior to Approval |  | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307500 | 315187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000 | 622687.5 | 622687.5 | 180 | 1800 | 82.35% | PR | PR769 | Augex | Std | Std | Substations
PS002 | Replacement of ASEA RI O/C relays | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8296.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PS | PS002s | Repex | Std | Std | Substations
PS004 | Underfrequency load shed program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PS | PS004s | Repex | Std | Unallocated | Unallocated
PS008 | Substation protection relay refurbishment | Program - Short Term Need | 3600000 | 4375000 | 4500000 | 4500000 | 4500000 | 4500000 | 4750000 | 4750000 | 4750000 | 4750000 | 4750000 | 4598385 | 4484375 | 4727812.5 | 4846007.8125 | 4967158.0078 | 5091336.958 | 5508543.7365 | 5646257.3299 | 5787413.7632 | 5932099.1073 | 6080401.5849 | 22375000 | 46125000 | 24116690.2783 | 53071405.8001 | 240 | 3600 | 42.68% | PS | PS008s | Repex | Std | Std | Substations
PS009 | Installation of SEF relays | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2850 | 66.11% | PS | PS009s | Repex | Std | Std | Substations
PS010 | Protection refurbishment (interfacing feeders) | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2550 | 68.67% | PS | PS010s | Repex | Std | Std | Substations
PS011 | Protection refurbishment (miscellaneous) | Program - Short Term Need | 895000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 1259449.92 | 717500 | 735437.5 | 753823.4375 | 772669.0234 | 791985.749 | 811785.3927 | 832080.0276 | 852882.0283 | 874204.079 | 896059.1809 | 3500000 | 7000000 | 3771415.71 | 8038426.4184 | 150 | 2250 | 70.85% | PS | PS011s | Repex | Std | Std | Substations
PS012 | Distribution feeder safety improvement | Program - Short Term Need | 4615800 | 3100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2633018.75 | 3177500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100000 | 3100000 | 3177500 | 3177500 | 310 | 4650 | 21% | PS | PS012s | Repex | Std | Std | Substations
PS013 | Feeder differential relay replacement | Program - Short Term Need | 330000 | 0 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 0 | 0 | 346706.25 | 355373.9062 | 364258.2539 | 373364.7103 | 382698.828 | 392266.2987 | 402072.9562 | 412124.7801 | 422427.8996 | 1320000 | 2970000 | 1439703.1204 | 3451293.883 | 240 | 3600 | 42.68% | PS | PS013s | Repex | Std | Std | Substations
PS014 | Under frequency load shedding | Program - Short Term Need | 500000 | 550000 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313232.73 | 563750 | 577843.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000 | 1141593.75 | 1141593.75 | 170 | 2550 | 68.67% | PS | PS014s | Repex | Std | Std | Substations
RC | Reliability compliance | Program - Short Term Need | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 3685231.26 | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 5120338.1768 | 20000000 | 40000000 | 21550946.9141 | 45933865.2482 | 400 | 6000 | 1.673% | RC | RCs | Reliability | Std | Std | Distribution lines and cables
RI | Reliability enhancement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359985.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6000 | 1.673% | RI | RIs | Reliability | Std | Std | Distribution lines and cables
SG001 | Smart grid fibre rollout & trial | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | SG | SG001s | Other | Std | Unallocated | Unallocated
SG002 | Smart meter rollout | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | SG | SG002s | Other | Std | Unallocated | Unallocated
SL001 | Streetlighting growth | Program - Short Term Need | 1400000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1100000 | 1793750 | 1838593.75 | 1884558.5937 | 1931672.5586 | 1979964.3726 | 2029463.4819 | 2080200.0689 | 2132205.0706 | 2185510.1974 | 2240147.9523 | 8750000 | 17500000 | 9428539.2749 | 20096066.0461 | 100 | 1500 | 92.18% | SL | SL001s | Other | Alt | Alt | Public lighting
SL002 | Streetlighting refurbishment | Program - Short Term Need | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 1900000 | 3075000 | 3151875 | 3230671.875 | 3311438.6719 | 3394224.6387 | 3479080.2546 | 3566057.261 | 3655208.6925 | 3746588.9098 | 3840253.6326 | 15000000 | 30000000 | 16163210.1855 | 34450398.9362 | 220 | 3300 | 54.32% | SL | SL002s | Other | Alt | Alt | Public lighting
SP | Essential spares | Program - Short Term Need | 1239026 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1423626.78 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 5000000 | 10000000 | 5387736.7285 | 11483466.3121 | 160 | 2400 | 69.74% | SP | SPs | Repex | Std | Std | Emergency Spares (Major Plant, Excludes Inventory)
TM004 | 66 & 33kV line refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM004s | Repex | Std | Unallocated | Unallocated
TM008 | 132kV tower refurb/safety upgrade | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM008s | Repex | Std | Std | Sub-transmission lines and cables
TM012 | Sub-transmission pole replacement | Program - Short Term Need | 2500000 | 2760000 | 2760000 | 2760000 | 2760000 | 3960000 | 4270000 | 4270000 | 4270000 | 4270000 | 4270000 | 2499999.99 | 2829000 | 2899725 | 2972218.125 | 3046523.5781 | 4480376.523 | 4951890.8958 | 5075688.1682 | 5202580.3724 | 5332644.8817 | 5465961.0037 | 15000000 | 36350000 | 16227843.2262 | 42256608.5479 | 310 | 4650 | 21% | TM | TM012s | Repex | Std | Std | Sub-transmission lines and cables
TM012 | Sub-transmission pole replacement | Program - Medium Term Need |  | 960000 | 960000 | 960000 | 960000 | 960000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 0 | 984000 | 1008600 | 1033815 | 1059660.375 | 1086151.8844 | 1472810.6411 | 1509630.9072 | 1547371.6798 | 1586055.9718 | 1625707.3711 | 4800000 | 11150000 | 5172227.2594 | 12913803.8305 | 310 | 3100 | 55.26% | TM | TM012m | Repex | Std | Std | Sub-transmission lines and cables
TM013 | Underground pilots | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM013s | Repex | Std | Unallocated | Unallocated
TM014 | Renewal of 33kV and 66kV gas and oil filled cables | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2700 | 66.47% | TM | TM014s | Repex | Std | Std | Sub-transmission lines and cables
TM014 | Renewal of 33kV and 66kV gas and oil filled cables | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250000 | 2250000 | 2250000 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2674542.9458 | 2741406.5194 | 2809941.6824 | 2880190.2244 | 0 | 9000000 | 0 | 11106081.372 | 180 | 1800 | 82.35% | TM | TM014m | Repex | Std | Std | Sub-transmission lines and cables
TM015 | Subtransmission tower replacement | Program - Short Term Need | 1600000 | 960000 | 960000 | 960000 | 960000 | 960000 | 1920000 | 1920000 | 1920000 | 1920000 | 1920000 | 0 | 984000 | 1008600 | 1033815 | 1059660.375 | 1086151.8844 | 2226611.363 | 2282276.647 | 2339333.5632 | 2397816.9023 | 2457762.3249 | 4800000 | 14400000 | 5172227.2594 | 16876028.0598 | 310 | 4650 | 21% | TM | TM015s | Repex | Std | Std | Sub-transmission lines and cables
TM016 | Cast iron UGOH replacement within zone substations | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | TM | TM016s | Repex | Std | Std | Sub-transmission lines and cables
TM017 | Installation of overhead earthwire | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM017s | Repex | Std | Unallocated | Unallocated
TM019 | Access track reconstruction | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4500 | 25.55% | TM | TM019s | Repex | Std | Std | Sub-transmission lines and cables
TM020 | Traffic blackspot remediation - transmission | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM020 | Repex | Std | Unallocated | Unallocated
TM021 | Capital works for compliance to NSW Maritime Waterways | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM021 | Repex | Std | Std | Sub-transmission lines and cables
TM023 | Renewal of 132kV cable 233 | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | TM | TM023 | Repex | Std | Std | Sub-transmission lines and cables
TM027 | Steel tower asbestos removal | Major Project - Committed Project | 3013000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3900 | 38.53% | TM | TM027 | Repex | Std | Std | Sub-transmission lines and cables
TM028 | 132kV oil cable replacement | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 10200000 | 9900000 | 9900000 | 10200000 | 10200000 | 0 | 0 | 0 | 0 | 0 | 0 | 11828872.8658 | 11767988.9613 | 12062188.6853 | 12738402.2935 | 13056862.3508 | 0 | 50400000 | 0 | 61454315.1567 | 260 | 1300 | 92.18% | TM | TM028l | Repex | Std | Std | Sub-transmission lines and cables
TM029 | Installation of aerial marker malls on high spans | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122585.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2100 | 78.28% | TM | TM029s | Repex | Std | Std | Sub-transmission lines and cables
TM030 | Feeder 7028 replacement | Major Project - Prior to Approval | 500000 | 1600000 | 1600000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640000 | 1681000 | 1723025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800000 | 4800000 | 5044025 | 5044025 | 200 | 2000 | 80.61% | TM | TM030 | Repex | Std | Std | Sub-transmission lines and cables
TM031 | Steel tower asbestos removal | Program - Short Term Need |  | 12195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112125 | 12499.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12195 | 12195 | 12499.875 | 12499.875 | 260 | 3900 | 38.53% | TM | TM031s | Repex | Std | Std | Sub-transmission lines and cables
TM031 | Steel tower asbestos removal | Program - Medium Term Need |  | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2870000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800000 | 2800000 | 2870000 | 2870000 | 260 | 2600 | 66.7% | TM | TM031m | Repex | Std | Std | Sub-transmission lines and cables
TM033 | Pole top structure/hardware refurbishment (TR) | Program - Short Term Need |  | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 1347670 | 734759.36 | 1381361.75 | 1415895.7937 | 1451293.1886 | 1487575.5183 | 1524764.9063 | 1562884.0289 | 1601956.1296 | 1642005.0329 | 1683055.1587 | 1725131.5377 | 6738350 | 13476700 | 7260891.1569 | 15475923.0448 | 330 | 4950 | 12.56% | TM | TM033s | Repex | Std | Std | Sub-transmission lines and cables
TM131 | Underground pilots replacement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1950 | 80.61% | TM | TM131s | Repex | Std | Std | Sub-transmission lines and cables
TM132 | Sub-transmission pilot cable renewal program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115000 | 1115000 | 1115000 | 1115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1325384.6153 | 1358519.2307 | 1392482.2115 | 1427294.2668 | 0 | 4460000 | 0 | 5503680.3243 | 160 | 2400 | 69.74% | TM | TM132s | Repex | Std | Std | Sub-transmission lines and cables
TM133 | Hardex pilot cable renewal | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.32% | TM | TM133s | Repex | Std | Std | Sub-transmission lines and cables
TM134 | Wollongong - Port Kembla pilot cable replacement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665000 | 1665000 | 1665000 | 1665000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1979161.7799 | 2028640.8244 | 2079356.845 | 2131340.7661 | 0 | 6660000 | 0 | 8218500.2153 | 110 | 1650 | 88.95% | TM | TM134s | Repex | Std | Std | Sub-transmission lines and cables
TM135 | Optical fibre protection and communication upgrades in the Blue Mountains | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 928000 | 928000 | 928000 | 928000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1103100.3794 | 1130677.8889 | 1158944.8361 | 1187918.457 | 0 | 3712000 | 0 | 4580641.5614 | 110 | 1650 | 88.95% | TM | TM135s | Repex | Std | Std | Sub-transmission lines and cables
TM137 | Optical fibre protection and communication upgrades in the Macarthur area | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908000 | 908000 | 908000 | 908000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079326.6643 | 1106309.8309 | 1133967.5767 | 1162316.7661 | 0 | 3632000 | 0 | 4481920.8381 | 110 | 1650 | 88.95% | TM | TM137s | Repex | Std | Std | Sub-transmission lines and cables
TM138 | 132kV optical fibre ring completion | Major Project - Committed Project | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1650 | 88.95% | TM | TM138 | Repex | Std | Std | Sub-transmission lines and cables
TM171 | Replacement of corroded earthwires | Program - Short Term Need | 2000000 | 0 | 0 | 0 | 0 | 138000 | 897000 | 897000 | 897000 | 897000 | 897000 | 3545011.83 | 0 | 0 | 0 | 0 | 156134.3334 | 1040244.9961 | 1066251.121 | 1092907.3991 | 1120230.084 | 1148235.8361 | 138000 | 4623000 | 156134.3334 | 5624003.7698 | 270 | 4050 | 37.22% | TM | TM171s | Repex | Std | Std | Sub-transmission lines and cables
TM172 | Earthwire replacement due to fault rating | Program - Short Term Need | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050625 | 1076890.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 2127515.625 | 2127515.625 | 170 | 2550 | 68.67% | TM | TM172s | Repex | Std | Std | Sub-transmission lines and cables
TM174 | Hardex earthwire replacement | Program - Short Term Need | 0 | 0 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 0 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 4000000 | 9000000 | 4362736.7285 | 10458466.3121 | 240 | 3600 | 42.68% | TM | TM174s | Repex | Std | Std | Sub-transmission lines and cables
TM302 | Oil filled cable auxiliary equipment refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.52% | TM | TM302s | Repex | Std | Std | Sub-transmission lines and cables
TM302 | Oil filled cable auxiliary equipment refurbishment | Program - Medium Term Need | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 75645 | 0 | 0 | 0 | 0 | 85585.3743 | 0 | 0 | 0 | 72000 | 144000 | 75645 | 161230.3743 | 200 | 2000 | 80.61% | TM | TM302m | Repex | Std | Std | Sub-transmission lines and cables
TM303 | Guilford and Camellia 132kV cables oil testing and flushing | Program - Short Term Need | 465136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3900 | 38.53% | TM | TM303s | Repex | Std | Std | Sub-transmission lines and cables
TM303 | Guilford and Camellia 132kV cables oil testing and flushing | Program - Medium Term Need |  | 0 | 90000 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 94556.25 | 0 | 0 | 0 | 0 | 106981.7178 | 0 | 0 | 0 | 90000 | 180000 | 94556.25 | 201537.9678 | 260 | 2600 | 66.7% | TM | TM303m | Repex | Std | Std | Sub-transmission lines and cables
TM401 | South Coast 33kV overhead line refurbishment | Program - Short Term Need | 998000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932355.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3600 | 42.68% | TM | TM401s | Repex | Std | Std | Sub-transmission lines and cables
TM404 | Avon/Nepean Dam feeder refurbishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5250 | 4.71% | TM | TM404 | Repex | Std | Std | Sub-transmission lines and cables
TM408 | Ringwood Feeder 7906 Refurbishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.32% | TM | TM408 | Repex | Std | Std | Sub-transmission lines and cables
TM410 | Hazelbook ZS to Springwood ZS Feeder 808 refurbishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4350 | 29.29% | TM | TM410 | Repex | Std | Std | Sub-transmission lines and cables
TM419 | Future sub-transmission feeder refurbishment works | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 7500000 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4264410.1413 | 9366472.2746 | 15361014.5304 | 0 | 23000000 | 0 | 28991896.9462 | 150 | 2250 | 70.85% | TM | TM419s | Repex | Std | Std | Sub-transmission lines and cables
TM419 | Future sub-transmission feeder refurbishment works | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 900000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609201.4488 | 1123976.673 | 1920126.8163 | 0 | 2900000 | 0 | 3653304.938 | 150 | 1500 | 92.18% | TM | TM419m | Repex | Std | Std | Sub-transmission lines and cables
TM419 | Future sub-transmission feeder refurbishment works | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 900000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609201.4488 | 1123976.673 | 1920126.8163 | 0 | 2900000 | 0 | 3653304.938 | 150 | 750 | 99.19% | TM | TM419l | Repex | Std | Std | Sub-transmission lines and cables
TM801 | Steel tower painting program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 800000 | 800000 | 800000 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 927754.7346 | 950948.6029 | 974722.318 | 999090.376 | 1024067.6354 | 0 | 4000000 | 0 | 4876583.6668 | 170 | 2550 | 68.67% | TM | TM801s | Repex | Std | Std | Sub-transmission lines and cables
TM803 | Steel tower below ground rectification work | Program - Short Term Need | 2599999.92 | 0 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1200000 | 750000 | 750000 | 4408559.12 | 0 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1739540.1273 | 1783028.6305 | 1462083.477 | 936647.2275 | 960063.4081 | 6000000 | 11700000 | 6544105.0928 | 13425467.9632 | 310 | 4650 | 21% | TM | TM803s | Repex | Std | Std | Sub-transmission lines and cables
TM805 | Earthing refurbishment of lines 940/941 | Program - Short Term Need | 178388.89 | 200000 | 200000 | 200000 | 200000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 46970 | 205000 | 210125 | 215378.125 | 220762.5781 | 22628.1643 | 23193.8684 | 23773.7151 | 24368.058 | 24977.2594 | 25601.6909 | 820000 | 920000 | 873893.8674 | 995808.4591 | 270 | 4050 | 37.22% | TM | TM805s | Repex | Std | Std | Sub-transmission lines and cables
TM805 | Earthing refurbishment of lines 940/941 | Program - Medium Term Need |  | 80000 | 80000 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000 | 84050 | 86151.25 | 88305.0312 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 320000 | 340506.2812 | 340506.2812 | 270 | 2700 | 66.47% | TM | TM805m | Repex | Std | Std | Sub-transmission lines and cables
TM809 | Subtransmission line earthing refurbishment | Program - Short Term Need | 0 | 0 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0 | 0 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | 384025.3633 | 1200000 | 2700000 | 1308821.0186 | 3137539.8936 | 150 | 2250 | 70.85% | TM | TM809s | Repex | Std | Std | Sub-transmission lines and cables
TM809 | Subtransmission line earthing refurbishment | Program - Medium Term Need | 0 | 0 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0 | 0 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | 384025.3633 | 1200000 | 2700000 | 1308821.0186 | 3137539.8936 | 150 | 1500 | 92.18% | TM | TM809m | Repex | Std | Std | Sub-transmission lines and cables
TS001 | Power transformer replacement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS001s | Repex | Std | Unallocated | Unallocated
TS004 | 132kV circuit breaker replacement | Program - Short Term Need | 903000 | 0 | 0 | 0 | 362000 | 362000 | 362000 | 362000 | 362000 | 362000 | 362000 | 100000 | 0 | 0 | 0 | 399580.2664 | 409569.7731 | 419809.0174 | 430304.2428 | 441061.8489 | 452088.3951 | 463390.605 | 724000 | 2534000 | 809150.0395 | 3015804.1487 | 240 | 3600 | 42.68% | TS | TS004s | Repex | Std | Std | Substations
TS005 | 33kV circuit breaker replacement | Program - Short Term Need | 3410000 | 0 | 0 | 0 | 770000 | 770000 | 1184000 | 1184000 | 1184000 | 1184000 | 1184000 | 1522311.51 | 0 | 0 | 0 | 849935.9258 | 871184.3239 | 1373077.0072 | 1407403.9323 | 1442589.0307 | 1478653.7564 | 1515620.1003 | 1540000 | 7460000 | 1721120.2497 | 8938464.0766 | 240 | 3600 | 42.68% | TS | TS005s | Repex | Std | Std | Substations
TS007 | 11kV circuit breaker replacement | Program - Short Term Need | 0 | 0 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.59 | 0 | 367718.75 | 376911.7187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 700000 | 744630.4688 | 744630.4688 | 230 | 3450 | 51.29% | TS | TS007s | Repex | Std | Std | Substations
TS008 | Battery replacement | Program - Short Term Need | 1253792 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 1300326.84 | 533000 | 546325 | 559983.125 | 573982.7031 | 588332.2707 | 603040.5775 | 618116.5919 | 633569.5067 | 649408.7444 | 665643.963 | 2600000 | 5200000 | 2801623.0988 | 5971402.4823 | 370 | 5550 | 1.951% | TS | TS008s | Repex | Std | Std | Substations
TS008 | Battery replacement | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 520000 | 520000 | 520000 | 520000 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 603040.5775 | 618116.5919 | 633569.5067 | 649408.7444 | 665643.963 | 0 | 2600000 | 0 | 3169779.3834 | 370 | 3700 | 38.64% | TS | TS008m | Repex | Std | Std | Substations
TS009 | Auxiliary switchgear replacement | Program - Short Term Need | 817000 | 0 | 0 | 0 | 282000 | 0 | 282000 | 0 | 0 | 0 | 0 | 647392 | 0 | 0 | 0 | 311275.2352 | 0 | 327033.5439 | 0 | 0 | 0 | 0 | 282000 | 564000 | 311275.2352 | 638308.7791 | 190 | 2850 | 66.11% | TS | TS009s | Repex | Std | Std | Substations
TS011 | Freq injection replacement/augmentation | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS011s | Repex | Std | Unallocated | Unallocated
TS015 | Replacement of surge arrester in zone and sub-transmission substations | Program - Short Term Need | 132000 | 37000 | 50000 | 50000 | 50000 | 25000 | 50000 | 50000 | 50000 | 50000 | 50000 | 57400 | 37925 | 52531.25 | 53844.5312 | 55190.6445 | 28285.2053 | 57984.6709 | 59434.2877 | 60920.1449 | 62443.1485 | 64004.2272 | 212000 | 462000 | 227776.6311 | 532563.1103 | 190 | 2850 | 66.11% | TS | TS015s | Repex | Std | Std | Substations
TS015 | Replacement of surge arrester in zone and sub-transmission substations | Program - Medium Term Need |  | 0 | 68000 | 68000 | 68000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71442.5 | 73228.5625 | 75059.2766 | 28285.2053 | 0 | 0 | 0 | 0 | 0 | 229000 | 229000 | 248015.5444 | 248015.5444 | 190 | 1900 | 80.68% | TS | TS015m | Repex | Std | Std | Substations
TS016 | VT and CT replacement | Program - Short Term Need | 1095000 | 0 | 0 | 0 | 698000 | 698000 | 698000 | 698000 | 698000 | 698000 | 698000 | 1131559.16 | 0 | 0 | 0 | 770461.3977 | 789722.9326 | 809466.0059 | 829702.6561 | 850445.2225 | 871706.353 | 893499.0118 | 1396000 | 4886000 | 1560184.3303 | 5815003.5796 | 240 | 3600 | 42.68% | TS | TS016s | Repex | Std | Std | Substations
TS017 | Power transformer refurbishment | Program - Short Term Need | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2100 | 78.28% | TS | TS017s | Repex | Std | Std | Transformers
TS020 | Portable earthing set cabinets | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1350 | 92.18% | TS | TS020s | Repex | Std | Std | Substations
TS024 | Building and amenities refurbishment | Program - Short Term Need | 500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 740909.15 | 1537500 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 7500000 | 12500000 | 8081605.0928 | 14177334.6763 | 200 | 3000 | 58.52% | TS | TS024s | Repex | Std | Std | Substations
TS024 | Building and amenities refurbishment | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 0 | 5000000 | 0 | 6095729.5835 | 200 | 2000 | 80.61% | TS | TS024m | Repex | Std | Std | Substations
TS025 | Asbestos and other hazardous material reporting, management and removal | Program - Short Term Need | 650000 | 89000 | 450000 | 450000 | 518000 | 520000 | 539000 | 450000 | 450000 | 518000 | 520000 | 641743.65 | 91225 | 472781.25 | 484600.7812 | 571775.0773 | 588332.2707 | 625074.7524 | 534908.5892 | 548281.3039 | 646911.0184 | 665643.963 | 2027000 | 4504000 | 2208714.3793 | 5229534.0062 | 160 | 2400 | 69.74% | TS | TS025s | Repex | Std | Std | Substations
TS026 | Noise attenuation in ZS and TS | Program - Short Term Need | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 1076890.625 | 0 | 1131408.2129 | 0 | 1188685.7537 | 0 | 1248862.9699 | 0 | 2000000 | 4000000 | 2208298.8379 | 4645847.5615 | 210 | 3150 | 54.86% | TS | TS026s | Repex | Std | Std | Substations
TS027 | Substation switchyard lighting improvement | Program - Short Term Need | 0 | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 110000 | 0 | 112750 | 115568.75 | 118457.9687 | 121419.418 | 124454.9034 | 127566.276 | 130755.4329 | 134024.3187 | 137374.9267 | 140809.2999 | 550000 | 1100000 | 592651.0401 | 1263181.2943 | 140 | 2100 | 78.28% | TS | TS027s | Repex | Std | Std | Substations
TS028 | Control cable trench and cover refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 600 | 99.19% | TS | TS028s | Repex | Std | Std | Substations
TS029 | Substation control room temperature reduction initiatives | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1500 | 92.18% | TS | TS029s | Repex | Std | Std | Substations
TS031 | Substation safety fence upgrade program | Program - Short Term Need | 300000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 646105.78 | 102500 | 105062.5 | 107689.0625 | 110381.2891 | 113140.8213 | 115969.3418 | 118868.5754 | 121840.2898 | 124886.297 | 128008.4544 | 500000 | 1000000 | 538773.6729 | 1148346.6312 | 230 | 3450 | 51.29% | TS | TS031s | Repex | Std | Std | Substations
TS032 | Substation security systems | Program - Short Term Need | 0 | 150000 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153750 | 157593.75 | 161533.5937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000 | 472877.3438 | 472877.3438 | 150 | 2250 | 70.85% | TS | TS032s | Repex | Std | Std | Substations
TS033 | Substation fire hydrant installations | Program - Short Term Need | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 191793 | 205000 | 210125 | 215378.125 | 220762.5781 | 226281.6426 | 231938.6836 | 237737.1507 | 243680.5795 | 249772.594 | 256016.9088 | 1000000 | 2000000 | 1077547.3457 | 2296693.2624 | 160 | 2400 | 69.74% | TS | TS033s | Repex | Std | Std | Substations
TS034 | Substation deluge showers and fire blankets | Program - Short Term Need | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 152066.08 | 164000 | 168100 | 172302.5 | 176610.0625 | 181025.3141 | 185550.9469 | 190189.7206 | 194944.4636 | 199818.0752 | 204813.5271 | 800000 | 1600000 | 862037.8766 | 1837354.6099 | 120 | 1800 | 82.35% | TS | TS034s | Repex | Std | Std | Substations
TS035 | Substation oil containment program - bund walls | Program - Short Term Need | 210000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 198616 | 71750 | 73543.75 | 75382.3437 | 77266.9023 | 79198.5749 | 81178.5393 | 83208.0028 | 85288.2028 | 87420.4079 | 89605.9181 | 350000 | 700000 | 377141.571 | 803842.6418 | 110 | 1650 | 88.95% | TS | TS035s | Repex | Std | Std | Substations
TS036 | Substation earthing | Program - Short Term Need | 998483 | 340000 | 408000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 755210 | 348500 | 428655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748000 | 748000 | 777155 | 777155 | 370 | 5550 | 1.951% | TS | TS036s | Repex | Std | Std | Substations
TS047 | Equipment labelling in TS & ZS | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS047s | Repex | Std | Unallocated | Unallocated
TS048 | Substation oil containment program - separators | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000 | 97.4% | TS | TS048s | Repex | Std | Std | Substations
TS049 | Tunnelboard refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 0 | 49671.5801 | 50913.3696 | 0 | 0 | 0 | 56198.8336 | 57603.8045 | 90000 | 180000 | 100584.9497 | 214387.5878 | 150 | 2250 | 70.85% | TS | TS049s | Repex | Std | Std | Substations
TS050 | POW switching for capacitors | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2250 | 70.85% | TS | TS050s | Repex | Std | Std | Substations
TS055 | 66kV circuit breaker replacement | Program - Short Term Need | 258000 | 258000 | 258000 | 0 | 0 | 0 | 258000 | 258000 | 258000 | 258000 | 258000 | 0 | 264450 | 271061.25 | 0 | 0 | 0 | 299200.9019 | 306680.9244 | 314347.9476 | 322206.6462 | 330261.8124 | 516000 | 1806000 | 535511.25 | 2108209.4826 | 240 | 3600 | 42.68% | TS | TS055s | Repex | Std | Std | Substations
TS057 | Substation insulation co-ordination | Program - Short Term Need | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2400 | 69.74% | TS | TS057s | Repex | Std | Std | Substations
TS060 | Lawson TS rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS060 | Repex | Std | Unallocated | Unallocated
TS067 | Rosehill ZS renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS067 | Repex | Std | Std | Substations
TS072 | Holroyd ZS renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS072 | Repex | Std | Std | Substations
TS086 | Busbar support and isolator replacement | Program - Short Term Need | 325000 | 0 | 94500 | 94500 | 94500 | 94500 | 94500 | 94500 | 94500 | 94500 | 94500 | 197917 | 0 | 99284.0625 | 101766.1641 | 104310.3182 | 106918.0761 | 109591.028 | 112330.8037 | 115139.0738 | 118017.5507 | 120967.9894 | 378000 | 850500 | 412278.6208 | 988325.0665 | 200 | 3000 | 58.52% | TS | TS086s | Repex | Std | Std | Substations
TS092 | Jasper Rd 11kV CB renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS092 | Repex | Std | Std | Substations
TS099 | Substation power outlet installation | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 750 | 99.19% | TS | TS099s | Repex | Std | Std | Substations
TS100 | Substation internal fence replacement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1350 | 92.18% | TS | TS100s | Repex | Std | Std | Substations
TS102 | Rydalmere Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.29% | TS | TS102 | Repex | Std | Std | Substations
TS111 | Blackheath ZS 11kV switchyard renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS111 | Repex | Std | Std | Substations
TS116 | Roof refurbishment for control and switch rooms | Program - Short Term Need | 500000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 556587.42 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442 | 5000000 | 10000000 | 5387736.7285 | 11483466.3121 | 280 | 4200 | 36.29% | TS | TS116s | Repex | Std | Std | Substations
TS116 | Roof refurbishment for control and switch rooms | Program - Medium Term Need |  | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0 | 512500 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | 640042.2721 | 2500000 | 5000000 | 2693868.3643 | 5741733.156 | 280 | 2800 | 66.39% | TS | TS116m | Repex | Std | Std | Substations
TS118 | Smithfield Zone Substation rebuilding | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS118 | Repex | Std | Unallocated | Unallocated
TS119 | Bomaderry ZS redevelopment (fmr PR403) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS119 | Repex | Std | Std | Substations
TS120 | Canley Vale ZS redevelopment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS120 | Repex | Std | Std | Substations
TS121 | Port Kembla ZS | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4200 | 36.29% | TS | TS121 | Repex | Std | Std | Substations
TS122 | Leabons Lane Zone Substation renewal | Major Project - Committed Project | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.29% | TS | TS122 | Repex | Std | Std | Substations
TS123 | St Marys Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.29% | TS | TS123 | Repex | Std | Std | Substations
TS124 | Substation control building fire alarm systems | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.52% | TS | TS124s | Repex | Std | Std | Substations
TS125 | Guildford Transmission Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6300 | 0% | TS | TS125 | Repex | Std | Std | Substations
TS126 | Comalco HVC renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS126 | Repex | Std | Std | Substations
TS127 | Castle Hill Zone Substation renewal | Major Project - Committed Project | 163333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.29% | TS | TS127 | Repex | Std | Std | Substations
TS128 | Capacitor bank refurbishment | Program - Short Term Need | 1270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1372467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4200 | 36.29% | TS | TS128s | Repex | Std | Std | Substations
TS130 | Northmead Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4500 | 25.55% | TS | TS130 | Repex | Std | Std | Substations
TS131 | Bulli Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4125 | 36.29% | TS | TS131 | Repex | Std | Std | Substations
TS133 | Corrimal ZS redevelopment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4575 | 21% | TS | TS133 | Repex | Std | Std | Substations
TS134 | South Granville Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.29% | TS | TS134 | Repex | Std | Std | Substations
TS135 | Ringwood ZS redevelopment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS135 | Repex | Std | Std | Substations
TS136 | Kandos ZS redevelopment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS136 | Repex | Std | Std | Substations
TS137 | Power transformer oil temperature indicator | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS137s | Repex | Std | Unallocated | Unallocated
TS138 | Baulkham Hills switchgear rearrangement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS138 | Repex | Std | Std | Substations
TS139 | Oakdale ZS swgr rearrangement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS139 | Repex | Std | Std | Substations
TS143 | Westmead Zone Substation renewal and augmentation | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5700 | 1.673% | TS | TS143 | Repex | Std | Std | Substations
TS144 | Substation fire stopping measures | Program - Short Term Need | 198000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 186676 | 67650 | 69341.25 | 71074.7812 | 72851.6508 | 74672.9421 | 76539.7656 | 78453.2597 | 80414.5912 | 82424.956 | 84485.5799 | 330000 | 660000 | 355590.6241 | 757908.7766 | 160 | 2400 | 69.74% | TS | TS144s | Repex | Std | Std | Substations
TS146 | Marayong Zone Substation renewal | Major Project - Committed Project | 13051000 | 8204878 | 1829077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2558031 | 8409999.95 | 1921674.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10033955 | 10033955 | 10331673.9731 | 10331673.9731 | 230 | 3450 | 51.29% | TS | TS146 | Repex | Std | Std | Substations
TS149 | South Windsor ZS refurbishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS149 | Repex | Std | Std | Substations
TS155 | Sussex Inlet Zone Substation - stage 2 renewal | Major Project - Committed Project | 2400000 | 1678556 | 37345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3841000.34 | 1720519.9 | 39235.5906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1715901 | 1715901 | 1759755.4906 | 1759755.4906 | 210 | 3150 | 54.86% | TS | TS155 | Repex | Std | Std | Substations
TS156 | Lawson TS - RailCorp connections works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3975 | 37.22% | TS | TS156 | Repex | Std | Std | Substations
TS167 | Carlingford Transmission Substation control building replacement | Major Project - Prior to Approval | 0 | 0 | 4500000 | 4500000 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4727812.5 | 4846007.8125 | 4967158.0078 | 0 | 0 | 0 | 0 | 0 | 0 | 13500000 | 13500000 | 14540978.3203 | 14540978.3203 | 180 | 1800 | 82.35% | TS | TS167 | Repex | Std | Std | Substations
TS168 | Carramar Zone Substation switchgear replacement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | TS | TS168 | Repex | Std | Std | Substations
TS173 | 11kV switchboard truck replacement program | Program - Short Term Need | 2894255 | 3648000 | 3648000 | 3648000 | 2928000 | 2928000 | 2928000 | 2928000 | 2928000 | 0 | 0 | 1841138 | 3739200 | 3832680 | 3928497 | 3231964.1437 | 3312763.2473 | 3395582.3285 | 3480471.8867 | 3567483.6839 | 0 | 0 | 16800000 | 25584000 | 18045104.3911 | 28488642.2903 | 290 | 4350 | 29.29% | TS | TS173s | Repex | Std | Std | Substations
TS175 | Defective CT replacement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2100 | 78.28% | TS | TS175s | Repex | Std | Std | Substations
TS177 | Substation battery duplication | Program - Short Term Need | 1582100 | 0 | 918000 | 765000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2245214.8 | 0 | 964473.75 | 823821.3281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683000 | 1683000 | 1788295.0781 | 1788295.0781 | 330 | 4950 | 12.56% | TS | TS177s | Repex | Std | Std | Substations
TS178 | Jerrara SS steel support structures | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.52% | TS | TS178 | Repex | Std | Std | Substations
TS179 | 33kV wall bushing replacement | Program - Short Term Need | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237836.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3150 | 54.86% | TS | TS179s | Repex | Std | Std | Substations
TS180 | Transformer fire wall installation | Program - Short Term Need | 200000 | 0 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | 0 | 630375 | 646134.375 | 662287.7344 | 678844.9277 | 695816.0509 | 713211.4522 | 731041.7385 | 749317.782 | 768050.7265 | 2400000 | 5400000 | 2617642.0371 | 6275079.7872 | 140 | 2100 | 78.28% | TS | TS180s | Repex | Std | Std | Substations
TS181 | 11kV capacitor bank refurbishment | Program - Short Term Need | 887526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4050 | 37.22% | TS | TS181s | Repex | Std | Std | Substations
TS182 | Substation civil capital works scoping | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.29% | TS | TS182s | Repex | Std | Std | Substations
TS183 | Carlingford TS/Dundas ZS Redevelopment | Major Project - Committed Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS183 | Repex | Std | Std | Substations
TS184 | Blaxland Zone Substation reinstatement | Major Project - Committed Project | 691500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 946244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4500 | 25.55% | TS | TS184 | Repex | Std | Std | Substations
TS185 | Penrith TS civil development | Major Project - Committed Project | 2101666.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086556.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.29% | TS | TS185 | Repex | Std | Std | Substations
TS187 | Mobile substation No 2 refurbishment | Program - Short Term Need | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2850 | 66.11% | TS | TS187s | Repex | Std | Std | Substations
TS188 | Bossley Park ZS civil refurbishment | Major Project - Committed Project | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.52% | TS | TS188 | Repex | Std | Std | Substations
TS199 | Future sub-transmission substation renewal programs | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 7500000 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4264410.1413 | 9366472.2746 | 15361014.5304 | 0 | 23000000 | 0 | 28991896.9462 | 180 | 2700 | 66.47% | TS | TS199s | Repex | Std | Std | Substations
TS199 | Future sub-transmission substation renewal programs | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 900000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609201.4488 | 1123976.673 | 1920126.8163 | 0 | 2900000 | 0 | 3653304.938 | 180 | 1800 | 82.35% | TS | TS199m | Repex | Std | Std | Substations
TS199 | Future sub-transmission substation renewal programs | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 900000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609201.4488 | 1123976.673 | 1920126.8163 | 0 | 2900000 | 0 | 3653304.938 | 180 | 900 | 97.4% | TS | TS199l | Repex | Std | Std | Substations
TS600 | Power transformer replacement | Program - Short Term Need | 0 | 1700000 | 11600000 | 7500000 | 11000000 | 11100000 | 12700000 | 12700000 | 12700000 | 12700000 | 12700000 | 0 | 1742500 | 12187250 | 8076679.6875 | 12141941.7969 | 12558631.1631 | 14728106.4113 | 15096309.0716 | 15473716.7984 | 15860559.7183 | 16257073.7113 | 42900000 | 106400000 | 46707002.6475 | 124122768.3584 | 340 | 5100 | 9.283% | TS | TS600s | Repex | Std | Std | Transformers
TS601 | Cranebrook ZS 33kV No 3 - transformer replacement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS601 | Repex | Std | Std | Transformers
TS602 | Prospect ZS 33kV No3 transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS602 | Repex | Std | Std | Transformers
TS603 | Kingwood ZS 33kV No 3 - transformer replacement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS603 | Repex | Std | Unallocated | Unallocated
TS604 | Liverpool TS 132kV No 3 - transformer replacement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS604 | Repex | Std | Std | Transformers
TS605 | West Liverpool 132 kV No 3 transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS605 | Repex | Std | Std | Substations
TS615 | Gerringong ZS 33kV No 2 transformer replacement | Major Project - Committed Project | 6894.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15251.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5100 | 9.283% | TS | TS615 | Repex | Std | Std | Transformers
TS616 | Camellia TS transformer replacement and 33kV busbar rearrangement | Major Project - Committed Project | 2608611 | 332642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2660563 | 340958.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332642 | 332642 | 340958.05 | 340958.05 | 340 | 5100 | 9.283% | TS | TS616 | Repex | Std | Std | Transformers
TS617 | Prospect ZS transformer replacement | Major Project - Committed Project | 2449406 | 29268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2449406 | 29999.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29268 | 29268 | 29999.7 | 29999.7 | 340 | 5100 | 9.283% | TS | TS617 | Repex | Std | Std | Transformers
TS618 | Albion Park ZS transformer replacement | Major Project - Committed Project | 2457614 | 1577261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248155.45 | 1616692.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1577261 | 1577261 | 1616692.525 | 1616692.525 | 340 | 5100 | 9.283% | TS | TS618 | Repex | Std | Std | Transformers
TS619 | Dundas ZS 66kV No 2 transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5100 | 9.283% | TS | TS619 | Repex | Std | Std | Transformers
TS620 | Minto 66/11kV No 1 transformer replacement | Major Project - Committed Project |  | 1080563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662423 | 1107577.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080563 | 1080563 | 1107577.075 | 1107577.075 | 340 | 4950 | 12.56% | TS | TS620 | Repex | Std | Std | Transformers
TS700 | 11kV zone substation switchboard replacement | Program - Short Term Need | 0 | 0 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0 | 0 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 5120338.1768 | 16000000 | 36000000 | 17450946.9141 | 41833865.2482 | 290 | 4350 | 29.29% | TS | TS700s | Repex | Std | Std | Substations
TS700 | 11kV zone substation switchboard replacement | Program - Medium Term Need | 0 | 0 | 0 | 0 | 4000000 | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4415251.5625 | 9051265.7031 | 0 | 0 | 0 | 0 | 0 | 12000000 | 12000000 | 13466517.2656 | 13466517.2656 | 290 | 2900 | 59.74% | TS | TS700m | Repex | Std | Std | Substations
TS701 | North Rocks ZS 11kV switchboard replacement | Major Project - Committed Project | 2100000 | 777546 | 36169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453893 | 796984.65 | 38000.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813715 | 813715 | 834984.7056 | 834984.7056 | 290 | 4350 | 29.29% | TS | TS701 | Repex | Std | Std | Substations
TS702 | Kellyville ZS 11kV switchboard replacement | Major Project - Committed Project | 1890000 | 953171 | 265366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573638 | 977000.275 | 278800.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218537 | 1218537 | 1255800.4287 | 1255800.4287 | 290 | 4350 | 29.29% | TS | TS702 | Repex | Std | Std | Substations
TS703 | Horsley Park ZS 11kV switchboard replacement | Major Project - Committed Project | 2610000 | 424390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1941242 | 434999.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424390 | 424390 | 434999.75 | 434999.75 | 290 | 4350 | 29.29% | TS | TS703 | Repex | Std | Std | Substations
TS704 | Port Central ZS 11kV switchboard replacement | Major Project - Committed Project | 1740000 | 488652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1583396.03 | 500868.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488652 | 488652 | 500868.3 | 500868.3 | 290 | 4350 | 29.29% | TS | TS704 | Repex | Std | Std | Substations
UR | Underground residential | Program - Short Term Need | 33939845.5741 | 21659051 | 14600685 | 11758786 | 11056595 | 10803669 | 10803669 | 10803669 | 10803669 | 10803669 | 10803669 | 27120000.008 | 22200527.275 | 15339844.6781 | 12662926.4048 | 12204412.0874 | 12223359.836 | 12528943.8319 | 12842167.4276 | 13163221.6133 | 13492302.1537 | 13829609.7075 | 69878786 | 123897131 | 74631070.2813 | 140487315.0153 | 190 | 2850 | 66.11% | UR | URs | Connections | Std | Std | Distribution lines and cables
SW | Network Switching | Overheads | 3277639.0026 | 6283900.8865 | 6382175.5445 | 6686467.7532 | 6495126.3573 | 6714861.5396 | 7423719.2767 | 7683873.5145 | 7944102.7058 | 8085985.7683 | 8183178.6979 | 3277485.76 | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | 10475160.5735 | [9 empty] | Overheads |  | Std | Overheads
OH | Capitalised Overheads | Overheads | 73255146 | 73106139.0812 | 73273110.1037 | 73775204.5564 | 73462071.757 | 73820942.4206 | 76860996.0999 | 77233408.4879 | 77593252.7624 | 77784338.9426 | 78058962.8601 | 66922514.26 | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | 99922071.8932 | [9 empty] | Overheads |  | Std | Overheads
|  | Total - Exc SWOH | 278268576.2497 | 230618406 | 226392736 | 232892481 | 253231614 | 250788792 | 252388669 | 261527529 | 289157626 | 309697865 | 321694374 | 246955911.5435 | 236383866.15 | 237853868.26 | 250799729.4219 | 279520319.847 | 283744498.9697 | 292693478.2708 | 310874047.9144 | 352310489.3555 | 386770195.4704 | 411795996.1123
|  | Total - Inc SWOH | 354801361.2523 | 310008445.9677 | 306048021.6482 | 313354153.3096 | 333188812.1143 | 331324595.9602 | 336673384.3766 | 346444811.0024 | 374694981.4683 | 395568189.7109 | 407936515.558 | 317155911.5635 | 317758657.1169 | 321541702.7441 | 337448150.0039 | 367778105.8238 | 374863369.0021 | 390437907.9489 | 411814011.2709 | 456529451.1034 | 494010464.2192 | 522193228.5791
|  |  | FY19 (R) | FY20 (R) | FY21 (R) | FY22 (R) | FY23 (R) | FY24 (R) | FY25 (R) | FY26 (R) | FY27 (R) | FY28 (R) | FY28 (R) | FY19 (N) | FY20 (N) | FY21 (N) | FY22 (N) | FY23 (N) | FY24 (N) | FY25 (N) | FY26 (N) | FY27 (N) | FY28 (N) | FY28 (N)
|  | Augex | 57522026 | 64808968 | 64514992 | 70132408 | 78309987 | 72071597 | 80244851 | 76142154 | 85054650 | 84625200 | 76412400 | 57478433.0865 | 66429192.2 | 67781063.47 | 75524932.6839 | 86439573.1153 | 81542396.7619 | 93059425.5502 | 90509093.7134 | 103630832.0067 | 105685278.6044 | 97814332.2249
|  | Repex | 146012101.7474 | 109287872 | 120299207 | 118788250 | 124144750 | 127818750 | 137115750 | 150242750 | 169045750 | 190290750 | 210402750 | 123680707.799 | 112020068.8 | 126389354.3544 | 127921952.7852 | 137032575.3534 | 144615183.5114 | 159012232.8083 | 178591416.5169 | 205965831.6117 | 237647071.1986 | 269333308.3314
|  | Connections | 48419634.5023 | 33956216 | 24446757 | 20808877 | 19862891 | 19577920 | 19577920 | 19577920 | 19577920 | 19577920 | 19760628 | 40340000.008 | 34805121.4 | 25684374.0731 | 22408884.5581 | 21924915.1309 | 22150619.4793 | 22704384.9663 | 23271994.5905 | 23853794.4552 | 24450139.3166 | 25295274.4864
|  | Reliability | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4045216.63 | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 5120338.1768
|  | Other | 17809814 | 13635350 | 8241780 | 6422946 | 6353986 | 6720525 | 6605148 | 6684705 | 6634306 | 6323995 | 6273596 | 18306554.02 | 13976233.75 | 8659020.1125 | 6916810.3323 | 7013611.6537 | 7603657.1799 | 7659946.6619 | 7946013.601 | 8083257.6534 | 7897803.1776 | 8030733.2761
|  | Overheads | 76532785.0026 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 86242141.558 | 70200000.02 | 81374790.9669 | 83687834.4841 | 86648420.582 | 88257785.9769 | 91118870.0324 | 97744429.6781 | 100939963.3565 | 104218961.7479 | 107240268.7488 | 110397232.4667
|  | Contingent | 0 | 0 | 0 | 7860000 | 15720000 | 15720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8464360.3125 | 17351938.6406 | 17785737.1066 | 0 | 0 | 0 | 0 | 0
|  | Alternate Control | 4505000 | 4930000 | 4890000 | 4880000 | 4840000 | 4880000 | 4845000 | 4880000 | 4845000 | 4880000 | 4845000 | 3105000 | 5053250 | 5137556.25 | 5255226.25 | 5342454.3906 | 5521272.0789 | 5618714.6112 | 5800786.4779 | 5903162.0384 | 6094451.2933 | 6202009.6166

## Non System
Non System - Final Submission
$m; Real 18/19 (Jun)
Non System | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Information & Communication Technology | 41.0643 | 30.6372 | 16.8163 | 16.5192 | 14.1439 | 13.0738 | 91.1904
Furniture, fittings, plant and equipment | 3.5844 | 4.7762 | 4.6724 | 2.8882 | 3.1906 | 3.1725 | 18.7
Motor Vehicles | 4.7456 | 6.8734 | 4.1203 | 4.4065 | 5.0878 | 1.612 | 22.1
Buildings | 3.7258 | 7.4 | 9.5 | 7.9 | 7.6 | 5.7 | 38.1
Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 53.1201 | 49.6867 | 35.1089 | 31.714 | 30.0224 | 23.5584 | 170.0904
$m; Nominal
CPI | 1.949% | 1.91% | 2.052% | 2.271% | 2.476% | 2.5%
Index | 1 | 1.0191 | 1.04 | 1.0636 | 1.09 | 1.1172
Non System | FY19 | FY20 | FY21 | FY22 | FY23 | FY24
| Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Information & Communication Technology | 40.67 | 30.9283 | 17.3124 | 17.3742 | 15.2289 | 14.4269
Furniture, fittings, plant and equipment | 3.55 | 4.8216 | 4.8102 | 3.0377 | 3.4354 | 3.5009
Motor Vehicles | 4.7 | 6.9387 | 4.2419 | 4.6345 | 5.4781 | 1.7788
Buildings | 3.69 | 7.4703 | 9.7803 | 8.3088 | 8.183 | 6.2899
Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0
Other non system assets | 0 | 0 | 0 | 0 | 0 | 0
Total | 52.61 | 50.1589 | 36.1447 | 33.3552 | 32.3255 | 25.9966
Check:

## RIN Cat Summary
RIN / Submission Categories
RIN Categories:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 48419634.5023 | 33956216 | 24446757 | 20808877 | 19862891 | 19577920 | 19577920 | 19577920 | 19577920 | 19577920 | 118652661
| Augex | 57522026 | 64808968 | 64514992 | 77992408 | 94029987 | 87791597 | 80244851 | 76142154 | 85054650 | 84625200 | 389137952
| Repex | 150012101.7474 | 113287872 | 124299207 | 122788250 | 128144750 | 131818750 | 130915750 | 144342750 | 163145750 | 184090750 | 620338829
| Other | 17809814 | 13635350 | 8241780 | 6422946 | 6353986 | 6720525 | 6605148 | 6684705 | 6634306 | 6323995 | 41374587
| Overheads | 76532785.0026 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Total System | 350296361.2523 | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 | 321628384.3766 | 331664811.0024 | 359949981.4683 | 380488189.7109 | 1569504029
| Non System | 53120118.5878 | 49686736.0244 | 35108941.55 | 31713950.6162 | 30022401.5922 | 23558369.2171 |  |  |  |  | 170090399
| Total Capex | 403416479.8402 | 354765181.9921 | 336266963.1982 | 340188103.9258 | 358371213.7066 | 350002965.1774 |  |  |  |  | 1739594428
Submission Categories:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 48419634.5023 | 33956216 | 24446757 | 20808877 | 19862891 | 19577920 | 19577920 | 19577920 | 19577920 | 19577920 | 118652661
| Augex | 57522026 | 64808968 | 64514992 | 77992408 | 94029987 | 87791597 | 80244851 | 76142154 | 85054650 | 84625200 | 389137952
| Repex | 146012101.7474 | 109287872 | 120299207 | 118788250 | 124144750 | 127818750 | 126915750 | 140342750 | 159145750 | 180090750 | 600338829
| Reliability | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 20000000
| Other | 17809814 | 13635350 | 8241780 | 6422946 | 6353986 | 6720525 | 6605148 | 6684705 | 6634306 | 6323995 | 41374587
| Overheads | 76532785.0026 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Total System | 350296361.2523 | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 | 321628384.3766 | 331664811.0024 | 359949981.4683 | 380488189.7109 | 1569504029
| Non System | 53120118.5878 | 49686736.0244 | 35108941.55 | 31713950.6162 | 30022401.5922 | 23558369.2171 |  |  |  |  | 170090399
| Total Capex | 403416479.8402 | 354765181.9921 | 336266963.1982 | 340188103.9258 | 358371213.7066 | 350002965.1774 |  |  |  |  | 1739594428
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calculation
Pivot RIN Categories:
| Row Labels | Sum of FY19 (R) | Sum of FY20 (R) | Sum of FY21 (R) | Sum of FY22 (R) | Sum of FY23 (R) | Sum of FY24 (R) | Sum of FY25 (R) | Sum of FY26 (R) | Sum of FY27 (R) | Sum of FY28 (R) | RCP
| Augex | 57522026 | 64808968 | 64514992 | 77992408 | 94029987 | 87791597 | 80244851 | 76142154 | 85054650 | 84625200 | 389137952
| Connections | 48419634.5023 | 33956216 | 24446757 | 20808877 | 19862891 | 19577920 | 19577920 | 19577920 | 19577920 | 19577920 | 118652661
| Other | 22314814 | 18565350 | 13131780 | 11302946 | 11193986 | 11600525 | 11450148 | 11564705 | 11479306 | 11203995 | 65794587
| Overheads | 76532785.0026 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Reliability | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 20000000
| Repex | 146012101.7474 | 109287872 | 120299207 | 118788250 | 124144750 | 127818750 | 137115750 | 150242750 | 169045750 | 190290750 | 600338829
| Grand Total | 354801361.2523 | 310008445.9677 | 306048021.6482 | 313354153.3096 | 333188812.1143 | 331324595.9602 | 336673384.3766 | 346444811.0024 | 374694981.4683 | 395568189.7109 | 1593924029
Adjustments
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP | Comment | RIN Category
[12 empty] | 0 | Contingent |  | PR741 (Western Sydney Airport 132kV supply) removed from exclusion list
TM028 | 132kV oil cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 10200000 | 9900000 | 9900000 | 10200000 | 0 | Remove | Std
MC101 | Meters - Growth | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Alt | Alt
MC104 | Meters - renewal | 25000 | 60000 | 60000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 150000 | Alt | Alt
MC106 | Labour (meter/relay renewal) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Alt | Alt
MC107 | Test equipment | 80000 | 120000 | 80000 | 120000 | 80000 | 120000 | 85000 | 120000 | 85000 | 120000 | 520000 | Alt | Alt
MC110 | Labour meter renewal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Alt | Alt
SL001 | Streetlighting growth | 1400000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 8750000 | Alt | Alt
SL002 | Streetlighting refurbishment | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 15000000 | Alt | Alt

## RAB Cat Summary
RAB Category
RAB Categories:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | 18783302.718 | 23214073.463 | 28890989.8087 | 31616423.5166 | 33216260.6573 | 34788098.8127 | 151725846.2583
| Distribution lines and cables | 133299457.146 | 112455150.7067 | 105231198.7863 | 106299143.4576 | 103343502.3445 | 106915872.2034 | 534244867.4984
| Substations | 147114004.0128 | 117667814.1647 | 123135176.8842 | 132752756.687 | 151099142.696 | 143546904.577 | 668201795.0088
| Transformers | 11398206.3943 | 7326224.9292 | 16723241.1354 | 11093638.5852 | 15532322.0467 | 15797282.6442 | 66472709.3408
| Low Voltage lines and cables | 14122994.2308 | 14910004.9872 | 16899990.8384 | 16816332.6359 | 16629498.8381 | 17164610.4697 | 82420437.7694
| Customer metering and Load control | 717832.0117 | 1647243.2926 | 1233420.6105 | 1159131.0035 | 1065961.4507 | 1003574.8163 | 6109331.1737
| Communication | 18131336.1951 | 14545522.2778 | 7684390.4843 | 2648755.0293 | 2174525.0865 | 1918241.4639 | 28971434.3419
| Land | 5143822.9714 | 11960643.7886 | 0 | 4735089.64 | 3965699.246 | 3982508.2296 | 24643940.9042
| Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1585405.5724 | 1351768.3579 | 1359613.1004 | 1352882.7543 | 1321899.7487 | 1327502.7432 | 6713666.7045
| Total System | 350296361.2523 | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 | 1569504029
| Information & Communication Technology | 41064345.6181 | 30637169 | 16816254 | 16519250 | 14143911 | 13073815 | 91190399
| Furniture, fittings, plant and equipment | 3584421.6116 | 4776208.7856 | 4672381.6498 | 2888212.8897 | 3190649.8926 | 3172546.7823 | 18700000
| Motor Vehicles | 4745572.2745 | 6873358.2388 | 4120305.9002 | 4406487.7265 | 5087840.6997 | 1612007.4348 | 22100000
| Buildings | 3725779.0836 | 7400000 | 9500000 | 7900000 | 7600000 | 5700000 | 38100000
| Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Capex | 403416479.8402 | 354765181.9921 | 336266963.1982 | 340188103.9258 | 358371213.7066 | 350002965.1774 | 1739594428
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live PTRM (Net Capex + Disposals):
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables |  | 23214073.463 | 28890989.8087 | 31616423.5166 | 33216260.6573 | 34788098.8127 | 151725846.2583
| Distribution lines and cables |  | 112455150.7067 | 105231198.7863 | 106299143.4576 | 103343502.3445 | 106915872.2034 | 534244867.4984
| Substations |  | 117667814.1647 | 123135176.8842 | 132752756.687 | 151099142.696 | 143546904.577 | 668201795.0088
| Transformers |  | 7326224.9292 | 16723241.1354 | 11093638.5852 | 15532322.0467 | 15797282.6442 | 66472709.3408
| Low Voltage lines and cables |  | 14910004.9872 | 16899990.8384 | 16816332.6359 | 16629498.8381 | 17164610.4697 | 82420437.7694
| Customer metering and Load control |  | 1647243.2926 | 1233420.6105 | 1159131.0035 | 1065961.4507 | 1003574.8163 | 6109331.1737
| Communication |  | 14545522.2778 | 7684390.4843 | 2648755.0293 | 2174525.0865 | 1918241.4639 | 28971434.3419
| Land |  | 11960643.7886 | 0 | 4735089.64 | 3965699.246 | 3982508.2296 | 24643940.9042
| Easements |  | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) |  | 1351768.3579 | 1359613.1004 | 1352882.7543 | 1321899.7487 | 1327502.7432 | 6713666.7045
| Total System |  | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 | 1569504029
| Information & Communication Technology |  | 30637169 | 16816254 | 16519250 | 14143911 | 13073815 | 91190399
| Furniture, fittings, plant and equipment |  | 4776208.7856 | 4672381.6498 | 2888212.8897 | 3190649.8926 | 3172546.7823 | 18700000
| Motor Vehicles |  | 6873358.2388 | 4120305.9002 | 4406487.7265 | 5087840.6997 | 1612007.4348 | 22100000
| Buildings |  | 7400000 | 9500000 | 7900000 | 7600000 | 5700000 | 38100000
| Land (non-system) |  | 0 | 0 | 0 | 0 | 0 | 0
| Other non system assets |  | 0 | 0 | 0 | 0 | 0 | 0
| Total Capex |  | 354765181.9921 | 336266963.1982 | 340188103.9258 | 358371213.7066 | 350002965.1774 | 1739594428
Variance:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables |  | 0 | 0 | 0 | 0 | 0 | 0
| Distribution lines and cables |  | 0 | 0 | 0 | 0 | 0 | 0
| Substations |  | 0 | 0 | 0 | 0 | 0 | 0
| Transformers |  | 0 | 0 | 0 | 0 | 0 | 0
| Low Voltage lines and cables |  | 0 | 0 | 0 | 0 | 0 | 0
| Customer metering and Load control |  | 0 | 0 | 0 | 0 | 0 | 0
| Communication |  | 0 | 0 | 0 | 0 | 0 | 0
| Land |  | 0 | 0 | 0 | 0 | 0 | 0
| Easements |  | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) |  | 0 | 0 | 0 | 0 | 0 | 0
| Total System |  | 0 | 0 | 0 | 0 | 0 | 0
| Information & Communication Technology |  | 0 | 0 | 0 | 0 | 0 | 0
| Furniture, fittings, plant and equipment |  | 0 | 0 | 0 | 0 | 0 | 0
| Motor Vehicles |  | 0 | 0 | 0 | 0 | 0 | 0
| Buildings |  | 0 | 0 | 0 | 0 | 0 | 0
| Land (non-system) |  | 0 | 0 | 0 | 0 | 0 | 0
| Other non system assets |  | 0 | 0 | 0 | 0 | 0 | 0
| Total Capex |  | 0 | 0 | 0 | 0 | 0 | 0
Calculation
Pivot RAB Categories:
| Row Labels | Sum of FY19 (R) | Sum of FY20 (R) | Sum of FY21 (R) | Sum of FY22 (R) | Sum of FY23 (R) | Sum of FY24 (R) | RCP | Comment
| Communications | 14170000 | 10760366 | 5651895 | 1957860 | 1645000 | 1445000 | 21460121
| Customer metering & load control | 561000 | 1218584 | 907185 | 856786 | 806386 | 755987 | 4544928
| Distribution lines and cables | 104176178.051 | 83191140 | 77397900 | 78572325 | 78178018 | 80539097 | 397878480
| Emergency Spares (Major Plant, Excludes Inventory) | 1239026 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
| Land | 4020000 | 8848146 | 0 | 3500000 | 3000000 | 3000000 | 18348146
| Low Voltage lines and cables | 11037401 | 11030000 | 12430000 | 12430000 | 12580000 | 12930000 | 61400000
| Metering & Load control | 105000 | 180000 | 140000 | 130000 | 90000 | 130000 | 670000 | Alt
| Overheads | 76532785.0026 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 400000000
| Public lighting | 4400000 | 4750000 | 4750000 | 4750000 | 4750000 | 4750000 | 23750000 | Alt
| Substations | 114972521.2988 | 87047321 | 90566336 | 98125840 | 114304540 | 108133038 | 498177075
| Sub-transmission lines and cables | 14679524.81 | 17173115 | 21249420 | 23369670 | 25127670 | 26205670 | 113125545
| Transformers | 8907925.09 | 5419734 | 12300000 | 8200000 | 11750000 | 11900000 | 49569734
| Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Check Zero
| Grand Total | 354801361.2523 | 310008445.9677 | 306048021.6482 | 313354153.3096 | 333188812.1143 | 331324595.9602 | 1593924029
| Check: | 0 | 0 | 0 | 0 | 0 | 0
Adjustments
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP | Comment | RAB Category
0
[8 empty] | 0 | Contingent |  | PR741 (Western Sydney Airport 132kV supply) removed from exclusion list
TM028 | 132kV oil cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Remove | Std
| Total (Remove Alt & Adjustments) | 350296361.2523 | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 | 1569504029
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAB Categories (PTRM Order / Overheads Not Allocated):
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | 14679524.81 | 17173115 | 21249420 | 23369670 | 25127670 | 26205670 | 113125545
| Distribution lines and cables | 104176178.051 | 83191140 | 77397900 | 78572325 | 78178018 | 80539097 | 397878480
| Substations | 114972521.2988 | 87047321 | 90566336 | 98125840 | 114304540 | 108133038 | 498177075
| Transformers | 8907925.09 | 5419734 | 12300000 | 8200000 | 11750000 | 11900000 | 49569734
| Low Voltage lines and cables | 11037401 | 11030000 | 12430000 | 12430000 | 12580000 | 12930000 | 61400000
| Customer metering and Load control | 561000 | 1218584 | 907185 | 856786 | 806386 | 755987 | 4544928
| Communication | 14170000 | 10760366 | 5651895 | 1957860 | 1645000 | 1445000 | 21460121
| Land | 4020000 | 8848146 | 0 | 3500000 | 3000000 | 3000000 | 18348146
| Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1239026 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
| Overheads | 76532785.0026 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 400000000
| Total | 350296361.2523 | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 | 1569504029
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0

## RAB Cat Summary ($Nom)
RAB Category
RAB Categories:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | 18783302.718 | 23214073.463 | 28890989.8087 | 31616423.5166 | 33216260.6573 | 34788098.8127 | 151725846.2583
| Distribution lines and cables | 133299457.146 | 112455150.7067 | 105231198.7863 | 106299143.4576 | 103343502.3445 | 106915872.2034 | 534244867.4984
| Substations | 147114004.0128 | 117667814.1647 | 123135176.8842 | 132752756.687 | 151099142.696 | 143546904.577 | 668201795.0088
| Transformers | 11398206.3943 | 7326224.9292 | 16723241.1354 | 11093638.5852 | 15532322.0467 | 15797282.6442 | 66472709.3408
| Low Voltage lines and cables | 14122994.2308 | 14910004.9872 | 16899990.8384 | 16816332.6359 | 16629498.8381 | 17164610.4697 | 82420437.7694
| Customer metering and Load control | 717832.0117 | 1647243.2926 | 1233420.6105 | 1159131.0035 | 1065961.4507 | 1003574.8163 | 6109331.1737
| Communication | 18131336.1951 | 14545522.2778 | 7684390.4843 | 2648755.0293 | 2174525.0865 | 1918241.4639 | 28971434.3419
| Land | 5143822.9714 | 11960643.7886 | 0 | 4735089.64 | 3965699.246 | 3982508.2296 | 24643940.9042
| Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1585405.5724 | 1351768.3579 | 1359613.1004 | 1352882.7543 | 1321899.7487 | 1327502.7432 | 6713666.7045
| Total System | 350296361.2523 | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 | 1569504029
| Information & Communication Technology | 41064345.6181 | 30637169 | 16816254 | 16519250 | 14143911 | 13073815 | 91190399
| Furniture, fittings, plant and equipment | 3584421.6116 | 4776208.7856 | 4672381.6498 | 2888212.8897 | 3190649.8926 | 3172546.7823 | 18700000
| Motor Vehicles | 4745572.2745 | 6873358.2388 | 4120305.9002 | 4406487.7265 | 5087840.6997 | 1612007.4348 | 22100000
| Buildings | 3725779.0836 | 7400000 | 9500000 | 7900000 | 7600000 | 5700000 | 38100000
| Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Capex | 403416479.8402 | 354765181.9921 | 336266963.1982 | 340188103.9258 | 358371213.7066 | 350002965.1774 | 1739594428
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPI Index
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24
| Dec-Dec sum of 4 quarters (Lagged - Pricing) | 1.949% | 1.91% | 2.052% | 2.271% | 2.476% | 2.5%
| Index (Real 18/19) | 1 | 1.0191 | 1.04 | 1.0636 | 1.09 | 1.1172
RAB Categories:
| $Nominal | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | 18602924.5089 | 23434689.6601 | 29743312.2179 | 33252656.3592 | 35764324.7667 | 38388585.8306 | 160583568.8346
| Distribution lines and cables | 132019367.1792 | 113523874.2868 | 108335658.3244 | 111800402.9396 | 111271121.6507 | 117981415.3924 | 562912472.594
| Substations | 145701251.369 | 118786076.5727 | 126767827.4551 | 139623060.0379 | 162690161.5179 | 158403674.1053 | 706270799.6888
| Transformers | 11288748.1117 | 7395850.1024 | 17216598.8662 | 11667763.4791 | 16723827.3986 | 17432264.5208 | 70436304.3671
| Low Voltage lines and cables | 13987369.4983 | 15051703.0225 | 17398562.9193 | 17686621.9568 | 17905170.0999 | 18941107.5844 | 86983165.5829
| Customer metering and Load control | 710938.5886 | 1662897.9579 | 1269808.1498 | 1219119.0732 | 1147732.7898 | 1107442.4671 | 6407000.4378
| Communication | 17957218.8952 | 14683756.432 | 7911090.1666 | 2785835.0494 | 2341335.8358 | 2116774.9775 | 29838792.4614
| Land | 5094426.2497 | 12074312.4109 | 0 | 4980142.9484 | 4269913.3784 | 4394688.5347 | 25719057.2723
| Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1570180.7409 | 1364614.9612 | 1399723.4851 | 1422897.9853 | 1423304.4595 | 1464896.1782 | 7075437.0692
| Total System | 346932425.1416 | 307977775.4066 | 310042581.5844 | 324438499.8288 | 353536891.8973 | 360230849.591 | 1656226598.3081
| Information & Communication Technology | 40670000 | 30928330.9853 | 17312355.7334 | 17374164.5152 | 15228909.4698 | 14426924.333 | 95270685.0368
| Furniture, fittings, plant and equipment | 3550000 | 4821599.7429 | 4810223.088 | 3037685.4821 | 3435408.9448 | 3500897.9683 | 19605815.2262
| Motor Vehicles | 4700000 | 6938679.569 | 4241860.3736 | 4634535.0239 | 5478135.8149 | 1778846.4413 | 23072057.2227
| Buildings | 3690000 | 7470326.2985 | 9780262.5643 | 8308845.7206 | 8183006.24 | 6289936.6939 | 40032377.5173
| Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Capex | 399542425.1416 | 358136712.0023 | 346187283.3436 | 357793730.5708 | 385862352.3668 | 386227455.0275 | 1834207533.311

## RAB Cat Lookup
Project ID | Classification | Project / Program Description | RAB Category
AR | Std | Asset Relocation | Distribution lines and cables
AU004 | Std | PM102 ZS SCADA refurbishment | Substations
AU013 | Std | SCADA master station development software | Substations
AU016 | Std | PM121 (MD1000) MD3 to DNP3 conversion | Substations
CC002 | Std | Communications development SCADA | Communications
CC007 | Std | SCADA radio repeaters | Communications
CC020 | Std | Microwave refurbishment and extension | Communications
DS002 | Std | Pole substation refurbishment | Transformers
DS003 | Std | Distribution Substation Refurbishment | Substations
DS004 | Std | Distribution mains refurbishment | Distribution lines and cables
DS005 | Std | Pole replacement capital | Distribution lines and cables
DS006 | Std | LV CONSAC cable replacement | Distribution lines and cables
DS007 | Std | Service wire replacement program | Low Voltage lines and cables
DS008 | Std | Traffic black spot remediation | Distribution lines and cables
DS009 | Std | Reliability focused distribution mains renewal | Distribution lines and cables
DS011 | Std | HV distribution steel mains replacement | Distribution lines and cables
DS012 | Std | HV expulsion drop-out fuse replacement program | Distribution lines and cables
DS013 | Std | Lapstone Distribution Network Renewal | Distribution lines and cables
DS014 | Std | LV cable network renewal | Low Voltage lines and cables
DS301 | Std | Ground substation refurbishment program | Substations
DS302 | Std | Distribution transformer replacement programs | Substations
DS305 | Std | Compact LV switchgear replacement | Substations
DS307 | Std | Holec MD4 epoxy switchgear replacement | Substations
DS308 | Std | HV oil and RGB12 switchgear replacement | Substations
DS310 | Std | Upgrading of direct connected substations | Substations
DS312 | Std | Miscellaneous substation renewal expenditure | Substations
DS313 | Std | Padmount substation fire risk mitigation | Substations
DS314 | Std | Basement Substation Refurbishment | Substations
DS315 | Std | Compact LV switchgear replacement | Substations
DS316 | Std | HV oil switchgear replacement program | Substations
DS404 | Std | Cast iron UGOH replacement program | Distribution lines and cables
DS405 | Std | Air-break switch replacement | Distribution lines and cables
DS409 | Std | Miscellaneous mains renewal expenditure | Distribution lines and cables
DS410 | Std | Capital works for Compliance to NSW Maritime Waterways - Crossing Codes | Distribution lines and cables
DS411 | Std | Capital works for compliance to NSW Maritime Waterways - Signage Replacement and Drawings update | Distribution lines and cables
DS413 | Std | Low Mains Remediation | Distribution lines and cables
DS414 | Std | Copper distribution mains replacement | Distribution lines and cables
DS415 | Std | LV Mains Refurbishment | Distribution lines and cables
DS416 | Std | Asbestos Service Fuse Replacement | Customer metering & load control
DU | Std | Duct installation RMS road works | Distribution lines and cables
EF001 | Std | Distribution Management System | Communications
EF002 | Std | Technology Pilots | Distribution lines and cables
EF003 | Std | BESS Pilot - West Dapto | Substations
EH | Std | DIST ENVIRON. ENHANCEMENT PROGRAM Total | Distribution lines and cables
HVW | Std | HV Development Works | Distribution lines and cables
IC | Std | Industrial & Commercial | Distribution lines and cables
LV001 | Std | Overloaded Distribution sub uprates | Low Voltage lines and cables
LV002 | Std | Quality of supply reactive projects | Low Voltage lines and cables
LV003 | Std | Quality of supply planned projects | Low Voltage lines and cables
LV004 | Std | Low Voltage System Augmentations | Low Voltage lines and cables
LV005 | Std | Dsub Monitoring & LV Feeder Monitoring for Solar PV | Low Voltage lines and cables
MC101 | Alt | Meters - Growth | Metering & Load control
MC102 | Std | Relays - Growth | Customer metering & load control
MC104 | Alt | Meters - Renewal | Metering & Load control
MC105 | Std | Relays - Renewal | Customer metering & load control
MC106 | Alt | Labour (meter/relay renewal) | Metering & load control
MC107 | Alt | Test Equipment | Metering & Load control
MC109 | Std | Demand Management Technology | Distribution lines and cables
MC112 | Std | Neutral integrity monitoring | Customer metering & load control
NU | Std | Non Urban Extension | Distribution lines and cables
OFP | Std | Overloaded Feeders (Compliance) | Distribution lines and cables
PQ001 | Std | PQ Monitoring | Substations
PQ002 | Std | PQ Monitoring – Statistical assessment of the LV network | Substations
PQ003 | Std | PQ Surveying | Substations
PR044 | Std | West Liverpool ZS (Hoxton Park ZS Rebuild) | Substations
PR052 | Std | Penrith TS transformer and Busbar Augment | Substations
PR054 | Std | Quakers Hill ZS augment (132kV bar + 1st 132/11kV tfr) | Sub-transmission lines and cables
PR059 | Std | ELTS 132kV Bus bar & Substation works | Substations
PR060 | Std | WLTS-ELTS first 132kV Cable Links | Sub-transmission lines and cables
PR061 | Std | Russell Vale ZS Augment | Substations
PR070 | Std | Caddens ZS Establishment + feeders | Substations
PR090 | Std | Doonside 132kV/11kV ZS rebuild | Substations
PR091 | Std | West Parramatta CBD 132kV/11kV ZS establishment | Substations
PR102 | Std | Kemps Creek / Luddenham Capacity uprate | Sub-transmission lines and cables
PR110 | Std | Edmondson Park ZS Establishment | Substations
PR113 | Std | Augment feeder 308 Nepean to Douglas Park | Sub-transmission lines and cables
PR123 | Std | Connection Works Associated with Tomerong / Bamarang BSP | Sub-transmission lines and cables
PR126 | Std | Chipping Norton 33/11kV ZS establishment | Substations
PR128 | Std | Convert Camden ZS to 66kV | Substations
PR144 | Std | Sherwood ZS Augment | Substations
PR148 | Std | Dapto ZS 3rd transformer & 33kV Bus Section CB's | Transformers
PR149 | Std | Gerringong ZS Augment | Substations
PR157 | Std | Richmond ZS rebuild | Substations
PR170 | Std | Holsworthy 33/11kV ZS establishment | Substations
PR172 | Std | PARKLEA ZS 3RD TRANSFORMER | Transformers
PR176 | Std | Cheriton Avenue 132/11kV ZS Establishment | Substations
PR184 | Std | Box Hill ZS Establishment (interim) | Substations
PR186 | Std | Glenorie ZS establishment | Substations
PR190 | Std | Eschol Park ZS Establishment | Distribution lines and cables
PR200 | Std | Cordeaux / Figtree 33/11kV ZS Establishment | Substations
PR204 | Std | Canley Vale Subtransmission Network Upgrade | Sub-transmission lines and cables
PR206 | Std | Cawdor 66/11kV ZS Establishment | Substations
PR208 | Std | Abbotsbury 132/11kV ZS Establishment | Substations
PR248 | Std | Penrith Lakes ZS Land Purchase | Land
PR255 | Std | Line works associated with Oran Park | Sub-transmission lines and cables
PR257 | Std | Menangle Park 66/11kV ZS Site Purchase | Land
PR258 | Std | Menangle Park 66/11kV ZS establishment (mobile) | Substations
PR261 | Std | Huntingwood ZS | Substations
PR278 | Std | Kemps Creek new BSP associated works | Sub-transmission lines and cables
PR280 | Std | Wilton Park 66/11kV ZS establishment & 66kV line works | Substations
PR288 | Std | Holroyd 330/132kV BSP associated works | Sub-transmission lines and cables
PR292 | Std | South Marsden Park (Industrial) 132/11kV ZS establishment | Substations
PR303 | Std | Mittagong ZS transformer augment | Transformers
PR308 | Std | Granville ZS & Camellia TS Rebuild | Substations
PR326 | Std | Casula 33/11kV ZS establishment with link to LTS or WLTS | Substations
PR329 | Std | Box Hill ZSSite Purchase | Land
PR339 | Std | North Eastern Creek ZS establishment | Substations
PR342 | Std | Jordan Springs establishment | Substations
PR353 | Std | SHOALHAVEN FEEDER 7510/7511 AUGMENT | Sub-transmission lines and cables
PR384 | Std | Glossodia ZS transformer augments | Substations
PR406 | Std | Tomerong ZS Establishment | Substations
PR408 | Std | Oran Park (permanent) ZS Establishment | Substations
PR413 | Std | Windsor Transformer | Transformers
PR423 | Std | Maryland ZS | Substations
PR424 | Std | Austral ZS Site Purchase | Land
PR425 | Std | Austral ZS Establishment (interim initially) | Substations
PR426 | Std | Leppington North ZS Site Purchase (Strategic) | Land
PR427 | Std | Leppington North ZS Establishment (interim initially) | Substations
PR429 | Std | Leppington South ZS Establishment (interim initially) | Substations
PR430 | Std | North Rossmore ZS Site Purchase | Land
PR432 | Std | Rossmore ZS Site Purchase | Land
PR435 | Std | Catherine Fields North ZS Establishment (Interim) | Substations
PR436 | Std | Catherine Fields ZS Site Purchase | Land
PR437 | Std | Catherine Fields ZS Establishment (interim) | Substations
PR438 | Std | North Bringelly ZS Site Purchase | Land
PR440 | Std | Feeder 443 and 458/1 Augmentation and Cattai Rebuild | Sub-transmission lines and cables
PR444 | Std | Culburra Beach Development (33kV fdr and single transformer ZS) | Substations
PR479 | Std | Far South Coast 132kV Voltage Constraints | Transformers
PR487 | Std | Connection Works Associated with Macarthur BSP | Sub-transmission lines and cables
PR499 | Std | Southpipe (Oakdale Estate) ZS 132/11kV establishment | Substations
PR517 | Std | Installation of OPGW on Feeders 98W and 98F | Sub-transmission lines and cables
PR521 | Std | Culburra ZS fdr deplication & provision for rural ZS's | Sub-transmission lines and cables
PR559 | Std | Mamre ZS Transformer Augment and 11kV busbar extension | Substations
PR596 | Std | Marsden Park (Residential) 132/11kV ZS establishment - Stage 1 | Substations
PR599 | Std | Penrith CBD ZS Site Purchase | Land
PR602 | Std | Riverstone West Site Purchase | Land
PR603 | Std | Eschol Park ZS Site Purchase | Land
PR615 | Std | Cordeaux Feeder - LFI installation | Sub-transmission lines and cables
PR620 | Std | West Dapto ZS Establishment (interim initially) | Substations
PR643 | Std | Fibre Works At Carlingford TS For Ausgrid | Substations
PR656 | Std | Leppington South ZS Establishment (permanent) | Substations
PR657 | Std | Calderwood ZS Establishment (interim initially) | Substations
PR659 | Std | Avondale (South West Dapto) 132/11kV Zone Substation Establishment Site Purchase | Land
PR673 | Std | Liverpool ZS 11kV Switchboard Extension & Distribution Works | Substations
PR674 | Std | South Marsden Park (Stage 1) | Substations
PR677 | Std | Penrith Panthers 132/11kV ZS Establishment | Substations
PR698 | Std | Marsden Park (Residential) 132/11kV ZS - Stage 2 | Substations
PR700 | Std | Riverstone East | Substations
PR701 | Std | Dapto 33kV Feeder Constraints | Sub-transmission lines and cables
PR702 | Std | Penrith ZS 11kV transformer cable constraints | Transformers
PR703 | Std | Riverstone East Site Purchase | Land
PR704 | Std | Oakdale (Southpipe) Site Purchase | Land
PR707 | Std | 132kV Ducts Bringelly Rd (ARP2273) | Sub-transmission lines and cables
PR709 | Std | Feeder 230 Undergrounding | Sub-transmission lines and cables
PR710 | Std | FDR 868 Rebuild & Rearrangement South32 | Sub-transmission lines and cables
PR715 | Std | Nepean TS Constraints | Substations
PR716 | Std | Box Hill ZS - 132kV Ducts Old Pitt Town | Sub-transmission lines and cables
PR717 | Std | Acquire improved site for West Dapto ZS | Land
PR722 | Std | Camellia TS - Connection of Ausgird | Substations
PR727 | Std | Luddenham ZS Additional Land Acquisition | Land
PR730 | Std | Feeder 7018 constraints | Sub-transmission lines and cables
PS008 | Std | Substation protection relay refurbishment | Substations
PS009 | Std | Installation of SEF relays | Substations
PS010 | Std | Protection refurbishment (interfacing feeders) | Substations
PS011 | Std | Protection refurbishment (miscellaneous) | Substations
PS012 | Std | Distribution feeder protection modernisation | Substations
RI | Std | Reliability HV Development | Distribution lines and cables
RIAR | Std | Line Fault Indicators | Distribution lines and cables
RIDFA | Std | DFA - Radio, SCADA, Software | Substations
RIHV | Std | Reliability HV Development | Distribution lines and cables
RILB | Std | Automated Load Break Switches | Distribution lines and cables
RIRR | Std | Automated Reclosers | Distribution lines and cables
RITR | Std | Reliability Transmission Development | Distribution lines and cables
SL001 | Alt | Streetlighting Growth | Public lighting
SL002 | Alt | Streetlighting Refurbishment | Public lighting
SLWSROC | Alt | WSROC SL Replacement Program | Public lighting
SP001 | Std | Spares Purchase | Emergency spares
TM008 | Std | 132KV TOWER REFURB/SAFETY UPGRADE | Sub-transmission lines and cables
TM012 | Std | Sub-transmission pole replacement | Sub-transmission lines and cables
TM014 | Std | Renewal of 33kV and 66kV gas and oil filled cables | Sub-transmission lines and cables
TM016 | Std | Cast iron UGOH replacement within zone substations | Sub-transmission lines and cables
TM019 | Std | Access track reconstruction | Sub-transmission lines and cables
TM021 | Std | Capital Works for compliance to NSW Maritime Waterways | Sub-transmission lines and cables
TM023 | Std | Renewal of 132kV cable 233 | Sub-transmission lines and cables
TM026 | Std | Installation of vibration dampers (sub-transmission) | Sub-transmission lines and cables
TM027 | Std | Steel Tower Asbestos Removal | Sub-transmission lines and cables
TM028 | Std | 132kV oil cable 228 replacement | Sub-transmission lines and cables
TM131 | Std | Underground Pilots Replacement | Sub-transmission lines and cables
TM132 | Std | Sub Transmission Pilot cable renewal program | Sub-transmission lines and cables
TM133 | Std | Hardex pilot cable renewal | Sub-transmission lines and cables
TM134 | Std | Wollongong - Port Kembla pilot cable replacement | Sub-transmission lines and cables
TM135 | Std | Optical fibre protection and communication upgrades in the Blue Mountains | Sub-transmission lines and cables
TM137 | Std | Optical fibre protection and communication upgrades in the Macarthur area | Sub-transmission lines and cables
TM171 | Std | Replacement of corroded earthwires | Sub-transmission lines and cables
TM172 | Std | Earthwire replacement due to fault rating | Sub-transmission lines and cables
TM174 | Std | Hardex Earthwire Replacement | Sub-transmission lines and cables
TM302 | Std | Oil filled cable auxiliary equipment refurbishment | Sub-transmission lines and cables
TM303 | Std | Guilford and Camellia 132kV feeder, oil testing and flushing | Sub-transmission lines and cables
TM401 | Std | South Coast 33kV overhead line refurbishment | Sub-transmission lines and cables
TM404 | Std | Avon/Nepean Dam feeder refurbishment | Sub-transmission lines and cables
TM408 | Std | Ringwood Feeder 7906 Refurbishment | Sub-transmission lines and cables
TM410 | Std | Hazelbook ZS to Springwood ZS Feeder 808 refurbishment | Sub-transmission lines and cables
TM419 | Std | Future feeder refurbishment works | Sub-transmission lines and cables
TM801 | Std | Steel tower painting program | Sub-transmission lines and cables
TM803 | Std | Steel tower below ground rectification work | Sub-transmission lines and cables
TM805 | Std | EARTHING REFURBISHMENT ON BLUE MOUNTAINS | Sub-transmission lines and cables
TM809 | Std | Steel tower earthing refurbishment works | Sub-transmission lines and cables
TS004 | Std | 132kV circuit breaker replacement | Substations
TS005 | Std | 33kV circuit breaker replacement | Substations
TS007 | Std | 11kV circuit breaker replacement | Substations
TS008 | Std | Battery replacement | Substations
TS009 | Std | Auxiliary switchgear replacement | Substations
TS015 | Std | Replacement of surge arrester in zone and sub-transmission substations | Substations
TS016 | Std | VT and CT replacement | Substations
TS020 | Std | Portable earthing set cabinets | Substations
TS024 | Std | Building and amenities refurbishment | Substations
TS025 | Std | Asbestos and other hazardous material reporting, management and removal | Substations
TS026 | Std | Noise attenuation in ZS and TS | Substations
TS027 | Std | Substation switchyard lighting improvement | Substations
TS028 | Std | Control cable trench and cover refurbishment | Substations
TS029 | Std | Substation control room temperature reduction initiatives | Substations
TS031 | Std | Substation safety fence upgrade program | Substations
TS032 | Std | Substation security systems | Substations
TS033 | Std | Substation fire hydrant installations | Substations
TS034 | Std | Substation deluge showers and fire blankets | Substations
TS035 | Std | Substation oil containment program - bund walls | Substations
TS036 | Std | Substation earthing | Substations
TS048 | Std | Substation oil containment program - separators | Substations
TS049 | Std | Tunnelboard refurbishment | Substations
TS050 | Std | POW switching for capacitors | Substations
TS055 | Std | 66kV circuit breaker replacement | Substations
TS057 | Std | Substation insulation co-ordination | Substations
TS067 | Std | Rosehill ZS Renewal | Substations
TS072 | Std | Holroyd ZS Renewal | Substations
TS086 | Std | Busbar support and isolator replacement | Substations
TS092 | Std | Jasper Rd 11kV CB Renewal | Substations
TS099 | Std | Substation power outlet installation | Substations
TS100 | Std | Substation internal fence replacement | Substations
TS102 | Std | Rydalmere Zone Substation renewal | Substations
TS111 | Std | Blackheath ZS 11kV Switchyard renewal | Substations
TS116 | Std | Roof refurbuishment for control and switch rooms | Substations
TS119 | Std | Bomaderry ZS Redevelopment (fmr PR403) | Substations
TS120 | Std | Canley Vale ZS Redevelopment | Substations
TS121 | Std | Port Kembla ZS | Substations
TS122 | Std | Leabons Lane Zone Substation renewal | Substations
TS123 | Std | St Marys Zone Substation renewal | Substations
TS124 | Std | Substation control building fire alarm systems | Substations
TS125 | Std | Guildford Transmission Substation renewal | Substations
TS126 | Std | Comalco HVC Substation Renewal | Substations
TS127 | Std | Castle Hill Zone Substation renewal | Substations
TS128 | Std | Capacitor bank replacement | Substations
TS130 | Std | Northmead Zone Substation Renewal | Substations
TS131 | Std | Bulli Zone Substation Renewal | Substations
TS133 | Std | Corrimal ZS Redevelopment | Substations
TS134 | Std | South Granville Zone Substation renewal | Substations
TS135 | Std | Ringwood ZS Redevelopment | Substations
TS136 | Std | Kandos ZS Redevelopment | Substations
TS138 | Std | Baulkham Hills Switchgear Rearrangement | Substations
TS139 | Std | Oakdale ZS Swgr Rearrangement | Substations
TS143 | Std | Westmead Zone Substation renewal and augmentation | Substations
TS144 | Std | Substation fire stopping measures | Substations
TS146 | Std | Marayong Zone Substation renewal | Substations
TS149 | Std | South Windsor ZS Refurbishment | Substations
TS155 | Std | Sussex Inlet Zone Substation - stage 2 renewal | Substations
TS156 | Std | Lawson TS - RailCorp Connections Works | Substations
TS163 | Std | Unanderra Zone Substation renewal | Substations
TS165 | Std | Greystanes Zone Substation renewal | Substations
TS167 | Std | Carlingford Transmission Substation control building replacement | Substations
TS168 | Std | Carramar Zone Substation switchgear replacement | Substations
TS173 | Std | 11kV Switchboard Truck Replacement Program | Substations
TS174 | Std | West Wollongong Zone Substation 11kV renewal | Substations
TS175 | Std | Defective CT Replacement Program | Substations
TS177 | Std | Substation Battery Redundancy Program | Substations
TS178 | Std | Jerrara SS Rearrangement | Substations
TS179 | Std | 33kV wall bushing replacement | Substations
TS180 | Std | Transformer fire wall installation | Substations
TS181 | Std | 11kV capacitor bank refurbishment | Substations
TS182 | Std | Substation civil capital works scoping | Substations
TS199 | Std | Substation renewal program to be identified | Substations
TS600 | Std | Power transformer replacement | Transformers
TS602 | Std | Prospect ZS 33kV No3 Transformer | Transformers
TS604 | Std | Liverpool TS 132kV No 3 - Transformer Replacement | Transformers
TS605 | Std | West Liverpool 132 kV No 3 Transformer | Substations
TS606 | Std | Jasper Road 33kV No 3 - Transformer Replacement | Substations
TS607 | Std | West Liverpool 132 kV No 1 - Demolition | Substations
TS615 | Std | Gerringong ZS No.2 TX Replacement | Transformers
UR | Std | Underground Residential | Distribution lines and cables
AG | Std | Automation - operational/capacity risk | Substations
DS318 | Std | Distribution substation earthing refurbishment | Substations
DS417 | Std | Distribution access track reconstruction | Distribution lines and cables
DS418 | Std | Pole top structure/hardware refurbishment | Distribution lines and cables
MC110 | Alt | Labour Meter Renewal | Metering & load control
PQ004 | Std | Power quality monitoring replacement | Substations
PR249 | Std | Establish Penrith Lakes 33/11kV Zone Substation | Substations
PR713 | Std | Box Hill 132/22kV ZS establishment | Substations
PR723 | Std | Supply to Luddenham Science Park | Substations
PR724 | Std | Establish Mt Gilead ZS | Substations
PR728 | Std | Western Sydney Employment Lands ZS | Substations
PR732 | Std | Feeder 214/215 contraints | Sub-transmission lines and cables
PR735 | Std | Termeil Area Distribution Works | Distribution lines and cables
PR739 | Std | South Gilead (South Campbelltown) | Substations
PR740 | Std | AFIC upgrade Minto, Prospect, Kingswood | Substations
PR741 | Std | Western Sydney Airport 132kV supply | Sub-transmission lines and cables
PR742 | Std | North Bomaderry ZS establishment | Substations
PR744 | Std | Termeil ZS establishment | Substations
PR748 | Std | Establish permanent Catherine Park ZS | Substations
PR750 | Std | Feeder 512 augmentation | Sub-transmission lines and cables
PR751 | Std | Parklea ZS to Bella Vista ZS load transfer | Substations
PR754 | Std | Augment Westmead Zone Substation | Substations
PS002 | Std | Replacement of ASEA RI O/C Relays | Substations
PS012 | Std | Distribution feeder safety improvement | Substations
PS013 | Std | Feeder differential relay replacement | Substations
PS014 | Std | Under frequency load shedding | Substations
RC | Std | Reliability compliance | Distribution lines and cables
SP | Std | Essential spares | Emergency Spares (Major Plant, Excludes Inventory)
TM015 | Std | Subtransmission tower replacement | Sub-transmission lines and cables
TM029 | Std | Installation of Aerial Marker Balls | Sub-transmission lines and cables
TM030 | Std | Feeder 7028 replacement | Sub-transmission lines and cables
TM138 | Std | 132kV optical fibre ring completion | Sub-transmission lines and cables
TS017 | Std | Power transformer refurbishment | Transformers
TS018 | Std | PCB Dechlorination | Transformers
TS184 | Std | Blaxland Zone Substation reinstatement | Substations
TS185 | Std | Penrith TS civil development | Substations
TS187 | Std | Mobile substation No 2 refurbishment | Substations
TS188 | Std | Bossley Park ZS civil refurbishment | Substations
TS616 | Std | Camellia TS transformer replacement and 33kV busbar rearrangement | Transformers
TS617 | Std | Prospect ZS transformer replacement | Transformers
TS618 | Std | Albion Park ZS transformer replacement | Transformers
TS619 | Std | Dundas 66/11kV Tx2 Replacement | Transformers
TS700 | Std | 11kV zone substation switchboard replacement | Substations
TS701 | Std | North Rocks ZS 11kV switchboard replacement | Substations
TS702 | Std | Kellyville ZS 11kV switchboard replacement | Substations
TS703 | Std | Horsley Park ZS 11kV switchboard replacement | Substations
TS704 | Std | Port Central ZS 11kV switchboard replacement | Substations
DS421 | Std | Pole top structure/hardware refurbishment (HV) | Distribution lines and cables
PR761 | Std | Glenfield Zone Substation site acquisition | Substations
PR765 | Std | Minto 66kV Reconfiguration | Substations
PR766 | Std | Baulkham Hills 132kV bus section CB | Substations
PR767 | Std | Mt Terry 132kV bus section CB | Substations
PR769 | Std | Nepean TS 132kV bus section CB | Substations
TM031 | Std | Steel tower asbestos removal | Sub-transmission lines and cables
TM031 | Std | Steel tower asbestos removal | Sub-transmission lines and cables
TM033 | Std | Pole top structure/hardware refurbishment (TR) | Sub-transmission lines and cables
TS601 | Std | Cranebrook ZS 33kV No 3 - transformer replacement | Transformers
TS620 | Std | Minto 66/11kV No 1 transformer replacement | Transformers
TS183 | Std | Carlingford TS/Dundas ZS Redevelopment | Substations
SW | Std | Network Switching | Overheads
OH | Std | Capitalised Overheads | Overheads

## Config (hidden)
Divisions
Program - Short Term Need |  | 15
Program - Medium Term Need |  | 10
Program - Long Term Need |  | 5
Major Project - Committed Project |  | 15
Major Project - Prior to Approval |  | 10
Major Project - Future/Planning Stage |  | 5
Land Purchases
PR248
PR257
PR291
PR329
PR424
PR426
PR430
PR432
PR434
PR436
PR438
PR599
PR602
PR603
PR652
PR659
PR703
PR704
PR717
PR727
PR761
Escalators
Base Year | FY19
CPI | 2.5%
FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29
0.90595 | 0.9286 | 0.95181 | 0.97561 | 1 | 1.025 | 1.0506 | 1.0769 | 1.1038 | 1.1314 | 1.1597 | 1.1887 | 1.2184 | 1.2489 | 1.2801

## Version Control (hidden)
Version | Change History
PIP 20.1 DRAFT v1 | Initial draft, noted green CASH ranking means default 4950, blue means carried over from previous PIP

## Doc - Charts (hidden)
| FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | 5Yr | 10Yr
Augex | 57478433.0865 | 66429192.2 | 67781063.47 | 75524932.6839 | 86439573.1153 | 81542396.7619 | 93059425.5502 | 90509093.7134 | 103630832.0067 | 105685278.6044 | 377717158.2311 | 404347391.5813
Repex | 123680707.799 | 112020068.8 | 126389354.3544 | 127921952.7852 | 137032575.3534 | 144615183.5114 | 159012232.8083 | 178591416.5169 | 205965831.6117 | 237647071.1986 | 647979134.8044 | 694971298.8127
Customer Connection | 40340000.008 | 34805121.4 | 25684374.0731 | 22408884.5581 | 21924915.1309 | 22150619.4793 | 22704384.9663 | 23271994.5905 | 23853794.4552 | 24450139.3166 | 126973914.6414 | 114873178.2077
Reliability | 4045216.63 | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 21550946.9141 | 22089720.5869
Other | 18306554.02 | 13976233.75 | 8659020.1125 | 6916810.3323 | 7013611.6537 | 7603657.1799 | 7659946.6619 | 7946013.601 | 8083257.6534 | 7897803.1776 | 44169333.0284 | 37853045.9403
Overheads | 70200000.02 | 81374790.9669 | 83687834.4841 | 86648420.582 | 88257785.9769 | 91118870.0324 | 97744429.6781 | 100939963.3565 | 104218961.7479 | 107240268.7488
Total | 314050911.5635 | 312705407.1169 | 316404146.4941 | 323728563.4414 | 345083712.7926 | 351556359.8165 | 384819193.3377 | 406013224.793 | 450626289.0649 | 487916012.9259
Major Projects
Automation Growth Program
Distribution Works Program
Low Voltage Development
Customer Connections
Reliability Compliance
Power Quality
SARP
Efficiency
Metering
Growth | FY19: 1025842176
Reliability | FY19: 51643338
Sustainability | FY19: 1447436579
Efficiency | FY19: 29295121
Miscellaneous | FY19: 26672878
| FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28
Actual | 26672878 FY09: 381; 26672878 FY10: 369; 26672878 FY11: 420; 26672878 FY12: 575.8589; 26672878 FY13: 545.2625; 26672878 FY14: 485; 26672878 FY15: 335; 26672878 FY16: 241; 26672878 FY17: 191
Budgeted | 26672878 FY18: #REF!
Projected | 26672878 FY19: 317.1559; 26672878 FY20: 317.7587; 26672878 FY21: 321.5417; 26672878 FY22: 337.4482; 26672878 FY23: 367.7781; 26672878 FY24: 374.8634; 26672878 FY25: 390.4379; 26672878 FY26: 411.814; 26672878 FY27: 456.5295; 26672878 FY28: 494.0105
| FY15 | FY16 | FY17 | FY18 | FY19
Initial Proposal | 26672878 FY09: 383577421.9343; 26672878 FY10: 352775925.0513; 26672878 FY11: 315527945.7458; 26672878 FY12: 322770777.9207; 26672878 FY13: 327119010.4636
Revised Proposal | 26672878 FY09: 381350412; 26672878 FY10: 337012327; 26672878 FY11: 289532929; 26672878 FY12: 284470000; 26672878 FY13: 277078966
Final Program | 26672878 FY09: #REF!; 26672878 FY10: #REF!; 26672878 FY11: #REF!; 26672878 FY12: #REF!; 26672878 FY13: 317155911.5635
| FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | Total | Total Reg
Augex | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Customer Connections | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Other System | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Repex | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Augex
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28
AG | Automation growth | 0 | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891
HV | Distribution works program | 8536573.1465 | 6970865.1 | 7462655.5644 | 7158488.2801 | 6926477.7679 | 6728594.3887 | 6958160.5093 | 7132114.522 | 7310417.3851 | 7493177.8197
LV | Low voltage development capital | 120000 | 82000 | 84050 | 86151.25 | 88305.0312 | 90512.657 | 92775.4735 | 95094.8603 | 97472.2318 | 99909.0376
PR | Major projects | 42200551.34 | 49999477.45 | 56767295.4056 | 72652469.0912 | 93134146.4177 | 88775379.7204 | 82413439.971 | 82925278.605 | 89765407.033 | 97717532.8561
PRL | Major projects - land | 6621308.6 | 9069349.65 | 3151875 | 3769117.1875 | 3311438.6719 | 3394224.6387 | 3247141.571 | 0 | 6092014.4875 | 0
Customer Connection
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28
AR | Asset relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DU | Duct installation RMS road works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IC | Industrial & commercial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NU | Non-urban extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UR | Underground residential | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28
EF | Efficiency | 14073634.24 | 9312500.15 | 4325312.8094 | 2253781.3134 | 2207625.7812 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399
LV | Low voltage development capital | 2730394.93 | 1793750 | 1838593.75 | 1884558.5937 | 1931672.5586 | 1979964.3726 | 2029463.4819 | 2080200.0689 | 2132205.0706 | 2185510.1974
MC | Metering capital | 815847.56 | 2601023.6 | 1888167.4906 | 1870328.561 | 1817302.0897 | 1850969.128 | 1798206.698 | 1824857.2935 | 1766428.3368 | 1791357.8043
PQ | Power quality capital | 791677.29 | 453460 | 754033.5625 | 1048137.6453 | 1156354.3842 | 1656990.3213 | 1623060.5204 | 1818113.8792 | 1863566.7262 | 1585561.4221
SL | Streetlighting capital | 3000000 | 4868750 | 4990468.75 | 5115230.4687 | 5243111.2305 | 5374189.0112 | 5508543.7365 | 5646257.3299 | 5787413.7632 | 5932099.1073
Reliability
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28
RC | Reliability compliance | 3685231.26 | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798
Repex
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28
AU | Automation capital | 1692166 | 3372250 | 3456556.25 | 4619860.7812 | 4735357.3008 | 3722333.0204 | 3815391.3459 | 3910776.1296 | 5226948.4303 | 5357622.1411
CC | Communications refurbishment | 1626275.49 | 2229375 | 2138021.875 | 2008401.0156 | 1815772.2051 | 1634884.8676 | 2470146.9808 | 3114356.6746 | 2790142.6353 | 3197089.2031
DS | Distribution refurbishment capital | 58236579.809 | 58817657 | 65386781.55 | 71822229.495 | 75203412.4498 | 81093208.4675 | 83671393.0528 | 92039438.6585 | 107249403.3241 | 126590470.4263
TM | Transmission mains capital (refurb) | 12910887.32 | 10987861.625 | 12785759.5437 | 12930947.2511 | 10384307.4167 | 11863573.1557 | 27629312.9901 | 36317523.5655 | 42145372.5548 | 49006219.6789
TS | Transmission substation capital (rebuild) | 38978789.98 | 26644800.175 | 35183810.1356 | 29508418.4609 | 37685827.8053 | 38913088.3701 | 33563267.0632 | 35150032.0788 | 40293193.0221 | 45028378.8129
PS | Protection systems capital | 8812382.42 | 8943125 | 6387800 | 5955205.1562 | 6104085.2852 | 6256687.4173 | 6703027.9573 | 6870603.6562 | 7042368.7476 | 7218427.9663
SP | Essential spares | 1423626.78 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699

## Doc - Prog (hidden)
Program/Project |  | #REF! | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | Total
Augex
PR | Major Projects
PR081 | Collimore Park ZS establishment | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5111443.8356 | 15717689.7946 | #REF!
PR110 | Edmondson Park ZS establishment | #REF! | 1810000.35 | 5369.7444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR113 | Augment feeder 308 Nepean to Douglas Park | #REF! | 1346081.25 | 4139199.8437 | 3771270.9687 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR170 | Holsworthy 33/11kV ZS establishment | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5120216.3365 | 10496443.4898 | #REF!
PR190 | Eschol Park ZS establishment | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 5264926.9401 | 10793100.2273 | 11062927.733 | #REF!
PR249 | Establish Penrith Lakes 33/11kV Zone Substation | #REF! | 0 | 0 | 0 | 0 | 0 | 1821879.5197 | 7469706.0308 | 0 | 0 | #REF!
PR258 | Menangle Park 66/11kV ZS establishment | #REF! | 4599367.7 | 8999.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR270 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
PR278 | Kemps Creek new BSP associated works | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557118.903 | 1596046.8756 | #REF!
PR292 | South Marsden Park (industrial) 132/11kV ZS establishment | #REF! | 1245387.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR423 | Maryland ZS establishment | #REF! | 0 | 4335635.2 | 8888052.16 | 9110253.464 | 0 | 0 | 0 | 0 | 0 | #REF!
PR425 | Austral ZS establishment (interim initially) | #REF! | 0 | 3736022.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR427 | Leppington North ZS establishment | #REF! | 1799807.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR433 | Rossmore ZS establishment | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR435 | Catherine Fields North ZS establishment (interim) | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5228410.5138 | 10718241.5533 | #REF!
PR437 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
PR439 | North Bringelly ZS establishment | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 5253991.0312 | 10770681.614 | 11039948.6543 | #REF!
PR444 | Culburra Beach development (33kV fdr and single transformer ZS) | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 4555638.1509 | 2334764.5524 | 0 | #REF!
PR499 | Southpipe (Oakdale Estate) ZS 132/11kV establishment | #REF! | 6505880 | 13337054 | 13670480.35 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR620 | West Dapto ZS establishment | #REF! | 0 | 0 | 4399744.3375 | 9019475.8919 | 5285034.0441 | 4058926.9637 | 0 | 0 | 0 | #REF!
PR653 | Avondale (South West Dapto) 132/11kV ZS establishment | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 5943428.7683 | 6092014.4875 | 6244314.8497 | #REF!
PR656 | Leppington South ZS establishment (permanent) | #REF! | 13905811.125 | 3705231.8331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR657 | Calderwood ZS establishment (interim initially) | #REF! | 1513412.5 | 1551247.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR673 | Liverpool ZS 11kV switchboard extension & distribution works | #REF! | 300000.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR677 | South Penrith Zone Substation | #REF! | 0 | 0 | 0 | 6430813.9008 | 13183168.4966 | 13512747.709 | 0 | 0 | 0 | #REF!
PR698 | Marsden Park (residential) 132/11kV ZS - stage 2 | #REF! | 3140600 | 3219115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR700 | Riverstone east ZS establishment | #REF! | 0 | 0 | 4399744.3375 | 9019475.8919 | 5285034.0441 | 4058926.9637 | 0 | 0 | 0 | #REF!
PR702 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
PR710 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
PR713 | Box Hill 132/22kV ZS establishment | #REF! | 7348840 | 15065122 | 15441750.05 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR722 | Camellia TS connection works for Ausgrid | #REF! | 281847.325 | 110304.0681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR723 | Supply to Luddenham Science Park | #REF! | 0 | 0 | 0 | 9511555.6785 | 19498689.141 | 19986156.3695 | 0 | 0 | 0 | #REF!
PR724 | Establish Mt Gilead ZS | #REF! | 0 | 0 | 4355591.8219 | 8928963.2348 | 5192258.5706 | 4058926.9637 | 0 | 0 | 0 | #REF!
PR728 | Western Sydney Employment Lands ZS | #REF! | 0 | 0 | 4864314.9531 | 9971845.6539 | 10221141.7953 | 0 | 0 | 0 | 0 | #REF!
PR729 | Cheriton Avenue 3rd transformer | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR732 | Feeder 214/215 contraints | #REF! | 5268500 | 5400212.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR733 | Bringelly ZS augmentation | #REF! | 0 | 0 | 0 | 0 | 0 | 4944932.7353 | 10137112.1073 | 10390539.91 | 0 | #REF!
PR739 | South Gilead (South Campbelltown) | #REF! | 0 | 0 | 0 | 0 | 0 | 4690495.9993 | 9615516.7986 | 9855904.7185 | 0 | #REF!
PR740 | AFIC upgrade Minto, Prospect, Kingswood | #REF! | 318942.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR741 | Western Sydney Airport 132kV supply | #REF! | 0 | 0 | 8464360.3125 | 17351938.6406 | 17785737.1066 | 0 | 0 | 0 | 0 | #REF!
PR742 | North Bomaderry ZS establishment | #REF! | 0 | 0 | 3966403.55 | 8131127.2775 | 4374476.7143 | 4058926.9637 | 0 | 0 | 0 | #REF!
PR744 | Termeil ZS establishment | #REF! | 0 | 0 | 0 | 0 | 0 | 4616449.5746 | 4731860.8139 | 0 | 0 | #REF!
PR745 | Austral Permanent ZS establishment | #REF! | 0 | 0 | 0 | 0 | 0 | 12198235.2195 | 12503191.1 | 0 | 0 | #REF!
PR746 | Sydney University - Western Sydney Employment Lands ZS establishment | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14932745.9119 | 15306064.5597 | #REF!
PR748 | Establish permanent Catherine Park ZS | #REF! | 0 | 0 | 0 | 0 | 2149675.6045 | 4406834.9892 | 4517005.8639 | 0 | 0 | #REF!
PR749 | Nepean ZS augmentation | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 4279268.7132 | 0 | 0 | #REF!
PR750 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
PR751 | Parklea ZS to Bella Vista ZS load transfer | #REF! | 0 | 1050625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR752 | Kemps Creek 132kV conversion | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR754 | Augment Westmead Zone Substation | #REF! | 0 | 0 | 0 | 5658696.7838 | 5800164.2034 | 0 | 0 | 0 | 0 | #REF!
PR755 | Narellan ZS busbar augmentation | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 8653632.2867 | 0 | 0 | #REF!
PR756 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
| Major Projects Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
PRL | Major Projects – Land
PR248 | Penrith Lakes ZS site acquisition | #REF! | 0 | 0 | 0 | 0 | 0 | 347908.0255 | 0 | 0 | 0 | #REF!
PR599 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
PR430 | North Rossmore ZS site purchase | #REF! | 0 | 0 | 0 | 3311438.6719 | 0 | 0 | 0 | 0 | 0 | #REF!
PR432 | Rossmore ZS site purchase | #REF! | 0 | 0 | 0 | 0 | 3394224.6387 | 0 | 0 | 0 | 0 | #REF!
PR438 | North Bringelly ZS site purchase | #REF! | 0 | 0 | 3769117.1875 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR602 | Riverstone West site purchase | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6092014.4875 | 0 | #REF!
PR603 | Eschol Park ZS site purchase | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR659 | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | #REF! | 0 | 0 | 0 | 0 | 0 | 2899233.5455 | 0 | 0 | 0 | #REF!
PR703 | Riverstone East site purchase | #REF! | 6150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR704 | Oakdale (Southpipe) site purchase | #REF! | 200000.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR717 | Acquire improved site for West Dapto ZS | #REF! | 2050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PR727 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
| Major Projects – Land Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AG | Automation growth | #REF! | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | #REF!
HVW | HV development works | #REF! | 6970865.1 | 7462655.5644 | 7158488.2801 | 6926477.7679 | 6728594.3887 | 6958160.5093 | 7132114.522 | 7310417.3851 | 7493177.8197 | #REF!
LV | Low Voltage Development
LV001 | Overloaded distribution sub uprates | #REF! | 82000 | 84050 | 86151.25 | 88305.0312 | 90512.657 | 92775.4735 | 95094.8603 | 97472.2318 | 99909.0376 | #REF!
| Low Voltage Development Total | #REF! | 82000 | 84050 | 86151.25 | 88305.0312 | 90512.657 | 92775.4735 | 95094.8603 | 97472.2318 | 99909.0376 | #REF!
| Augex Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
Repex
TS | Transmission Substation Refurbishment
TS004 | 132kV circuit breaker replacement | #REF! | 0 | 0 | 0 | 399580.2664 | 409569.7731 | 419809.0174 | 430304.2428 | 441061.8489 | 452088.3951 | #REF!
TS005 | 33kV circuit breaker replacement | #REF! | 0 | 0 | 0 | 849935.9258 | 871184.3239 | 1373077.0072 | 1407403.9323 | 1442589.0307 | 1478653.7564 | #REF!
TS007 | 11kV circuit breaker replacement | #REF! | 0 | 367718.75 | 376911.7187 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS008 | Battery replacement | #REF! | 533000 | 546325 | 559983.125 | 573982.7031 | 588332.2707 | 1206081.1549 | 1236233.1838 | 1267139.0134 | 1298817.4887 | #REF!
TS009 | Auxiliary switchgear replacement | #REF! | 0 | 0 | 0 | 311275.2352 | 0 | 327033.5439 | 0 | 0 | 0 | #REF!
TS015 | Replacement of surge arrester in zone and sub-transmission substations | #REF! | 37925 | 123973.75 | 127073.0937 | 130249.9211 | 56570.4106 | 57984.6709 | 59434.2877 | 60920.1449 | 62443.1485 | #REF!
TS016 | VT and CT replacement | #REF! | 0 | 0 | 0 | 770461.3977 | 789722.9326 | 809466.0059 | 829702.6561 | 850445.2225 | 871706.353 | #REF!
TS017 | Transformer Renewals Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS024 | Building and amenities refurbishment | #REF! | 1537500 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | #REF!
TS025 | Asbestos and other hazardous material reporting, management and removal | #REF! | 91225 | 472781.25 | 484600.7812 | 571775.0773 | 588332.2707 | 625074.7524 | 534908.5892 | 548281.3039 | 646911.0184 | #REF!
TS026 | Noise attenuation in ZS and TS | #REF! | 0 | 0 | 1076890.625 | 0 | 1131408.2129 | 0 | 1188685.7537 | 0 | 1248862.9699 | #REF!
TS027 | Substation switchyard lighting improvement | #REF! | 112750 | 115568.75 | 118457.9687 | 121419.418 | 124454.9034 | 127566.276 | 130755.4329 | 134024.3187 | 137374.9267 | #REF!
TS031 | Substation safety fence upgrade program | #REF! | 102500 | 105062.5 | 107689.0625 | 110381.2891 | 113140.8213 | 115969.3418 | 118868.5754 | 121840.2898 | 124886.297 | #REF!
TS032 | Substation security systems | #REF! | 153750 | 157593.75 | 161533.5937 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS033 | Substation fire hydrant installations | #REF! | 205000 | 210125 | 215378.125 | 220762.5781 | 226281.6426 | 231938.6836 | 237737.1507 | 243680.5795 | 249772.594 | #REF!
TS034 | Substation deluge showers and fire blankets | #REF! | 164000 | 168100 | 172302.5 | 176610.0625 | 181025.3141 | 185550.9469 | 190189.7206 | 194944.4636 | 199818.0752 | #REF!
TS035 | Substation oil containment program - bund walls | #REF! | 71750 | 73543.75 | 75382.3437 | 77266.9023 | 79198.5749 | 81178.5393 | 83208.0028 | 85288.2028 | 87420.4079 | #REF!
TS036 | Substation earthing | #REF! | 348500 | 428655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS049 | Circuit Breakers Renewals Total | #REF! | 0 | 0 | 0 | 49671.5801 | 50913.3696 | 0 | 0 | 0 | 56198.8336 | #REF!
TS050 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS055 | 66kV circuit breaker replacement | #REF! | 264450 | 271061.25 | 0 | 0 | 0 | 299200.9019 | 306680.9244 | 314347.9476 | 322206.6462 | #REF!
TS057 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS086 | Busbar support and isolator replacement | #REF! | 0 | 99284.0625 | 101766.1641 | 104310.3182 | 106918.0761 | 109591.028 | 112330.8037 | 115139.0738 | 118017.5507 | #REF!
TS116 | Roof refurbishment for control and switch rooms | #REF! | 1537500 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1739540.1273 | 1783028.6305 | 1827604.3463 | 1873294.4549 | #REF!
TS122 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS127 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS128 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS144 | Substation fire stopping measures | #REF! | 67650 | 69341.25 | 71074.7812 | 72851.6508 | 74672.9421 | 76539.7656 | 78453.2597 | 80414.5912 | 82424.956 | #REF!
TS146 | Marayong Zone Substation renewal | #REF! | 8409999.95 | 1921674.0231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS155 | Sussex Inlet Zone Substation - stage 2 renewal | #REF! | 1720519.9 | 39235.5906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS163 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS165 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS167 | Carlingford Transmission Substation control building replacement | #REF! | 0 | 4727812.5 | 4846007.8125 | 4967158.0078 | 0 | 0 | 0 | 0 | 0 | #REF!
TS173 | 11kV switchboard truck replacement program | #REF! | 3739200 | 3832680 | 3928497 | 3231964.1437 | 3312763.2473 | 3395582.3285 | 3480471.8867 | 3567483.6839 | 0 | #REF!
TS174 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS177 | Substation battery duplication | #REF! | 0 | 964473.75 | 823821.3281 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS179 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS180 | Transformer fire wall installation | #REF! | 0 | 630375 | 646134.375 | 662287.7344 | 678844.9277 | 695816.0509 | 713211.4522 | 731041.7385 | 749317.782 | #REF!
TS181 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS184 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS185 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS187 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS188 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS199 | Future sub-transmission substation renewal programs | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5482813.0388 | 11614425.6205 | #REF!
TS600 | Power transformer replacement | #REF! | 1742500 | 12187250 | 8076679.6875 | 12141941.7969 | 12558631.1631 | 14728106.4113 | 15096309.0716 | 15473716.7984 | 15860559.7183 | #REF!
TS615 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TS616 | Camellia TS transformer replacement and 33kV busbar rearrangement | #REF! | 340958.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS617 | Prospect ZS transformer replacement | #REF! | 29999.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS618 | Albion Park ZS transformer replacement | #REF! | 1616692.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS700 | 11kV zone substation switchboard replacement | #REF! | 0 | 4202500 | 4307562.5 | 8830503.125 | 13576898.5547 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | #REF!
TS701 | North Rocks ZS 11kV switchboard replacement | #REF! | 796984.65 | 38000.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS702 | Kellyville ZS 11kV switchboard replacement | #REF! | 977000.275 | 278800.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS703 | Horsley Park ZS 11kV switchboard replacement | #REF! | 434999.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TS704 | Port Central ZS 11kV switchboard replacement | #REF! | 500868.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
| Transmission Substation Refurbishment Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TM | Transmission Mains Refurbishment
TM012 | Sub-transmission pole replacement | #REF! | 3813000 | 3908325 | 4006033.125 | 4106183.9531 | 5566528.4074 | 6424701.5369 | 6585319.0753 | 6749952.0522 | 6918700.8535 | #REF!
TM014 | Renewal of 33kV and 66kV gas and oil filled cables | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 2674542.9458 | 2741406.5194 | 2809941.6824 | #REF!
TM015 | Subtransmission tower replacement | #REF! | 984000 | 1008600 | 1033815 | 1059660.375 | 1086151.8844 | 2226611.363 | 2282276.647 | 2339333.5632 | 2397816.9023 | #REF!
TM027 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TM028 | 132kV oil cable replacement | #REF! | 0 | 0 | 0 | 0 | 0 | 11828872.8658 | 11767988.9613 | 12062188.6853 | 12738402.2935 | #REF!
TM030 | Feeder 7028 replacement | #REF! | 1640000 | 1681000 | 1723025 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TM132 | Sub-transmission pilot cable renewal program | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 1325384.6153 | 1358519.2307 | 1392482.2115 | #REF!
TM134 | Wollongong - Port Kembla pilot cable replacement | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 1979161.7799 | 2028640.8244 | 2079356.845 | #REF!
TM135 | Optical fibre protection and communication upgrades in the Blue Mountains | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 1103100.3794 | 1130677.8889 | 1158944.8361 | #REF!
TM137 | Optical fibre protection and communication upgrades in the Macarthur area | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 1079326.6643 | 1106309.8309 | 1133967.5767 | #REF!
TM138 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TM171 | Replacement of corroded earthwires | #REF! | 0 | 0 | 0 | 0 | 156134.3334 | 1040244.9961 | 1066251.121 | 1092907.3991 | 1120230.084 | #REF!
TM172 | Earthwire replacement due to fault rating | #REF! | 0 | 1050625 | 1076890.625 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
TM174 | Hardex earthwire replacement | #REF! | 0 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | #REF!
TM302 | Oil filled cable auxiliary equipment refurbishment | #REF! | 0 | 75645 | 0 | 0 | 0 | 0 | 85585.3743 | 0 | 0 | #REF!
TM303 | Guilford and Camellia 132kV cables oil testing and flushing | #REF! | 0 | 94556.25 | 0 | 0 | 0 | 0 | 106981.7178 | 0 | 0 | #REF!
TM401 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TM419 | Future sub-transmission feeder refurbishment works | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5482813.0388 | 11614425.6205 | #REF!
TM801 | Steel tower painting program | #REF! | 0 | 0 | 0 | 0 | 0 | 927754.7346 | 950948.6029 | 974722.318 | 999090.376 | #REF!
TM803 | Steel tower below ground rectification work | #REF! | 0 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1739540.1273 | 1783028.6305 | 1462083.477 | 936647.2275 | #REF!
TM805 | Earthing refurbishment of lines 940/941 | #REF! | 287000 | 294175 | 301529.375 | 309067.6094 | 22628.1643 | 23193.8684 | 23773.7151 | 24368.058 | 24977.2594 | #REF!
TM809 | Subtransmission line earthing refurbishment | #REF! | 0 | 630375 | 646134.375 | 662287.7344 | 678844.9277 | 695816.0509 | 713211.4522 | 731041.7385 | 749317.782 | #REF!
| Transmission Mains Capital Refurbishment Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
DS | Distribution Refurbishment
DS002 | Pole substation refurbishment | #REF! | 717500 | 735437.5 | 753823.4375 | 827859.668 | 905126.5703 | 927754.7346 | 950948.6029 | 974722.318 | 999090.376 | #REF!
DS005 | Distribution pole replacement | #REF! | 11613250 | 12712562.5 | 13859582.3437 | 15056007.8281 | 16303592.3478 | 17604146.0885 | 19874825.8013 | 21309866.6774 | 21842613.3444 | #REF!
DS006 | LV CONSAC cable replacement | #REF! | 6918750 | 7879687.5 | 10499683.5937 | 10762175.6836 | 12728342.395 | 13046550.9549 | 14264229.044 | 14620834.7701 | 15923002.8668 | #REF!
DS007 | Service wire replacement program | #REF! | 9430000 | 9770812.5 | 10015082.8125 | 10431031.8164 | 11087800.4863 | 11364995.4985 | 12243463.2628 | 12549549.8444 | 13487720.0754 | #REF!
DS008 | Traffic black spot remediation | #REF! | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | #REF!
DS011 | HV distribution steel mains replacement | #REF! | 3788400 | 4530295 | 5638599.3125 | 5949551.4805 | 6795237.7266 | 6965118.6698 | 7139246.6365 | 7317727.8024 | 7500670.9975 | #REF!
DS014 | LV cable network renewal | #REF! | 0 | 1365812.5 | 1399957.8125 | 1434956.7578 | 1470830.6768 | 1507601.4437 | 1545291.4798 | 1583923.7668 | 1623521.8609 | #REF!
DS301 | Ground substation refurbishment program | #REF! | 522750 | 535818.75 | 915357.0312 | 938240.957 | 1154036.3771 | 1478609.1082 | 1515574.3359 | 1553463.6943 | 1592300.2867 | #REF!
DS302 | Distribution transformer replacement program | #REF! | 1281250 | 1313281.25 | 1346113.2812 | 1724707.6416 | 1767825.3326 | 1812020.966 | 1857321.4901 | 2056054.8895 | 2107456.2618 | #REF!
DS305 | Compact LV switchgear replacement | #REF! | 512500 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | #REF!
DS307 | Holec MD4 epoxy switchgear replacement | #REF! | 6098750 | 5883500 | 6407499.2187 | 6567686.6992 | 6731878.8667 | 6900175.8384 | 9152880.3032 | 9381702.3108 | 11801755.066 | #REF!
DS308 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
DS312 | Miscellaneous substation renewal expenditure | #REF! | 1537500 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1739540.1273 | 2377371.5073 | 2436805.795 | 3122157.4249 | #REF!
DS315 | Low voltage switchgear replacement | #REF! | 725700 | 743842.5 | 762438.5625 | 781499.5266 | 801037.0147 | 821062.9401 | 841589.5136 | 862629.2514 | 884194.9827 | #REF!
DS317 | Future distribution substation renewals | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5482813.0388 | 11614425.6205 | #REF!
DS318 | Distribution substation earthing refurbishment | #REF! | 276750 | 283668.75 | 290760.4687 | 298029.4805 | 305480.2175 | 313117.2229 | 320945.1535 | 328968.7823 | 337193.0019 | #REF!
DS405 | Air break switch replacement program | #REF! | 3731000 | 3824275 | 3919881.875 | 4017878.9219 | 4118325.8949 | 4221284.0423 | 4326816.1434 | 4434986.5469 | 4545861.2106 | #REF!
DS409 | Miscellaneous mains renewal expenditure | #REF! | 1122375 | 1150434.375 | 1179195.2344 | 1208675.1152 | 1238891.9931 | 1391632.1019 | 1426422.9044 | 1462083.477 | 1498635.5639 | #REF!
DS413 | Low mains remediation | #REF! | 1665625 | 1707265.625 | 1749947.2656 | 1793695.9473 | 1838538.3459 | 1130701.0828 | 1158968.6098 | 1187942.8251 | 1217641.3957 | #REF!
DS414 | Copper distribution mains replacement | #REF! | 0 | 1008600 | 1033815 | 1059660.375 | 1086151.8844 | 1113305.6815 | 1426422.9044 | 2046916.8678 | 2397816.9023 | #REF!
DS415 | LV mains replacement | #REF! | 1127500 | 1155687.5 | 1184579.6875 | 1214194.1797 | 1244549.0342 | 1269864.2929 | 1301610.9003 | 1334151.1728 | 1367504.9521 | #REF!
DS416 | Asbestos service fuse replacement | #REF! | 267525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
DS417 | Distribution access track reconstruction | #REF! | 451000 | 1479280 | 1326729.25 | 1359897.4812 | 1493458.841 | 1530795.312 | 1569065.1948 | 1876340.4622 | 1923248.9737 | #REF!
DS418 | Pole top structure/hardware refurbishment (LV) | #REF! | 2674891.25 | 2741763.5312 | 2810307.6195 | 2880565.31 | 2952579.4428 | 3026393.9288 | 3102053.7771 | 3179605.1215 | 3259095.2495 | #REF!
DS420 | Future distribution feeder refurbishment works | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5482813.0388 | 11614425.6205 | #REF!
| Distribution Refurbishment Capital Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AU | Automation
AU004 | Substation SCADA RTU replacement | #REF! | 2234500 | 2290362.5 | 2347621.5625 | 2406312.1016 | 2466469.9041 | 2528131.6517 | 2591334.943 | 2656118.3166 | 2722521.2745 | #REF!
AU013 | SCADA master station development software | #REF! | 1137750 | 1166193.75 | 2272239.2187 | 2329045.1992 | 1255863.1163 | 1287259.6942 | 1319441.1866 | 2570830.1137 | 2635100.8666 | #REF!
| Automation Total | #REF! | 3372250 | 3456556.25 | 4619860.7812 | 4735357.3008 | 3722333.0204 | 3815391.3459 | 3910776.1296 | 5226948.4303 | 5357622.1411 | #REF!
CC | Communications
CC002 | Communications development SCADA | #REF! | 640625 | 551578.125 | 565367.5781 | 579501.7676 | 593989.3118 | 521862.0382 | 534908.5892 | 548281.3039 | 561988.3365 | #REF!
CC007 | SCADA radio repeaters | #REF! | 902000 | 882525 | 915357.0312 | 761630.8945 | 724101.2562 | 858173.1295 | 736985.1673 | 743225.7675 | 736829.1523 | #REF!
CC020 | Microwave refurbishment and extension | #REF! | 686750 | 703918.75 | 527676.4062 | 474639.543 | 316794.2996 | 1090111.8131 | 1842462.9182 | 1498635.5639 | 1898271.7143 | #REF!
| Communications Total | #REF! | 2229375 | 2138021.875 | 2008401.0156 | 1815772.2051 | 1634884.8676 | 2470146.9808 | 3114356.6746 | 2790142.6353 | 3197089.2031 | #REF!
PS | Protection Refurbishment
PS008 | Substation protection relay refurbishment | #REF! | 4484375 | 4727812.5 | 4846007.8125 | 4967158.0078 | 5091336.958 | 5508543.7365 | 5646257.3299 | 5787413.7632 | 5932099.1073 | #REF!
PS011 | Protection refurbishment (miscellaneous) | #REF! | 717500 | 735437.5 | 753823.4375 | 772669.0234 | 791985.749 | 811785.3927 | 832080.0276 | 852882.0283 | 874204.079 | #REF!
PS012 | Distribution feeder safety improvement | #REF! | 3177500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
PS013 | Feeder differential relay replacement | #REF! | 0 | 346706.25 | 355373.9062 | 364258.2539 | 373364.7103 | 382698.828 | 392266.2987 | 402072.9562 | 412124.7801 | #REF!
PS014 | Under frequency load shedding | #REF! | 563750 | 577843.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
| Protection Refurbishment Total | #REF! | 8943125 | 6387800 | 5955205.1562 | 6104085.2852 | 6256687.4173 | 6703027.9573 | 6870603.6562 | 7042368.7476 | 7218427.9663 | #REF!
SP | Essential spares | #REF! | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | #REF!
| Total Repex | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
Customer Connection
AR | Asset relocation | #REF! | 1664241.25 | 1643020.9569 | 1661087.6357 | 1694353.8909 | 1734526.8575 | 1777890.029 | 1822337.2797 | 1867895.7117 | 1914593.1045 | #REF!
DU | Duct installation RMS road works | #REF! | 2206549.275 | 2318255.5431 | 2435617.5261 | 2558919.7528 | 2688465.7724 | 2755677.4167 | 2824569.3521 | 2895183.5859 | 2967563.1755 | #REF!
IC | Industrial & commercial | #REF! | 7688980.1 | 5602510.3438 | 4936560.3145 | 4769957.4197 | 4803453.5325 | 4923539.8708 | 5046628.3675 | 5172794.0767 | 5302113.9287 | #REF!
NU | Non urban extension | #REF! | 1044823.5 | 780742.5512 | 712692.677 | 697271.9801 | 700813.481 | 718333.818 | 736292.1635 | 754699.4676 | 773566.9543 | #REF!
UR | Underground residential | #REF! | 22200527.275 | 15339844.6781 | 12662926.4048 | 12204412.0874 | 12223359.836 | 12528943.8319 | 12842167.4276 | 13163221.6133 | 13492302.1537 | #REF!
| Customer Connection Total | #REF! | 34805121.4 | 25684374.0731 | 22408884.5581 | 21924915.1309 | 22150619.4793 | 22704384.9663 | 23271994.5905 | 23853794.4552 | 24450139.3166 | #REF!
Reliability
RC | Reliability compliance | #REF! | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | #REF!
| Reliability Total | #REF! | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | #REF!
Other System
LV | Low Voltage Development
LV002 | Quality of supply reactive projects | #REF! | 512500 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | #REF!
LV003 | LV planning reactive projects | #REF! | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | #REF!
LV005 | Dsub monitoring & LV feeder monitoring for solar PV | #REF! | 256250 | 262656.25 | 269222.6562 | 275953.2227 | 282852.0532 | 289923.3546 | 297171.4384 | 304600.7244 | 312215.7425 | #REF!
| Low Voltage Development Total | #REF! | 1793750 | 1838593.75 | 1884558.5937 | 1931672.5586 | 1979964.3726 | 2029463.4819 | 2080200.0689 | 2132205.0706 | 2185510.1974 | #REF!
PQ | Power Quality
PQ001 | Permanent power quality monitoring | #REF! | 102500 | 105062.5 | 107689.0625 | 110381.2891 | 113140.8213 | 115969.3418 | 118868.5754 | 121840.2898 | 124886.297 | #REF!
PQ004 | Power quality monitoring replacement | #REF! | 350960 | 648971.0625 | 940448.5828 | 1045973.0952 | 1543849.5 | 1507091.1786 | 1699245.3038 | 1741726.4364 | 1460675.1251 | #REF!
| Power Quality Total | #REF! | 453460 | 754033.5625 | 1048137.6453 | 1156354.3842 | 1656990.3213 | 1623060.5204 | 1818113.8792 | 1863566.7262 | 1585561.4221 | #REF!
EF | Efficiency
EF001 | Distribution management system | #REF! | 8800000.15 | 3800000.3094 | 100000.0634 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
EF002 | Technology pilots | #REF! | 512500 | 525312.5 | 2153781.25 | 2207625.7812 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | #REF!
EF003 | #N/A | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
| Efficiency Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
MC | Metering
MC104 | Meters - renewal | #REF! | 61500 | 63037.5 | 10768.9062 | 11038.1289 | 11314.0821 | 11596.9342 | 11886.8575 | 12184.029 | 12488.6297 | #REF!
MC105 | Relays - renewal | #REF! | 981523.6 | 953111.2406 | 922664.811 | 890099.2616 | 855329.9006 | 818265.7596 | 778813.8303 | 736877.8884 | 692358.3908 | #REF!
MC107 | Test equipment | #REF! | 123000 | 84050 | 129226.875 | 88305.0312 | 135768.9855 | 98573.9405 | 142642.2904 | 103564.2463 | 149863.5564 | #REF!
MC109 | Demand management technology | #REF! | 1435000 | 787968.75 | 807667.9687 | 827859.668 | 848556.1597 | 869770.0637 | 891514.3153 | 913802.1731 | 936647.2275 | #REF!
| Metering Total | #REF! | 2601023.6 | 1888167.4906 | 1870328.561 | 1817302.0897 | 1850969.128 | 1798206.698 | 1824857.2935 | 1766428.3368 | 1791357.8043 | #REF!
SL | Streetlighting
SL001 | Streetlighting growth | #REF! | 1793750 | 1838593.75 | 1884558.5937 | 1931672.5586 | 1979964.3726 | 2029463.4819 | 2080200.0689 | 2132205.0706 | 2185510.1974 | #REF!
SL002 | Streetlighting refurbishment | #REF! | 3075000 | 3151875 | 3230671.875 | 3311438.6719 | 3394224.6387 | 3479080.2546 | 3566057.261 | 3655208.6925 | 3746588.9098 | #REF!
| Streetlighting | #REF! | 4868750 | 4990468.75 | 5115230.4687 | 5243111.2305 | 5374189.0112 | 5508543.7365 | 5646257.3299 | 5787413.7632 | 5932099.1073 | #REF!
| Other System Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
Overheads
SW | Network Switching Total | #REF! | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | #REF!
OH | Capitalised Overheads Total | #REF! | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | #REF!
| Overheads Total | #REF! | 81374790.9669 | 83687834.4841 | 86648420.582 | 88257785.9769 | 91118870.0324 | 97744429.6781 | 100939963.3565 | 104218961.7479 | 107240268.7488 | #REF!
| Total Capex | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
|  | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
Program/Project |  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | Total
Augex
PR | Major Projects | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
PRL | Major Projects – Land | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AG | Automation growth | #REF! | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | #REF!
HVW | HV development works | #REF! | 6970865.1 | 7462655.5644 | 7158488.2801 | 6926477.7679 | 6728594.3887 | 6958160.5093 | 7132114.522 | 7310417.3851 | 7493177.8197 | #REF!
LV | Low Voltage Development | #REF! | 82000 | 84050 | 86151.25 | 88305.0312 | 90512.657 | 92775.4735 | 95094.8603 | 97472.2318 | 99909.0376 | #REF!
| Augex Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
Repex
TS | Transmission Substation Refurbishment | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
TM | Transmission Mains Refurbishment | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
DS | Distribution Refurbishment | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AU | Automation | #REF! | 3372250 | 3456556.25 | 4619860.7812 | 4735357.3008 | 3722333.0204 | 3815391.3459 | 3910776.1296 | 5226948.4303 | 5357622.1411 | #REF!
CC | Communications | #REF! | 2229375 | 2138021.875 | 2008401.0156 | 1815772.2051 | 1634884.8676 | 2470146.9808 | 3114356.6746 | 2790142.6353 | 3197089.2031 | #REF!
PS | Protection Refurbishment | #REF! | 8943125 | 6387800 | 5955205.1562 | 6104085.2852 | 6256687.4173 | 6703027.9573 | 6870603.6562 | 7042368.7476 | 7218427.9663 | #REF!
SP | Essential spares | #REF! | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | #REF!
| Repex Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
Customer Connection
AR | Asset relocation | #REF! | 1664241.25 | 1643020.9569 | 1661087.6357 | 1694353.8909 | 1734526.8575 | 1777890.029 | 1822337.2797 | 1867895.7117 | 1914593.1045 | #REF!
DU | Duct installation RMS road works | #REF! | 2206549.275 | 2318255.5431 | 2435617.5261 | 2558919.7528 | 2688465.7724 | 2755677.4167 | 2824569.3521 | 2895183.5859 | 2967563.1755 | #REF!
IC | Industrial & commercial | #REF! | 7688980.1 | 5602510.3438 | 4936560.3145 | 4769957.4197 | 4803453.5325 | 4923539.8708 | 5046628.3675 | 5172794.0767 | 5302113.9287 | #REF!
NU | Non urban extension | #REF! | 1044823.5 | 780742.5512 | 712692.677 | 697271.9801 | 700813.481 | 718333.818 | 736292.1635 | 754699.4676 | 773566.9543 | #REF!
UR | Underground residential | #REF! | 22200527.275 | 15339844.6781 | 12662926.4048 | 12204412.0874 | 12223359.836 | 12528943.8319 | 12842167.4276 | 13163221.6133 | 13492302.1537 | #REF!
| Customer Connection Total | #REF! | 34805121.4 | 25684374.0731 | 22408884.5581 | 21924915.1309 | 22150619.4793 | 22704384.9663 | 23271994.5905 | 23853794.4552 | 24450139.3166 | #REF!
Reliability
RC | Reliability compliance | #REF! | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | #REF!
| Reliability Total | #REF! | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | #REF!
Other System
LV | Low Voltage Development | #REF! | 1793750 | 1838593.75 | 1884558.5937 | 1931672.5586 | 1979964.3726 | 2029463.4819 | 2080200.0689 | 2132205.0706 | 2185510.1974 | #REF!
PQ | Power Quality | #REF! | 453460 | 754033.5625 | 1048137.6453 | 1156354.3842 | 1656990.3213 | 1623060.5204 | 1818113.8792 | 1863566.7262 | 1585561.4221 | #REF!
EF | Efficiency | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
MC | Metering | #REF! | 2601023.6 | 1888167.4906 | 1870328.561 | 1817302.0897 | 1850969.128 | 1798206.698 | 1824857.2935 | 1766428.3368 | 1791357.8043 | #REF!
SL | Streetlighting | #REF! | 4868750 | 4990468.75 | 5115230.4687 | 5243111.2305 | 5374189.0112 | 5508543.7365 | 5646257.3299 | 5787413.7632 | 5932099.1073 | #REF!
| Other System Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
Overheads
SW | Network Switching Total | #REF! | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | #REF!
OH | Capitalised Overheads Total | #REF! | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | #REF!
| Overheads Total | #REF! | 81374790.9669 | 83687834.4841 | 86648420.582 | 88257785.9769 | 91118870.0324 | 97744429.6781 | 100939963.3565 | 104218961.7479 | 107240268.7488 | #REF!
| Capex Total | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
|  | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!

## Doc - CASH (hidden)
Program/Project Description |  | Division | RIN Category | Rank | Weighted Rank | Percent | Plant
AG | Automation - operational/capacity risk | Program - Short Term Need | Augex | 190 | 2850 | 66.11% | AGs
AR | Asset relocation | Program - Short Term Need | Customer Connection | 140 | 2100 | 78.28% | ARs
AU004 | Substation SCADA RTU replacement | Program - Short Term Need | Repex | 220 | 3300 | 54.32% | AU004s
AU013 | SCADA master station development software | Program - Short Term Need | Repex | 310 | 4650 | 21% | AU013s
CC002 | Communications development SCADA | Program - Short Term Need | Repex | 150 | 2250 | 70.85% | CC002s
CC007 | SCADA radio repeaters | Program - Short Term Need | Repex | 270 | 4050 | 37.22% | CC007s
CC020 | Microwave refurbishment and extension | Program - Short Term Need | Repex | 230 | 3450 | 51.29% | CC020s
DS002 | Pole substation refurbishment | Program - Short Term Need | Repex | 280 | 4200 | 36.29% | DS002s
DS005 | Distribution pole replacement | Program - Short Term Need | Repex | 310 | 4650 | 21% | DS005s
DS006 | LV CONSAC cable replacement | Program - Short Term Need | Repex | 230 | 3450 | 51.29% | DS006s
DS007 | Service wire replacement program | Program - Short Term Need | Repex | 300 | 4500 | 25.55% | DS007s
DS008 | Traffic black spot remediation | Program - Short Term Need | Repex | 150 | 2250 | 70.85% | DS008s
DS011 | HV distribution steel mains replacement | Program - Short Term Need | Repex | 280 | 4200 | 36.29% | DS011s
DS014 | LV cable network renewal | Program - Short Term Need | Repex | 230 | 3450 | 51.29% | DS014s
DS301 | Ground substation refurbishment program | Program - Short Term Need | Repex | 240 | 3600 | 42.68% | DS301s
DS302 | Distribution transformer replacement program | Program - Short Term Need | Repex | 270 | 4050 | 37.22% | DS302s
DS305 | Compact LV switchgear replacement | Program - Short Term Need | Repex | 240 | 3600 | 42.68% | DS305s
DS307 | Holec MD4 epoxy switchgear replacement | Program - Short Term Need | Repex | 280 | 4200 | 36.29% | DS307s
DS308 | HV RGB12 switchgear replacement | Program - Short Term Need | Repex |  | 4200 | 36.29% | DS308s
DS312 | Miscellaneous substation renewal expenditure | Program - Short Term Need | Repex | 230 | 3450 | 51.29% | DS312s
DS315 | Low voltage switchgear replacement | Program - Short Term Need | Repex | 280 | 4200 | 36.29% | DS315s
DS317 | Future distribution substation renewals | Program - Short Term Need | Repex | 180 | 2700 | 66.47% | DS317s
DS318 | Distribution substation earthing refurbishment | Program - Short Term Need | Repex | 340 | 5100 | 9.283% | DS318s
DS405 | Air break switch replacement program | Program - Short Term Need | Repex | 280 | 4200 | 36.29% | DS405s
DS409 | Miscellaneous mains renewal expenditure | Program - Short Term Need | Repex | 290 | 4350 | 29.29% | DS409s
DS413 | Low mains remediation | Program - Short Term Need | Repex | 230 | 3450 | 51.29% | DS413s
DS414 | Copper distribution mains replacement | Program - Short Term Need | Repex | 260 | 3900 | 38.53% | DS414s
DS415 | LV mains replacement | Program - Short Term Need | Repex | 190 | 2850 | 66.11% | DS415s
DS416 | Asbestos service fuse replacement | Program - Short Term Need | Repex | 200 | 3000 | 58.52% | DS416s
DS417 | Distribution access track reconstruction | Program - Short Term Need | Repex | 290 | 4350 | 29.29% | DS417s
DS418 | Pole top structure/hardware refurbishment (LV) | Program - Short Term Need | Repex | 330 | 4950 | 12.56% | DS418s
DS420 | Future distribution feeder refurbishment works | Program - Short Term Need | Repex | 180 | 2700 | 66.47% | DS420s
DU | Duct installation RMS road works | Program - Short Term Need | Customer Connection | 170 | 2550 | 68.67% | DUs
EF001 | Distribution management system | Program - Short Term Need | Other | 260 | 3900 | 38.53% | EF001s
EF002 | Technology pilots | Program - Short Term Need | Other | 230 | 3450 | 51.29% | EF002s
EF003 | Battery energy storage system pilot | Program - Short Term Need | Other |  | 3450 | 51.29% | EF003s
EH | Dist environmental enhancement program | Program - Short Term Need | Other | 190 | 2850 | 66.11% | EHs
HVW | HV development works | Program - Short Term Need | Augex | 350 | 5250 | 4.71% | HVWs
IC | Industrial & commercial | Program - Short Term Need | Customer Connection | 200 | 3000 | 58.52% | ICs
LV001 | Overloaded distribution sub uprates | Program - Short Term Need | Augex | 330 | 4950 | 12.56% | LV001s
LV002 | Quality of supply reactive projects | Program - Short Term Need | Other | 300 | 4500 | 25.55% | LV002s
LV003 | LV planning reactive projects | Program - Short Term Need | Other | 300 | 4500 | 25.55% | LV003s
LV005 | Dsub monitoring & LV feeder monitoring for solar PV | Program - Short Term Need | Other | 250 | 3750 | 38.64% | LV005s
MC104 | Meters - renewal | Program - Short Term Need | Other | 50 | 750 | 99.19% | MC104s
MC105 | Relays - renewal | Program - Short Term Need | Other | 100 | 1500 | 92.18% | MC105s
MC107 | Test equipment | Program - Short Term Need | Other | 50 | 750 | 99.19% | MC107s
MC109 | Demand management technology | Program - Short Term Need | Other | 80 | 1200 | 94.48% | MC109s
NU | Non urban extension | Program - Short Term Need | Customer Connection | 120 | 1800 | 82.35% | NUs
PQ001 | Permanent power quality monitoring | Program - Short Term Need | Other | 300 | 4500 | 25.55% | PQ001s
PQ004 | Power quality monitoring replacement | Program - Short Term Need | Other | 200 | 3000 | 58.52% | PQ004s
PR081 | Collimore Park ZS establishment | Major Project - Future/Planning Stage | Augex | 210 | 1050 | 95.93% | PR081
PR110 | Edmondson Park ZS establishment | Major Project - Committed Project | Augex | 170 | 2550 | 68.67% | PR110
PR113 | Augment feeder 308 Nepean to Douglas Park | Major Project - Committed Project | Augex | 340 | 5100 | 9.283% | PR113
PR170 | Holsworthy 33/11kV ZS establishment | Major Project - Future/Planning Stage | Augex | 40 | 200 | 100% | PR170
PR190 | Eschol Park ZS establishment | Major Project - Future/Planning Stage | Augex | 80 | 400 | 99.71% | PR190
PR248 | Penrith Lakes ZS site acquisition | Major Project - Future/Planning Stage | Augex | 140 | 700 | 99.19% | PR248
PR249 | Establish Penrith Lakes 33/11kV Zone Substation | Major Project - Future/Planning Stage | Augex | 140 | 700 | 99.19% | PR249
PR258 | Menangle Park 66/11kV ZS establishment | Major Project - Committed Project | Augex | 170 | 2550 | 68.67% | PR258
#N/A | #N/A | #N/A | Augex | #N/A | #N/A | #N/A | PR270
PR278 | Kemps Creek new BSP associated works | Major Project - Future/Planning Stage | Augex | 20 | 100 | 100% | PR278
PR292 | South Marsden Park (industrial) 132/11kV ZS establishment | Major Project - Committed Project | Augex | 210 | 3150 | 54.86% | PR292
PR423 | Maryland ZS establishment | Major Project - Prior to Approval | Augex | 80 | 800 | 99.13% | PR423
PR425 | Austral ZS establishment (interim initially) | Major Project - Prior to Approval | Augex | 160 | 1600 | 91.18% | PR425
PR427 | Leppington North ZS establishment | Major Project - Committed Project | Augex | 210 | 3150 | 54.86% | PR427
PR430 | North Rossmore ZS site purchase | Major Project - Prior to Approval | Augex | 40 | 400 | 99.71% | PR430
PR432 | Rossmore ZS site purchase | Major Project - Prior to Approval | Augex | 40 | 400 | 99.71% | PR432
PR433 | Rossmore ZS establishment | Major Project - Future/Planning Stage | Augex | 160 | 800 | 99.13% | PR433
PR435 | Catherine Fields North ZS establishment (interim) | Major Project - Future/Planning Stage | Augex | 140 | 700 | 99.19% | PR435
PR437 | Catherine Fields 11kV feeder works | Major Project - Committed Project | Augex |  | 2400 | 69.74% | PR437
PR438 | North Bringelly ZS site purchase | Major Project - Prior to Approval | Augex | 20 | 200 | 100% | PR438
PR439 | North Bringelly ZS establishment | Major Project - Future/Planning Stage | Augex | 40 | 200 | 100% | PR439
PR444 | Culburra Beach development (33kV fdr and single transformer ZS) | Major Project - Future/Planning Stage | Augex | 110 | 550 | 99.19% | PR444
PR499 | Southpipe (Oakdale Estate) ZS 132/11kV establishment | Major Project - Committed Project | Augex | 140 | 2100 | 78.28% | PR499
PR599 | Penrith CBD ZS site purchase | Major Project - Committed Project | Augex |  | 2100 | 78.28% | PR599
PR602 | Riverstone West site purchase | Major Project - Future/Planning Stage | Augex | 70 | 350 | 99.71% | PR602
PR603 | Eschol Park ZS site purchase | Major Project - Future/Planning Stage | Augex | 100 | 500 | 99.19% | PR603
PR620 | West Dapto ZS establishment | Major Project - Prior to Approval | Augex | 110 | 1100 | 95.93% | PR620
PR653 | Avondale (South West Dapto) 132/11kV ZS establishment | Major Project - Future/Planning Stage | Augex | 110 | 550 | 99.19% | PR653
PR656 | Leppington South ZS establishment (permanent) | Major Project - Committed Project | Augex | 230 | 3450 | 51.29% | PR656
PR657 | Calderwood ZS establishment (interim initially) | Major Project - Committed Project | Augex | 170 | 2550 | 68.67% | PR657
PR659 | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | Major Project - Future/Planning Stage | Augex | 60 | 300 | 99.71% | PR659
PR673 | Liverpool ZS 11kV switchboard extension & distribution works | Major Project - Committed Project | Augex | 360 | 5400 | 1.974% | PR673
PR677 | South Penrith Zone Substation | Major Project - Prior to Approval | Augex | 210 | 2100 | 78.28% | PR677
PR698 | Marsden Park (residential) 132/11kV ZS - stage 2 | Major Project - Prior to Approval | Augex | 200 | 2000 | 80.61% | PR698
PR700 | Riverstone east ZS establishment | Major Project - Prior to Approval | Augex | 120 | 1200 | 94.48% | PR700
PR702 | Penrith ZS 11kV transformer cable constraints | Major Project - Committed Project | Augex |  | 3750 | 38.64% | PR702
PR703 | Riverstone East site purchase | Major Project - Prior to Approval | Augex | 120 | 1200 | 94.48% | PR703
PR704 | Oakdale (Southpipe) site purchase | Major Project - Committed Project | Augex | 160 | 2400 | 69.74% | PR704
PR710 | Feeder 868 rebuild & rearrangement South32 | Major Project - Committed Project | Augex |  | 1050 | 95.93% | PR710
PR713 | Box Hill 132/22kV ZS establishment | Major Project - Prior to Approval | Augex | 170 | 1700 | 88.92% | PR713
PR717 | Acquire improved site for West Dapto ZS | Major Project - Committed Project | Augex | 140 | 2100 | 78.28% | PR717
PR722 | Camellia TS connection works for Ausgrid | Major Project - Committed Project | Augex | 170 | 2550 | 68.67% | PR722
PR723 | Supply to Luddenham Science Park | Major Project - Prior to Approval | Augex | 210 | 2100 | 78.28% | PR723
PR724 | Establish Mt Gilead ZS | Major Project - Prior to Approval | Augex | 200 | 2000 | 80.61% | PR724
PR727 | Luddenham ZS site purchase | Major Project - Committed Project | Augex |  | 4950 | 12.56% | PR727
PR728 | Western Sydney Employment Lands ZS | Major Project - Prior to Approval | Augex | 160 | 1600 | 91.18% | PR728
PR729 | Cheriton Avenue 3rd transformer | Major Project - Future/Planning Stage | Augex | 210 | 1050 | 95.93% | PR729
PR732 | Feeder 214/215 contraints | Major Project - Committed Project | Augex | 220 | 3300 | 54.32% | PR732
PR733 | Bringelly ZS augmentation | Major Project - Future/Planning Stage | Augex | 140 | 700 | 99.19% | PR733
PR739 | South Gilead (South Campbelltown) | Major Project - Future/Planning Stage | Augex | 110 | 550 | 99.19% | PR739
PR740 | AFIC upgrade Minto, Prospect, Kingswood | Major Project - Committed Project | Augex | 150 | 2250 | 70.85% | PR740
PR741 | Western Sydney Airport 132kV supply | Major Project - Prior to Approval | Augex | 170 | 1700 | 88.92% | PR741
PR742 | North Bomaderry ZS establishment | Major Project - Prior to Approval | Augex | 100 | 1000 | 97.4% | PR742
PR744 | Termeil ZS establishment | Major Project - Future/Planning Stage | Augex | 270 | 1350 | 92.18% | PR744
PR745 | Austral Permanent ZS establishment | Major Project - Future/Planning Stage | Augex | 160 | 800 | 99.13% | PR745
PR746 | Sydney University - Western Sydney Employment Lands ZS establishment | Major Project - Future/Planning Stage | Augex | 80 | 400 | 99.71% | PR746
PR748 | Establish permanent Catherine Park ZS | Major Project - Prior to Approval | Augex | 240 | 2400 | 69.74% | PR748
PR749 | Nepean ZS augmentation | Major Project - Future/Planning Stage | Augex | 250 | 1250 | 92.18% | PR749
PR750 | Feeder 512 augmentation | Major Project - Committed Project | Augex |  | 2300 | 69.74% | PR750
PR751 | Parklea ZS to Bella Vista ZS load transfer | Major Project - Prior to Approval | Augex | 360 | 3600 | 42.68% | PR751
PR752 | Kemps Creek 132kV conversion | Major Project - Future/Planning Stage | Augex | 340 | 1700 | 88.92% | PR752
PR754 | Augment Westmead Zone Substation | Major Project - Prior to Approval | Augex | 360 | 3600 | 42.68% | PR754
PR755 | Narellan ZS busbar augmentation | Major Project - Future/Planning Stage | Augex | 360 | 1800 | 82.35% | PR755
#N/A | #N/A | #N/A | Augex | #N/A | #N/A | #N/A | PR756
PS008 | Substation protection relay refurbishment | Program - Short Term Need | Repex | 240 | 3600 | 42.68% | PS008s
PS011 | Protection refurbishment (miscellaneous) | Program - Short Term Need | Repex | 150 | 2250 | 70.85% | PS011s
PS012 | Distribution feeder safety improvement | Program - Short Term Need | Repex | 310 | 4650 | 21% | PS012s
PS013 | Feeder differential relay replacement | Program - Short Term Need | Repex | 240 | 3600 | 42.68% | PS013s
PS014 | Under frequency load shedding | Program - Short Term Need | Repex | 170 | 2550 | 68.67% | PS014s
RC | Reliability compliance | Program - Short Term Need | Reliability | 400 | 6000 | 1.673% | RCs
SL001 | Streetlighting growth | Program - Short Term Need | Other | 100 | 1500 | 92.18% | SL001s
SL002 | Streetlighting refurbishment | Program - Short Term Need | Other | 220 | 3300 | 54.32% | SL002s
SP | Essential spares | Program - Short Term Need | Repex | 160 | 2400 | 69.74% | SPs
TM012 | Sub-transmission pole replacement | Program - Short Term Need | Repex | 310 | 4650 | 21% | TM012s
TM014 | Renewal of 33kV and 66kV gas and oil filled cables | Program - Short Term Need | Repex |  | 2700 | 66.47% | TM014s
TM015 | Subtransmission tower replacement | Program - Short Term Need | Repex | 310 | 4650 | 21% | TM015s
TM027 | Steel tower asbestos removal | Major Project - Committed Project | Repex |  | 3900 | 38.53% | TM027
TM028 | 132kV oil cable replacement | Program - Long Term Need | Repex | 260 | 1300 | 92.18% | TM028l
TM030 | Feeder 7028 replacement | Major Project - Prior to Approval | Repex | 200 | 2000 | 80.61% | TM030
TM132 | Sub-transmission pilot cable renewal program | Program - Short Term Need | Repex | 160 | 2400 | 69.74% | TM132s
TM134 | Wollongong - Port Kembla pilot cable replacement | Program - Short Term Need | Repex | 110 | 1650 | 88.95% | TM134s
TM135 | Optical fibre protection and communication upgrades in the Blue Mountains | Program - Short Term Need | Repex | 110 | 1650 | 88.95% | TM135s
TM137 | Optical fibre protection and communication upgrades in the Macarthur area | Program - Short Term Need | Repex | 110 | 1650 | 88.95% | TM137s
TM138 | 132kV optical fibre ring completion | Major Project - Committed Project | Repex |  | 1650 | 88.95% | TM138
TM171 | Replacement of corroded earthwires | Program - Short Term Need | Repex | 270 | 4050 | 37.22% | TM171s
TM172 | Earthwire replacement due to fault rating | Program - Short Term Need | Repex | 170 | 2550 | 68.67% | TM172s
TM174 | Hardex earthwire replacement | Program - Short Term Need | Repex | 240 | 3600 | 42.68% | TM174s
TM302 | Oil filled cable auxiliary equipment refurbishment | Program - Short Term Need | Repex |  | 3000 | 58.52% | TM302s
TM303 | Guilford and Camellia 132kV cables oil testing and flushing | Program - Short Term Need | Repex |  | 3900 | 38.53% | TM303s
TM401 | South Coast 33kV overhead line refurbishment | Program - Short Term Need | Repex |  | 3600 | 42.68% | TM401s
TM419 | Future sub-transmission feeder refurbishment works | Program - Short Term Need | Repex | 150 | 2250 | 70.85% | TM419s
TM801 | Steel tower painting program | Program - Short Term Need | Repex | 170 | 2550 | 68.67% | TM801s
TM803 | Steel tower below ground rectification work | Program - Short Term Need | Repex | 310 | 4650 | 21% | TM803s
TM805 | Earthing refurbishment of lines 940/941 | Program - Short Term Need | Repex | 270 | 4050 | 37.22% | TM805s
TM809 | Subtransmission line earthing refurbishment | Program - Short Term Need | Repex | 150 | 2250 | 70.85% | TM809s
TS004 | 132kV circuit breaker replacement | Program - Short Term Need | Repex | 240 | 3600 | 42.68% | TS004s
TS005 | 33kV circuit breaker replacement | Program - Short Term Need | Repex | 240 | 3600 | 42.68% | TS005s
TS007 | 11kV circuit breaker replacement | Program - Short Term Need | Repex | 230 | 3450 | 51.29% | TS007s
TS008 | Battery replacement | Program - Short Term Need | Repex | 370 | 5550 | 1.951% | TS008s
TS009 | Auxiliary switchgear replacement | Program - Short Term Need | Repex | 190 | 2850 | 66.11% | TS009s
TS015 | Replacement of surge arrester in zone and sub-transmission substations | Program - Short Term Need | Repex | 190 | 2850 | 66.11% | TS015s
TS016 | VT and CT replacement | Program - Short Term Need | Repex | 240 | 3600 | 42.68% | TS016s
TS017 | Power transformer refurbishment | Program - Short Term Need | Repex |  | 2100 | 78.28% | TS017s
TS024 | Building and amenities refurbishment | Program - Short Term Need | Repex | 200 | 3000 | 58.52% | TS024s
TS025 | Asbestos and other hazardous material reporting, management and removal | Program - Short Term Need | Repex | 160 | 2400 | 69.74% | TS025s
TS026 | Noise attenuation in ZS and TS | Program - Short Term Need | Repex | 210 | 3150 | 54.86% | TS026s
TS027 | Substation switchyard lighting improvement | Program - Short Term Need | Repex | 140 | 2100 | 78.28% | TS027s
TS031 | Substation safety fence upgrade program | Program - Short Term Need | Repex | 230 | 3450 | 51.29% | TS031s
TS032 | Substation security systems | Program - Short Term Need | Repex | 150 | 2250 | 70.85% | TS032s
TS033 | Substation fire hydrant installations | Program - Short Term Need | Repex | 160 | 2400 | 69.74% | TS033s
TS034 | Substation deluge showers and fire blankets | Program - Short Term Need | Repex | 120 | 1800 | 82.35% | TS034s
TS035 | Substation oil containment program - bund walls | Program - Short Term Need | Repex | 110 | 1650 | 88.95% | TS035s
TS036 | Substation earthing | Program - Short Term Need | Repex | 370 | 5550 | 1.951% | TS036s
TS049 | Tunnelboard refurbishment | Program - Short Term Need | Repex | 150 | 2250 | 70.85% | TS049s
TS050 | POW switching for capacitors | Program - Short Term Need | Repex |  | 2250 | 70.85% | TS050s
TS055 | 66kV circuit breaker replacement | Program - Short Term Need | Repex | 240 | 3600 | 42.68% | TS055s
TS057 | Substation insulation co-ordination | Program - Short Term Need | Repex |  | 2400 | 69.74% | TS057s
TS086 | Busbar support and isolator replacement | Program - Short Term Need | Repex | 200 | 3000 | 58.52% | TS086s
TS116 | Roof refurbishment for control and switch rooms | Program - Short Term Need | Repex | 280 | 4200 | 36.29% | TS116s
TS122 | Leabons Lane Zone Substation renewal | Major Project - Committed Project | Repex |  | 3450 | 51.29% | TS122
TS127 | Castle Hill Zone Substation renewal | Major Project - Committed Project | Repex |  | 3450 | 51.29% | TS127
TS128 | Capacitor bank refurbishment | Program - Short Term Need | Repex |  | 4200 | 36.29% | TS128s
TS144 | Substation fire stopping measures | Program - Short Term Need | Repex | 160 | 2400 | 69.74% | TS144s
TS146 | Marayong Zone Substation renewal | Major Project - Committed Project | Repex | 230 | 3450 | 51.29% | TS146
TS155 | Sussex Inlet Zone Substation - stage 2 renewal | Major Project - Committed Project | Repex | 210 | 3150 | 54.86% | TS155
#N/A | #N/A | #N/A | Repex | #N/A | #N/A | #N/A | TS163
#N/A | #N/A | #N/A | Repex | #N/A | #N/A | #N/A | TS165
TS167 | Carlingford Transmission Substation control building replacement | Major Project - Prior to Approval | Repex | 180 | 1800 | 82.35% | TS167
TS173 | 11kV switchboard truck replacement program | Program - Short Term Need | Repex | 290 | 4350 | 29.29% | TS173s
#N/A | #N/A | #N/A | Repex | #N/A | #N/A | #N/A | TS174
TS177 | Substation battery duplication | Program - Short Term Need | Repex | 330 | 4950 | 12.56% | TS177s
TS179 | 33kV wall bushing replacement | Program - Short Term Need | Repex |  | 3150 | 54.86% | TS179s
TS180 | Transformer fire wall installation | Program - Short Term Need | Repex | 140 | 2100 | 78.28% | TS180s
TS181 | 11kV capacitor bank refurbishment | Program - Short Term Need | Repex |  | 4050 | 37.22% | TS181s
TS184 | Blaxland Zone Substation reinstatement | Major Project - Committed Project | Repex |  | 4500 | 25.55% | TS184
TS185 | Penrith TS civil development | Major Project - Committed Project | Repex |  | 3450 | 51.29% | TS185
TS187 | Mobile substation No 2 refurbishment | Program - Short Term Need | Repex |  | 2850 | 66.11% | TS187s
TS188 | Bossley Park ZS civil refurbishment | Major Project - Committed Project | Repex |  | 3000 | 58.52% | TS188
TS199 | Future sub-transmission substation renewal programs | Program - Short Term Need | Repex | 180 | 2700 | 66.47% | TS199s
TS600 | Power transformer replacement | Program - Short Term Need | Repex | 340 | 5100 | 9.283% | TS600s
TS615 | Gerringong ZS 33kV No 2 transformer replacement | Major Project - Committed Project | Repex |  | 5100 | 9.283% | TS615
TS616 | Camellia TS transformer replacement and 33kV busbar rearrangement | Major Project - Committed Project | Repex | 340 | 5100 | 9.283% | TS616
TS617 | Prospect ZS transformer replacement | Major Project - Committed Project | Repex | 340 | 5100 | 9.283% | TS617
TS618 | Albion Park ZS transformer replacement | Major Project - Committed Project | Repex | 340 | 5100 | 9.283% | TS618
TS700 | 11kV zone substation switchboard replacement | Program - Short Term Need | Repex | 290 | 4350 | 29.29% | TS700s
TS701 | North Rocks ZS 11kV switchboard replacement | Major Project - Committed Project | Repex | 290 | 4350 | 29.29% | TS701
TS702 | Kellyville ZS 11kV switchboard replacement | Major Project - Committed Project | Repex | 290 | 4350 | 29.29% | TS702
TS703 | Horsley Park ZS 11kV switchboard replacement | Major Project - Committed Project | Repex | 290 | 4350 | 29.29% | TS703
TS704 | Port Central ZS 11kV switchboard replacement | Major Project - Committed Project | Repex | 290 | 4350 | 29.29% | TS704
UR | Underground residential | Program - Short Term Need | Customer Connection | 190 | 2850 | 66.11% | URs

## SRP Prog Comp (hidden)
ID | Program | PIP SRP | PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL | Change | % Change
AR | Asset relocation | 18773713.7429 | 15779946.7158 | -2993767.0271 | -15.95%
AU004 | PM102 ZS SCADA refurbishment | 18774222.4529 | 22243372.2539 | 3469149.8011 | 18.48%
AU013 | SCADA master station development software | 18226060.0201 | 15973723.1454 | -2252336.8747 | -12.36%
CC002 | Communications development SCADA | 5101690.8839 | 5098102.0502 | -3588.8338 | -0.07035%
CC007 | SCADA radio repeaters | 7101553.7104 | 7260827.3985 | 159273.6881 | 2.243%
CC020 | Microwave refurbishment and extension | 5554650.8034 | 9039261.0084 | 3484610.205 | 62.73%
DS002 | Pole substation refurbishment | 8626635.1923 | 7792263.2073 | -834371.985 | -9.672%
DS005 | Distribution pole replacement | 150176446.9313 | 150176446.9313 | 0 | 0%
DS006 | LV CONSAC cable replacement | 101150508.9009 | 106643256.8082 | 5492747.9074 | 5.43%
DS007 | Service wire replacement program | 107208406.791 | 100380456.2963 | -6827950.4947 | -6.369%
DS008 | Traffic black spot remediation | 10203381.7679 | 10203381.7679 | 0 | 0%
DS011 | HV distribution steel mains replacement | 58469441.4315 | 55624847.6259 | -2844593.8056 | -4.865%
DS014 | LV cable network renewal | 15548984.2045 | 11931896.2982 | -3617087.9062 | -23.26%
DS301 | Ground substation refurbishment program | 10206150.5406 | 10206150.5406 | 0 | 0%
DS302 | Distribution transformer replacement program | 15408911.1892 | 15266031.1129 | -142880.0763 | -0.9273%
DS305 | Compact LV switchgear replacement | 5101690.8839 | 5101690.8839 | 0 | 0%
DS307 | Holec MD4 epoxy switchgear replacement | 76723772.0469 | 68925828.3031 | -7797943.7437 | -10.16%
DS308 | HV RGB12 switchgear replacement | 0 | 0 | 0
DS312 | Miscellaneous substation renewal expenditure | 38119658.7072 | 17757479.9473 | -20362178.7598 | -53.42%
DS315 | Low voltage switchgear replacement | 7223994.2916 | 7223994.2916 | 0 | 0%
DS317 | Future distribution substation renewals | 74599819.5799 | 17097238.6593 | -57502580.9206 | -77.08%
DS318 | Distribution substation earthing refurbishment | 2754913.0773 | 2754913.0773 | 0 | 0%
DS405 | Air break switch replacement | 37650478.7234 | 37140309.635 | -510169.0884 | -1.355%
DS409 | Miscellaneous mains renewal expenditure | 12998311.348 | 11678345.7649 | -1319965.5831 | -10.15%
DS413 | Low mains remediation | 13450326.0972 | 13450326.0972 | 0 | 0%
DS414 | Copper distribution mains replacement | 23504116.2429 | 11172689.6154 | -12331426.6275 | -52.46%
DS415 | LV mains replacement | 11238097.3314 | 11199641.7194 | -38455.6119 | -0.3422%
DS416 | Asbestos service fuse replacement | 267525 | 267525 | 0 | 0%
DS417 | Distribution access track reconstruction | 6056171.0516 | 13009815.515 | 6953644.4635 | 114.8%
DS418 | Pole top structure/hardware refurbishment | 85804569.7678 | 26627255.2305 | -59177314.5374 | -68.97%
DU | Duct installation RMS road works | 24313476.3407 | 23650801.3996 | -662674.941 | -2.726%
EF001 | Distribution management system | 12700000 | 12700000.5228 | 0.52281 | 4.117e-06%
EF002 | Technology pilots | 17293326.0357 | 17293326.0357 | 0 | 0%
EF003 | Battery energy storage system pilot | 0 | 0 | 0
HVW | HV development works | 64140951.3371 | 64140951.3371 | 0 | 0%
IC | Industrial & commercial | 137965604.4043 | 48246537.954 | -89719066.4502 | -65.03%
LV001 | Overloaded distribution sub uprates | 1224405.8121 | 816270.5414 | -408135.2707 | -33.33%
LV002 | Quality of supply reactive projects | 5101690.8839 | 5101690.8839 | 0 | 0%
LV003 | LV planning reactive projects | 10203381.7679 | 10203381.7679 | 0 | 0%
LV004 | Low voltage system augmentations | 0 | 0 | 0
LV005 | Dsub monitoring & LV feeder monitoring for solar PV | 2550845.442 | 2550845.442 | 0 | 0%
MC102 | Relays - growth | 0 | 0 | 0
MC104 | Meters - renewal | 25625 | 205815.0677 | 180190.0677 | 703.2%
MC105 | Relays - renewal | 7629044.6829 | 7629044.6829 | 0 | 0%
MC107 | Test equipment | 846005.8077 | 1054994.9255 | 208989.1178 | 24.7%
MC109 | Demand management technology | 8318786.3259 | 8318786.3259 | 0 | 0%
NU | Non urban extension | 17304965.5589 | 6919236.5927 | -10385728.9662 | -60.02%
OH | Capitalised Overheads | 768597450.532 | 768597450.532 | 0 | 0%
PQ001 | Permanent power quality monitoring | 1020338.1768 | 1020338.1768 | 0 | 0%
PR110 | Edmondson Park ZS establishment | 1941000 | 1815370.0944 | -125629.9056 | -6.472%
PR113 | Augment feeder 308 Nepean to Douglas Park | 6223800 | 9256552.0625 | 3032752.0625 | 48.73%
PR170 | Holsworthy 33/11kV ZS establishment | 24994973.7884 | 15616659.8263 | -9378313.9621 | -37.52%
PR190 | Eschol Park ZS establishment | 25766499.192 | 27120954.9004 | 1354455.7085 | 5.257%
PR248 | Penrith Lakes ZS site acquisition | 1103812.8906 | 347908.0255 | -755904.8652 | -68.48%
PR249 | Establish Penrith Lakes 33/11kV Zone Substation | 20830356.6075 | 9291585.5505 | -11538771.057 | -55.39%
PR258 | Menangle Park 66/11kV ZS establishment | 3587500 | 4608367.3537 | 1020867.3537 | 28.46%
PR278 | Kemps Creek new BSP associated works | 5279948.9564 | 3153165.7786 | -2126783.1777 | -40.28%
PR292 | South Marsden Park (industrial) 132/11kV ZS establishment | 9800000 | 1245387.3 | -8554612.7 | -87.29%
PR423 | Maryland ZS | 22550855.0678 | 22333940.824 | -216914.2438 | -0.9619%
PR425 | Austral ZS establishment (interim initially) | 2500000 | 3736022.5 | 1236022.5 | 49.44%
PR427 | Leppington North ZS establishment | 3283215 | 1799807.75 | -1483407.25 | -45.18%
PR430 | North Rossmore ZS site purchase | 3311438.6719 | 3311438.6719 | 0 | 0%
PR432 | Rossmore ZS site purchase | 3394224.6387 | 3394224.6387 | 0 | 0%
PR435 | Catherine Fields North ZS establishment (interim) | 33764317.3127 | 15946652.0671 | -17817665.2456 | -52.77%
PR437 | Catherine Fields 11kV feeder works | 0 | 0 | 0
PR438 | North Bringelly ZS site purchase | 3959928.7451 | 3769117.1875 | -190811.5576 | -4.819%
PR444 | Culburra Beach development (33kV fdr and single transformer ZS) | 9042529.4042 | 6890402.7033 | -2152126.7009 | -23.8%
PR499 | Southpipe (Oakdale Estate) ZS 132/11kV establishment | 28734199.125 | 33513414.35 | 4779215.225 | 16.63%
PR599 | Penrith CBD ZS site purchase | 0 | 0 | 0
PR602 | Riverstone West site purchase | 5943428.7683 | 6092014.4875 | 148585.7192 | 2.5%
PR603 | Eschol Park ZS site purchase | 3479080.2546 | 0 | -3479080.2546 | -100%
PR620 | West Dapto ZS establishment | 13685270.0966 | 22763181.2372 | 9077911.1406 | 66.33%
PR656 | Leppington South ZS establishment (permanent) | 14500000 | 17611042.9581 | 3111042.9581 | 21.46%
PR657 | Calderwood ZS establishment (interim initially) | 16295731.875 | 3064660.3125 | -13231071.5625 | -81.19%
PR659 | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | 2899233.5455 | 2899233.5455 | 0 | 0%
PR673 | Liverpool ZS 11kV switchboard extension & distribution works | 0 | 300000.075 | 300000.075 | Added
PR677 | South Penrith Zone Substation | 29646734.8438 | 33126730.1064 | 3479995.2626 | 11.74%
PR698 | Marsden Park (residential) 132/11kV ZS - stage 2 | 9288101.5625 | 6359715 | -2928386.5625 | -31.53%
PR700 | Riverstone east | 22904937.2635 | 22763181.2372 | -141756.0263 | -0.6189%
PR702 | Penrith ZS 11kV transformer cable constraints | 0 | 0 | 0
PR703 | Riverstone East site purchase | 6150000 | 6150000 | 0 | 0%
PR704 | Oakdale (Southpipe) site purchase | 0 | 200000.05 | 200000.05 | Added
PR710 | Feeder 868 rebuild & rearrangement South32 | 0 | 0 | 0
PR713 | Box Hill 132/22kV ZS establishment | 36821387.625 | 37855712.05 | 1034324.425 | 2.809%
PR717 | Acquire improved site for West Dapto ZS | 2050000 | 2050000 | 0 | 0%
PR722 | Camellia TS connection works for Ausgrid | 132418 | 392151.3931 | 259733.3931 | 196.1%
PR723 | Supply to Luddenham Science Park | 42840623.25 | 48996401.189 | 6155777.939 | 14.37%
PR724 | Establish Mt Gilead ZS | 21379420.7346 | 22535740.5911 | 1156319.8564 | 5.409%
PR727 | Luddenham ZS site purchase | 1000000 | 0 | -1000000 | -100%
PR728 | Western Sydney Employment Lands ZS | 26050274.9792 | 25057302.4023 | -992972.5769 | -3.812%
PR729 | Cheriton Avenue 3rd transformer | 8891369.4374 | 0 | -8891369.4374 | -100%
PR732 | Feeder 214/215 contraints | 9807328.125 | 10668712.5 | 861384.375 | 8.783%
PR733 | Bringelly ZS augmentation | 25313381.0978 | 25472584.7525 | 159203.6547 | 0.6289%
PR739 | South Gilead (South Campbelltown) | 22461753.9093 | 24161917.5164 | 1700163.6071 | 7.569%
PR740 | AFIC upgrade Minto, Prospect, Kingswood | 0 | 318942.075 | 318942.075 | Added
PR741 | Western Sydney Airport 132kV supply | 67604065.6134 | 43602036.0598 | -24002029.5536 | -35.5%
PR742 | North Bomaderry | 20480752.8159 | 20530934.5056 | 50181.6897 | 0.245%
PR744 | Termeil ZS | 8879415.8337 | 9348310.3885 | 468894.5547 | 5.281%
PR745 | Austral Permanent ZS | 26524942.7464 | 24701426.3194 | -1823516.427 | -6.875%
PR746 | Sydney University - Western Sydney Employment Lands | 30199334.2177 | 30238810.4716 | 39476.2539 | 0.1307%
PS008 | Substation protection relay refurbishment | 43037864.2968 | 46991004.2152 | 3953139.9184 | 9.185%
PS010 | Protection refurbishment (interfacing feeders) | 0 | 0 | 0
PS011 | Protection refurbishment (miscellaneous) | 7142367.2375 | 7142367.2375 | 0 | 0%
PS012 | Distribution feeder safety improvement | 3177500 | 3177500 | 0 | 0%
PS013 | Feeder differential relay replacement | 3367115.9834 | 3028865.9834 | -338250 | -10.05%
PS014 | Under frequency load shedding | 1141593.75 | 1141593.75 | 0 | 0%
RI | Reliability enhancement | 0 | 0 | 0
SL001 | Streetlighting growth | 17855918.0937 | 17855918.0937 | 0 | 0%
SL002 | Streetlighting refurbishment | 30610145.3036 | 30610145.3036 | 0 | 0%
SP | Essential spares | 10203381.7679 | 10203381.7679 | 0 | 0%
SW | Network Switching | 72633875.0416 | 72633875.0416 | 0 | 0%
TM012 | Sub-transmission pole replacement | 45093044.0791 | 48078744.0035 | 2985699.9244 | 6.621%
TM014 | Renewal of 33kV and 66kV gas and oil filled cables | 7184358.3945 | 8225891.1475 | 1041532.753 | 14.5%
TM028 | 132kV oil cable 228 replacement | 48156450.3934 | 48397452.8059 | 241002.4125 | 0.5005%
TM132 | Sub-transmission pilot cable renewal program | 9693212.6795 | 4076386.0576 | -5616826.6219 | -57.95%
TM134 | Wollongong - Port Kembla pilot cable replacement | 16478461.5551 | 6087159.4492 | -10391302.1059 | -63.06%
TM135 | Optical fibre protection and communication upgrades in the Blue Mountains | 6632198.1491 | 3392723.1044 | -3239475.0447 | -48.84%
TM137 | Optical fibre protection and communication upgrades in the Macarthur area | 13060328.6629 | 3319604.072 | -9740724.5909 | -74.58%
TM138 | 132kV optical fibre ring completion | 0 | 0 | 0
TM171 | Replacement of corroded earthwires | 9739106.0911 | 4475767.9337 | -5263338.1574 | -54.04%
TM172 | Earthwire replacement due to fault rating | 10203381.7679 | 2127515.625 | -8075866.1429 | -79.15%
TM174 | Hardex earthwire replacement | 10203381.7679 | 9178381.7679 | -1025000 | -10.05%
TM302 | Oil filled cable auxiliary equipment refurbishment | 161230.3743 | 161230.3743 | 0 | 0%
TM303 | Guilford and Camellia 132kV cables oil testing and flushing | 201537.9678 | 201537.9678 | 0 | 0%
TM401 | South Coast 33kV overhead line refurbishment | 11994983.1214 | 0 | -11994983.1214 | -100%
TM419 | Future feeder refurbishment works | 74599819.5799 | 17097238.6593 | -57502580.9206 | -77.08%
TM801 | Steel tower painting program | 3852516.0315 | 3852516.0315 | 0 | 0%
TM803 | Steel tower below ground rectification work | 21427101.7125 | 12465404.5551 | -8961697.1574 | -41.82%
TM805 | Earthing refurbishment of lines 940/941 | 1310713.0494 | 1310713.0494 | 0 | 0%
TM809 | Subtransmission line earthing refurbishment | 5507029.0607 | 5507029.0607 | 0 | 0%
TS004 | 132kV circuit breaker replacement | 3693624.2 | 2552413.5437 | -1141210.6562 | -30.9%
TS005 | 33kV circuit breaker replacement | 8688179.5753 | 7422843.9763 | -1265335.599 | -14.56%
TS007 | 11kV circuit breaker replacement | 744630.4688 | 744630.4688 | 0 | 0%
TS008 | Battery replacement | 12244058.1214 | 7809893.9397 | -4434164.1817 | -36.21%
TS009 | Auxiliary switchgear replacement | 6257506.7922 | 638308.7791 | -5619198.0131 | -89.8%
TS015 | Replacement of surge arrester in zone and sub-transmission substations | 729866.4798 | 716574.4275 | -13292.0524 | -1.821%
TS016 | VT and CT replacement | 7142367.2375 | 4921504.5677 | -2220862.6698 | -31.09%
TS018 | Transformer oil replacement | 0 | 0 | 0
TS024 | Building and amenities refurbishment | 20406763.5357 | 17712895.1715 | -2693868.3643 | -13.2%
TS025 | Asbestos and other hazardous material reporting, management and removal | 5305758.5193 | 4563890.0432 | -741868.4761 | -13.98%
TS026 | Noise attenuation in ZS and TS | 10203381.7679 | 4645847.5615 | -5557534.2063 | -54.47%
TS027 | Substation switchyard lighting improvement | 1224405.8121 | 1122371.9945 | -102033.8177 | -8.333%
TS031 | Substation safety fence upgrade program | 1020338.1768 | 1020338.1768 | 0 | 0%
TS032 | Substation security systems | 472877.3438 | 472877.3438 | 0 | 0%
TS033 | Substation fire hydrant installations | 2040676.3536 | 2040676.3536 | 0 | 0%
TS034 | Substation deluge showers and fire blankets | 1632541.0829 | 1632541.0829 | 0 | 0%
TS035 | Substation oil containment program - bund walls | 714236.7237 | 714236.7237 | 0 | 0%
TS036 | Substation earthing | 5614190.8839 | 777155 | -4837035.8839 | -86.16%
TS049 | Tunnelboard refurbishment | 459152.1796 | 156783.7833 | -302368.3962 | -65.85%
TS050 | POW switching for capacitors | 662287.7344 | 0 | -662287.7344 | -100%
TS055 | 66kV circuit breaker replacement | 2632472.4961 | 1777947.6701 | -854524.826 | -32.46%
TS057 | Substation insulation co-ordination | 1530507.2652 | 0 | -1530507.2652 | -100%
TS086 | Busbar support and isolator replacement | 964219.5771 | 867357.0771 | -96862.5 | -10.05%
TS116 | Roof refurbishment for control and switch rooms | 15305072.6518 | 15305072.6518 | 0 | 0%
TS122 | Leabons Lane Zone Substation renewal | 0 | 0 | 0
TS127 | Castle Hill Zone Substation renewal | 0 | 0 | 0
TS128 | Capacitor bank refurbishment | 0 | 0 | 0
TS144 | Substation fire stopping measures | 673423.1967 | 673423.1967 | 0 | 0%
TS146 | Marayong Zone Substation renewal | 6865450 | 10331673.9731 | 3466223.9731 | 50.49%
TS155 | Sussex Inlet Zone Substation - stage 2 renewal | 7716932.1429 | 1759755.4906 | -5957176.6522 | -77.2%
TS163 | Unanderra Zone Substation renewal | 16615076.2305 | 0 | -16615076.2305 | -100%
TS165 | Greystanes Zone Substation renewal | 24289778.6445 | 0 | -24289778.6445 | -100%
TS167 | Carlingford Transmission Substation control building replacement | 14186320.3125 | 14540978.3203 | 354658.0078 | 2.5%
TS173 | 11kV switchboard truck replacement program | 0 | 28488642.2903 | 28488642.2903 | Added
TS174 | West Wollongong Zone Substation 11kV renewal | 13530408.3984 | 0 | -13530408.3984 | -100%
TS177 | Substation battery duplication | 9703836.5799 | 1788295.0781 | -7915541.5018 | -81.57%
TS179 | 33kV wall bushing replacement | 1712071.2182 | 0 | -1712071.2182 | -100%
TS180 | Transformer fire wall installation | 2040676.3536 | 5507029.0607 | 3466352.7071 | 169.9%
TS181 | 11kV capacitor bank refurbishment | 0 | 0 | 0
TS183 | Carlingford Transmission Substation redevelopment | 0 | 0 | 0
TS184 | Blaxland Zone Substation reinstatement | 0 | 0 | 0
TS185 | Penrith TS civil development | 2050000 | 0 | -2050000 | -100%
TS199 | Future substation renewal programs | 126094234.3812 | 17097238.6593 | -108996995.7219 | -86.44%
TS600 | Power transformer replacement | 144123603.5786 | 107865694.6471 | -36257908.9316 | -25.16%
TS615 | Gerringong ZS 33kV No 2 transformer replacement | 0 | 0 | 0
TS616 | Camellia TS transformer replacement and 33kV busbar rearrangement | 0 | 340958.05 | 340958.05 | Added
TS617 | Prospect ZS transformer replacement | 0 | 29999.7 | 29999.7 | Added
TS618 | Albion Park ZS transformer replacement | 0 | 1616692.525 | 1616692.525 | Added
UR | Underground residential | 437446932.4127 | 126657705.3078 | -310789227.105 | -71.05%

## CASH (hidden)
Proj | Rank
AG | 190
AR | 140
AU004 | 220
AU013 | 310
CC002 | 150
CC007 | 270
CC020 | 230
DS002 | 280
DS005 | 310
DS006 | 230
DS007 | 300
DS008 | 150
DS011 | 280
DS014 | 230
DS301 | 240
DS302 | 270
DS305 | 240
DS307 | 280
DS312 | 230
DS315 | 280
DS317 | 180
DS318 | 340
DS405 | 280
DS409 | 290
DS413 | 230
DS414 | 260
DS415 | 190
DS416 | 200
DS417 | 290
DS418 | 330
DS420 | 180
DS421 | 330
DU | 170
EF001 | 260
EF002 | 230
EH | 190
HVW | 350
IC | 200
LV001 | 330
LV002 | 300
LV003 | 300
LV005 | 250
MC104 | 50
MC105 | 100
MC107 | 50
MC109 | 80
NU | 120
PQ001 | 300
PQ004 | 200
PR081 | 210
PR110 | 170
PR113 | 340
PR170 | 40
PR190 | 80
PR248 | 140
PR249 | 140
PR258 | 170
PR278 | 20
PR292 | 210
PR423 | 80
PR425 | 160
PR427 | 210
PR430 | 40
PR432 | 40
PR433 | 160
PR435 | 140
PR436 | 240
PR438 | 20
PR439 | 40
PR444 | 110
PR499 | 140
PR602 | 70
PR603 | 100
PR620 | 110
PR653 | 110
PR656 | 230
PR657 | 170
PR659 | 60
PR673 | 360
PR677 | 210
PR698 | 200
PR700 | 120
PR703 | 120
PR704 | 160
PR713 | 170
PR717 | 140
PR722 | 170
PR723 | 210
PR724 | 200
PR728 | 160
PR729 | 210
PR732 | 220
PR733 | 140
PR739 | 110
PR740 | 150
PR741 | 170
PR742 | 100
PR744 | 270
PR745 | 160
PR746 | 80
PR748 | 240
PR749 | 250
PR751 | 360
PR752 | 340
PR754 | 360
PR755 | 360
PR761 | 170
PR765 | 180
PR766 | 180
PR767 | 180
PR768 | 170
PR769 | 180
PS008 | 240
PS011 | 150
PS012 | 310
PS013 | 240
PS014 | 170
RC | 400
SL001 | 100
SL002 | 220
SP | 160
TM012 | 310
TM014 | 180
TM015 | 310
TM028 | 260
TM030 | 200
TM031 | 260
TM033 | 330
TM132 | 160
TM134 | 110
TM135 | 110
TM137 | 110
TM171 | 270
TM172 | 170
TM174 | 240
TM302 | 200
TM303 | 260
TM419 | 150
TM801 | 170
TM803 | 310
TM805 | 270
TM809 | 150
TS004 | 240
TS005 | 240
TS007 | 230
TS008 | 370
TS009 | 190
TS015 | 190
TS016 | 240
TS024 | 200
TS025 | 160
TS026 | 210
TS027 | 140
TS031 | 230
TS032 | 150
TS033 | 160
TS034 | 120
TS035 | 110
TS036 | 370
TS049 | 150
TS055 | 240
TS086 | 200
TS116 | 280
TS144 | 160
TS146 | 230
TS155 | 210
TS167 | 180
TS173 | 290
TS177 | 330
TS180 | 140
TS199 | 180
TS600 | 340
TS616 | 340
TS617 | 340
TS618 | 340
TS620 | 340
TS700 | 290
TS701 | 290
TS702 | 290
TS703 | 290
TS704 | 290
UR | 190

## SRP Comp (hidden)
| PIP SRP | [13 empty] | PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL
| FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29
AG | 0 | 0 | 0 | 0 | 300000 | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | #REF! | #REF! | #REF! | #REF! | 0 | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | 384025.3633
AR | 2476817.3 | 1549055.28 | 1518424.87 | 1660155.1572 | 1674562.9105 | 1863202.975 | 1901068.115 | 1955611.8372 | 2013924.28 | 2080036.2976 | 2141221.9769 | 2204145.5211 | 2268923.2782 | 2345579.462 | #REF! | #REF! | #REF! | #REF! | 1670000 | 1664241.25 | 1643020.9569 | 1661087.6357 | 1694353.8909 | 1734526.8575 | 1777890.029 | 1822337.2797 | 1867895.7117 | 1914593.1045 | 1962457.9321
AU | 1967261.47 | 1625078.35 | 1830879.78 | 3068701 | 2044144 | 3936000 | 4034400 | 3058369.375 | 3134828.6094 | 4344607.5375 | 4453222.7259 | 4564553.2941 | 4678667.1264 | 4795633.8046 | #REF! | #REF! | #REF! | #REF! | 1692166 | 3372250 | 3456556.25 | 4619860.7812 | 4735357.3008 | 3722333.0204 | 3815391.3459 | 3910776.1296 | 5226948.4303 | 5357622.1411 | 4211478.1504
CC | 1800876.2 | 1637900.32 | 2612846.84 | 2679463 | 2170000 | 1687150 | 1729328.75 | 1772561.9687 | 1816876.018 | 1862297.9184 | 2140794.05 | 2194313.9013 | 2249171.7488 | 2305401.0425 | #REF! | #REF! | #REF! | #REF! | 1626275.49 | 2229375 | 2138021.875 | 2008401.0156 | 1815772.2051 | 1634884.8676 | 2470146.9808 | 3114356.6746 | 2790142.6353 | 3197089.2031 | 2393758.0976
DS | 62476667.99 | 51604984.79 | 46667028.99 | 70304887.1328 | 62411426.2174 | 68376725 | 75556747.5 | 82527513.0469 | 86704502.5586 | 86949286.8648 | 113615744.029 | 130235977.2292 | 147101437.0251 | 156024197.4245 | #REF! | #REF! | #REF! | #REF! | 58236579.809 | 58817657 | 65386781.55 | 71822229.495 | 75203412.4498 | 81093208.4675 | 83671393.0528 | 92039438.6585 | 107249403.3241 | 126590470.4263 | 144348195.9908
DU | 0 | 0 | 0 | 0 | 1955226.0176 | 2206549.275 | 2318255.5431 | 2435617.5261 | 2558919.7528 | 2688465.7724 | 2824569.0042 | 2967563.4935 | 3117795.5425 | 3195740.4311 | #REF! | #REF! | #REF! | #REF! | 700000 | 2206549.275 | 2318255.5431 | 2435617.5261 | 2558919.7528 | 2688465.7724 | 2755677.4167 | 2824569.3521 | 2895183.5859 | 2967563.1755 | 3275633.9418
EF | 295763.84 | 531294.06 | 1321329 | 4004600.99 | 14244814 | 9312500 | 4325312.5 | 2253781.25 | 2207625.7812 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | #REF! | #REF! | #REF! | #REF! | 14073634.24 | 9312500.15 | 4325312.8094 | 2253781.3134 | 2207625.7812 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | 2560169.0884
EH | 190546.42 | 770.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HV | 11023877.7 | 3151822.81 | 3840236.18 | 4480000 | 7057544 | 6970865.1 | 7462655.5644 | 7158488.2801 | 6926477.7679 | 6728594.3887 | 6958160.5093 | 7132114.522 | 7310417.3851 | 7493177.8197 | #REF! | #REF! | #REF! | #REF! | 8536573.1465 | 6970865.1 | 7462655.5644 | 7158488.2801 | 6926477.7679 | 6728594.3887 | 6958160.5093 | 7132114.522 | 7310417.3851 | 7493177.8197 | 7680507.2652
IC | 5231966.27 | 4695952.82 | 3865150.26 | 8725596.4249 | 10000000 | 14182418.65 | 13958796.0144 | 14282150.9943 | 14690991.2548 | 15327508.38 | 15736695.2562 | 16154393.9215 | 16583267.581 | 17049382.3521 | #REF! | #REF! | #REF! | #REF! | 10000000 | 7688980.1 | 5602510.3438 | 4936560.3145 | 4769957.4197 | 4803453.5325 | 4923539.8708 | 5046628.3675 | 5172794.0767 | 5302113.9287 | 5434666.7769
LV | 1589763.42 | 1216003.38 | 1249268.58 | 1882222.76 | 1870000 | 1916750 | 1964668.75 | 2013785.4687 | 2064130.1055 | 2115733.3581 | 2168626.6921 | 2222842.3594 | 2278413.4183 | 2335373.7538 | #REF! | #REF! | #REF! | #REF! | 2850394.93 | 1875750 | 1922643.75 | 1970709.8437 | 2019977.5898 | 2070477.0296 | 2122238.9553 | 2175294.9292 | 2229677.3024 | 2285419.235 | 2342554.7159
MC | 3221857.17 | 3263055.68 | 3134267.72 | 1838337.59 | 905000 | 2524148.6 | 1825129.9906 | 1816484.0298 | 1806263.9608 | 1800055.7584 | 1786609.7638 | 1771366.4346 | 1754244.3078 | 1735158.9707 | #REF! | #REF! | #REF! | #REF! | 815847.56 | 2601023.6 | 1888167.4906 | 1870328.561 | 1817302.0897 | 1850969.128 | 1798206.698 | 1824857.2935 | 1766428.3368 | 1791357.8043 | 1726823.8094
NU | 833787.12 | 629075.45 | 642906.63 | 1123423.0321 | 850000 | 1774809.025 | 1750945.3594 | 1792149.5323 | 1843593.809 | 1922175.4353 | 1973837.6274 | 2026602.2283 | 2080788.4684 | 2140064.0739 | #REF! | #REF! | #REF! | #REF! | 850000 | 1044823.5 | 780742.5512 | 712692.677 | 697271.9801 | 700813.481 | 718333.818 | 736292.1635 | 754699.4676 | 773566.9543 | 792906.1281
OF | 1699996.93 | 32789.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PF | 2927.37 | 63.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PQ | 443536.59 | 221293.09 | 305785.27 | 624192.51 | 1015000 | 453460 | 754033.5625 | 1048137.6453 | 1156354.3842 | 1656990.3213 | 1623060.5204 | 1818113.8792 | 1863566.7262 | 1585561.4221 | #REF! | #REF! | #REF! | #REF! | 791677.29 | 453460 | 754033.5625 | 1048137.6453 | 1156354.3842 | 1656990.3213 | 1623060.5204 | 1818113.8792 | 1863566.7262 | 1585561.4221 | 1625200.4576
PR | 63472217.36 | 39664972.21 | 24319449.9 | 28454496.13 | 46024482 | 79265204.5 | 91556178.0625 | 106359928.5532 | 89009006.6858 | 90250359.271 | 106981067.2704 | 101878689.8896 | 112255114.1563 | 113432974.6974 | #REF! | #REF! | #REF! | #REF! | 42200551.34 | 49999477.45 | 56767295.4056 | 72652469.0912 | 93134146.4177 | 88775379.7204 | 82413439.971 | 82925278.605 | 89765407.033 | 97717532.8561 | 83246970.112
PRL | 1470607.69 | 1860811.77 | 207188.55 | 3276626 | 4020000 | 9200000 | 0 | 0 | 4415251.5625 | 7354153.3838 | 6378313.8002 | 5943428.7683 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | 6621308.6 | 9069349.65 | 3151875 | 3769117.1875 | 3311438.6719 | 3394224.6387 | 3247141.571 | 0 | 6092014.4875 | 0 | 6400422.721
PS | 5127462.17 | 4612247.21 | 4808456.14 | 11018722.87 | 9940800 | 9120450 | 6091523.75 | 5651522 | 5792810.05 | 5937630.3012 | 6086071.0588 | 6238222.8353 | 6394178.4061 | 6554032.8663 | #REF! | #REF! | #REF! | #REF! | 8812382.42 | 8943125 | 6387800 | 5955205.1562 | 6104085.2852 | 6256687.4173 | 6703027.9573 | 6870603.6562 | 7042368.7476 | 7218427.9663 | 7398888.6655
RC | 0 | 0 | 0 | 0 | 4000000 | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | #REF! | #REF! | #REF! | #REF! | 3685231.26 | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 5120338.1768
RI | 5714178.64 | 4384034.22 | 2536950.44 | 1406985.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | 359985.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SG | 19136.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SL | 5795400.72 | 7548081.11 | 3709551.81 | 4120000 | 4400000 | 4868750 | 4990468.75 | 5115230.4687 | 5243111.2305 | 5374189.0112 | 5508543.7365 | 5646257.3299 | 5787413.7632 | 5932099.1073 | #REF! | #REF! | #REF! | #REF! | 3000000 | 4868750 | 4990468.75 | 5115230.4687 | 5243111.2305 | 5374189.0112 | 5508543.7365 | 5646257.3299 | 5787413.7632 | 5932099.1073 | 6080401.5849
SP | 2530605.28 | -314236.5 | 470065.27 | 1034008.5 | 1239026 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | #REF! | #REF! | #REF! | #REF! | 1423626.78 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 1280084.5442
TM | 22516607.74 | 15948267.66 | 11744813.05 | 7845649.79 | 13859524.81 | 18721625 | 20210873.125 | 23147763.9844 | 25492558.709 | 28008010.3101 | 49402939.6159 | 57089010.6914 | 63990520.1772 | 67838236.5276 | #REF! | #REF! | #REF! | #REF! | 12910887.32 | 10987861.625 | 12785759.5437 | 12930947.2511 | 10384307.4167 | 11863573.1557 | 27629312.9901 | 36317523.5655 | 42145372.5548 | 49006219.6789 | 57527857.0728
TS | 47379651.77 | 21535716.33 | 13563079.26 | 30511887.39 | 54347180.72 | 51955200 | 52083083.3929 | 54772810.9687 | 56942395.5887 | 67195465.1718 | 64526501.4828 | 70632896.1687 | 68134308.4317 | 73084709.8643 | #REF! | #REF! | #REF! | #REF! | 38978789.98 | 26644800.175 | 35183810.1356 | 29508418.4609 | 37685827.8053 | 38913088.3701 | 33563267.0632 | 35150032.0788 | 40293193.0221 | 45028378.8129 | 52173045.8101
UR | 7082081.57 | 9523549.7 | 9019850.87 | 26952400.4014 | 33939845.5741 | 45068788.75 | 44256646.2206 | 45265989.3014 | 46558252.64 | 48607408.0335 | 49896500.4959 | 51211713.2663 | 52561847.3889 | 54019786.3161 | #REF! | #REF! | #REF! | #REF! | 27120000.008 | 22200527.275 | 15339844.6781 | 12662926.4048 | 12204412.0874 | 12223359.836 | 12528943.8319 | 12842167.4276 | 13163221.6133 | 13492302.1537 | 13829609.7075
SW | 6126287.18 | 4148553.29 | 3276845.76 | 2862677.78 | 3277639.0026 | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | #REF! | #REF! | #REF! | #REF! | 3277485.76 | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | 10475160.5735
OH | 74576259.2666 | 62325137.79 | 50381358.71 | 75239328.1381 | 73255146 | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | #REF! | #REF! | #REF! | #REF! | 66922514.26 | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | 99922071.8932
| 335066142.0166 | 241396274.29 | 191025733.88 | 293114362.5465 | 354801361.2523 | 420211887.8419 | 426026261.9345 | 454783837.1256 | 454485869.0457 | 479581117.5015 | 550412671.2467 | 581549575.092 | 613523377.8308 | 638224078.3653 | #REF! | #REF! | #REF! | #REF! | 317155911.5635 | 317758657.1169 | 321541702.7441 | 337448150.0039 | 367778105.8238 | 374863369.0021 | 390437907.9489 | 411814011.2709 | 456529451.1034 | 494010464.2192 | 522193228.5791
|  | Cur Reg (5yrs) |  | Next Reg (5yrs) |  | Total (9yrs) | [5 empty] | Cur Reg Diff (5yrs) | Next Reg Diff (5yrs) | Total Diff (9yrs) | PIP SRP | PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL
|  | Diff $M | Diff % | Diff $M | Diff % | Diff $M | Diff % | PIP SRP | PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL |  | Cust Conn | #REF! | -206330360.1327 | -414550464.4896 | 635804692.4595 | 221254227.97
AG | PIP SRP FY15: PR; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 1.521e-14%; PIP SRP FY22: 3061014.5304; PIP SRP FY23: 3061014.5304; PIP SRP FY25: PR; PIP SRP FY26: #REF!; PIP SRP FY27: -93385308.7859; PIP SRP FY28: -178094082.8444; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 927340685.1315; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 749246602.2871
AR | PIP SRP FY15: Cust Conn; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: -1416612.9137; PIP SRP FY19: -14.43%; PIP SRP FY20: -2993767.0271; PIP SRP FY21: -15.95%; PIP SRP FY22: 18773713.7429; PIP SRP FY23: 15779946.7158; PIP SRP FY25: Efficiency; PIP SRP FY26: #REF!; PIP SRP FY27: 0.52281; PIP SRP FY28: 0.52281; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 29993326.0357; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 29993326.5585
AU | PIP SRP FY15: SARP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 1398151.8306; PIP SRP FY19: 7.554%; PIP SRP FY20: 1216812.9264; PIP SRP FY21: 3.289%; PIP SRP FY22: 37000282.4729; PIP SRP FY23: 38217095.3993; PIP SRP FY25: SARP; PIP SRP FY26: #REF!; PIP SRP FY27: -216023519.4232; PIP SRP FY28: -553953353.8543; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 1972945659.0264; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 1418992305.1721
CC | PIP SRP FY15: SARP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 958240.3082; PIP SRP FY19: 10.81%; PIP SRP FY20: 3640295.0593; PIP SRP FY21: 20.5%; PIP SRP FY22: 17757895.3978; PIP SRP FY23: 21398190.4571; PIP SRP FY25: Metering; PIP SRP FY26: #REF!; PIP SRP FY27: 255708.5297; PIP SRP FY28: 389179.1855; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 16819461.8165; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 17208641.0019
DS | PIP SRP FY15: SARP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: -47791486.008; PIP SRP FY19: -11.94%; PIP SRP FY20: -185218136.254; PIP SRP FY21: -19.56%; PIP SRP FY22: 947092130.6779; PIP SRP FY23: 761873994.424; PIP SRP FY25: Power Qual; PIP SRP FY26: #REF!; PIP SRP FY27: 0; PIP SRP FY28: 0; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 11959278.4612; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 11959278.4612
DU | PIP SRP FY15: Cust Conn; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: -662674.941; PIP SRP FY21: -2.726%; PIP SRP FY22: 24313476.3407; PIP SRP FY23: 23650801.3996; PIP SRP FY25: Spares; PIP SRP FY26: #REF!; PIP SRP FY27: 0; PIP SRP FY28: 0; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 10203381.7679; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 10203381.7679
EF | PIP SRP FY15: Efficiency; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0.52281; PIP SRP FY19: 2.568e-06%; PIP SRP FY20: 0.52281; PIP SRP FY21: 1.743e-06%; PIP SRP FY22: 29993326.0357; PIP SRP FY23: 29993326.5585; PIP SRP FY25: DWP; PIP SRP FY26: #REF!; PIP SRP FY27: 0; PIP SRP FY28: 0; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 64140951.3371; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 64140951.3371
EH | PIP SRP FY15: DWP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 0%; PIP SRP FY22: 0; PIP SRP FY23: 0; PIP SRP FY25: Streetlight; PIP SRP FY26: #REF!; PIP SRP FY27: 0; PIP SRP FY28: 0; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 48466063.3973; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 48466063.3973
HV | PIP SRP FY15: DWP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 1.162e-14%; PIP SRP FY22: 64140951.3371; PIP SRP FY23: 64140951.3371; PIP SRP FY25: RWP; PIP SRP FY26: #REF!; PIP SRP FY27: 0; PIP SRP FY28: 0; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 40813527.0714; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 40813527.0714
IC | PIP SRP FY15: Cust Conn; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: -44640403.5831; PIP SRP FY19: -61.62%; PIP SRP FY20: -89719066.4502; PIP SRP FY21: -65.03%; PIP SRP FY22: 137965604.4043; PIP SRP FY23: 48246537.954; PIP SRP FY25: LV; PIP SRP FY26: #REF!; PIP SRP FY27: -215509.4691; PIP SRP FY28: -408135.2707; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 19080323.9059; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 18672188.6352
LV | PIP SRP FY15: LV; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: -215509.4691; PIP SRP FY19: -2.139%; PIP SRP FY20: -408135.2707; PIP SRP FY21: -2.139%; PIP SRP FY22: 19080323.9059; PIP SRP FY23: 18672188.6352; PIP SRP FY25: SWOH; PIP SRP FY26: #REF!; PIP SRP FY27: 0; PIP SRP FY28: 0; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 841231325.5736; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 841231325.5736
MC | PIP SRP FY15: Metering; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 255708.5297; PIP SRP FY19: 2.617%; PIP SRP FY20: 389179.1855; PIP SRP FY21: 2.314%; PIP SRP FY22: 16819461.8165; PIP SRP FY23: 17208641.0019; PIP SRP FY25: Total; PIP SRP FY26: #REF!; PIP SRP FY27: -515698988.7583; PIP SRP FY28: -1146616856.7507; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY15: 4618798675.9839; PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL FY16: 3472181819.2332
NU | PIP SRP FY15: Cust Conn; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: -5147328.9716; PIP SRP FY19: -56.67%; PIP SRP FY20: -10385728.9662; PIP SRP FY21: -60.02%; PIP SRP FY22: 17304965.5589; PIP SRP FY23: 6919236.5927
OF | PIP SRP FY15: DWP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 0%; PIP SRP FY22: 0; PIP SRP FY23: 0
PF | PIP SRP FY15: Other; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 0%; PIP SRP FY22: 0; PIP SRP FY23: 0
PQ | PIP SRP FY15: Power Qual; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 1.557e-14%; PIP SRP FY22: 11959278.4612; PIP SRP FY23: 11959278.4612
PR | PIP SRP FY15: PR; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: -95111908.9876; PIP SRP FY19: -20.84%; PIP SRP FY20: -176838096.5362; PIP SRP FY21: -19.85%; PIP SRP FY22: 890988523.0863; PIP SRP FY23: 714150426.5501
PRL | PIP SRP FY15: PR; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 1726600.2018; PIP SRP FY19: 8.234%; PIP SRP FY20: -1255986.3082; PIP SRP FY21: -3.773%; PIP SRP FY22: 33291147.5148; PIP SRP FY23: 32035161.2066
PS | PIP SRP FY15: SARP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 1052966.7574; PIP SRP FY19: 3.231%; PIP SRP FY20: 3614889.9184; PIP SRP FY21: 6.247%; PIP SRP FY22: 57866441.2677; PIP SRP FY23: 61481331.1861
RC | PIP SRP FY15: RWP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 0%; PIP SRP FY22: 40813527.0714; PIP SRP FY23: 40813527.0714
RI | PIP SRP FY15: RWP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 0%; PIP SRP FY22: 0; PIP SRP FY23: 0
SG | PIP SRP FY15: Other; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 0%; PIP SRP FY22: 0; PIP SRP FY23: 0
SL | PIP SRP FY15: Streetlight; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 1.537e-14%; PIP SRP FY22: 48466063.3973; PIP SRP FY23: 48466063.3973
SP | PIP SRP FY15: Spares; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 0%; PIP SRP FY22: 10203381.7679; PIP SRP FY23: 10203381.7679
TM | PIP SRP FY15: SARP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: -56628382.1362; PIP SRP FY19: -48.99%; PIP SRP FY20: -139850660.3589; PIP SRP FY21: -39.52%; PIP SRP FY22: 353901538.1405; PIP SRP FY23: 214050877.7816
TS | PIP SRP FY15: SARP; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: -115013010.1752; PIP SRP FY19: -40.65%; PIP SRP FY20: -237356555.1455; PIP SRP FY21: -42.44%; PIP SRP FY22: 559327371.0695; PIP SRP FY23: 321970815.924
UR | PIP SRP FY15: Cust Conn; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: -155126014.6643; PIP SRP FY19: -67.52%; PIP SRP FY20: -310789227.105; PIP SRP FY21: -71.05%; PIP SRP FY22: 437446932.4127; PIP SRP FY23: 126657705.3078
SW | PIP SRP FY15: SWOH; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 0%; PIP SRP FY22: 72633875.0416; PIP SRP FY23: 72633875.0416
OH | PIP SRP FY15: SWOH; PIP SRP FY16: #REF!; PIP SRP FY17: 0%; PIP SRP FY18: 0; PIP SRP FY19: 0%; PIP SRP FY20: 0; PIP SRP FY21: 0%; PIP SRP FY22: 768597450.532; PIP SRP FY23: 768597450.532
| FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29
PIP SRP ($Nom) | 420211887.8419 | 426026261.9345 | 454783837.1256 | 454485869.0457 | 479581117.5015 | 550412671.2467 | 581549575.092 | 613523377.8308 | 638224078.3653
PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL ($Nom) | 317758657.1169 | 321541702.7441 | 337448150.0039 | 367778105.8238 | 374863369.0021 | 390437907.9489 | 411814011.2709 | 456529451.1034 | 494010464.2192 | 522193228.5791
PIP SRP ($Real) | 409962817.4067 | 405497929.2654 | 422312003.2507 | 411741766.1143 | 423879826.9602 | 474619121.4009 | 489237440.0024 | 503547208.4683 | 511044120.7109
PIP Resubmission - v2 with Escalator - Revised Proposal - FINAL ($Real) | 310008445.9677 | 306048021.6482 | 313354153.3096 | 333188812.1143 | 331324595.9602 | 336673384.3766 | 346444811.0024 | 374694981.4683 | 395568189.7109 | 407936515.558

## SRP (hidden)
ID | Code | Description | FY15 (N) | FY16 (N) | FY17 (N) | FY18 (N) | FY19 (N) | FY20 (N) | FY21 (N) | FY22 (N) | FY23 (N) | FY24 (N) | FY25 (N) | FY26 (N) | FY27 (N) | FY28 (N) | 9 Yr Tot
AG | AG | Automation - operational/capacity risk | 0 | 0 | 0 | 0 | 300000 | 307500 | 315187.5 | 323067.1875 | 331143.8672 | 339422.4639 | 347908.0255 | 356605.7261 | 365520.8693 | 374658.891 | 3061014.5304
AR | AR | Asset relocation | 2476817.3 | 1549055.28 | 1518424.87 | 1660155.1572 | 1674562.9105 | 1863202.975 | 1901068.115 | 1955611.8372 | 2013924.28 | 2080036.2976 | 2141221.9769 | 2204145.5211 | 2268923.2782 | 2345579.462 | 18773713.7429
AU002 | AU | Transmission substation SCADA upgrade | 277011.96 | 822.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AU004 | AU | Substation SCADA RTU replacement | 105711.33 | 1042816.85 | 1057915.43 | 2052335 | 1044144 | 1886000 | 1933150 | 1981478.75 | 2031015.7187 | 2081791.1117 | 2133835.8895 | 2187181.7867 | 2241861.3314 | 2297907.8647 | 18774222.4529
AU008 | AU | Western Sydney Ramtel SCADA upgrades | 0 | 22540.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AU013 | AU | SCADA master station development software | 1528226.6 | 517960.21 | 772964.35 | 1016366 | 1000000 | 2050000 | 2101250 | 1076890.625 | 1103812.8906 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | 18226060.0201
AU014 | AU | SCADA substation refurbishments | 745.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AU016 | AU | PM121 (MD1000) MD3 to DNP3 conversion | 18102.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AU017 | AU | AFIC availability and SCADA control | 37463.72 | 40937.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CC002 | CC | Communications development SCADA | 718551.66 | 577121.69 | 834883.25 | 1108931 | 750000 | 512500 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | 5101690.8839
CC007 | CC | SCADA radio repeaters | 418374.49 | 531890.9 | 614658.16 | 721201 | 870000 | 713400 | 731235 | 749515.875 | 768253.7719 | 787460.1162 | 807146.6191 | 827325.2846 | 848008.4167 | 869208.6271 | 7101553.7104
CC020 | CC | Microwave refurbishment and extension | 663950.05 | 528887.73 | 1163305.43 | 849331 | 550000 | 461250 | 472781.25 | 484600.7812 | 496715.8008 | 509133.6958 | 753800.7218 | 772645.7399 | 791961.8834 | 811760.9305 | 5554650.8034
DS002 | DS | Pole substation refurbishment | 1194567.82 | 1096682.32 | 425751.6 | 300000 | 735000 | 753375 | 772209.375 | 791514.6094 | 869252.6514 | 950382.8988 | 1035026.3758 | 1123308.0372 | 1151390.7381 | 1180175.5066 | 8626635.1923
DS003 | DS | Distribution substation refurbishment | 0 | 0 | 2533.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS004 | DS | Distribution mains refurbishment | 0 | 0 | 234418.69 | 23869.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS005 | DS | Distribution pole replacement | 12600819.11 | 8786150.41 | 9900636.96 | 15100000 | 10800000 | 11613250 | 12712562.5 | 13859582.3437 | 15056007.8281 | 16303592.3478 | 17604146.0885 | 19874825.8013 | 21309866.6774 | 21842613.3444 | 150176446.9313
DS006 | DS | LV CONSAC cable replacement | 7472708.55 | 5379508.07 | 1565780.47 | 4240174.3128 | 6000000 | 7123750 | 9140437.5 | 10499683.5937 | 11645225.9961 | 11936356.646 | 12234765.5621 | 12540634.7012 | 12854150.5687 | 13175504.3329 | 101150508.9009
DS007 | DS | Service wire replacement program | 11238777.88 | 10839341 | 14362477.09 | 15000000 | 9167401 | 9430000 | 9770812.5 | 10015082.8125 | 10431031.8164 | 11087800.4863 | 11944842.2076 | 13432149.0165 | 14986355.6394 | 16110332.3123 | 107208406.791
DS008 | DS | Traffic black spot remediation | 1174528.22 | 594868.19 | 926136.31 | 2220000 | 1700000 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 10203381.7679
DS009 | DS | Reliability focused distribution mains renewal | 1176436.2 | 1061805.85 | 18800.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS011 | DS | HV distribution steel mains replacement | 7430280.2 | 6877196.79 | 7175942.45 | 4528898 | 4800000 | 4920000 | 5043000 | 5169075 | 6181352.1875 | 6335885.9922 | 7422037.8766 | 7607588.8235 | 7797778.5441 | 7992723.0077 | 58469441.4315
DS012 | DS | HV porcelain expulsion drop-out fuse replacement program | 188903.27 | 734645.81 | 849197.61 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS014 | DS | LV cable network renewal | 0 | 0 | 0 | 7993.28 | 0 | 666250 | 2048718.75 | 2519924.0625 | 2582922.1641 | 1470830.6768 | 1507601.4437 | 1545291.4798 | 1583923.7668 | 1623521.8609 | 15548984.2045
DS301 | DS | Ground substation refurbishment program | 2853380.77 | 1319331.04 | 562755.18 | 1244873 | 510000 | 522750 | 535818.75 | 915357.0312 | 938240.957 | 1154036.3771 | 1478609.1082 | 1515574.3359 | 1553463.6943 | 1592300.2867 | 10206150.5406
DS302 | DS | Distribution transformer replacement program | 2210560.84 | 1592198.98 | 1382088.37 | 1000000 | 1170000 | 1199250 | 1229231.25 | 1259962.0312 | 1614326.3525 | 1654684.5114 | 2035261.949 | 2086143.4977 | 2138297.0851 | 2191754.5123 | 15408911.1892
DS305 | DS | Compact LV switchgear replacement | 97201.38 | 83054.99 | 84530.85 | 80000 | 508400 | 512500 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | 5101690.8839
DS307 | DS | Holec MD4 epoxy switchgear replacement | 1999771.21 | 553962.32 | 366358.18 | 3902000 | 4035224.6688 | 6098750 | 6618937.5 | 8480513.6719 | 8692526.5137 | 8909839.6765 | 9132585.6684 | 9360900.3101 | 9594922.8179 | 9834795.8883 | 76723772.0469
DS308 | DS | HV RGB12 switchgear replacement | 1196553.17 | 732215.76 | 95377.78 | 507000 | 598000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS312 | DS | Miscellaneous substation renewal expenditure | 321827.29 | 385972.26 | 554524.67 | 615000 | 750000 | 3587500 | 3677187.5 | 3769117.1875 | 3863345.1172 | 3959928.7451 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 38119658.7072
DS313 | DS | Padmount substation fire risk mitigation | 458938.22 | 347407.83 | 197107.24 | 2344.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS315 | DS | Low voltage switchgear replacement | 0 | 0 | 378564.79 | 1686026 | 354000 | 725700 | 743842.5 | 762438.5625 | 781499.5266 | 801037.0147 | 821062.9401 | 841589.5136 | 862629.2514 | 884194.9827 | 7223994.2916
DS316 | DS | HV oil switchgear replacement program | 0 | 0 | 418848.02 | 1441000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS317 | DS | Future distribution substation renewals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10669179.4476 | 16284994.8253 | 22418613.3142 | 25227031.9929 | 74599819.5799
DS318 | DS | Distribution substation earthing refurbishment | 0 | 0 | 0 | 0 | 676000 | 276750 | 283668.75 | 290760.4687 | 298029.4805 | 305480.2175 | 313117.2229 | 320945.1535 | 328968.7823 | 337193.0019 | 2754913.0773
DS404 | DS | Cast iron UGOH replacement program | 2104335.27 | 1136670.92 | 344608.13 | 1270.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS405 | DS | Air break switch replacement | 3413480.72 | 4212084.45 | 3094169.76 | 3398754 | 6146400.5487 | 3782250 | 3876806.25 | 3973726.4062 | 4073069.5664 | 4174896.3056 | 4279268.7132 | 4386250.431 | 4495906.6918 | 4608304.3591 | 37650478.7234
DS409 | DS | Miscellaneous mains renewal expenditure | 1834674.87 | 867253.43 | 893526.11 | 12000000 | 750000 | 1127500 | 1208218.75 | 1238424.2187 | 1324575.4687 | 1357689.8555 | 1623570.7855 | 1664160.0551 | 1705764.0565 | 1748408.1579 | 12998311.348
DS410 | DS | Capital works for compliance to NSW Maritime Waterways - crossing codes | 721397.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS411 | DS | Capital works for compliance to NSW Maritime Waterways - signage replacement and drawings update | 300196.15 | 1197.96 | 40118.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS413 | DS | Low mains remediation | 2487329.41 | 4924343.12 | 2726211.68 | 2300000 | 1800000 | 1665625 | 1707265.625 | 1749947.2656 | 1793695.9473 | 1838538.3459 | 1130701.0828 | 1158968.6098 | 1187942.8251 | 1217641.3957 | 13450326.0972
DS414 | DS | Copper distribution mains replacement | 0 | 0 | 0 | 0 | 5600000 | 1476000 | 2521500 | 2584537.5 | 2649150.9375 | 2715379.7109 | 2783264.2037 | 2852845.8088 | 2924166.954 | 2997271.1279 | 23504116.2429
DS415 | DS | LV mains replacement | 0 | 79093.29 | 237.26 | 0 | 550000 | 902000 | 1155687.5 | 1303037.6562 | 1335613.5977 | 1244549.0342 | 1275662.76 | 1307554.329 | 1340243.1873 | 1373749.2669 | 11238097.3314
DS416 | DS | Asbestos service fuse replacement | 0 | 0 | 66327.41 | 5684.21 | 261000 | 267525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267525
DS417 | DS | Distribution access track reconstruction | 0 | 0 | 0 | 0 | 500000 | 451000 | 1479280 | 2037477.0625 | 2088413.9891 | 0 | 0 | 0 | 0 | 0 | 6056171.0516
DS418 | DS | Pole top structure/hardware refurbishment | 0 | 0 | 0 | 0 | 5000000 | 10250000 | 9455625 | 9692015.625 | 8830503.125 | 9051265.7031 | 9277547.3457 | 9509486.0293 | 9747223.1801 | 9990903.7596 | 85804569.7678
DS420 | DS | Future distribution feeder refurbishment works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10669179.4476 | 16284994.8253 | 22418613.3142 | 25227031.9929 | 74599819.5799
DU | DU | Duct installation RMS road works | 0 | 0 | 0 | 0 | 1955226.0176 | 2206549.275 | 2318255.5431 | 2435617.5261 | 2558919.7528 | 2688465.7724 | 2824569.0042 | 2967563.4935 | 3117795.5425 | 3195740.4311 | 24313476.3407
EF001 | EF | Distribution management system | 65196.34 | 112081.01 | 816411 | 2213234.13 | 12000000 | 8800000 | 3800000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 12700000
EF002 | EF | Technology pilots | 230567.5 | 417554.49 | 414250 | 661579.57 | 552599 | 512500 | 525312.5 | 2153781.25 | 2207625.7812 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | 17293326.0357
EF003 | EF | Battery energy storage system pilot | 0 | 1658.56 | 90668 | 1129787.29 | 1692215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EH | EH | Dist environmental enhancement program | 190546.42 | 770.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HVW | HV | HV development works | 11023877.7 | 3151822.81 | 3840236.18 | 4480000 | 7057544 | 6970865.1 | 7462655.5644 | 7158488.2801 | 6926477.7679 | 6728594.3887 | 6958160.5093 | 7132114.522 | 7310417.3851 | 7493177.8197 | 64140951.3371
IC | IC | Industrial & commercial | 5231966.27 | 4695952.82 | 3865150.26 | 8725596.4249 | 10000000 | 14182418.65 | 13958796.0144 | 14282150.9943 | 14690991.2548 | 15327508.38 | 15736695.2562 | 16154393.9215 | 16583267.581 | 17049382.3521 | 137965604.4043
LV001 | LV | Overloaded distribution sub uprates | 12993.06 | 1232.26 | 67276.15 | 15284.76 | 120000 | 123000 | 126075 | 129226.875 | 132457.5469 | 135768.9855 | 139163.2102 | 142642.2904 | 146208.3477 | 149863.5564 | 1224405.8121
LV002 | LV | Quality of supply reactive projects | 521975.39 | 380645.43 | 380046.2 | 650000 | 500000 | 512500 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | 5101690.8839
LV003 | LV | LV planning reactive projects | 837877.25 | 609078.78 | 510717.83 | 800000 | 1000000 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 10203381.7679
LV004 | LV | Low voltage system augmentations | 138232.19 | 131741.51 | 178945.75 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LV005 | LV | Dsub monitoring & LV feeder monitoring for solar PV | 78685.53 | 93305.4 | 112282.65 | 166938 | 250000 | 256250 | 262656.25 | 269222.6562 | 275953.2227 | 282852.0532 | 289923.3546 | 297171.4384 | 304600.7244 | 312215.7425 | 2550845.442
MC101 | MC | Meters - Growth | 1470352.76 | 1330593.74 | 1752673.44 | 565255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MC102 | MC | Relays - growth | 159852.73 | 129121.81 | 33376.73 | 102991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MC104 | MC | Meters - renewal | 658594.28 | 660314.34 | 176748.65 | 274637 | 25000 | 25625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25625
MC105 | MC | Relays - renewal | 110373.7 | 190069.84 | 184700.23 | 230000 | 300000 | 981523.6 | 953111.2406 | 922664.811 | 890099.2616 | 855329.9006 | 818265.7596 | 778813.8303 | 736877.8884 | 692358.3908 | 7629044.6829
MC106 | MC | Labour (meter/relay renewal) | 806560.26 | 267694.17 | 61092.23 | 2996.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MC107 | MC | Test equipment | 0 | 0 | 0 | 80000 | 80000 | 82000 | 84050 | 86151.25 | 88305.0312 | 96169.6981 | 98573.9405 | 101038.2891 | 103564.2463 | 106153.3524 | 846005.8077
MC108 | MC | Smart metering pilot | 16123.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MC109 | MC | Demand management technology | 0 | 0 | 0 | 300000 | 500000 | 1435000 | 787968.75 | 807667.9687 | 827859.668 | 848556.1597 | 869770.0637 | 891514.3153 | 913802.1731 | 936647.2275 | 8318786.3259
MC110 | MC | Labour meter renewal | 0 | 669856.45 | 110255.72 | 175795.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MC111 | MC | Labour relay renewal | 0 | 11844.88 | 3039.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MC112 | MC | Neutral integrity monitoring | 0 | 3560.45 | 812381.64 | 106662.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NU | NU | Non urban extension | 833787.12 | 629075.45 | 642906.63 | 1123423.0321 | 850000 | 1774809.025 | 1750945.3594 | 1792149.5323 | 1843593.809 | 1922175.4353 | 1973837.6274 | 2026602.2283 | 2080788.4684 | 2140064.0739 | 17304965.5589
OFP | OF | Overloaded feeders (compliance) | 1699996.93 | 32789.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OH | OH | Capitalised Overheads | 74576259.2666 | 62325137.79 | 50381358.71 | 75239328.1381 | 73255146 | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | 768597450.532
PF | PF | Power factor | 2927.37 | 63.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PQ001 | PQ | Permanent power quality monitoring | 383521.09 | 221293.09 | 305785.27 | 624192.51 | 615000 | 102500 | 105062.5 | 107689.0625 | 110381.2891 | 113140.8213 | 115969.3418 | 118868.5754 | 121840.2898 | 124886.297 | 1020338.1768
PQ003 | PQ | PQ surveying | 60015.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PQ004 | PQ | Power quality monitoring replacement | 0 | 0 | 0 | 0 | 400000 | 350960 | 648971.0625 | 940448.5828 | 1045973.0952 | 1543849.5 | 1507091.1786 | 1699245.3038 | 1741726.4364 | 1460675.1251 | 10938940.2844
PR017 | PR | Werrington ZS rebuild to 132kV | 0 | 34009.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR035 | PR | Baulkham Hills TS 11kV supply | 2947.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR044 | PR | West Liverpool ZS (Hoxton Park ZS rebuild) | 26441.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR052 | PR | Penrith TS transformer and busbar augment | 1278241.35 | 811326.13 | 111412.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR054 | PR | Quakers Hill ZS augment (132kV bar + 1st 132/11kV tfr) | 16166.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR059 | PR | ELTS 132kV busbar & substation works | 130715.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR060 | PR | WLTS-ELTS first 132kV cable links | 562823.55 | 54937.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR061 | PR | Russell Vale ZS augment | 610289.86 | 210376.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR070 | PR | Caddens ZS establishment and feeders | 227677.03 | 113264.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR073 | PR | Campbelltown 66kV busbar & line to Ambarvale | 430.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR081 | PR | Collimore Park ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6628111.7625 | 13587629.113 | 13927319.8409 | 34143060.7163
PR090 | PR | Doonside 132kV/11kV ZS rebuild | 1202721.24 | 1035013.33 | 142087.35 | 47751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR091 | PR | West Parramatta CBD 132kV/11kV ZS establishment | 3986595.42 | 942338.23 | 84498.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR096 | PR | Berry ZS LDC CT's | 4475.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR102 | PR | Kemps Creek/Luddenham capacity uprate | 887102.28 | 4991.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR110 | PR | Edmondson Park ZS establishment | 8617104.31 | 3323306.31 | 138426.17 | 1457484.54 | 2187000 | 1935000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1941000
PR113 | PR | Augment feeder 308 Nepean to Douglas Park | 2897.16 | 0 | 0 | 0 | 518000 | 6223800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6223800
PR123 | PR | Connection works associated with Tomerong/Bamarang BSP | 749604.79 | 2942.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR126 | PR | Chipping Norton 33/11kV ZS establishment | 972016.95 | 155.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR128 | PR | Nepean ZS establishment | 322475.42 | 241217.95 | 15533.5 | 19739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR144 | PR | Sherwood ZS augment | 28868.17 | 2939.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR148 | PR | Dapto ZS 3rd transformer & 33kV bus section CB's | 15792.63 | -146.91 | 1589.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR149 | PR | Gerringong ZS augment | 75091.98 | 76573.96 | 4206.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR157 | PR | Richmond ZS rebuild | 2933160.9 | 1232616.01 | 312351.94 | 11289.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR170 | PR | Holsworthy 33/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4852215.2465 | 9947041.2553 | 10195717.2867 | 24994973.7884
PR172 | PR | Parklea ZS 3rd transformer | 89393.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR176 | PR | Cheriton Av 132/11kV ZS establishment | 9504.78 | 5442.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR183 | PR | Schofields ZS establishment | 9200.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR184 | PR | Box Hill 22kV conversion | 0 | 131759.71 | 3637954.23 | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR186 | PR | Glenorie ZS establishment | 715666.26 | 49326.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR190 | PR | Eschol Park ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5001989.6514 | 10254078.7854 | 10510430.7551 | 25766499.192
PR192 | PR | Feeder 7158 augment from Albion Park to Warilla | 10546.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR200 | PR | Cordeaux/Figtree 33/11kV ZS establishment | 33785.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR204 | PR | Canley Vale subtransmission network upgrade | 1009051.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR206 | PR | Cawdor 66/11kV ZS establishment | 45057.39 | 4268.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR208 | PR | Abbotsbury 132/11kV ZS establishment | 2248995.89 | 562165.02 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR244 | PR | Bellavista ZS establishment with two 132kV cable links | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR248 | PRL | Penrith Lakes ZS site acquisition | 0 | 36411.19 | 76.42 | 0 | 0 | 0 | 0 | 0 | 1103812.8906 | 0 | 0 | 0 | 0 | 0 | 1103812.8906
PR249 | PR | Establish Penrith Lakes 33/11kV Zone Substation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4084383.6485 | 16745972.959 | 0 | 0 | 0 | 20830356.6075
PR255 | PR | Line works associated with Oran Park | 3223784.23 | 2446482.21 | 441808.38 | 55100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR257 | PRL | Menangle Park 66/11kV ZS site purchase | 10947 | 0 | 0 | 1036355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR258 | PR | Menangle Park 66/11kV ZS establishment | 0 | 0 | 0 | 466666.68 | 3800000 | 3587500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3587500
PR261 | PR | Huntingwood ZS establishment | 247800.45 | 595.4 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR270 | PR | West Epping Zone Substation establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7693174.1977 | 15771007.1054 | 16165282.283 | 39629463.5861
PR278 | PR | Kemps Creek new BSP associated works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607382.2007 | 2672566.7557 | 5279948.9564
PR280 | PR | Wilton Park 66/11kV ZS establishment & 66kV line works | 36059.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR288 | PR | Holroyd 330/132kV BSP associated works | 30305.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR291 | PRL | Marsden Park Zone Substation site acquisition | 167362 | 2565.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR292 | PR | South Marsden Park (industrial) 132/11kV ZS establishment | 0 | 1254.28 | 75771.95 | 4482575.33 | 14500000 | 9800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9800000
PR303 | PR | Mittagong ZS transformer augment | 290876.86 | 9272.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR308 | PR | Granville ZS & Camellia TS rebuild | 2244308.6 | 176746.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR311 | PR | Quakers Hill ZS 2nd 132kV feeder | 5811.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR326 | PR | Casula 33/11kV ZS establishment with link to LTS or WLTS | 450800.3 | 45063.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR329 | PRL | Box Hill site purchase | 5576.94 | 55805.15 | 48347.5 | 340271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR339 | PR | North Eastern Creek ZS establishment | 106678.71 | 791.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR342 | PR | Jordan Springs establishment | 3088505.17 | 220528.62 | 9502.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR343 | PR | Wetherill Park ZS augmentation | 116.2 | 25300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR353 | PR | Shoalhaven Feeder 7510/7511 Augment | -179847.73 | 35304.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR384 | PR | Glossodia ZS transformer augments | 1877.28 | 1263.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR406 | PR | Tomerong ZS establishment | 653015.06 | 475721.94 | 100941.3 | 145461.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR408 | PR | Oran Park (permanent) ZS establishment | 5739431.13 | 2651529.48 | 1227831.08 | 140757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR413 | PR | Windsor transformer | 1083353.77 | 173438.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR423 | PR | Maryland ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 4377744.25 | 8974375.7125 | 9198735.1053 | 0 | 0 | 0 | 0 | 0 | 22550855.0678
PR424 | PRL | Austral ZS site purchase | 0 | 8000 | 4500 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR425 | PR | Austral ZS establishment (interim initially) | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
PR426 | PRL | Leppington North ZS site purchase (strategic) | 293492 | 1717024.29 | 10133.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR427 | PR | Leppington North ZS establishment | 654.93 | 83359.47 | 556871.78 | 10077970.73 | 10000000 | 2984220 | 298995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3283215
PR429 | PR | Leppington South ZS establishment (interim initially) | 2005514.51 | 110434.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR430 | PRL | North Rossmore ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3311438.6719 | 0 | 0 | 0 | 0 | 0 | 3311438.6719
PR432 | PRL | Rossmore ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3394224.6387 | 0 | 0 | 0 | 0 | 3394224.6387
PR433 | PR | Rossmore ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12488629.6995 | 12488629.6995
PR434 | PRL | Catherine Fields North land purchase | 928168.55 | 41006.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR435 | PR | Catherine Fields North ZS establishment (interim) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6554587.1997 | 13436903.7595 | 13772826.3535 | 0 | 33764317.3127
PR436 | PRL | Catherine Fields ZS site purchase | 5000 | 0 | 133942.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR437 | PR | Catherine Fields 11kV feeder works | 0 | 298.73 | 57341.43 | 3240300 | 530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR438 | PRL | North Bringelly ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3959928.7451 | 0 | 0 | 0 | 0 | 3959928.7451
PR439 | PR | North Bringelly ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5253991.0312 | 10770681.614 | 11039948.6543 | 27064621.2995
PR440 | PR | Feeder 443 and 458/1 augmentation and Cattai rebuild | 2027627.62 | 491798.52 | 327531.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR444 | PR | Culburra Beach development (33kV fdr and single transformer ZS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4465446.6194 | 4577082.7849 | 9042529.4042
PR479 | PR | Far South Coast 132kV voltage constraints | 203908.9 | 2741836.51 | 1863329.51 | 390833.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR487 | PR | Connection works associated with Macarthur BSP | 3951387.23 | 1778945.91 | 269677.92 | 185998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR499 | PR | Southpipe (Oakdale Estate) ZS 132/11kV establishment | 0 | 0 | 0 | 0 | 0 | 5588300 | 13557265 | 9588634.125 | 0 | 0 | 0 | 0 | 0 | 0 | 28734199.125
PR517 | PR | Installation of OPGW on Feeders 98W and 98F | 589034.4 | 8731.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR521 | PR | Culburra ZS fdr duplication & provision for rural ZS's | 2064644.09 | 246337.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR559 | PR | Mamre ZS transformer augment and 11kV busbar extension | 104579.24 | 117039.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR563 | PR | Shoalhaven TS 132kV capacitor install | 418.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR595 | PR | The Oaks ZS establishment | 611.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR596 | PR | Marsden Park (residential) 132/11kV ZS establishment - stage 1 | 6467745.66 | 5295506.04 | 4681329.14 | 307213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR599 | PRL | Penrith CBD ZS site purchase | 0 | 0 | 0 | 100000 | 3720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR602 | PRL | Riverstone West site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5943428.7683 | 0 | 0 | 5943428.7683
PR603 | PRL | Eschol Park ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3479080.2546 | 0 | 0 | 0 | 3479080.2546
PR620 | PR | West Dapto ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2656689.1719 | 5446212.8023 | 5582368.1224 | 0 | 0 | 0 | 0 | 13685270.0966
PR632 | PR | Mt Druitt TS automation scheme | 2035.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR642 | PR | Auxiliary transformer at Shoalhaven TS | 82911.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR643 | PR | Fibre works at Carlingford TS for Ausgrid | 9130.74 | 55092.28 | 168497.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR652 | PRL | Purchase of additional land Lawson TS | 60061.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR653 | PR | Avondale (South West Dapto) 132/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5943428.7683 | 6092014.4875 | 6244314.8497 | 18279758.1056
PR656 | PR | Leppington South ZS establishment (permanent) | 0 | 0 | 0 | 666666.68 | 10900000 | 12500000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500000
PR657 | PR | Calderwood ZS establishment (interim initially) | 0 | 0 | 0 | 0 | 200000 | 8047275 | 8248456.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16295731.875
PR659 | PRL | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2899233.5455 | 0 | 0 | 0 | 2899233.5455
PR660 | PR | Install 66kV iso Douglas Pk/Appin/Wcliff | 603.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR673 | PR | Liverpool ZS 11kV switchboard extension & distribution works | 97623.61 | 1753205.69 | 2940893.21 | 1254766 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR674 | PR | South Marsden Park (stage 1) | 2002339.83 | 11789971.83 | 2957288.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR677 | PR | South Penrith Zone Substation | 0 | 0 | 1406.48 | 0 | 0 | 4730375 | 13899768.75 | 11016591.0937 | 0 | 0 | 0 | 0 | 0 | 0 | 29646734.8438
PR698 | PR | Marsden Park (residential) 132/11kV ZS - stage 2 | 0 | 0 | 0 | 0 | 0 | 3549062.5 | 5739039.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9288101.5625
PR700 | PR | Riverstone east ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4446481.3906 | 9115286.8508 | 9343169.0221 | 0 | 0 | 0 | 0 | 22904937.2635
PR701 | PR | Dapto 33kV feeder constraints | 1235.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR702 | PR | Penrith ZS 11kV transformer cable constraints | 0 | 5479.9 | 430900.85 | 964883 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR703 | PRL | Riverstone East site purchase | 0 | 0 | 0 | 0 | 0 | 6150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6150000
PR704 | PRL | Oakdale (Southpipe) site purchase | 0 | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR707 | PR | 132kV ducts Bringelly Rd | 3691.43 | 18434.02 | 328477.84 | 1063563.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR709 | PR | Feeder 230 undergrounding | 0 | 44863.22 | 2677569.92 | 12440.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR710 | PR | Feeder 868 rebuild & rearrangement South32 | 0 | 0 | 118718.51 | 1392160 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR713 | PR | Box Hill 132/22kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 5088100 | 16734355 | 14998932.625 | 0 | 0 | 0 | 0 | 0 | 0 | 36821387.625
PR715 | PR | Nepean TS constraints | 0 | 13921.51 | 282849.06 | 136411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR716 | PR | Box Hill ZS - 132kV ducts Old Pitt Town | 0 | 3535.15 | 326330.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR717 | PRL | Acquire improved site for West Dapto ZS | 0 | 0 | 0 | 0 | 0 | 2050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050000
PR722 | PR | Camellia TS connection works for Ausgrid | 0 | 0 | 13420.09 | 136773 | 187082 | 31847 | 100571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132418
PR723 | PR | Supply to Luddenham Science Park | 0 | 4063.43 | 7491.03 | 0 | 0 | 6256600 | 19129780 | 17454243.25 | 0 | 0 | 0 | 0 | 0 | 0 | 42840623.25
PR724 | PR | Establish Mt Gilead ZS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4150336.4687 | 8508189.7609 | 8720894.505 | 0 | 0 | 0 | 0 | 21379420.7346
PR727 | PRL | Luddenham ZS site purchase | 0 | 0 | 10188 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
PR728 | PR | Western Sydney Employment Lands ZS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5057078.375 | 10367010.6687 | 10626185.9355 | 0 | 0 | 0 | 0 | 26050274.9792
PR729 | PR | Cheriton Avenue 3rd transformer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8891369.4374 | 0 | 0 | 8891369.4374
PR730 | PR | Feeder 7018 constraints | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR732 | PR | Feeder 214/215 contraints | 0 | 0 | 0 | 0 | 0 | 4843125 | 4964203.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9807328.125
PR733 | PR | Bringelly ZS augmentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4914026.9057 | 10073755.1566 | 10325599.0355 | 25313381.0978
PR735 | PR | Termeil area distribution works | 0 | 0 | 1708.99 | 700000.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR739 | PR | South Gilead (South Campbelltown) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4360447.2525 | 8938916.8676 | 9162389.7893 | 0 | 0 | 22461753.9093
PR740 | PR | AFIC upgrade Minto, Prospect, Kingswood | 0 | 0 | 0 | 0 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR741 | PR | Western Sydney Airport 132kV supply | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21980594.3876 | 22530109.2473 | 23093361.9785 | 0 | 0 | 0 | 0 | 67604065.6134
PR742 | PR | North Bomaderry ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3975880.1875 | 8150554.3844 | 8354318.244 | 0 | 0 | 0 | 0 | 20480752.8159
PR744 | PR | Termeil ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4384896.708 | 4494519.1257 | 0 | 0 | 0 | 0 | 8879415.8337
PR745 | PR | Austral Permanent ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13098737.1587 | 13426205.5877 | 0 | 0 | 26524942.7464
PR746 | PR | Sydney University - Western Sydney Employment Lands ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14913251.4655 | 15286082.7522 | 30199334.2177
PR748 | PR | Establish permanent Catherine Park ZS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060091.7656 | 4224291.9324 | 4329899.2307 | 0 | 0 | 0 | 0 | 10614282.9288
PR749 | PR | Nepean ZS augmentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8236651.7898 | 0 | 0 | 0 | 8236651.7898
PR750 | PR | Feeder 512 augmentation | 0 | 0 | 0 | 991692.25 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR751 | PR | Parklea ZS to Bella Vista ZS load transfer | 0 | 0 | 0 | 0 | 0 | 4100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100000
PR752 | PR | Kemps Creek 132kV conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24077554.7489 | 10576925.8361 | 0 | 0 | 34654480.5851
PR754 | PR | Augment Westmead Zone Substation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7083719.2256 | 7260812.2062 | 7004548.246 | 0 | 0 | 0 | 21349079.6778
PR755 | PR | Narellan ZS busbar augmentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8442568.0846 | 0 | 0 | 0 | 8442568.0846
PR756 | PR | Luddenham ZS augmentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13881530.216 | 6097957.9163 | 0 | 0 | 19979488.1323
PS002 | PS | Replacement of ASEA RI O/C relays | 0 | 0 | 219.76 | 102331.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS004 | PS | Underfrequency load shed program | 156.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS008 | PS | Substation protection relay refurbishment | 3039467.82 | 2094580.72 | 1138404.34 | 3769753 | 3600000 | 4323450 | 4431536.25 | 4542324.6562 | 4655882.7727 | 4772279.842 | 4891586.838 | 5013876.509 | 5139223.4217 | 5267704.0072 | 43037864.2968
PS009 | PS | Installation of SEF relays | 619270.33 | 1132982.57 | 195906.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS010 | PS | Protection refurbishment (interfacing feeders) | 1137045.31 | 557126.12 | 95849.8 | 149093.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS011 | PS | Protection refurbishment (miscellaneous) | 315234.23 | 174607.22 | 15871.24 | 463447.41 | 895000 | 717500 | 735437.5 | 753823.4375 | 772669.0234 | 791985.749 | 811785.3927 | 832080.0276 | 852882.0283 | 874204.079 | 7142367.2375
PS012 | PS | Distribution feeder safety improvement | 16288.18 | 652950.58 | 3362204.29 | 6534097 | 4615800 | 3177500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3177500
PS013 | PS | Feeder differential relay replacement | 0 | 0 | 0 | 0 | 330000 | 338250 | 346706.25 | 355373.9062 | 364258.2539 | 373364.7103 | 382698.828 | 392266.2987 | 402072.9562 | 412124.7801 | 3367115.9834
PS014 | PS | Under frequency load shedding | 0 | 0 | 0 | 0 | 500000 | 563750 | 577843.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141593.75
RC | RC | Reliability compliance | 0 | 0 | 0 | 0 | 4000000 | 4100000 | 4202500 | 4307562.5 | 4415251.5625 | 4525632.8516 | 4638773.6729 | 4754743.0147 | 4873611.59 | 4995451.8798 | 40813527.0714
RI | RI | Reliability enhancement | 5714178.64 | 4384034.22 | 2536950.44 | 1406985.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SG001 | SG | Smart grid fibre rollout & trial | 14159.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SG002 | SG | Smart meter rollout | 4977.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SL001 | SL | Streetlighting growth | 871598.59 | 979246.73 | 1311152.31 | 1420000 | 1400000 | 1793750 | 1838593.75 | 1884558.5937 | 1931672.5586 | 1979964.3726 | 2029463.4819 | 2080200.0689 | 2132205.0706 | 2185510.1974 | 17855918.0937
SL002 | SL | Streetlighting refurbishment | 4923802.13 | 6568834.38 | 2398399.5 | 2700000 | 3000000 | 3075000 | 3151875 | 3230671.875 | 3311438.6719 | 3394224.6387 | 3479080.2546 | 3566057.261 | 3655208.6925 | 3746588.9098 | 30610145.3036
SP | SP | Essential spares | 2530605.28 | -314236.5 | 470065.27 | 1034008.5 | 1239026 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 10203381.7679
SW | SW | Network Switching | 6126287.18 | 4148553.29 | 3276845.76 | 2862677.78 | 3277639.0026 | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | 72633875.0416
TM004 | TM | 66 & 33kV line refurbishment | 1384559.6 | -36721.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM008 | TM | 132kV tower refurb/safety upgrade | 6307.47 | 125218.01 | 235634.38 | 4149.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM012 | TM | Sub-transmission pole replacement | 1974228.52 | 3458414.1 | 2916617.14 | 3000000.01 | 2500000 | 3813000 | 3908325 | 4006033.125 | 4106183.9531 | 5566528.4074 | 5705691.6176 | 5848333.908 | 5994542.2557 | 6144405.8121 | 45093044.0791
TM013 | TM | Underground pilots | -21461.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM014 | TM | Renewal of 33kV and 66kV gas and oil filled cables | 1057811.65 | 2929639.61 | 2764891.85 | 15250.91 | 0 | 0 | 0 | 0 | 0 | 814613.9133 | 887165.4649 | 1818689.2031 | 1809328.3028 | 1854561.5104 | 7184358.3945
TM015 | TM | Subtransmission tower replacement | 0 | 0 | 0 | 0 | 1600000 | 1640000 | 1681000 | 4307562.5 | 6181352.1875 | 6335885.9922 | 6494283.142 | 6656640.2205 | 6823056.2261 | 6993632.6317 | 47113412.9
TM016 | TM | Cast iron UGOH replacement within zone substations | 561.36 | 7896.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM017 | TM | Installation of overhead earthwire | 187.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM019 | TM | Access track reconstruction | 1221369.34 | 1333317.75 | 479926.45 | 214470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM020 | TM | Traffic blackspot remediation - transmission | 773.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM021 | TM | Capital works for compliance to NSW Maritime Waterways | 100889.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM023 | TM | Renewal of 132kV cable 233 | 105493.31 | 232.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM027 | TM | Steel tower asbestos removal | 0 | 28671.31 | 71490.9 | 181000 | 3013000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM028 | TM | 132kV oil cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11596934.1821 | 11886857.5367 | 12184028.9751 | 12488629.6995 | 48156450.3934
TM029 | TM | Installation of aerial marker malls on high spans | 0 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM030 | TM | Feeder 7028 replacement | 0 | 0 | 0 | 0 | 500000 | 1691250 | 2311375 | 2369159.375 | 2428388.3594 | 2489098.0684 | 0 | 0 | 0 | 0 | 11289270.8027
TM131 | TM | Underground pilots replacement | 655120.53 | 9136.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM132 | TM | Sub-transmission pilot cable renewal program | 4531769.99 | 495326.58 | 42861.4 | 3711 | 0 | 973750 | 998093.75 | 1023046.0937 | 1048622.2461 | 1074837.8022 | 1101708.7473 | 1129251.466 | 1157482.7526 | 1186419.8215 | 9693212.6795
TM133 | TM | Hardex pilot cable renewal | 8692723.7 | 933474.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM134 | TM | Wollongong - Port Kembla pilot cable replacement | 0 | 0 | 0 | 0 | 0 | 1655375 | 1696759.375 | 1739178.3594 | 1782657.8184 | 1827224.2638 | 1872904.8704 | 1919727.4922 | 1967720.6795 | 2016913.6965 | 16478461.5551
TM135 | TM | Optical fibre protection and communication upgrades in the Blue Mountains | 0 | 0 | 0 | 0 | 0 | 666250 | 682906.25 | 699978.9062 | 717478.3789 | 735415.3384 | 753800.7218 | 772645.7399 | 791961.8834 | 811760.9305 | 6632198.1491
TM137 | TM | Optical fibre protection and communication upgrades in the Macarthur area | 0 | 0 | 0 | 0 | 0 | 1312000 | 1344800 | 1378420 | 1412880.5 | 1448202.5125 | 1484407.5753 | 1521517.7647 | 1559555.7088 | 1598544.6015 | 13060328.6629
TM138 | TM | 132kV optical fibre ring completion | 0 | 10547.01 | 171620.02 | 459030 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM171 | TM | Replacement of corroded earthwires | 140715.05 | 1912211.42 | 2257077.62 | 1730441.85 | 2000000 | 1373500 | 1050625 | 969201.5625 | 993431.6016 | 1018267.3916 | 1043724.0764 | 1069817.1783 | 1096562.6078 | 1123976.673 | 9739106.0911
TM172 | TM | Earthwire replacement due to fault rating | 0 | 0 | 0 | 0 | 0 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 10203381.7679
TM174 | TM | Hardex earthwire replacement | 0 | 37128.28 | 3403.58 | 0 | 0 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 10203381.7679
TM302 | TM | Oil filled cable auxiliary equipment refurbishment | 467.8 | 8425.81 | 40830.06 | 324875 | 0 | 0 | 75645 | 0 | 0 | 0 | 0 | 85585.3743 | 0 | 0 | 161230.3743
TM303 | TM | Guilford and Camellia 132kV cables oil testing and flushing | 467.8 | 14221.76 | 38664.84 | 162681 | 465136 | 0 | 94556.25 | 0 | 0 | 0 | 0 | 106981.7178 | 0 | 0 | 201537.9678
TM401 | TM | South Coast 33kV overhead line refurbishment | 447327.58 | 598241.23 | 614955.62 | 464955.07 | 998000 | 1107000 | 1134675 | 1292268.75 | 1324575.4687 | 1357689.8555 | 1391632.1019 | 1426422.9044 | 1462083.477 | 1498635.5639 | 11994983.1214
TM404 | TM | Avon/Nepean Dam feeder refurbishment | 580189.62 | 3437434.67 | 1688532.73 | 34512.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM408 | TM | Ringwood Feeder 7906 Refurbishment | 0 | 0 | 13428.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM410 | TM | Hazelbook ZS to Springwood ZS Feeder 808 refurbishment | 1160250.43 | 244772.52 | 58694.07 | 36862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM419 | TM | Future sub-transmission feeder refurbishment works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10669179.4476 | 16284994.8253 | 22418613.3142 | 25227031.9929 | 74599819.5799
TM801 | TM | Steel tower painting program | 445362.38 | 191732.13 | 86397.5 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 927754.7346 | 950948.6029 | 974722.318 | 999090.376 | 3852516.0315
TM803 | TM | Steel tower below ground rectification work | 31493.03 | 208947.05 | 256110.57 | 499999.96 | 2599999.92 | 2152500 | 2206312.5 | 2261470.3125 | 2318007.0703 | 2375957.2471 | 2435356.1782 | 2496240.0827 | 2558646.0848 | 2622612.2369 | 21427101.7125
TM805 | TM | Earthing refurbishment of lines 940/941 | 0 | 0 | 3676.09 | 555711.11 | 178388.89 | 287000 | 294175 | 301529.375 | 309067.6094 | 22628.1643 | 23193.8684 | 23773.7151 | 24368.058 | 24977.2594 | 1310713.0494
TM809 | TM | Subtransmission line earthing refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 630375 | 646134.375 | 662287.7344 | 678844.9277 | 695816.0509 | 713211.4522 | 731041.7385 | 749317.782 | 5507029.0607
TS001 | TS | Power transformer replacement | 166128.58 | 11270.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS004 | TS | 132kV circuit breaker replacement | 5809.62 | 131967.6 | 0 | 0 | 903000 | 371050 | 380326.25 | 389834.4062 | 399580.2664 | 409569.7731 | 419809.0174 | 430304.2428 | 441061.8489 | 452088.3951 | 3693624.2
TS005 | TS | 33kV circuit breaker replacement | 961491.77 | 774489.38 | 98729.48 | 1494290.37 | 3410000 | 872787.5 | 894607.1875 | 916972.3672 | 939896.6764 | 963394.0933 | 987478.9456 | 1012165.9192 | 1037470.0672 | 1063406.8189 | 8688179.5753
TS007 | TS | 11kV circuit breaker replacement | 0 | 0 | 0 | 5000 | 0 | 0 | 367718.75 | 376911.7187 | 0 | 0 | 0 | 0 | 0 | 0 | 744630.4688
TS008 | TS | Battery replacement | 326014.56 | 149579.63 | 248814.78 | 1181071.26 | 1253792 | 1230000 | 1260750 | 1292268.75 | 1324575.4687 | 1357689.8555 | 1391632.1019 | 1426422.9044 | 1462083.477 | 1498635.5639 | 12244058.1214
TS009 | TS | Auxiliary switchgear replacement | 71609.02 | 529762.06 | 1083588.52 | 1161162.01 | 817000 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 869770.0637 | 0 | 0 | 0 | 6257506.7922
TS011 | TS | Freq injection replacement/augmentation | 513.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS015 | TS | Replacement of surge arrester in zone and sub-transmission substations | 49751.7 | 20531.8 | 21401.92 | 169683 | 132000 | 112750 | 115568.75 | 118457.9687 | 121419.418 | 49781.9614 | 51026.5104 | 52302.1732 | 53609.7275 | 54949.9707 | 729866.4798
TS016 | TS | VT and CT replacement | 1492872.88 | 617290.48 | 218121.61 | 295677.11 | 1095000 | 717500 | 735437.5 | 753823.4375 | 772669.0234 | 791985.749 | 811785.3927 | 832080.0276 | 852882.0283 | 874204.079 | 7142367.2375
TS017 | TS | Power transformer refurbishment | 597961.17 | 0 | 0 | 1368.37 | 600000 | 615000 | 630375 | 646134.375 | 662287.7344 | 678844.9277 | 695816.0509 | 713211.4522 | 731041.7385 | 749317.782 | 6122029.0607
TS018 | TS | Transformer oil replacement | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS020 | TS | Portable earthing set cabinets | 26129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS024 | TS | Building and amenities refurbishment | 1772852.21 | 208396.9 | 227449.05 | 1711100 | 500000 | 2050000 | 2101250 | 2153781.25 | 2207625.7812 | 2262816.4258 | 2319386.8364 | 2377371.5073 | 2436805.795 | 2497725.9399 | 20406763.5357
TS025 | TS | Asbestos and other hazardous material reporting, management and removal | 1368849.67 | 352910.96 | 133694.5 | 200000 | 650000 | 533000 | 546325 | 559983.125 | 573982.7031 | 588332.2707 | 603040.5775 | 618116.5919 | 633569.5067 | 649408.7444 | 5305758.5193
TS026 | TS | Noise attenuation in ZS and TS | 2298403.59 | 56249.3 | 243352.43 | 2060.91 | 0 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 1248862.9699 | 10203381.7679
TS027 | TS | Substation switchyard lighting improvement | 481385.25 | 384972.4 | 272719.34 | 35500 | 0 | 123000 | 126075 | 129226.875 | 132457.5469 | 135768.9855 | 139163.2102 | 142642.2904 | 146208.3477 | 149863.5564 | 1224405.8121
TS028 | TS | Control cable trench and cover refurbishment | 12318.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS029 | TS | Substation control room temperature reduction initiatives | 86865.37 | 14816.92 | 400.72 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS031 | TS | Substation safety fence upgrade program | 135640.54 | 223948.89 | 3441.68 | 100000 | 300000 | 102500 | 105062.5 | 107689.0625 | 110381.2891 | 113140.8213 | 115969.3418 | 118868.5754 | 121840.2898 | 124886.297 | 1020338.1768
TS032 | TS | Substation security systems | 2341750.5 | 43126.13 | 256139.98 | 0 | 0 | 153750 | 157593.75 | 161533.5937 | 0 | 0 | 0 | 0 | 0 | 0 | 472877.3438
TS033 | TS | Substation fire hydrant installations | 697620.41 | 644076.77 | 302793.32 | 557206.68 | 200000 | 205000 | 210125 | 215378.125 | 220762.5781 | 226281.6426 | 231938.6836 | 237737.1507 | 243680.5795 | 249772.594 | 2040676.3536
TS034 | TS | Substation deluge showers and fire blankets | 405857.15 | 332977.39 | 141556.62 | 0 | 160000 | 164000 | 168100 | 172302.5 | 176610.0625 | 181025.3141 | 185550.9469 | 190189.7206 | 194944.4636 | 199818.0752 | 1632541.0829
TS035 | TS | Substation oil containment program - bund walls | 534382.54 | 524176.9 | 18875.65 | 0 | 210000 | 71750 | 73543.75 | 75382.3437 | 77266.9023 | 79198.5749 | 81178.5393 | 83208.0028 | 85288.2028 | 87420.4079 | 714236.7237
TS036 | TS | Substation earthing | 1739315.57 | 1393861.09 | 1947930.91 | 2179501 | 998483 | 1025000 | 525312.5 | 538445.3125 | 551906.4453 | 565704.1064 | 579846.7091 | 594342.8768 | 609201.4488 | 624431.485 | 5614190.8839
TS047 | TS | Equipment labelling in TS & ZS | -55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS048 | TS | Substation oil containment program - separators | 30860.53 | 287.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS049 | TS | Tunnelboard refurbishment | 9101.84 | 30714.68 | 0 | 0 | 0 | 46125 | 47278.125 | 48460.0781 | 49671.5801 | 50913.3696 | 52186.2038 | 53490.8589 | 54828.1304 | 56198.8336 | 459152.1796
TS050 | TS | POW switching for capacitors | 145405.16 | 56199.85 | 0 | 0 | 0 | 0 | 0 | 0 | 662287.7344 | 0 | 0 | 0 | 0 | 0 | 662287.7344
TS055 | TS | 66kV circuit breaker replacement | 479068.87 | 29315.24 | 0 | 0 | 258000 | 264450 | 271061.25 | 277837.7812 | 284783.7258 | 291903.3189 | 299200.9019 | 306680.9244 | 314347.9476 | 322206.6462 | 2632472.4961
TS057 | TS | Substation insulation co-ordination | 72403.32 | 0 | 0 | 0 | 150000 | 153750 | 157593.75 | 161533.5937 | 165571.9336 | 169711.2319 | 173954.0127 | 178302.8631 | 182760.4346 | 187329.4455 | 1530507.2652
TS060 | TS | Lawson TS rebuild | 2155.75 | 34.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS067 | TS | Rosehill ZS renewal | 15210.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS072 | TS | Holroyd ZS renewal | 316616.25 | 1761.6 | -1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS086 | TS | Busbar support and isolator replacement | 0 | 0 | 12384.13 | 566900.85 | 325000 | 96862.5 | 99284.0625 | 101766.1641 | 104310.3182 | 106918.0761 | 109591.028 | 112330.8037 | 115139.0738 | 118017.5507 | 964219.5771
TS092 | TS | Jasper Rd 11kV CB renewal | 7979.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS099 | TS | Substation power outlet installation | 77489.53 | 57396.78 | 61679.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS100 | TS | Substation internal fence replacement | 70163.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS102 | TS | Rydalmere Zone Substation renewal | 3079542.45 | 1660072.91 | 1890306.46 | 52398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS111 | TS | Blackheath ZS 11kV switchyard renewal | 58023.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS116 | TS | Roof refurbishment for control and switch rooms | 1201076.7 | 741568.61 | 179316.19 | 1300000 | 500000 | 1537500 | 1575937.5 | 1615335.9375 | 1655719.3359 | 1697112.3193 | 1739540.1273 | 1783028.6305 | 1827604.3463 | 1873294.4549 | 15305072.6518
TS118 | TS | Smithfield Zone Substation rebuilding | 9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS119 | TS | Bomaderry ZS redevelopment (fmr PR403) | 3653.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS120 | TS | Canley Vale ZS redevelopment | 880445.23 | 92618.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS121 | TS | Port Kembla ZS | 1702771.63 | 486291.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS122 | TS | Leabons Lane Zone Substation renewal | 2754675.05 | 1522340.95 | 2449149.16 | 2689732 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS123 | TS | St Marys Zone Substation renewal | 4917373.24 | 3562017.14 | 200262.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS124 | TS | Substation control building fire alarm systems | 3215.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS125 | TS | Guildford Transmission Substation renewal | 4085476.25 | 2194828.55 | 434100.13 | 1220.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS126 | TS | Comalco HVC renewal | 9769.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS127 | TS | Castle Hill Zone Substation renewal | -1385445.45 | 377423.8 | 772793.46 | 661524 | 163333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS128 | TS | Capacitor bank refurbishment | 0 | 0 | 0 | 107615.86 | 1270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS130 | TS | Northmead Zone Substation renewal | 3728085.42 | 1331129.93 | 435639.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS131 | TS | Bulli Zone Substation renewal | 976408.78 | 245733.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS133 | TS | Corrimal ZS redevelopment | 1232751.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS134 | TS | South Granville Zone Substation renewal | 2469884.25 | 216682.15 | 41837.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS135 | TS | Ringwood ZS redevelopment | 6861.56 | 6804.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS136 | TS | Kandos ZS redevelopment | 44300.95 | 99.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS137 | TS | Power transformer oil temperature indicator | 3246.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS138 | TS | Baulkham Hills switchgear rearrangement | 18156.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS139 | TS | Oakdale ZS swgr rearrangement | 38476.89 | 13690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS143 | TS | Westmead Zone Substation renewal and augmentation | 2204132.14 | 679379.21 | 2206.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS144 | TS | Substation fire stopping measures | 132981.39 | 104842.75 | 50123.47 | 0 | 198000 | 67650 | 69341.25 | 71074.7812 | 72851.6508 | 74672.9421 | 76539.7656 | 78453.2597 | 80414.5912 | 82424.956 | 673423.1967
TS146 | TS | Marayong Zone Substation renewal | 0 | 0 | 26957.5 | 1634062 | 13051000 | 6865450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6865450
TS149 | TS | South Windsor ZS refurbishment | 8407.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS155 | TS | Sussex Inlet Zone Substation - stage 2 renewal | 0 | 0 | 0 | 299999.98 | 2400000 | 3754575 | 3962357.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7716932.1429
TS156 | TS | Lawson TS - RailCorp connections works | 239576.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS163 | TS | Unanderra Zone Substation renewal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4307562.5 | 5519064.4531 | 6788449.2773 | 0 | 0 | 0 | 0 | 16615076.2305
TS165 | TS | Greystanes Zone Substation renewal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7885915.2438 | 8083063.1249 | 8320800.2757 | 0 | 0 | 24289778.6445
TS167 | TS | Carlingford Transmission Substation control building replacement | 0 | 0 | 0 | 0 | 0 | 4612500 | 4727812.5 | 4846007.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 14186320.3125
TS168 | TS | Carramar Zone Substation switchgear replacement | 38413.28 | 317757.29 | 945369.93 | 69717.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS173 | TS | 11kV switchboard truck replacement program | 0 | 17939.94 | 48337.08 | 863184.06 | 2894255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS174 | TS | West Wollongong Zone Substation 11kV renewal | 0 | 0 | 0 | 0 | 0 | 0 | 3151875 | 4307562.5 | 6070970.8984 | 0 | 0 | 0 | 0 | 0 | 13530408.3984
TS175 | TS | Defective CT replacement program | 9942.53 | 1186090.77 | 128378.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS177 | TS | Substation battery duplication | 0 | 3753.99 | 285875.3 | 2015606.51 | 1582100 | 1025000 | 1050625 | 1076890.625 | 1103812.8906 | 1131408.2129 | 1159693.4182 | 1188685.7537 | 1218402.8975 | 749317.782 | 9703836.5799
TS178 | TS | Jerrara SS steel support structures | 0 | 6035.49 | 271435.09 | 115742.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS179 | TS | 33kV wall bushing replacement | 0 | 0 | 0 | 669212.3 | 38000 | 123000 | 126075 | 193840.3125 | 198686.3203 | 203653.4783 | 208744.8153 | 213963.4357 | 219312.5216 | 224795.3346 | 1712071.2182
TS180 | TS | Transformer fire wall installation | 0 | 0 | 0 | 0 | 200000 | 205000 | 210125 | 215378.125 | 220762.5781 | 226281.6426 | 231938.6836 | 237737.1507 | 243680.5795 | 249772.594 | 2040676.3536
TS181 | TS | 11kV capacitor bank refurbishment | 0 | 0 | 3706.31 | 2666415 | 887526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS182 | TS | Substation civil capital works scoping | 0 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS184 | TS | Blaxland Zone Substation reinstatement | 0 | 0 | 0 | 1050900 | 691500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS185 | TS | Penrith TS civil development | 0 | 0 | 0 | 750000 | 2101666.63 | 2050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050000
TS187 | TS | Mobile substation No 2 refurbishment | 0 | 0 | 0 | 132000 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS188 | TS | Bossley Park ZS civil refurbishment | 0 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS199 | TS | Future sub-transmission substation renewal programs | 0 | 0 | 0 | 0 | 0 | 4100000 | 6303750 | 6461343.75 | 6622877.3437 | 13576898.5547 | 14496167.7277 | 20207657.8124 | 24977259.399 | 29348279.7938 | 126094234.3812
TS600 | TS | Power transformer replacement | 0 | 0 | 0 | 0 | 0 | 10250000 | 12607500 | 12922687.5 | 15453380.4687 | 15839714.9805 | 18555094.6914 | 19018972.0587 | 19494446.3602 | 19981807.5192 | 144123603.5786
TS601 | TS | Cranebrook ZS 33kV No 3 - transformer replacement | 90141.18 | 2824.07 | -12.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS602 | TS | Prospect ZS 33kV No3 transformer | 653418.7 | 44171.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS603 | TS | Kingwood ZS 33kV No 3 - transformer replacement | 60216.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS604 | TS | Liverpool TS 132kV No 3 - transformer replacement | 513651.72 | 68381.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS605 | TS | West Liverpool 132 kV No 3 transformer | 790743.28 | 63124.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS615 | TS | Gerringong ZS 33kV No 2 transformer replacement | 0 | 0 | 105267.94 | 396609.39 | 6894.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS616 | TS | Camellia TS transformer replacement and 33kV busbar rearrangement | 0 | 0 | 0 | 1169340 | 2608611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS617 | TS | Prospect ZS transformer replacement | 0 | 0 | 0 | 792486 | 2449406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS618 | TS | Albion Park ZS transformer replacement | 0 | 0 | 0 | 507041.82 | 2457614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS619 | TS | Dundas ZS 66kV No 2 transformer | 0 | 0 | 0 | 256666.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS700 | TS | 11kV zone substation switchboard replacement | 0 | 0 | 0 | 0 | 0 | 6406250 | 7223046.875 | 7403623.0469 | 8278596.6797 | 8485561.5967 | 8697700.6366 | 8915143.1525 | 9138021.7313 | 9366472.2746 | 73914415.9933
TS701 | TS | North Rocks ZS 11kV switchboard replacement | 0 | 0 | 0 | 548574.04 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS702 | TS | Kellyville ZS 11kV switchboard replacement | 0 | 0 | 0 | 538929 | 1890000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS703 | TS | Horsley Park ZS 11kV switchboard replacement | 0 | 0 | 0 | 496138.68 | 2610000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS704 | TS | Port Central ZS 11kV switchboard replacement | 0 | 0 | 0 | 464250.3 | 1740000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UR | UR | Underground residential | 7082081.57 | 9523549.7 | 9019850.87 | 26952400.4014 | 33939845.5741 | 45068788.75 | 44256646.2206 | 45265989.3014 | 46558252.64 | 48607408.0335 | 49896500.4959 | 51211713.2663 | 52561847.3889 | 54019786.3161 | 437446932.4127

## Totals (hidden)
| FY20 | FY21 | FY22 | FY23 | FY24 | Total | Target
Repex | 109287872 | 120299207 | 118788250 | 124144750 | 127818750 | 600338829 | 600000000
Augex | 64808968 | 64514992 | 70132408 | 78309987 | 72071597 | 349837952 | 350000000
Connections | 33956216 | 24446757 | 20808877 | 19862891 | 19577920 | 118652661 | 119000000
Other Network | 13635350 | 8241780 | 6422946 | 6353986 | 6720525 | 41374587 | 41000000
Reliability | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 20000000 | 20000000
Overheads | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 400000000 | 400000000
Total | 305078445.9677 | 301158021.6482 | 300614153.3096 | 312628812.1143 | 310724595.9602 | 1530204029 | 1530000000

## PIP 19.1 (hidden)
ID | Description | FY20 (R) | FY21 (R) | FY22 (R) | FY23 (R) | FY24 (R) | Tot (R)
AG | Automation - operational/capacity risk | 300000 | 300000 | 300000 | 300000 | 300000 | 1500000
AR | Asset relocation | 1817759 | 1809464 | 1815980 | 1824516 | 1838449 | 9106168
AU002 | Transmission substation SCADA upgrade | 0 | 0 | 0 | 0 | 0 | 0
AU004 | Substation SCADA RTU replacement | 1840000 | 1840000 | 1840000 | 1840000 | 1840000 | 9200000
AU008 | Western Sydney Ramtel SCADA upgrades | 0 | 0 | 0 | 0 | 0 | 0
AU013 | SCADA master station development software | 2000000 | 2000000 | 1000000 | 1000000 | 2000000 | 8000000
AU014 | SCADA substation refurbishments | 0 | 0 | 0 | 0 | 0 | 0
AU016 | PM121 (MD1000) MD3 to DNP3 conversion | 0 | 0 | 0 | 0 | 0 | 0
AU017 | AFIC availability and SCADA control | 0 | 0 | 0 | 0 | 0 | 0
CC002 | Communications development SCADA | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000
CC007 | SCADA radio repeaters | 696000 | 696000 | 696000 | 696000 | 696000 | 3480000
CC020 | Microwave refurbishment and extension | 450000 | 450000 | 450000 | 450000 | 450000 | 2250000
DS002 | Pole substation refurbishment | 735000 | 735000 | 735000 | 787500 | 840000 | 3832500
DS003 | Distribution substation refurbishment | 0 | 0 | 0 | 0 | 0 | 0
DS004 | Distribution mains refurbishment | 0 | 0 | 0 | 0 | 0 | 0
DS005 | Distribution pole replacement | 11330000 | 12100000 | 12870000 | 13640000 | 14410000 | 64350000
DS006 | LV CONSAC cable replacement | 8750000 | 11000000 | 12250000 | 13250000 | 13250000 | 58500000
DS007 | Service wire replacement program | 12600000 | 12600000 | 12600000 | 12950000 | 13300000 | 64050000
DS008 | Traffic black spot remediation | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
DS009 | Reliability focused distribution mains renewal | 0 | 0 | 0 | 0 | 0 | 0
DS011 | HV distribution steel mains replacement | 4800000 | 4800000 | 4800000 | 5600000 | 5600000 | 25600000
DS012 | HV porcelain expulsion drop-out fuse replacement program | 0 | 0 | 0 | 0 | 0 | 0
DS014 | LV cable network renewal | 650000 | 1950000 | 2340000 | 2340000 | 1300000 | 8580000
DS301 | Ground substation refurbishment program | 510000 | 510000 | 850000 | 850000 | 1020000 | 3740000
DS302 | Distribution transformer replacement program | 1170000 | 1170000 | 1170000 | 1462500 | 1462500 | 6435000
DS305 | Compact LV switchgear replacement | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000
DS307 | Holec MD4 epoxy switchgear replacement | 5950000 | 6300000 | 7875000 | 7875000 | 7875000 | 35875000
DS308 | HV RGB12 switchgear replacement | 0 | 0 | 0 | 0 | 0 | 0
DS312 | Miscellaneous substation renewal expenditure | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 17500000
DS313 | Padmount substation fire risk mitigation | 0 | 0 | 0 | 0 | 0 | 0
DS315 | Low voltage switchgear replacement | 708000 | 708000 | 708000 | 708000 | 708000 | 3540000
DS316 | HV oil switchgear replacement program | 0 | 0 | 0 | 0 | 0 | 0
DS317 | Future distribution substation renewals | 0 | 0 | 0 | 0 | 0 | 0
DS318 | Distribution substation earthing refurbishment | 270000 | 270000 | 270000 | 270000 | 270000 | 1350000
DS404 | Cast iron UGOH replacement program | 0 | 0 | 0 | 0 | 0 | 0
DS405 | Air break switch replacement | 3690000 | 3690000 | 3690000 | 3690000 | 3690000 | 18450000
DS409 | Miscellaneous mains renewal expenditure | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 12500000
DS410 | Capital works for compliance to NSW Maritime Waterways - crossing codes | 0 | 0 | 0 | 0 | 0 | 0
DS411 | Capital works for compliance to NSW Maritime Waterways - signage replacement and drawings update | 0 | 0 | 0 | 0 | 0 | 0
DS413 | Low mains remediation | 1625000 | 1625000 | 1625000 | 1625000 | 1625000 | 8125000
DS414 | Copper distribution mains replacement | 1440000 | 2400000 | 2400000 | 2400000 | 2400000 | 11040000
DS415 | LV mains replacement | 1200000 | 1500000 | 1650000 | 1650000 | 1500000 | 7500000
DS416 | Asbestos service fuse replacement | 261000 | 0 | 0 | 0 | 0 | 261000
DS417 | Distribution access track reconstruction | 440000 | 1408000 | 1892000 | 1892000 | 0 | 5632000
DS418 | Pole top structure/hardware refurbishment | 10000000 | 9000000 | 9000000 | 8000000 | 8000000 | 44000000
DS420 | Future distribution feeder refurbishment works | 0 | 0 | 0 | 0 | 0 | 0
DU | Duct installation RMS road works | 2152731 | 2206549 | 2261713 | 2318255 | 2376212 | 11315460
EF001 | Distribution management system | 8585365.8537 | 3616894.7055 | 92859.9411 | 0 | 0 | 12295120.5003
EF002 | Technology pilots | 500000 | 500000 | 2000000 | 2000000 | 2000000 | 7000000
EF003 | Battery energy storage system pilot | 0 | 0 | 0 | 0 | 0 | 0
EH | Dist environmental enhancement program | 0 | 0 | 0 | 0 | 0 | 0
HVW | HV development works | 6800844 | 7103063 | 6647368 | 6275047 | 5947097 | 32773419
IC | Industrial & commercial | 13836506 | 13286183 | 13262397 | 13309313 | 13547284 | 67241683
LV001 | Overloaded distribution sub uprates | 120000 | 120000 | 120000 | 120000 | 120000 | 600000
LV002 | Quality of supply reactive projects | 500000 | 500000 | 500000 | 500000 | 500000 | 2500000
LV003 | LV planning reactive projects | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
LV004 | Low voltage system augmentations | 0 | 0 | 0 | 0 | 0 | 0
LV005 | Dsub monitoring & LV feeder monitoring for solar PV | 250000 | 250000 | 250000 | 250000 | 250000 | 1250000
MC101 | Meters - Growth | 0 | 0 | 0 | 0 | 0 | 0
MC102 | Relays - growth | 0 | 0 | 0 | 0 | 0 | 0
MC104 | Meters - renewal | 25000 | 0 | 0 | 0 | 0 | 25000
MC105 | Relays - renewal | 957584 | 907185 | 856786 | 806386 | 755987 | 4283928
MC106 | Labour (meter/relay renewal) | 0 | 0 | 0 | 0 | 0 | 0
MC107 | Test equipment | 80000 | 80000 | 80000 | 80000 | 85000 | 405000
MC108 | Smart metering pilot | 0 | 0 | 0 | 0 | 0 | 0
MC109 | Demand management technology | 1400000 | 750000 | 750000 | 750000 | 750000 | 4400000
MC110 | Labour meter renewal | 0 | 0 | 0 | 0 | 0 | 0
MC111 | Labour relay renewal | 0 | 0 | 0 | 0 | 0 | 0
MC112 | Neutral integrity monitoring | 0 | 0 | 0 | 0 | 0 | 0
NU | Non urban extension | 1731521 | 1666575 | 1664189 | 1670205 | 1698923 | 8431413
OFP | Overloaded feeders (compliance) | 0 | 0 | 0 | 0 | 0 | 0
PF | Power factor | 0 | 0 | 0 | 0 | 0 | 0
PQ001 | Permanent power quality monitoring | 100000 | 100000 | 100000 | 100000 | 100000 | 500000
PQ003 | PQ surveying | 0 | 0 | 0 | 0 | 0 | 0
PQ004 | Power quality monitoring replacement | 342400 | 617700 | 873300 | 947600 | 1364538 | 4145538
PR017 | Werrington ZS rebuild to 132kV | 0 | 0 | 0 | 0 | 0 | 0
PR035 | Baulkham Hills TS 11kV supply | 0 | 0 | 0 | 0 | 0 | 0
PR044 | West Liverpool ZS (Hoxton Park ZS rebuild) | 0 | 0 | 0 | 0 | 0 | 0
PR052 | Penrith TS transformer and busbar augment | 0 | 0 | 0 | 0 | 0 | 0
PR054 | Quakers Hill ZS augment (132kV bar + 1st 132/11kV tfr) | 0 | 0 | 0 | 0 | 0 | 0
PR059 | ELTS 132kV busbar & substation works | 0 | 0 | 0 | 0 | 0 | 0
PR060 | WLTS-ELTS first 132kV cable links | 0 | 0 | 0 | 0 | 0 | 0
PR061 | Russell Vale ZS augment | 0 | 0 | 0 | 0 | 0 | 0
PR070 | Caddens ZS establishment and feeders | 0 | 0 | 0 | 0 | 0 | 0
PR073 | Campbelltown 66kV busbar & line to Ambarvale | 0 | 0 | 0 | 0 | 0 | 0
PR081 | Collimore Park ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR090 | Doonside 132kV/11kV ZS rebuild | 0 | 0 | 0 | 0 | 0 | 0
PR091 | West Parramatta CBD 132kV/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR096 | Berry ZS LDC CT's | 0 | 0 | 0 | 0 | 0 | 0
PR102 | Kemps Creek/Luddenham capacity uprate | 0 | 0 | 0 | 0 | 0 | 0
PR110 | Edmondson Park ZS establishment | 1887804.878 | 5710.8864 | 0 | 0 | 0 | 1893515.7644
PR113 | Augment feeder 308 Nepean to Douglas Park | 6072000 | 0 | 0 | 0 | 0 | 6072000
PR123 | Connection works associated with Tomerong/Bamarang BSP | 0 | 0 | 0 | 0 | 0 | 0
PR126 | Chipping Norton 33/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR128 | Nepean ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR144 | Sherwood ZS augment | 0 | 0 | 0 | 0 | 0 | 0
PR148 | Dapto ZS 3rd transformer & 33kV bus section CB's | 0 | 0 | 0 | 0 | 0 | 0
PR149 | Gerringong ZS augment | 0 | 0 | 0 | 0 | 0 | 0
PR157 | Richmond ZS rebuild | 0 | 0 | 0 | 0 | 0 | 0
PR170 | Holsworthy 33/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR172 | Parklea ZS 3rd transformer | 0 | 0 | 0 | 0 | 0 | 0
PR176 | Cheriton Av 132/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR183 | Schofields ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR184 | Box Hill 22kV conversion | 0 | 0 | 0 | 0 | 0 | 0
PR186 | Glenorie ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR190 | Eschol Park ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR192 | Feeder 7158 augment from Albion Park to Warilla | 0 | 0 | 0 | 0 | 0 | 0
PR200 | Cordeaux/Figtree 33/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR204 | Canley Vale subtransmission network upgrade | 0 | 0 | 0 | 0 | 0 | 0
PR206 | Cawdor 66/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR208 | Abbotsbury 132/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR244 | Bellavista ZS establishment with two 132kV cable links | 0 | 0 | 0 | 0 | 0 | 0
PR248 | Penrith Lakes ZS site acquisition | 0 | 0 | 0 | 1000000 | 0 | 1000000
PR249 | Establish Penrith Lakes 33/11kV Zone Substation | 0 | 0 | 0 | 0 | 3610000 | 3610000
PR255 | Line works associated with Oran Park | 0 | 0 | 0 | 0 | 0 | 0
PR257 | Menangle Park 66/11kV ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0
PR258 | Menangle Park 66/11kV ZS establishment | 10270000 | 0 | 0 | 0 | 0 | 10270000
PR261 | Huntingwood ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR270 | West Epping Zone Substation establishment | 0 | 0 | 0 | 0 | 0 | 0
PR278 | Kemps Creek new BSP associated works | 0 | 0 | 0 | 0 | 0 | 0
PR280 | Wilton Park 66/11kV ZS establishment & 66kV line works | 0 | 0 | 0 | 0 | 0 | 0
PR288 | Holroyd 330/132kV BSP associated works | 0 | 0 | 0 | 0 | 0 | 0
PR291 | Marsden Park Zone Substation site acquisition | 0 | 0 | 0 | 0 | 0 | 0
PR292 | South Marsden Park (industrial) 132/11kV ZS establishment | 9560975.6098 | 0 | 0 | 0 | 0 | 9560975.6098
PR303 | Mittagong ZS transformer augment | 0 | 0 | 0 | 0 | 0 | 0
PR308 | Granville ZS & Camellia TS rebuild | 0 | 0 | 0 | 0 | 0 | 0
PR311 | Quakers Hill ZS 2nd 132kV feeder | 0 | 0 | 0 | 0 | 0 | 0
PR326 | Casula 33/11kV ZS establishment with link to LTS or WLTS | 0 | 0 | 0 | 0 | 0 | 0
PR329 | Box Hill site purchase | 0 | 0 | 0 | 0 | 0 | 0
PR339 | North Eastern Creek ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR342 | Jordan Springs establishment | 0 | 0 | 0 | 0 | 0 | 0
PR343 | Wetherill Park ZS augmentation | 0 | 0 | 0 | 0 | 0 | 0
PR353 | Shoalhaven Feeder 7510/7511 Augment | 0 | 0 | 0 | 0 | 0 | 0
PR384 | Glossodia ZS transformer augments | 0 | 0 | 0 | 0 | 0 | 0
PR406 | Tomerong ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR408 | Oran Park (permanent) ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR413 | Windsor transformer | 0 | 0 | 0 | 0 | 0 | 0
PR423 | Maryland ZS establishment | 0 | 4166800 | 8333600 | 8333600 | 0 | 20834000
PR424 | Austral ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0
PR425 | Austral ZS establishment (interim initially) | 0 | 2379535.9905 | 0 | 0 | 0 | 2379535.9905
PR426 | Leppington North ZS site purchase (strategic) | 0 | 0 | 0 | 0 | 0 | 0
PR427 | Leppington North ZS establishment | 2911434.1463 | 284587.7454 | 0 | 0 | 0 | 3196021.8917
PR429 | Leppington South ZS establishment (interim initially) | 0 | 0 | 0 | 0 | 0 | 0
PR430 | North Rossmore ZS site purchase | 0 | 0 | 0 | 3000000 | 0 | 3000000
PR432 | Rossmore ZS site purchase | 0 | 0 | 0 | 0 | 3000000 | 3000000
PR433 | Rossmore ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR434 | Catherine Fields North land purchase | 0 | 0 | 0 | 0 | 0 | 0
PR435 | Catherine Fields North ZS establishment (interim) | 0 | 0 | 0 | 0 | 0 | 0
PR436 | Catherine Fields ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0
PR437 | Catherine Fields 11kV feeder works | 0 | 0 | 0 | 0 | 0 | 0
PR438 | North Bringelly ZS site purchase | 0 | 0 | 0 | 0 | 3500000 | 3500000
PR439 | North Bringelly ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR440 | Feeder 443 and 458/1 augmentation and Cattai rebuild | 0 | 0 | 0 | 0 | 0 | 0
PR444 | Culburra Beach development (33kV fdr and single transformer ZS) | 0 | 0 | 0 | 0 | 0 | 0
PR479 | Far South Coast 132kV voltage constraints | 0 | 0 | 0 | 0 | 0 | 0
PR487 | Connection works associated with Macarthur BSP | 0 | 0 | 0 | 0 | 0 | 0
PR499 | Southpipe (Oakdale Estate) ZS 132/11kV establishment | 5452000 | 12904000 | 8904000 | 0 | 0 | 27260000
PR517 | Installation of OPGW on Feeders 98W and 98F | 0 | 0 | 0 | 0 | 0 | 0
PR521 | Culburra ZS fdr duplication & provision for rural ZS's | 0 | 0 | 0 | 0 | 0 | 0
PR559 | Mamre ZS transformer augment and 11kV busbar extension | 0 | 0 | 0 | 0 | 0 | 0
PR563 | Shoalhaven TS 132kV capacitor install | 0 | 0 | 0 | 0 | 0 | 0
PR595 | The Oaks ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR596 | Marsden Park (residential) 132/11kV ZS establishment - stage 1 | 0 | 0 | 0 | 0 | 0 | 0
PR599 | Penrith CBD ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0
PR602 | Riverstone West site purchase | 0 | 0 | 0 | 0 | 0 | 0
PR603 | Eschol Park ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0
PR620 | West Dapto ZS establishment | 0 | 0 | 4129000 | 8258000 | 8258000 | 20645000
PR632 | Mt Druitt TS automation scheme | 0 | 0 | 0 | 0 | 0 | 0
PR642 | Auxiliary transformer at Shoalhaven TS | 0 | 0 | 0 | 0 | 0 | 0
PR643 | Fibre works at Carlingford TS for Ausgrid | 0 | 0 | 0 | 0 | 0 | 0
PR652 | Purchase of additional land Lawson TS | 0 | 0 | 0 | 0 | 0 | 0
PR653 | Avondale (South West Dapto) 132/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR656 | Leppington South ZS establishment (permanent) | 12195121.9512 | 1903628.7924 | 0 | 0 | 0 | 14098750.7436
PR657 | Calderwood ZS establishment (interim initially) | 7851000 | 7851000 | 0 | 0 | 0 | 15702000
PR659 | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | 0 | 0 | 0 | 0 | 2500000 | 2500000
PR660 | Install 66kV iso Douglas Pk/Appin/Wcliff | 0 | 0 | 0 | 0 | 0 | 0
PR673 | Liverpool ZS 11kV switchboard extension & distribution works | 0 | 0 | 0 | 0 | 0 | 0
PR674 | South Marsden Park (stage 1) | 0 | 0 | 0 | 0 | 0 | 0
PR677 | South Penrith Zone Substation | 4615000 | 13230000 | 10230000 | 0 | 0 | 28075000
PR698 | Marsden Park (residential) 132/11kV ZS - stage 2 | 3462500 | 5462500 | 0 | 0 | 0 | 8925000
PR700 | Riverstone east ZS establishment | 0 | 0 | 4129000 | 8258000 | 8258000 | 20645000
PR701 | Dapto 33kV feeder constraints | 0 | 0 | 0 | 0 | 0 | 0
PR702 | Penrith ZS 11kV transformer cable constraints | 0 | 0 | 0 | 0 | 0 | 0
PR703 | Riverstone East site purchase | 6000000 | 0 | 0 | 0 | 0 | 6000000
PR704 | Oakdale (Southpipe) site purchase | 0 | 0 | 0 | 0 | 0 | 0
PR707 | 132kV ducts Bringelly Rd | 0 | 0 | 0 | 0 | 0 | 0
PR709 | Feeder 230 undergrounding | 0 | 0 | 0 | 0 | 0 | 0
PR710 | Feeder 868 rebuild & rearrangement South32 | 0 | 0 | 0 | 0 | 0 | 0
PR713 | Box Hill 132/22kV ZS establishment | 4964000 | 15928000 | 13928000 | 0 | 0 | 34820000
PR715 | Nepean TS constraints | 0 | 0 | 0 | 0 | 0 | 0
PR716 | Box Hill ZS - 132kV ducts Old Pitt Town | 0 | 0 | 0 | 0 | 0 | 0
PR717 | Acquire improved site for West Dapto ZS | 2000000 | 0 | 0 | 0 | 0 | 2000000
PR722 | Camellia TS connection works for Ausgrid | 31070.2439 | 95724.9256 | 0 | 0 | 0 | 126795.1695
PR723 | Supply to Luddenham Science Park | 6104000 | 18208000 | 16208000 | 0 | 0 | 40520000
PR724 | Establish Mt Gilead ZS | 0 | 0 | 3854000 | 7708000 | 7708000 | 19270000
PR727 | Luddenham ZS site purchase | 975609.7561 | 0 | 0 | 0 | 0 | 975609.7561
PR728 | Western Sydney Employment Lands ZS | 0 | 0 | 4696000 | 9392000 | 9392000 | 23480000
PR729 | Cheriton Avenue 3rd transformer | 0 | 0 | 0 | 0 | 0 | 0
PR730 | Feeder 7018 constraints | 0 | 0 | 0 | 0 | 0 | 0
PR732 | Feeder 214/215 contraints | 4725000 | 4725000 | 0 | 0 | 0 | 9450000
PR733 | Bringelly ZS augmentation | 0 | 0 | 0 | 0 | 0 | 0
PR735 | Termeil area distribution works | 0 | 0 | 0 | 0 | 0 | 0
PR739 | South Gilead (South Campbelltown) | 0 | 0 | 0 | 0 | 3854000 | 3854000
PR740 | AFIC upgrade Minto, Prospect, Kingswood | 0 | 0 | 0 | 0 | 0 | 0
PR741 | Western Sydney Airport 132kV supply | 0 | 0 | 20411167 | 20411167 | 20411167 | 61233501
PR742 | North Bomaderry ZS establishment | 0 | 0 | 3692000 | 7384000 | 7384000 | 18460000
PR744 | Termeil ZS establishment | 0 | 0 | 0 | 3972500 | 3972500 | 7945000
PR745 | Austral Permanent ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR746 | Sydney University - Western Sydney Employment Lands ZS establishment | 0 | 0 | 0 | 0 | 0 | 0
PR748 | Establish permanent Catherine Park ZS | 0 | 0 | 4395600 | 8791200 | 8791200 | 21978000
PR749 | Nepean ZS augmentation | 0 | 0 | 0 | 0 | 0 | 0
PR750 | Feeder 512 augmentation | 0 | 0 | 0 | 0 | 0 | 0
PR751 | Parklea ZS to Bella Vista ZS load transfer | 4000000 | 0 | 0 | 0 | 0 | 4000000
PR752 | Kemps Creek 132kV conversion | 0 | 0 | 0 | 0 | 0 | 0
PR754 | Augment Westmead Zone Substation | 0 | 0 | 0 | 6417500 | 6417500 | 12835000
PR755 | Narellan ZS busbar augmentation | 0 | 0 | 0 | 0 | 0 | 0
PR756 | Luddenham ZS augmentation | 0 | 0 | 0 | 0 | 0 | 0
PS002 | Replacement of ASEA RI O/C relays | 0 | 0 | 0 | 0 | 0 | 0
PS004 | Underfrequency load shed program | 0 | 0 | 0 | 0 | 0 | 0
PS008 | Substation protection relay refurbishment | 4218000 | 4218000 | 4218000 | 4218000 | 4218000 | 21090000
PS009 | Installation of SEF relays | 0 | 0 | 0 | 0 | 0 | 0
PS010 | Protection refurbishment (interfacing feeders) | 0 | 0 | 0 | 0 | 0 | 0
PS011 | Protection refurbishment (miscellaneous) | 700000 | 700000 | 700000 | 700000 | 700000 | 3500000
PS012 | Distribution feeder safety improvement | 3100000 | 0 | 0 | 0 | 0 | 3100000
PS013 | Feeder differential relay replacement | 330000 | 330000 | 330000 | 330000 | 330000 | 1650000
PS014 | Under frequency load shedding | 550000 | 550000 | 0 | 0 | 0 | 1100000
RC | Reliability compliance | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 20000000
RI | Reliability enhancement | 0 | 0 | 0 | 0 | 0 | 0
SG001 | Smart grid fibre rollout & trial | 0 | 0 | 0 | 0 | 0 | 0
SG002 | Smart meter rollout | 0 | 0 | 0 | 0 | 0 | 0
SL001 | Streetlighting growth | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 8750000
SL002 | Streetlighting refurbishment | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 15000000
SP | Essential spares | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
TM004 | 66 & 33kV line refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TM008 | 132kV tower refurb/safety upgrade | 0 | 0 | 0 | 0 | 0 | 0
TM012 | Sub-transmission pole replacement | 3720000 | 3720000 | 3720000 | 3720000 | 4920000 | 19800000
TM013 | Underground pilots | 0 | 0 | 0 | 0 | 0 | 0
TM014 | Renewal of 33kV and 66kV gas and oil filled cables | 0 | 0 | 0 | 0 | 720000 | 720000
TM015 | Subtransmission tower replacement | 1600000 | 1600000 | 4000000 | 5600000 | 5600000 | 18400000
TM016 | Cast iron UGOH replacement within zone substations | 0 | 0 | 0 | 0 | 0 | 0
TM017 | Installation of overhead earthwire | 0 | 0 | 0 | 0 | 0 | 0
TM019 | Access track reconstruction | 0 | 0 | 0 | 0 | 0 | 0
TM020 | Traffic blackspot remediation - transmission | 0 | 0 | 0 | 0 | 0 | 0
TM021 | Capital works for compliance to NSW Maritime Waterways | 0 | 0 | 0 | 0 | 0 | 0
TM023 | Renewal of 132kV cable 233 | 0 | 0 | 0 | 0 | 0 | 0
TM027 | Steel tower asbestos removal | 0 | 0 | 0 | 0 | 0 | 0
TM028 | 132kV oil cable replacement | 0 | 9900000 | 9900000 | 9900000 | 9900000 | 39600000
TM029 | Installation of aerial marker malls on high spans | 0 | 0 | 0 | 0 | 0 | 0
TM030 | Feeder 7028 replacement | 1650000 | 2200000 | 2200000 | 2200000 | 2200000 | 10450000
TM131 | Underground pilots replacement | 0 | 0 | 0 | 0 | 0 | 0
TM132 | Sub-transmission pilot cable renewal program | 950000 | 950000 | 950000 | 950000 | 950000 | 4750000
TM133 | Hardex pilot cable renewal | 0 | 0 | 0 | 0 | 0 | 0
TM134 | Wollongong - Port Kembla pilot cable replacement | 1615000 | 1615000 | 1615000 | 1615000 | 1615000 | 8075000
TM135 | Optical fibre protection and communication upgrades in the Blue Mountains | 650000 | 650000 | 650000 | 650000 | 650000 | 3250000
TM137 | Optical fibre protection and communication upgrades in the Macarthur area | 1280000 | 1280000 | 1280000 | 1280000 | 1280000 | 6400000
TM138 | 132kV optical fibre ring completion | 0 | 0 | 0 | 0 | 0 | 0
TM171 | Replacement of corroded earthwires | 4080000 | 4080000 | 3060000 | 3060000 | 3060000 | 17340000
TM172 | Earthwire replacement due to fault rating | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
TM174 | Hardex earthwire replacement | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
TM302 | Oil filled cable auxiliary equipment refurbishment | 0 | 72000 | 0 | 0 | 0 | 72000
TM303 | Guilford and Camellia 132kV cables oil testing and flushing | 0 | 90000 | 0 | 0 | 0 | 90000
TM401 | South Coast 33kV overhead line refurbishment | 1080000 | 1080000 | 1200000 | 1200000 | 1200000 | 5760000
TM404 | Avon/Nepean Dam feeder refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TM408 | Ringwood Feeder 7906 Refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TM410 | Hazelbook ZS to Springwood ZS Feeder 808 refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TM419 | Future sub-transmission feeder refurbishment works | 0 | 0 | 0 | 0 | 0 | 0
TM801 | Steel tower painting program | 0 | 0 | 0 | 0 | 0 | 0
TM803 | Steel tower below ground rectification work | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 10500000
TM805 | Earthing refurbishment of lines 940/941 | 280000 | 280000 | 280000 | 280000 | 20000 | 1140000
TM809 | Subtransmission line earthing refurbishment | 0 | 600000 | 600000 | 600000 | 600000 | 2400000
TS001 | Power transformer replacement | 0 | 0 | 0 | 0 | 0 | 0
TS004 | 132kV circuit breaker replacement | 362000 | 362000 | 362000 | 362000 | 362000 | 1810000
TS005 | 33kV circuit breaker replacement | 851500 | 851500 | 851500 | 851500 | 851500 | 4257500
TS007 | 11kV circuit breaker replacement | 0 | 350000 | 350000 | 0 | 0 | 700000
TS008 | Battery replacement | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 6000000
TS009 | Auxiliary switchgear replacement | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
TS011 | Freq injection replacement/augmentation | 0 | 0 | 0 | 0 | 0 | 0
TS015 | Replacement of surge arrester in zone and sub-transmission substations | 110000 | 110000 | 110000 | 110000 | 44000 | 484000
TS016 | VT and CT replacement | 700000 | 700000 | 700000 | 700000 | 700000 | 3500000
TS017 | Power transformer refurbishment | 600000 | 600000 | 600000 | 600000 | 600000 | 3000000
TS018 | Transformer oil replacement | 0 | 0 | 0 | 0 | 0 | 0
TS020 | Portable earthing set cabinets | 0 | 0 | 0 | 0 | 0 | 0
TS024 | Building and amenities refurbishment | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 10000000
TS025 | Asbestos and other hazardous material reporting, management and removal | 520000 | 520000 | 520000 | 520000 | 520000 | 2600000
TS026 | Noise attenuation in ZS and TS | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
TS027 | Substation switchyard lighting improvement | 120000 | 120000 | 120000 | 120000 | 120000 | 600000
TS028 | Control cable trench and cover refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TS029 | Substation control room temperature reduction initiatives | 0 | 0 | 0 | 0 | 0 | 0
TS031 | Substation safety fence upgrade program | 100000 | 100000 | 100000 | 100000 | 100000 | 500000
TS032 | Substation security systems | 150000 | 150000 | 150000 | 0 | 0 | 450000
TS033 | Substation fire hydrant installations | 200000 | 200000 | 200000 | 200000 | 200000 | 1000000
TS034 | Substation deluge showers and fire blankets | 160000 | 160000 | 160000 | 160000 | 160000 | 800000
TS035 | Substation oil containment program - bund walls | 70000 | 70000 | 70000 | 70000 | 70000 | 350000
TS036 | Substation earthing | 1000000 | 500000 | 500000 | 500000 | 500000 | 3000000
TS047 | Equipment labelling in TS & ZS | 0 | 0 | 0 | 0 | 0 | 0
TS048 | Substation oil containment program - separators | 0 | 0 | 0 | 0 | 0 | 0
TS049 | Tunnelboard refurbishment | 45000 | 45000 | 45000 | 45000 | 45000 | 225000
TS050 | POW switching for capacitors | 0 | 0 | 0 | 600000 | 0 | 600000
TS055 | 66kV circuit breaker replacement | 258000 | 258000 | 258000 | 258000 | 258000 | 1290000
TS057 | Substation insulation co-ordination | 150000 | 150000 | 150000 | 150000 | 150000 | 750000
TS060 | Lawson TS rebuild | 0 | 0 | 0 | 0 | 0 | 0
TS067 | Rosehill ZS renewal | 0 | 0 | 0 | 0 | 0 | 0
TS072 | Holroyd ZS renewal | 0 | 0 | 0 | 0 | 0 | 0
TS086 | Busbar support and isolator replacement | 94500 | 94500 | 94500 | 94500 | 94500 | 472500
TS092 | Jasper Rd 11kV CB renewal | 0 | 0 | 0 | 0 | 0 | 0
TS099 | Substation power outlet installation | 0 | 0 | 0 | 0 | 0 | 0
TS100 | Substation internal fence replacement | 0 | 0 | 0 | 0 | 0 | 0
TS102 | Rydalmere Zone Substation renewal | 0 | 0 | 0 | 0 | 0 | 0
TS111 | Blackheath ZS 11kV switchyard renewal | 0 | 0 | 0 | 0 | 0 | 0
TS116 | Roof refurbishment for control and switch rooms | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 7500000
TS118 | Smithfield Zone Substation rebuilding | 0 | 0 | 0 | 0 | 0 | 0
TS119 | Bomaderry ZS redevelopment (fmr PR403) | 0 | 0 | 0 | 0 | 0 | 0
TS120 | Canley Vale ZS redevelopment | 0 | 0 | 0 | 0 | 0 | 0
TS121 | Port Kembla ZS | 0 | 0 | 0 | 0 | 0 | 0
TS122 | Leabons Lane Zone Substation renewal | 0 | 0 | 0 | 0 | 0 | 0
TS123 | St Marys Zone Substation renewal | 0 | 0 | 0 | 0 | 0 | 0
TS124 | Substation control building fire alarm systems | 0 | 0 | 0 | 0 | 0 | 0
TS125 | Guildford Transmission Substation renewal | 0 | 0 | 0 | 0 | 0 | 0
TS126 | Comalco HVC renewal | 0 | 0 | 0 | 0 | 0 | 0
TS127 | Castle Hill Zone Substation renewal | 0 | 0 | 0 | 0 | 0 | 0
TS128 | Capacitor bank refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TS130 | Northmead Zone Substation renewal | 0 | 0 | 0 | 0 | 0 | 0
TS131 | Bulli Zone Substation renewal | 0 | 0 | 0 | 0 | 0 | 0
TS133 | Corrimal ZS redevelopment | 0 | 0 | 0 | 0 | 0 | 0
TS134 | South Granville Zone Substation renewal | 0 | 0 | 0 | 0 | 0 | 0
TS135 | Ringwood ZS redevelopment | 0 | 0 | 0 | 0 | 0 | 0
TS136 | Kandos ZS redevelopment | 0 | 0 | 0 | 0 | 0 | 0
TS137 | Power transformer oil temperature indicator | 0 | 0 | 0 | 0 | 0 | 0
TS138 | Baulkham Hills switchgear rearrangement | 0 | 0 | 0 | 0 | 0 | 0
TS139 | Oakdale ZS swgr rearrangement | 0 | 0 | 0 | 0 | 0 | 0
TS143 | Westmead Zone Substation renewal and augmentation | 0 | 0 | 0 | 0 | 0 | 0
TS144 | Substation fire stopping measures | 66000 | 66000 | 66000 | 66000 | 66000 | 330000
TS146 | Marayong Zone Substation renewal | 6698000 | 0 | 0 | 0 | 0 | 6698000
TS149 | South Windsor ZS refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TS155 | Sussex Inlet Zone Substation - stage 2 renewal | 3663000 | 3771428.5714 | 0 | 0 | 0 | 7434428.5714
TS156 | Lawson TS - RailCorp connections works | 0 | 0 | 0 | 0 | 0 | 0
TS163 | Unanderra Zone Substation renewal | 0 | 0 | 4000000 | 5000000 | 6000000 | 15000000
TS165 | Greystanes Zone Substation renewal | 0 | 0 | 0 | 0 | 6970000 | 6970000
TS167 | Carlingford Transmission Substation control building replacement | 4500000 | 4500000 | 4500000 | 0 | 0 | 13500000
TS168 | Carramar Zone Substation switchgear replacement | 0 | 0 | 0 | 0 | 0 | 0
TS173 | 11kV switchboard truck replacement program | 0 | 0 | 0 | 0 | 0 | 0
TS174 | West Wollongong Zone Substation 11kV renewal | 0 | 3000000 | 4000000 | 5500000 | 0 | 12500000
TS175 | Defective CT replacement program | 0 | 0 | 0 | 0 | 0 | 0
TS177 | Substation battery duplication | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5000000
TS178 | Jerrara SS steel support structures | 0 | 0 | 0 | 0 | 0 | 0
TS179 | 33kV wall bushing replacement | 120000 | 120000 | 180000 | 180000 | 180000 | 780000
TS180 | Transformer fire wall installation | 200000 | 200000 | 200000 | 200000 | 200000 | 1000000
TS181 | 11kV capacitor bank refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TS182 | Substation civil capital works scoping | 0 | 0 | 0 | 0 | 0 | 0
TS184 | Blaxland Zone Substation reinstatement | 0 | 0 | 0 | 0 | 0 | 0
TS185 | Penrith TS civil development | 2000000 | 0 | 0 | 0 | 0 | 2000000
TS187 | Mobile substation No 2 refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TS188 | Bossley Park ZS civil refurbishment | 0 | 0 | 0 | 0 | 0 | 0
TS199 | Future sub-transmission substation renewal programs | 4000000 | 6000000 | 6000000 | 6000000 | 12000000 | 34000000
TS600 | Power transformer replacement | 10000000 | 12000000 | 12000000 | 14000000 | 14000000 | 62000000
TS601 | Cranebrook ZS 33kV No 3 - transformer replacement | 0 | 0 | 0 | 0 | 0 | 0
TS602 | Prospect ZS 33kV No3 transformer | 0 | 0 | 0 | 0 | 0 | 0
TS603 | Kingwood ZS 33kV No 3 - transformer replacement | 0 | 0 | 0 | 0 | 0 | 0
TS604 | Liverpool TS 132kV No 3 - transformer replacement | 0 | 0 | 0 | 0 | 0 | 0
TS605 | West Liverpool 132 kV No 3 transformer | 0 | 0 | 0 | 0 | 0 | 0
TS615 | Gerringong ZS 33kV No 2 transformer replacement | 0 | 0 | 0 | 0 | 0 | 0
TS616 | Camellia TS transformer replacement and 33kV busbar rearrangement | 0 | 0 | 0 | 0 | 0 | 0
TS617 | Prospect ZS transformer replacement | 0 | 0 | 0 | 0 | 0 | 0
TS618 | Albion Park ZS transformer replacement | 0 | 0 | 0 | 0 | 0 | 0
TS619 | Dundas ZS 66kV No 2 transformer | 0 | 0 | 0 | 0 | 0 | 0
TS700 | 11kV zone substation switchboard replacement | 6250000 | 6875000 | 6875000 | 7500000 | 7500000 | 35000000
TS701 | North Rocks ZS 11kV switchboard replacement | 0 | 0 | 0 | 0 | 0 | 0
TS702 | Kellyville ZS 11kV switchboard replacement | 0 | 0 | 0 | 0 | 0 | 0
TS703 | Horsley Park ZS 11kV switchboard replacement | 0 | 0 | 0 | 0 | 0 | 0
TS704 | Port Central ZS 11kV switchboard replacement | 0 | 0 | 0 | 0 | 0 | 0
UR | Underground residential | 43969550 | 42124113 | 42033971 | 42179479 | 42961866 | 213268979

## Comp (hidden)
ID | Description | PIP FY20 | PIP FY19 | Diff | % Diff
AG | Automation - operational/capacity risk | 1500000 | 1500000 | 0 | 0%
AR | Asset relocation | 7798056 | 9106168 | -1308112 | -14.37%
AU004 | Substation SCADA RTU replacement | 10900000 | 9200000 | 1700000 | 18.48%
AU013 | SCADA master station development software | 7550000 | 8000000 | -450000 | -5.625%
CC002 | Communications development SCADA | 2725000 | 2500000 | 225000 | 9%
CC007 | SCADA radio repeaters | 3900000 | 3480000 | 420000 | 12.07%
CC020 | Microwave refurbishment and extension | 2540000 | 2250000 | 290000 | 12.89%
DS002 | Pole substation refurbishment | 3650000 | 3832500 | -182500 | -4.762%
DS005 | Distribution pole replacement | 64350000 | 64350000 | 0 | 0%
DS006 | LV CONSAC cable replacement | 45000000 | 58500000 | -13500000 | -23.08%
DS007 | Service wire replacement program | 47050000 | 64050000 | -17000000 | -26.54%
DS008 | Traffic black spot remediation | 5000000 | 5000000 | 0 | 0%
DS011 | HV distribution steel mains replacement | 24640000 | 25600000 | -960000 | -3.75%
DS014 | LV cable network renewal | 5200000 | 8580000 | -3380000 | -39.39%
DS301 | Ground substation refurbishment program | 3740000 | 3740000 | 0 | 0%
DS302 | Distribution transformer replacement program | 6875000 | 6435000 | 440000 | 6.838%
DS305 | Compact LV switchgear replacement | 2500000 | 2500000 | 0 | 0%
DS307 | Holec MD4 epoxy switchgear replacement | 29400000 | 35875000 | -6475000 | -18.05%
DS312 | Miscellaneous substation renewal expenditure | 7500000 | 17500000 | -10000000 | -57.14%
DS315 | Low voltage switchgear replacement | 3540000 | 3540000 | 0 | 0%
DS318 | Distribution substation earthing refurbishment | 1350000 | 1350000 | 0 | 0%
DS405 | Air break switch replacement program | 18200000 | 18450000 | -250000 | -1.355%
DS409 | Miscellaneous mains renewal expenditure | 5475000 | 12500000 | -7025000 | -56.2%
DS413 | Low mains remediation | 8125000 | 8125000 | 0 | 0%
DS414 | Copper distribution mains replacement | 3840000 | 11040000 | -7200000 | -65.22%
DS415 | LV mains replacement | 5500000 | 7500000 | -2000000 | -26.67%
DS416 | Asbestos service fuse replacement | 261000 | 261000 | 0 | 0%
DS417 | Distribution access track reconstruction | 5632000 | 5632000 | 0 | 0%
DS418 | Pole top structure/hardware refurbishment (LV) | 13048250 | 44000000 | -30951750 | -70.34%
DS421 | Pole top structure/hardware refurbishment (HV) | 16242150 | 0 | 16242150 | New
DU | Duct installation RMS road works | 11315460 | 11315460 | 0 | 0%
EF001 | Distribution management system | 12295121 | 12295120.5003 | 0.49972 | 4.064e-06%
EF002 | Technology pilots | 7000000 | 7000000 | 0 | 0%
HVW | HV development works | 32773419 | 32773419 | 0 | 0%
IC | Industrial & commercial | 25984980 | 67241683 | -41256703 | -61.36%
LV001 | Overloaded distribution sub uprates | 400000 | 600000 | -200000 | -33.33%
LV002 | Quality of supply reactive projects | 2500000 | 2500000 | 0 | 0%
LV003 | LV planning reactive projects | 5000000 | 5000000 | 0 | 0%
LV005 | Dsub monitoring & LV feeder monitoring for solar PV | 1250000 | 1250000 | 0 | 0%
MC104 | Meters - renewal | 150000 | 25000 | 125000 | 500%
MC105 | Relays - renewal | 4283928 | 4283928 | 0 | 0%
MC107 | Test equipment | 520000 | 405000 | 115000 | 28.4%
MC109 | Demand management technology | 4400000 | 4400000 | 0 | 0%
NU | Non urban extension | 3675379 | 8431413 | -4756034 | -56.41%
PQ001 | Permanent power quality monitoring | 500000 | 500000 | 0 | 0%
PQ004 | Power quality monitoring replacement | 4145538 | 4145538 | 0 | 0%
PR110 | Edmondson Park ZS establishment | 1770965 | 1893515.7644 | -122550.7644 | -6.472%
PR113 | Augment feeder 308 Nepean to Douglas Park | 8755000 | 6072000 | 2683000 | 44.19%
PR248 | Penrith Lakes ZS site acquisition | 0 | 1000000 | -1000000 | -100%
PR249 | Establish Penrith Lakes 33/11kV Zone Substation | 0 | 3610000 | -3610000 | -100%
PR258 | Menangle Park 66/11kV ZS establishment | 4495754 | 10270000 | -5774246 | -56.22%
PR292 | South Marsden Park (industrial) 132/11kV ZS establishment | 1215012 | 9560975.6098 | -8345963.6098 | -87.29%
PR423 | Maryland ZS establishment | 20633600 | 20834000 | -200400 | -0.9619%
PR425 | Austral ZS establishment (interim initially) | 3556000 | 2379535.9905 | 1176464.0095 | 49.44%
PR427 | Leppington North ZS establishment | 1755910 | 3196021.8917 | -1440111.8917 | -45.06%
PR430 | North Rossmore ZS site purchase | 3000000 | 3000000 | 0 | 0%
PR432 | Rossmore ZS site purchase | 3000000 | 3000000 | 0 | 0%
PR436 | Catherine Fields ZS site purchase | 653024 | 0 | 653024 | New
PR438 | North Bringelly ZS site purchase | 3500000 | 3500000 | 0 | 0%
PR499 | Southpipe (Oakdale Estate) ZS 132/11kV establishment | 31736000 | 27260000 | 4476000 | 16.42%
PR620 | West Dapto ZS establishment | 16928000 | 20645000 | -3717000 | -18%
PR656 | Leppington South ZS establishment (permanent) | 17093338 | 14098750.7436 | 2994587.2564 | 21.24%
PR657 | Calderwood ZS establishment (interim initially) | 2953000 | 15702000 | -12749000 | -81.19%
PR659 | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | 0 | 2500000 | -2500000 | -100%
PR673 | Liverpool ZS 11kV switchboard extension & distribution works | 292683 | 0 | 292683 | New
PR677 | South Penrith Zone Substation | 17478000 | 28075000 | -10597000 | -37.75%
PR698 | Marsden Park (residential) 132/11kV ZS - stage 2 | 6128000 | 8925000 | -2797000 | -31.34%
PR700 | Riverstone east ZS establishment | 16928000 | 20645000 | -3717000 | -18%
PR703 | Riverstone East site purchase | 6000000 | 6000000 | 0 | 0%
PR704 | Oakdale (Southpipe) site purchase | 195122 | 0 | 195122 | New
PR713 | Box Hill 132/22kV ZS establishment | 35848000 | 34820000 | 1028000 | 2.952%
PR717 | Acquire improved site for West Dapto ZS | 2000000 | 2000000 | 0 | 0%
PR722 | Camellia TS connection works for Ausgrid | 379962 | 126795.1695 | 253166.8305 | 199.7%
PR723 | Supply to Luddenham Science Park | 25851000 | 40520000 | -14669000 | -36.2%
PR724 | Establish Mt Gilead ZS | 16723000 | 19270000 | -2547000 | -13.22%
PR727 | Luddenham ZS site purchase | 0 | 975609.7561 | -975609.7561 | -100%
PR728 | Western Sydney Employment Lands ZS | 22585000 | 23480000 | -895000 | -3.812%
PR732 | Feeder 214/215 contraints | 10280000 | 9450000 | 830000 | 8.783%
PR739 | South Gilead (South Campbelltown) | 0 | 3854000 | -3854000 | -100%
PR740 | AFIC upgrade Minto, Prospect, Kingswood | 311163 | 0 | 311163 | New
PR741 | Western Sydney Airport 132kV supply | 39300000 | 61233501 | -21933501 | -35.82%
PR742 | North Bomaderry ZS establishment | 14916000 | 18460000 | -3544000 | -19.2%
PR744 | Termeil ZS establishment | 0 | 7945000 | -7945000 | -100%
PR748 | Establish permanent Catherine Park ZS | 1900000 | 21978000 | -20078000 | -91.35%
PR751 | Parklea ZS to Bella Vista ZS load transfer | 1000000 | 4000000 | -3000000 | -75%
PR754 | Augment Westmead Zone Substation | 10253000 | 12835000 | -2582000 | -20.12%
PR761 | Glenfield Zone Substation site acquisition | 3000000 | 0 | 3000000 | New
PR765 | Minto 66kV Reconfiguration | 700000 | 0 | 700000 | New
PR766 | Baulkham Hills 132kV bus section CB | 350000 | 0 | 350000 | New
PR767 | Mt Terry 132kV bus section CB | 400000 | 0 | 400000 | New
PR769 | Nepean TS 132kV bus section CB | 600000 | 0 | 600000 | New
PS008 | Substation protection relay refurbishment | 22375000 | 21090000 | 1285000 | 6.093%
PS011 | Protection refurbishment (miscellaneous) | 3500000 | 3500000 | 0 | 0%
PS012 | Distribution feeder safety improvement | 3100000 | 3100000 | 0 | 0%
PS013 | Feeder differential relay replacement | 1320000 | 1650000 | -330000 | -20%
PS014 | Under frequency load shedding | 1100000 | 1100000 | 0 | 0%
RC | Reliability compliance | 20000000 | 20000000 | 0 | 0%
SL001 | Streetlighting growth | 8750000 | 8750000 | 0 | 0%
SL002 | Streetlighting refurbishment | 15000000 | 15000000 | 0 | 0%
SP | Essential spares | 5000000 | 5000000 | 0 | 0%
TM012 | Sub-transmission pole replacement | 19800000 | 19800000 | 0 | 0%
TM014 | Renewal of 33kV and 66kV gas and oil filled cables | 0 | 720000 | -720000 | -100%
TM015 | Subtransmission tower replacement | 4800000 | 18400000 | -13600000 | -73.91%
TM028 | 132kV oil cable replacement | 0 | 39600000 | -39600000 | -100%
TM030 | Feeder 7028 replacement | 4800000 | 10450000 | -5650000 | -54.07%
TM031 | Steel tower asbestos removal | 2812195 | 0 | 2812195 | New
TM033 | Pole top structure/hardware refurbishment (TR) | 6738350 | 0 | 6738350 | New
TM132 | Sub-transmission pilot cable renewal program | 0 | 4750000 | -4750000 | -100%
TM134 | Wollongong - Port Kembla pilot cable replacement | 0 | 8075000 | -8075000 | -100%
TM135 | Optical fibre protection and communication upgrades in the Blue Mountains | 0 | 3250000 | -3250000 | -100%
TM137 | Optical fibre protection and communication upgrades in the Macarthur area | 0 | 6400000 | -6400000 | -100%
TM171 | Replacement of corroded earthwires | 138000 | 17340000 | -17202000 | -99.2%
TM172 | Earthwire replacement due to fault rating | 2000000 | 5000000 | -3000000 | -60%
TM174 | Hardex earthwire replacement | 4000000 | 5000000 | -1000000 | -20%
TM302 | Oil filled cable auxiliary equipment refurbishment | 72000 | 72000 | 0 | 0%
TM303 | Guilford and Camellia 132kV cables oil testing and flushing | 90000 | 90000 | 0 | 0%
TM401 | South Coast 33kV overhead line refurbishment | 0 | 5760000 | -5760000 | -100%
TM803 | Steel tower below ground rectification work | 6000000 | 10500000 | -4500000 | -42.86%
TM805 | Earthing refurbishment of lines 940/941 | 1140000 | 1140000 | 0 | 0%
TM809 | Subtransmission line earthing refurbishment | 2400000 | 2400000 | 0 | 0%
TS004 | 132kV circuit breaker replacement | 724000 | 1810000 | -1086000 | -60%
TS005 | 33kV circuit breaker replacement | 1540000 | 4257500 | -2717500 | -63.83%
TS007 | 11kV circuit breaker replacement | 700000 | 700000 | 0 | 0%
TS008 | Battery replacement | 2600000 | 6000000 | -3400000 | -56.67%
TS009 | Auxiliary switchgear replacement | 282000 | 5000000 | -4718000 | -94.36%
TS015 | Replacement of surge arrester in zone and sub-transmission substations | 441000 | 484000 | -43000 | -8.884%
TS016 | VT and CT replacement | 1396000 | 3500000 | -2104000 | -60.11%
TS017 | Power transformer refurbishment | 0 | 3000000 | -3000000 | -100%
TS024 | Building and amenities refurbishment | 7500000 | 10000000 | -2500000 | -25%
TS025 | Asbestos and other hazardous material reporting, management and removal | 2027000 | 2600000 | -573000 | -22.04%
TS026 | Noise attenuation in ZS and TS | 2000000 | 5000000 | -3000000 | -60%
TS027 | Substation switchyard lighting improvement | 550000 | 600000 | -50000 | -8.333%
TS031 | Substation safety fence upgrade program | 500000 | 500000 | 0 | 0%
TS032 | Substation security systems | 450000 | 450000 | 0 | 0%
TS033 | Substation fire hydrant installations | 1000000 | 1000000 | 0 | 0%
TS034 | Substation deluge showers and fire blankets | 800000 | 800000 | 0 | 0%
TS035 | Substation oil containment program - bund walls | 350000 | 350000 | 0 | 0%
TS036 | Substation earthing | 748000 | 3000000 | -2252000 | -75.07%
TS049 | Tunnelboard refurbishment | 90000 | 225000 | -135000 | -60%
TS050 | POW switching for capacitors | 0 | 600000 | -600000 | -100%
TS055 | 66kV circuit breaker replacement | 516000 | 1290000 | -774000 | -60%
TS057 | Substation insulation co-ordination | 0 | 750000 | -750000 | -100%
TS086 | Busbar support and isolator replacement | 378000 | 472500 | -94500 | -20%
TS116 | Roof refurbishment for control and switch rooms | 7500000 | 7500000 | 0 | 0%
TS144 | Substation fire stopping measures | 330000 | 330000 | 0 | 0%
TS146 | Marayong Zone Substation renewal | 10033955 | 6698000 | 3335955 | 49.81%
TS155 | Sussex Inlet Zone Substation - stage 2 renewal | 1715901 | 7434428.5714 | -5718527.5714 | -76.92%
TS163 | Unanderra Zone Substation renewal | 0 | 15000000 | -15000000 | -100%
TS165 | Greystanes Zone Substation renewal | 0 | 6970000 | -6970000 | -100%
TS167 | Carlingford Transmission Substation control building replacement | 13500000 | 13500000 | 0 | 0%
TS173 | 11kV switchboard truck replacement program | 16800000 | 0 | 16800000 | New
TS174 | West Wollongong Zone Substation 11kV renewal | 0 | 12500000 | -12500000 | -100%
TS177 | Substation battery duplication | 1683000 | 5000000 | -3317000 | -66.34%
TS179 | 33kV wall bushing replacement | 0 | 780000 | -780000 | -100%
TS180 | Transformer fire wall installation | 2400000 | 1000000 | 1400000 | 140%
TS185 | Penrith TS civil development | 0 | 2000000 | -2000000 | -100%
TS199 | Future sub-transmission substation renewal programs | 0 | 34000000 | -34000000 | -100%
TS600 | Power transformer replacement | 42900000 | 62000000 | -19100000 | -30.81%
TS616 | Camellia TS transformer replacement and 33kV busbar rearrangement | 332642 | 0 | 332642 | New
TS617 | Prospect ZS transformer replacement | 29268 | 0 | 29268 | New
TS618 | Albion Park ZS transformer replacement | 1577261 | 0 | 1577261 | New
TS620 | Minto 66/11kV No 1 transformer replacement | 1080563 | 0 | 1080563 | New
TS700 | 11kV zone substation switchboard replacement | 28000000 | 35000000 | -7000000 | -20%
TS701 | North Rocks ZS 11kV switchboard replacement | 813715 | 0 | 813715 | New
TS702 | Kellyville ZS 11kV switchboard replacement | 1218537 | 0 | 1218537 | New
TS703 | Horsley Park ZS 11kV switchboard replacement | 424390 | 0 | 424390 | New
TS704 | Port Central ZS 11kV switchboard replacement | 488652 | 0 | 488652 | New
UR | Underground residential | 69878786 | 213268979 | -143390193 | -67.23%

## Excl. Escalators --->
Capex Listing Exclusive of Escalators

## Escalators
Escalators
Labour escalators
| FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28
Labour - WPI utility |  | 0.4866% | 0.7667% | 1.172% | 1.303% | 1.105% | 0% | 0% | 0% | 0% | <--- Inputs
System capex labour proportion |  | 23.8% | 23.8% | 23.8% | 23.8% | 23.8% | 23.8% | 23.8% | 23.8% | 23.8% | <--- Inputs
Labour escalator |  | 0.1158% | 0.1825% | 0.2789% | 0.3101% | 0.2631% | 0% | 0% | 0% | 0%
Index | 1 | 1.0012 | 1.003 | 1.0058 | 1.0089 | 1.0116 | 1.0116 | 1.0116 | 1.0116 | 1.0116

## Plan Lvl (excl. Esc)
SAMP | Description | FY20 (R) | FY21 (R) | FY22 (R) | FY23 (R) | FY24 (R) | FY25 (R) | FY26 (R) | FY27 (R) | FY28 (R) | FY29 (R) | FY20 (N) | FY21 (N) | FY22 (N) | FY23 (N) | FY24 (N) | FY25 (N) | FY26 (N) | FY27 (N) | FY28 (N) | FY29 (N) | Total (R) | Total (N)
PR | Major projects | 48723555.1824 | 53871125.8528 | 67077176.1351 | 83630508.7034 | 77568136.4019 | 70253019.5917 | 68965204.3556 | 72833004.7418 | 77351341.6436 | 65032400 | 49941644.062 | 56598351.5991 | 72234782.1313 | 92312433.5563 | 87761226.5837 | 81471964.43 | 81977955.9164 | 88739944.0118 | 96601226.2545 | 83246970.112 | 685305472.6083 | 790886498.6572 | Growth
PRL | Major projects - land | 8837911.5278 | 2991071.7709 | 3479878.1187 | 2973531.3129 | 2965728.5678 | 2768013.3299 | 0 | 4942880.9463 | 0 | 5000000 | 9058859.316 | 3142494.7793 | 3747448.1222 | 3282222.1938 | 3355449.6588 | 3210046.8402 | 0 | 6022420.467 | 0 | 6400422.721 | 33959015.5742 | 38219364.0983 | Growth
AG | Automation growth | 299652.996 | 299107.1771 | 298275.2673 | 297353.1313 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 300000 | 307144.3209 | 314249.4779 | 321209.839 | 328222.2194 | 335544.9659 | 343933.59 | 352531.9298 | 361345.228 | 370378.8587 | 384025.3633 | 2977252.8556 | 3418585.793 | Growth
HV | Distribution works program | 6792977.6008 | 7081923.742 | 6609151.5572 | 6219682.9147 | 5879158.4894 | 5931457.1355 | 5931457.1355 | 5931457.1355 | 5931457.1355 | 6000000 | 6962802.0408 | 7440446.1315 | 7117333.3511 | 6865366.1769 | 6651728.1998 | 6878671.8005 | 7050638.5955 | 7226904.5604 | 7407577.1744 | 7680507.2652 | 62308722.8463 | 71281975.2961 | Growth
EH | Dist environmental enhancement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Growth
LV | Low voltage development capital | 1827883.2759 | 1824553.7802 | 1819479.1306 | 1813854.1008 | 1809094.4263 | 1809094.4263 | 1809094.4263 | 1809094.4263 | 1809094.4263 | 1830000 | 1873580.3578 | 1916921.8154 | 1959380.0182 | 2002155.5382 | 2046824.2919 | 2097994.8992 | 2150444.7716 | 2204205.8909 | 2259311.0382 | 2342554.7159 | 18161242.4193 | 20853373.3372 | Growth
AR | Asset relocation | 1621771.9568 | 1559196.86 | 1533617.0857 | 1521457.8463 | 1515555.5099 | 1515555.5099 | 1515555.5099 | 1515555.5099 | 1515555.5099 | 1533069 | 1662316.2557 | 1638131.201 | 1651537.8619 | 1679404.7832 | 1714711.951 | 1757579.7498 | 1801519.2435 | 1846557.2246 | 1892721.1552 | 1962457.9321 | 15346890.2981 | 17606937.358 | Growth
DU | Duct installation RMS road works | 2150240.9794 | 2199982.1417 | 2248710.1656 | 2297801.2779 | 2349066.6038 | 2349066.6038 | 2349066.6038 | 2349066.6038 | 2349066.6038 | 2558920 | 2203997.0039 | 2311356.2376 | 2421614.8956 | 2536342.6706 | 2657753.2482 | 2724197.0794 | 2792302.0064 | 2862109.5565 | 2933662.2955 | 3275633.9418 | 23200987.5837 | 26718968.9356 | Growth
IC | Industrial & commercial | 7492767.2309 | 5316679.9239 | 4557732.5844 | 4283219.2149 | 4197052.606 | 4197052.606 | 4197052.606 | 4197052.606 | 4197052.606 | 4245553 | 7680086.4117 | 5585836.8451 | 4908179.4914 | 4727872.5828 | 4748579.7884 | 4867294.2831 | 4988976.6402 | 5113701.0562 | 5241543.5826 | 5434666.7769 | 46881214.9843 | 53296737.4583 | Growth
NU | Non-urban extension | 1018160.95 | 740910.4122 | 658001.2052 | 626120.6297 | 612340.8974 | 612340.8974 | 612340.8974 | 612340.8974 | 612340.8974 | 619417 | 1043614.9737 | 778419.0018 | 708595.3291 | 691120.0222 | 692807.5204 | 710127.7084 | 727880.9012 | 746077.9237 | 764729.8718 | 792906.1281 | 6724314.6842 | 7656279.3804 | Growth
UR | Underground residential | 21633998.4122 | 14557232.2464 | 11691183.4582 | 10959043.8153 | 10680249.93 | 10680249.93 | 10680249.93 | 10680249.93 | 10680249.93 | 10803669 | 22174848.3725 | 15294192.1288 | 12590125.8613 | 12096733.8323 | 12083722.4865 | 12385815.5487 | 12695460.9374 | 13012847.4609 | 13338168.6474 | 13829609.7075 | 123046376.5821 | 139501524.9833 | Growth
RC | Reliability compliance | 3995373.2806 | 3988095.6945 | 3977003.5642 | 3964708.4171 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 4000000 | 4095257.6126 | 4189993.0391 | 4282797.8539 | 4376296.2584 | 4473932.8784 | 4585781.2003 | 4700425.7303 | 4817936.3736 | 4938384.7829 | 5120338.1768 | 39696704.7416 | 45581143.9063 | Reliability
PQ | Power quality capital | 441888.2848 | 715564.07 | 967704.3923 | 1038357.1344 | 1447807.3951 | 1383571.6914 | 1512043.0987 | 1512043.0987 | 1255100.2842 | 1269604 | 452935.492 | 751789.501 | 1042111.7878 | 1146151.9901 | 1638061.1775 | 1604518.9842 | 1797344.0903 | 1842277.6926 | 1567448.2685 | 1625200.4576 | 11543683.4496 | 13467839.4416 | Reliability
TS | Transmission substation capital (rebuild) | 25964859.1918 | 33388792.7944 | 27243965.7913 | 33840273.1059 | 34000595.1652 | 28610877.7814 | 29232692.2044 | 32692708.8668 | 35643608.7917 | 40757500 | 26613980.6716 | 35079100.4296 | 29338771.3484 | 37353329.6766 | 38468552.6131 | 33179846.6523 | 34748484.7647 | 39832891.2108 | 44513983.1353 | 52173045.8101 | 321375873.6929 | 371301986.3125 | Sustainability
TM | Transmission mains capital (refurb) | 10707465.5482 | 12133452.1327 | 11938636.597 | 9324667.1087 | 10365883.6904 | 23552501.4789 | 30203642.0802 | 34195512.7324 | 38792392.0125 | 44940670 | 10975152.1869 | 12747708.1469 | 12856605.8266 | 10292687.7553 | 11728045.9412 | 27313680.9475 | 35902639.0496 | 41663911.795 | 48446381.9001 | 57527857.0728 | 226154823.3809 | 269454670.622 | Sustainability
DS | Distribution refurbishment capital | 57316706.1477 | 62050860.6729 | 66310648.4681 | 67529470.9976 | 70855783.163 | 71325356.8529 | 76545039.1321 | 87019003.8573 | 100206610.222 | 112764580 | 58749623.8014 | 65192185.4945 | 71409315.673 | 74539900.5843 | 80166815.0014 | 82715546.8939 | 90987997.5303 | 106024206.4382 | 125144324.8502 | 144348195.9908 | 771924059.5136 | 899278112.2579 | Sustainability
AU | Automation capital | 3286194.5233 | 3280208.7087 | 4265336.3226 | 4252149.7774 | 3252415.6627 | 3252415.6627 | 3252415.6627 | 4240991.8519 | 4240991.8519 | 3290000 | 3368349.3864 | 3446269.2746 | 4593300.6983 | 4693577.7371 | 3679809.7925 | 3771805.0373 | 3866100.1632 | 5167236.7607 | 5296417.6797 | 4211478.1504 | 36613120.0238 | 42094344.6802 | Sustainability
CC | Communications refurbishment | 2172484.2213 | 2028943.6846 | 1854277.9118 | 1630486.3365 | 1428492.5935 | 2105667.2831 | 2590069.6159 | 2263839.4734 | 2530755.0445 | 1870000 | 2226796.3269 | 2131658.9586 | 1996854.4994 | 1799751.8363 | 1616208.2523 | 2441928.4892 | 3078778.8534 | 2758268.5739 | 3160566.2611 | 2393758.0976 | 20475016.1646 | 23604570.1486 | Sustainability
PS | Protection systems capital | 8714907.9683 | 6061905.4557 | 5498207.4275 | 5481209.3867 | 5466826.3266 | 5713970.3739 | 5713970.3739 | 5713970.3739 | 5713970.3739 | 5780000 | 8932780.6675 | 6368789.4194 | 5920968.033 | 6050229.5772 | 6185212.2043 | 6626453.8345 | 6792115.1803 | 6961918.0598 | 7135966.0113 | 7398888.6655 | 59858938.0604 | 68373321.653 | Sustainability
EF | Efficiency | 9074857.1402 | 4104642.8061 | 2080827.9199 | 1982354.2086 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 2000000 | 9301728.5687 | 4312440.3481 | 2240824.0791 | 2188148.1292 | 2236966.4392 | 2292890.6002 | 2350212.8652 | 2408968.1868 | 2469192.3915 | 2560169.0884 | 29128443.9673 | 32361540.6964 | Efficiency
MC | Metering capital | 2534648.8277 | 1791836.4402 | 1726801.0281 | 1631860.108 | 1617297.7941 | 1532874.3761 | 1517651.2914 | 1433227.8734 | 1418004.7887 | 1348992 | 2598015.0484 | 1882548.16 | 1859575.8384 | 1801268.2229 | 1829824.007 | 1777664.325 | 1804010.4691 | 1746248.9938 | 1770893.6718 | 1726823.8094 | 16553194.5278 | 18796872.5458 | Miscellaneous
SL | Streetlighting capital | 4744505.7707 | 4735863.6372 | 4722691.7325 | 4708091.2454 | 4695736.899 | 4695736.899 | 4695736.899 | 4695736.899 | 4695736.899 | 4750000 | 4863118.415 | 4975616.7339 | 5085822.4515 | 5196851.8069 | 5312795.2931 | 5445615.1754 | 5581755.5548 | 5721299.4436 | 5864331.9297 | 6080401.5849 | 47139836.8807 | 54127608.3888
SP | Essential spares | 998843.3202 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 1023814.4032 | 1047498.2598 | 1070699.4635 | 1094074.0646 | 1118483.2196 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 9924176.1854 | 11395285.9766 | Miscellaneous
SW | Network switching | 6283900.8865 | 6382175.5445 | 6686467.7532 | 6495126.3573 | 6714861.5396 | 7423719.2767 | 7683873.5145 | 7944102.7058 | 8085985.7683 | 8183178.6979 | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | 10475160.5735 | 71883392.0442 | 83109035.6151 | Switching & Overheads
OH | Capitalised overheads | 73106139.0812 | 73273110.1037 | 73775204.5564 | 73462071.757 | 73820942.4206 | 76860996.0999 | 77233408.4879 | 77593252.7624 | 77784338.9426 | 78058962.8601 | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | 99922071.8932 | 754968427.0719 | 868519522.4252 | Switching & Overheads
| Total | 309741694.3046 | 305374259.576 | 312015229.0639 | 330954575.9922 | 328459632.2638 | 333790143.9881 | 343457170.0069 | 371391699.4738 | 392030259.9135 | 407936515.558 | 317485236.6622 | 320833831.4671 | 336006275.0361 | 365311927.1915 | 371621925.5463 | 387094233.0473 | 408262644.9824 | 452504722.75 | 489592074.7049 | 522193228.5791 | 3435151180.1408 | 3970906099.967
| Check | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK

## Program Lvl (excl. Esc)
Code | ID | Description | FY20 (R) | FY21 (R) | FY22 (R) | FY23 (R) | FY24 (R) | FY25 (R) | FY26 (R) | FY27 (R) | FY28 (R) | FY29 (R) | FY20 (N) | FY21 (N) | FY22 (N) | FY23 (N) | FY24 (N) | FY25 (N) | FY26 (N) | FY27 (N) | FY28 (N) | FY29 (N) | Total (R) | Total (N)
AG | AG | Automation - operational/capacity risk | 299652.996 | 299107.1771 | 298275.2673 | 297353.1313 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 300000 | 307144.3209 | 314249.4779 | 321209.839 | 328222.2194 | 335544.9659 | 343933.59 | 352531.9298 | 361345.228 | 370378.8587 | 384025.3633 | 2977252.8556 | 3418585.793
AR | AR | Asset relocation | 1621771.9568 | 1559196.86 | 1533617.0857 | 1521457.8463 | 1515555.5099 | 1515555.5099 | 1515555.5099 | 1515555.5099 | 1515555.5099 | 1533069 | 1662316.2557 | 1638131.201 | 1651537.8619 | 1679404.7832 | 1714711.951 | 1757579.7498 | 1801519.2435 | 1846557.2246 | 1892721.1552 | 1962457.9321 | 15346890.2981 | 17606937.358
AU | AU004 | Substation SCADA RTU replacement | 2177478.4379 | 2173512.1535 | 2167466.9425 | 2160766.0873 | 2155096.0926 | 2155096.0926 | 2155096.0926 | 2155096.0926 | 2155096.0926 | 2180000 | 2231915.3989 | 2283546.2063 | 2334124.8304 | 2385081.4608 | 2438293.4187 | 2499250.7542 | 2561732.023 | 2625775.3236 | 2691419.7067 | 2790584.3063 | 21634704.0842 | 24841723.429
AU | AU013 | SCADA master station development software | 1108716.0854 | 1106696.5552 | 2097869.3801 | 2091383.69 | 1097319.5701 | 1097319.5701 | 1097319.5701 | 2085895.7593 | 2085895.7593 | 1110000 | 1136433.9875 | 1162723.0683 | 2259175.8679 | 2308496.2763 | 1241516.3737 | 1272554.2831 | 1304368.1402 | 2541461.4371 | 2604997.973 | 1420893.8441 | 14978415.9396 | 17252621.2512
CC | CC002 | Communications development SCADA | 624277.0751 | 523437.5599 | 521981.7178 | 520367.9797 | 519002.4994 | 444859.2852 | 444859.2852 | 444859.2852 | 444859.2852 | 450000 | 639884.002 | 549936.5864 | 562117.2183 | 574388.8839 | 587203.6903 | 515900.385 | 528797.8947 | 542017.842 | 555568.2881 | 576038.0449 | 4938503.9726 | 5631852.8356
CC | CC007 | SCADA radio repeaters | 878982.1217 | 837500.0958 | 845113.2574 | 683912.202 | 632688.7611 | 731546.38 | 612917.2373 | 603031.4754 | 583259.9517 | 490000 | 900956.6748 | 879898.5382 | 910094.544 | 754911.1046 | 715829.2605 | 848369.5221 | 728565.9882 | 734735.297 | 728411.7555 | 627241.4267 | 6898951.4826 | 7829014.1114
CC | CC020 | Microwave refurbishment and extension | 669225.0245 | 668006.0288 | 487182.9366 | 426206.1548 | 276801.333 | 929261.6179 | 1532293.0933 | 1215948.7128 | 1502635.8077 | 930000 | 685955.6501 | 701823.834 | 524642.7371 | 470451.8478 | 313175.3015 | 1077658.5821 | 1821414.9705 | 1481515.4349 | 1876586.2175 | 1190478.6261 | 8637560.7095 | 10143703.2016
DS | DS002 | Pole substation refurbishment | 699190.3241 | 697916.7465 | 695975.6237 | 743382.8282 | 790860.9514 | 790860.9514 | 790860.9514 | 790860.9514 | 790860.9514 | 800000 | 716670.0822 | 733248.7818 | 749489.6244 | 820555.5485 | 894786.5757 | 917156.2401 | 940085.1461 | 963587.2747 | 987676.9566 | 1024067.6354 | 7590770.2796 | 8747323.8654
DS | DS005 | Distribution pole replacement | 11316894.8173 | 12063989.4759 | 12796008.9679 | 13519655.7024 | 14245382.8872 | 15006586.5529 | 16528993.8844 | 17290197.5501 | 17290197.5501 | 17490000 | 11599817.1877 | 12674728.9431 | 13779902.0949 | 14923170.2412 | 16117343.1943 | 17403039.6553 | 19647779.5528 | 21066426.7936 | 21593087.4634 | 22388678.678 | 147547907.3882 | 171193973.8043
DS | DS006 | LV CONSAC cable replacement | 6742192.411 | 7477679.4272 | 9693946.1878 | 9663976.7668 | 11121482.1291 | 11121482.1291 | 11862914.2711 | 11862914.2711 | 12604346.413 | 12750000 | 6910747.2213 | 7856236.9482 | 10439319.7689 | 10667222.1299 | 12582936.2204 | 12897509.6259 | 14101277.191 | 14453809.1208 | 15741101.4956 | 16321077.9385 | 104900934.0062 | 121971237.6605
DS | DS007 | Service wire replacement program | 9189358.5454 | 9272322.4897 | 9246533.2868 | 9366623.6355 | 9688046.6547 | 9688046.6547 | 10182334.7493 | 10182334.7493 | 10676622.844 | 10800000 | 9419092.509 | 9741733.8158 | 9957505.0103 | 10338999.9105 | 10961135.552 | 11235163.9408 | 12103596.2556 | 12406186.162 | 13333638.9139 | 13824913.0773 | 98292223.6095 | 113321965.1473
DS | DS008 | Traffic black spot remediation | 998843.3202 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 1023814.4032 | 1047498.2598 | 1070699.4635 | 1094074.0646 | 1118483.2196 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 9924176.1854 | 11395285.9766
DS | DS011 | HV distribution steel mains replacement | 3691724.9113 | 4299167.1587 | 5205897.6656 | 5342444.5921 | 5937388.5927 | 5937388.5927 | 5937388.5927 | 5937388.5927 | 5937388.5927 | 6006000 | 3784018.0341 | 4516812.4961 | 5606182.3908 | 5897059.2082 | 6717610.2169 | 6885550.4723 | 7057689.2341 | 7234131.465 | 7414984.7516 | 7688187.7724 | 54232177.291 | 62802226.0414
DS | DS014 | LV cable network renewal | 0 | 1296131.1007 | 1292526.1584 | 1288530.2356 | 1285149.046 | 1285149.046 | 1285149.046 | 1285149.046 | 1285149.046 | 1300000 | 0 | 1361747.7377 | 1391909.3025 | 1422296.284 | 1454028.1855 | 1490378.8901 | 1527638.3624 | 1565829.3214 | 1604975.0545 | 1664109.9075 | 11602932.7248 | 13482913.0455
DS | DS301 | Ground substation refurbishment program | 509410.0933 | 508482.2011 | 845113.2574 | 842500.5386 | 1008347.713 | 1260434.6413 | 1260434.6413 | 1260434.6413 | 1260434.6413 | 1275000 | 522145.3456 | 534224.1125 | 910094.544 | 929962.9549 | 1140852.884 | 1461717.7576 | 1498260.7015 | 1535717.2191 | 1574110.1496 | 1632107.7939 | 10030592.3686 | 11739193.4626
DS | DS302 | Distribution transformer replacement program | 1248554.1502 | 1246279.9045 | 1242813.6138 | 1548714.2254 | 1544650.2957 | 1544650.2957 | 1544650.2957 | 1668222.3194 | 1668222.3194 | 1687500 | 1279768.0039 | 1309372.8247 | 1338374.3293 | 1709490.7259 | 1747630.0306 | 1791320.7814 | 1836103.8009 | 2032566.9076 | 2083381.0803 | 2160142.6683 | 14944257.4199 | 17288151.1531
DS | DS305 | Compact LV switchgear replacement | 499421.6601 | 498511.9618 | 497125.4455 | 495588.5521 | 494288.0946 | 494288.0946 | 494288.0946 | 494288.0946 | 494288.0946 | 500000 | 511907.2016 | 523749.1299 | 535349.7317 | 547037.0323 | 559241.6098 | 573222.65 | 587553.2163 | 602242.0467 | 617298.0979 | 640042.2721 | 4962088.0927 | 5697642.9883
DS | DS307 | Holec MD4 epoxy switchgear replacement | 5943117.7549 | 5583333.9723 | 5915792.8018 | 5897503.7705 | 5882028.3261 | 5882028.3261 | 7612036.6573 | 7612036.6573 | 9342044.9885 | 9450000 | 6091695.6988 | 5865990.2547 | 6370661.8077 | 6509740.6844 | 6654975.1566 | 6821349.5355 | 9048319.5309 | 9274527.5192 | 11666934.0497 | 12096798.9427 | 69119923.2547 | 80400993.18
DS | DS312 | Miscellaneous substation renewal expenditure | 1498264.9802 | 1495535.8854 | 1491376.3366 | 1486765.6564 | 1482864.2839 | 1482864.2839 | 1977152.3785 | 1977152.3785 | 2471440.4731 | 2500000 | 1535721.6047 | 1571247.3896 | 1606049.1952 | 1641111.0969 | 1677724.8294 | 1719667.9501 | 2350212.8652 | 2408968.1868 | 3086490.4893 | 3200211.3605 | 17863416.6566 | 20797404.9678
DS | DS315 | Low voltage switchgear replacement | 707181.0707 | 705892.9379 | 703929.6309 | 701753.3898 | 699911.942 | 699911.942 | 699911.942 | 699911.942 | 699911.942 | 708000 | 724860.5974 | 741628.7679 | 758055.2201 | 774604.4377 | 791886.1195 | 811683.2725 | 831975.3543 | 852774.7381 | 874094.1066 | 906299.8573 | 7026316.7393 | 8067862.4714
DS | DS317 | Future distribution substation renewals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4448592.8517 | 9193758.5601 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5420178.4203 | 11481744.6203 | 19201268.1629 | 28642351.4117 | 36103191.2036
DS | DS318 | Distribution substation earthing refurbishment | 269687.6964 | 269196.4594 | 268447.7406 | 267617.8182 | 266915.5711 | 266915.5711 | 266915.5711 | 266915.5711 | 266915.5711 | 270000 | 276429.8889 | 282824.5301 | 289088.8551 | 295399.9974 | 301990.4693 | 309540.231 | 317278.7368 | 325210.7052 | 333340.9728 | 345622.8269 | 2679527.5701 | 3076727.2137
DS | DS405 | Air break switch replacement program | 3635789.6853 | 3629167.082 | 3619073.2434 | 3607884.6596 | 3598417.3289 | 3598417.3289 | 3598417.3289 | 3598417.3289 | 3598417.3289 | 3640000 | 3726684.4275 | 3812893.6655 | 3897346.0471 | 3982429.5952 | 4071278.9193 | 4173060.8923 | 4277387.4146 | 4384322.1 | 4493930.1525 | 4659507.7409 | 36124001.3149 | 41478840.9548
DS | DS409 | Miscellaneous mains renewal expenditure | 1093733.4356 | 1091741.1964 | 1088704.7257 | 1085338.9292 | 1082490.9272 | 1186291.4271 | 1186291.4271 | 1186291.4271 | 1186291.4271 | 1200000 | 1121076.7715 | 1147010.5944 | 1172415.9125 | 1198011.1007 | 1224739.1255 | 1375734.3601 | 1410127.7191 | 1445380.9121 | 1481515.4349 | 1536101.453 | 11387174.9225 | 13112113.3838
DS | DS413 | Low mains remediation | 1623120.3952 | 1620163.8759 | 1615657.698 | 1610662.7945 | 1606436.3075 | 963861.7845 | 963861.7845 | 963861.7845 | 963861.7845 | 975000 | 1663698.4051 | 1702184.6721 | 1739886.6281 | 1777870.355 | 1817535.2318 | 1117784.1676 | 1145728.7718 | 1174371.9911 | 1203731.2908 | 1248082.4306 | 12906488.2092 | 14590873.9441
DS | DS414 | Copper distribution mains replacement | 0 | 957142.9667 | 954480.8554 | 951530.0201 | 949033.1417 | 949033.1417 | 1186291.4271 | 1660807.998 | 1898066.2834 | 1920000 | 0 | 1005598.3294 | 1027871.4849 | 1050311.102 | 1073743.8908 | 1100587.4881 | 1410127.7191 | 2023533.2769 | 2370424.6958 | 2457762.3249 | 11426385.834 | 13519960.3119
DS | DS415 | LV mains replacement | 1098727.6522 | 1096726.316 | 1093675.9802 | 1090294.8147 | 1087433.8082 | 1082490.9272 | 1082490.9272 | 1082490.9272 | 1082490.9272 | 1095000 | 1126195.8435 | 1152248.0857 | 1177769.4098 | 1203481.4711 | 1230331.5416 | 1255357.6036 | 1286741.5437 | 1318910.0823 | 1351882.8343 | 1401692.5759 | 10891822.2802 | 12504610.9914
DS | DS416 | Asbestos service fuse replacement | 260698.1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267215.5592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260698.1066 | 267215.5592
DS | DS417 | Distribution access track reconstruction | 439491.0609 | 1403809.6845 | 1224917.0978 | 1221130.1925 | 1304920.5698 | 1304920.5698 | 1304920.5698 | 1522407.3315 | 1522407.3315 | 1540000 | 450478.3374 | 1474877.5497 | 1319101.739 | 1347899.2476 | 1476397.8499 | 1513307.7961 | 1551140.491 | 1854905.5038 | 1901278.1414 | 1971330.1981 | 12788924.408 | 14860716.854
DS | DS418 | Pole top structure/hardware refurbishment (LV) | 2606631.4704 | 2601883.4823 | 2594646.8378 | 2586625.3302 | 2579837.8523 | 2579837.8523 | 2579837.8523 | 2579837.8523 | 2579837.8523 | 2609650 | 2671797.2572 | 2733603.8336 | 2794150.8549 | 2855150.3827 | 2918849.734 | 2991820.9774 | 3066616.5018 | 3143281.9143 | 3221863.9622 | 3340572.6308 | 25898626.3822 | 29737708.0488
DS | DS420 | Future distribution feeder refurbishment works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4448592.8517 | 9193758.5601 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5420178.4203 | 11481744.6203 | 19201268.1629 | 28642351.4117 | 36103191.2036
DS | DS421 | Pole top structure/hardware refurbishment (HV) | 3244672.6065 | 3238762.4242 | 3229754.422 | 3219769.4409 | 3211320.5505 | 3211320.5505 | 3211320.5505 | 3211320.5505 | 3211320.5505 | 3248430 | 3325789.4216 | 3402724.772 | 3478092.2581 | 3554023.0137 | 3633314.445 | 3724147.3061 | 3817250.9888 | 3912682.2635 | 4010499.3201 | 4158265.0359 | 32237991.6459 | 37016788.8249
DU | DU | Duct installation RMS road works | 2150240.9794 | 2199982.1417 | 2248710.1656 | 2297801.2779 | 2349066.6038 | 2349066.6038 | 2349066.6038 | 2349066.6038 | 2349066.6038 | 2558920 | 2203997.0039 | 2311356.2376 | 2421614.8956 | 2536342.6706 | 2657753.2482 | 2724197.0794 | 2792302.0064 | 2862109.5565 | 2933662.2955 | 3275633.9418 | 23200987.5837 | 26718968.9356
EF | EF001 | Distribution management system | 8575435.4802 | 3606130.8443 | 92326.1377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8789821.3672 | 3788691.2182 | 99425.1522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12273892.4621 | 12677937.7376
EF | EF002 | Technology pilots | 499421.6601 | 498511.9618 | 1988501.7821 | 1982354.2086 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 2000000 | 511907.2016 | 523749.1299 | 2141398.927 | 2188148.1292 | 2236966.4392 | 2292890.6002 | 2350212.8652 | 2408968.1868 | 2469192.3915 | 2560169.0884 | 16854551.5051 | 19683602.9588
HV | HVW | HV development works | 6792977.6008 | 7081923.742 | 6609151.5572 | 6219682.9147 | 5879158.4894 | 5931457.1355 | 5931457.1355 | 5931457.1355 | 5931457.1355 | 6000000 | 6962802.0408 | 7440446.1315 | 7117333.3511 | 6865366.1769 | 6651728.1998 | 6878671.8005 | 7050638.5955 | 7226904.5604 | 7407577.1744 | 7680507.2652 | 62308722.8463 | 71281975.2961
IC | IC | Industrial & commercial | 7492767.2309 | 5316679.9239 | 4557732.5844 | 4283219.2149 | 4197052.606 | 4197052.606 | 4197052.606 | 4197052.606 | 4197052.606 | 4245553 | 7680086.4117 | 5585836.8451 | 4908179.4914 | 4727872.5828 | 4748579.7884 | 4867294.2831 | 4988976.6402 | 5113701.0562 | 5241543.5826 | 5434666.7769 | 46881214.9843 | 53296737.4583
LV | LV001 | Overloaded distribution sub uprates | 79907.4656 | 79761.9139 | 79540.0713 | 79294.1683 | 79086.0951 | 79086.0951 | 79086.0951 | 79086.0951 | 79086.0951 | 80000 | 81905.1523 | 83799.8608 | 85655.9571 | 87525.9252 | 89478.6576 | 91715.624 | 94008.5146 | 96358.7275 | 98767.6957 | 102406.7635 | 793934.0948 | 911622.8781
LV | LV002 | Quality of supply reactive projects | 499421.6601 | 498511.9618 | 497125.4455 | 495588.5521 | 494288.0946 | 494288.0946 | 494288.0946 | 494288.0946 | 494288.0946 | 500000 | 511907.2016 | 523749.1299 | 535349.7317 | 547037.0323 | 559241.6098 | 573222.65 | 587553.2163 | 602242.0467 | 617298.0979 | 640042.2721 | 4962088.0927 | 5697642.9883
LV | LV003 | LV planning reactive projects | 998843.3202 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 1023814.4032 | 1047498.2598 | 1070699.4635 | 1094074.0646 | 1118483.2196 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 9924176.1854 | 11395285.9766
LV | LV005 | Dsub monitoring & LV feeder monitoring for solar PV | 249710.83 | 249255.9809 | 248562.7228 | 247794.2761 | 247144.0473 | 247144.0473 | 247144.0473 | 247144.0473 | 247144.0473 | 250000 | 255953.6008 | 261874.5649 | 267674.8659 | 273518.5162 | 279620.8049 | 286611.325 | 293776.6081 | 301121.0233 | 308649.0489 | 320021.136 | 2481044.0464 | 2848821.4941
MC | MC104 | Meters - renewal | 59930.5992 | 59821.4354 | 9942.5089 | 9911.771 | 9885.7619 | 9885.7619 | 9885.7619 | 9885.7619 | 9885.7619 | 10000 | 61428.8642 | 62849.8956 | 10706.9946 | 10940.7406 | 11184.8322 | 11464.453 | 11751.0643 | 12044.8409 | 12345.962 | 12800.8454 | 199035.124 | 217518.4929
MC | MC105 | Relays - renewal | 956476.3819 | 904485.1482 | 851860.2439 | 799271.3404 | 747350.7476 | 697527.4962 | 647704.2449 | 597880.9935 | 548057.7421 | 503992 | 980388.2914 | 950274.7088 | 917360.3105 | 882246.0087 | 845558.7737 | 808918.0464 | 769916.8085 | 728459.9348 | 684449.0195 | 645152.3696 | 7254606.3387 | 8212724.272
MC | MC107 | Test equipment | 119861.1984 | 79761.9139 | 119310.1069 | 79294.1683 | 118629.1427 | 84028.9761 | 118629.1427 | 84028.9761 | 118629.1427 | 85000 | 122857.7284 | 83799.8608 | 128483.9356 | 87525.9252 | 134217.9864 | 97447.8505 | 141012.7719 | 102381.1479 | 148151.5435 | 108807.1863 | 1007172.7679 | 1154685.9364
MC | MC109 | Demand management technology | 1398380.6482 | 747767.9427 | 745688.1683 | 743382.8282 | 741432.1419 | 741432.1419 | 741432.1419 | 741432.1419 | 741432.1419 | 750000 | 1433340.1644 | 785623.6948 | 803024.5976 | 820555.5485 | 838862.4147 | 859833.9751 | 881329.8244 | 903363.07 | 925947.1468 | 960063.4081 | 8092380.2971 | 9211943.8445
NU | NU | Non urban extension | 1018160.95 | 740910.4122 | 658001.2052 | 626120.6297 | 612340.8974 | 612340.8974 | 612340.8974 | 612340.8974 | 612340.8974 | 619417 | 1043614.9737 | 778419.0018 | 708595.3291 | 691120.0222 | 692807.5204 | 710127.7084 | 727880.9012 | 746077.9237 | 764729.8718 | 792906.1281 | 6724314.6842 | 7656279.3804
PQ | PQ001 | Permanent power quality monitoring | 99884.332 | 99702.3924 | 99425.0891 | 99117.7104 | 98857.6189 | 98857.6189 | 98857.6189 | 98857.6189 | 98857.6189 | 100000 | 102381.4403 | 104749.826 | 107069.9463 | 109407.4065 | 111848.322 | 114644.53 | 117510.6433 | 120448.4093 | 123459.6196 | 128008.4544 | 992417.6185 | 1139528.5977
PQ | PQ004 | Power quality monitoring replacement | 342003.9528 | 615861.6776 | 868279.3032 | 939239.424 | 1348949.7761 | 1284714.0725 | 1413185.4798 | 1413185.4798 | 1156242.6653 | 1169604 | 350554.0516 | 647039.6751 | 935041.8415 | 1036744.5836 | 1526212.8555 | 1489874.4542 | 1679833.4471 | 1721829.2833 | 1443988.6489 | 1497192.0032 | 10551265.8311 | 12328310.8439
PR | PR081 | Collimore Park ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4147274.8292 | 12441824.4875 | 11187200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5053051.6686 | 15538133.881 | 14320561.8128 | 27776299.3167 | 34911747.3625
PR | PR110 | Edmondson Park ZS establishment | 1763811.4723 | 5095.7893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1807906.7591 | 5353.7636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768907.2615 | 1813260.5227
PR | PR113 | Augment feeder 308 Nepean to Douglas Park | 1311730.9902 | 3928025.0031 | 3481866.6205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344524.2649 | 4126881.2689 | 3749589.5211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8721622.6138 | 9220995.0549
PR | PR170 | Holsworthy 33/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4154392.5777 | 8308785.1555 | 8404800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5061723.9541 | 10376534.1059 | 10758854.5771 | 20867977.7332 | 26197112.6371
PR | PR190 | Eschol Park ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 4378601.6575 | 8757203.3149 | 8757203.3149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204781.4112 | 10669801.893 | 10936546.9403 | 0 | 21893008.2873 | 26811130.2445
PRL | PR248 | Penrith Lakes ZS site acquisition | 0 | 0 | 0 | 0 | 0 | 296572.8568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343933.59 | 0 | 0 | 0 | 0 | 296572.8568 | 343933.59
PR | PR249 | Establish Penrith Lakes 33/11kV Zone Substation | 0 | 0 | 0 | 0 | 0 | 1553054.1819 | 6212216.7276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801066.7129 | 7384373.5228 | 0 | 0 | 0 | 7765270.9095 | 9185440.2357
PR | PR258 | Menangle Park 66/11kV ZS establishment | 4481997.7601 | 8540.5069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4594047.7041 | 8972.8701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4490538.267 | 4603020.5742
PR | PR278 | Kemps Creek new BSP associated works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263400.3699 | 1263400.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1539330.6714 | 1577813.9381 | 0 | 2526800.7397 | 3117144.6095
PR | PR292 | South Marsden Park (industrial) 132/11kV ZS establishment | 1213606.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1243946.7856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213606.6201 | 1243946.7856
PR | PR423 | Maryland ZS establishment | 0 | 4114438.5661 | 8205990.0743 | 8180620.7596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4322732.0185 | 8836953.7798 | 9029874.6477 | 0 | 0 | 0 | 0 | 0 | 0 | 20501049.4 | 22189560.4461
PR | PR425 | Austral ZS establishment (interim initially) | 0 | 3545417.0724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3724903.8117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3545417.0724 | 3724903.8117
PR | PR427 | Leppington North ZS establishment | 1753878.9743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1797725.9486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753878.9743 | 1797725.9486
PRL | PR430 | North Rossmore ZS site purchase | 0 | 0 | 0 | 2973531.3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3282222.1938 | 0 | 0 | 0 | 0 | 0 | 0 | 2973531.3129 | 3282222.1938
PRL | PR432 | Rossmore ZS site purchase | 0 | 0 | 0 | 0 | 2965728.5678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3355449.6588 | 0 | 0 | 0 | 0 | 0 | 2965728.5678 | 3355449.6588
PR | PR433 | Rossmore ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12800845.442 | 10000000 | 12800845.442
PR | PR435 | Catherine Fields North ZS establishment (interim) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4242178.1433 | 8484356.2867 | 8582400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5168682.1416 | 10595798.3903 | 10986197.5921 | 21308934.43 | 26750678.124
PRL | PR436 | Catherine Fields ZS site purchase | 652268.6603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668575.3768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652268.6603 | 668575.3768
PRL | PR438 | North Bringelly ZS site purchase | 0 | 0 | 3479878.1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747448.1222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3479878.1187 | 3747448.1222
PR | PR439 | North Bringelly ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 4369506.7565 | 8739013.513 | 8739013.513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193970.432 | 10647639.3857 | 10913830.3703 | 0 | 21847533.7826 | 26755440.188
PR | PR444 | Culburra Beach development (33kV fdr and single transformer ZS) | 0 | 0 | 0 | 0 | 0 | 0 | 3788718.2453 | 1894359.1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4503595.4029 | 2308092.644 | 0 | 0 | 5683077.368 | 6811688.0469
PR | PR499 | Southpipe (Oakdale Estate) ZS 132/11kV establishment | 6339858.3217 | 12656620.4961 | 12621418.5114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6498354.7797 | 13297361.9087 | 13591887.2691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31617897.3292 | 33387603.9576
PRL | PR602 | Riverstone West site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4942880.9463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6022420.467 | 0 | 0 | 4942880.9463 | 6022420.467
PRL | PR603 | Eschol Park ZS site purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400422.721 | 5000000 | 6400422.721
PR | PR620 | West Dapto ZS establishment | 0 | 0 | 4062111.4405 | 8099106.3545 | 4617837.0953 | 3460016.6624 | 0 | 0 | 0 | 0 | 0 | 0 | 4374449.728 | 8939897.9967 | 5224658.8154 | 4012558.5503 | 0 | 0 | 0 | 0 | 20239071.5527 | 22551565.0903
PR | PR653 | Avondale (South West Dapto) 132/11kV ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 4942880.9463 | 4942880.9463 | 4942880.9463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5875532.1629 | 6022420.467 | 6172980.9787 | 0 | 14828642.8388 | 18070933.6086
PR | PR656 | Leppington South ZS establishment (permanent) | 13550952.7351 | 3516197.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13889726.5535 | 3694204.7802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17067150.0274 | 17583931.3337
PR | PR657 | Calderwood ZS establishment (interim initially) | 1474792.1622 | 1472105.8232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1511661.9663 | 1546631.1805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2946897.9854 | 3058293.1468
PRL | PR659 | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | 0 | 0 | 0 | 0 | 0 | 2471440.4731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2866113.2502 | 0 | 0 | 0 | 0 | 2471440.4731 | 2866113.2502
PR | PR673 | Liverpool ZS 11kV switchboard extension & distribution works | 292344.4595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299653.071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292344.4595 | 299653.071
PR | PR677 | South Penrith Zone Substation | 0 | 0 | 0 | 5774597.8096 | 11518889.7572 | 11518889.7572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6374075.5004 | 13032566.4747 | 13358380.6366 | 0 | 0 | 0 | 0 | 28812377.324 | 32765022.6116
PR | PR698 | Marsden Park (residential) 132/11kV ZS - stage 2 | 3060455.9329 | 3054881.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3136967.3313 | 3209534.6679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6115337.2349 | 6346501.9992
PR | PR700 | Riverstone east ZS establishment | 0 | 0 | 4062111.4405 | 8099106.3545 | 4617837.0953 | 3460016.6624 | 0 | 0 | 0 | 0 | 0 | 0 | 4374449.728 | 8939897.9967 | 5224658.8154 | 4012558.5503 | 0 | 0 | 0 | 0 | 20239071.5527 | 22551565.0903
PRL | PR703 | Riverstone East site purchase | 5993059.9209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6142886.4189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5993059.9209 | 6142886.4189
PRL | PR704 | Oakdale (Southpipe) site purchase | 194896.3063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199768.714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194896.3063 | 199768.714
PR | PR713 | Box Hill 132/22kV ZS establishment | 7161307.0682 | 14296525.4457 | 14256762.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7340339.7449 | 15020287.0464 | 15352973.7467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35714594.8909 | 37713600.5379
PRL | PR717 | Acquire improved site for West Dapto ZS | 1997686.6403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2047628.8063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1997686.6403 | 2047628.8063
PR | PR722 | Camellia TS connection works for Ausgrid | 274654.9443 | 104676.5447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281521.3179 | 109975.7948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379331.489 | 391497.1127
PR | PR723 | Supply to Luddenham Science Park | 0 | 0 | 0 | 8540973.1076 | 17037122.0456 | 17037122.0456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9427636.2147 | 19275939.8065 | 19757838.3016 | 0 | 0 | 0 | 0 | 42615217.1989 | 48461414.3228
PR | PR724 | Establish Mt Gilead ZS | 0 | 0 | 4021347.154 | 8017829.832 | 4536773.8477 | 3460016.6624 | 0 | 0 | 0 | 0 | 0 | 0 | 4330551.05 | 8850183.9234 | 5132943.1914 | 4012558.5503 | 0 | 0 | 0 | 0 | 20035967.4961 | 22326236.715
PR | PR728 | Western Sydney Employment Lands ZS | 0 | 0 | 4491031.2749 | 8954293.9601 | 8930797.2937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4836349.4765 | 9883865.0996 | 10104377.4058 | 0 | 0 | 0 | 0 | 0 | 22376122.5287 | 24824591.9819
PR | PR729 | Cheriton Avenue 3rd transformer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7066066.684 | 5520000 | 7066066.684
PR | PR732 | Feeder 214/215 contraints | 5134054.6656 | 5124702.9675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5262406.0322 | 5384141.0552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10258757.633 | 10646547.0874
PR | PR733 | Bringelly ZS augmentation | 0 | 0 | 0 | 0 | 0 | 4215288.871 | 8430577.742 | 8430577.742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4888442.7596 | 10021307.6571 | 10271840.3485 | 0 | 0 | 21076444.3549 | 25181590.7651
PR | PR739 | South Gilead (South Campbelltown) | 0 | 0 | 0 | 0 | 0 | 3998395.2551 | 7996790.5101 | 7996790.5101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4636912.6607 | 9505670.9545 | 9743312.7283 | 0 | 0 | 19991976.2753 | 23885896.3435
PR | PR740 | AFIC upgrade Minto, Prospect, Kingswood | 310803.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318573.1611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310803.084 | 318573.1611
PR | PR741 | Western Sydney Airport 132kV supply | 0 | 0 | 7814812.0037 | 15581304.0794 | 15540417.6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8415697.7829 | 17198844.2955 | 17582556.212 | 0 | 0 | 0 | 0 | 0 | 38936533.7782 | 43197098.2905
PR | PR742 | North Bomaderry ZS establishment | 0 | 0 | 3662024.8819 | 7301407.021 | 3822230.9781 | 3460016.6624 | 0 | 0 | 0 | 0 | 0 | 0 | 3943600.2639 | 8059387.1895 | 4324503.5202 | 4012558.5503 | 0 | 0 | 0 | 0 | 18245679.5435 | 20340049.5239
PR | PR744 | Termeil ZS establishment | 0 | 0 | 0 | 0 | 0 | 3935274.6654 | 3935274.6654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4563712.1283 | 4677804.9315 | 0 | 0 | 0 | 7870549.3308 | 9241517.0598
PR | PR745 | Austral Permanent ZS establishment | 0 | 0 | 0 | 0 | 0 | 10398338.6467 | 10398338.6467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12058884.8889 | 12360357.0111 | 0 | 0 | 0 | 20796677.2934 | 24419241.9001
PR | PR746 | Sydney University - Western Sydney Employment Lands ZS establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12115989.7755 | 12115989.7755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14762157.0487 | 15131210.9749 | 0 | 24231979.5511 | 29893368.0236
PR | PR748 | Establish permanent Catherine Park ZS | 0 | 0 | 0 | 0 | 1878294.7596 | 3756589.5192 | 3756589.5192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125118.1172 | 4356492.1403 | 4465404.4438 | 0 | 0 | 0 | 9391473.7979 | 10947014.7014
PR | PR749 | Nepean ZS augmentation | 0 | 0 | 0 | 0 | 0 | 0 | 3558874.2813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4230383.1573 | 0 | 0 | 0 | 3558874.2813 | 4230383.1573
PR | PR751 | Parklea ZS to Bella Vista ZS load transfer | 0 | 997023.9236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1047498.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997023.9236 | 1047498.2598
PR | PR752 | Kemps Creek 132kV conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8898000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11390192.2743 | 8898000 | 11390192.2743
PR | PR754 | Augment Westmead Zone Substation | 0 | 0 | 0 | 5081269.4251 | 5067935.8342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5608770.6922 | 5733904.2252 | 0 | 0 | 0 | 0 | 0 | 10149205.2593 | 11342674.9174
PR | PR755 | Narellan ZS busbar augmentation | 0 | 0 | 0 | 0 | 0 | 0 | 7196834.6578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8554774.8292 | 0 | 0 | 0 | 7196834.6578 | 8554774.8292
PRL | PR761 | Glenfield Zone Substation site acquisition | 0 | 2991071.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3142494.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2991071.7709 | 3142494.7793
PR | PR765 | Minto 66kV Reconfiguration | 299652.996 | 398809.5695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307144.3209 | 418999.3039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698462.5655 | 726143.6249
PR | PR766 | Baulkham Hills 132kV bus section CB | 0 | 348958.3733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366624.3909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348958.3733 | 366624.3909
PR | PR767 | Mt Terry 132kV bus section CB | 0 | 0 | 397700.3564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428279.7854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397700.3564 | 428279.7854
PR | PR768 | Establish Glenfield 66/11kV Zone Substation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6148943.8972 | 12297887.7944 | 12440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7491891.0609 | 15358376.6749 | 15924251.7298 | 30886831.6915 | 38774519.4657
PR | PR769 | Nepean TS 132kV bus section CB | 299652.996 | 299107.1771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307144.3209 | 314249.4779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598760.1731 | 621393.7989
PS | PS008 | Substation protection relay refurbishment | 4369939.5257 | 4486607.6563 | 4474129.0097 | 4460296.9693 | 4448592.8517 | 4695736.899 | 4695736.899 | 4695736.899 | 4695736.899 | 4750000 | 4479188.0138 | 4713742.1689 | 4818147.5856 | 4923333.2907 | 5033174.4882 | 5445615.1754 | 5581755.5548 | 5721299.4436 | 5864331.9297 | 6080401.5849 | 45772513.6085 | 52660989.2357
PS | PS011 | Protection refurbishment (miscellaneous) | 699190.3241 | 697916.7465 | 695975.6237 | 693823.973 | 692003.3325 | 692003.3325 | 692003.3325 | 692003.3325 | 692003.3325 | 700000 | 716670.0822 | 733248.7818 | 749489.6244 | 765851.8452 | 782938.2537 | 802511.7101 | 822574.5028 | 843138.8654 | 864217.337 | 896059.1809 | 6946923.3298 | 7976700.1836
PS | PS012 | Distribution feeder safety improvement | 3096414.2925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3173824.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3096414.2925 | 3173824.6498
PS | PS013 | Feeder differential relay replacement | 0 | 329017.8948 | 328102.794 | 327088.4444 | 326230.1425 | 326230.1425 | 326230.1425 | 326230.1425 | 326230.1425 | 330000 | 0 | 345674.4257 | 353330.8229 | 361044.4413 | 369099.4625 | 378326.949 | 387785.1228 | 397479.7508 | 407416.7446 | 422427.8996 | 2945359.8455 | 3422585.6192
PS | PS014 | Under frequency load shedding | 549363.8261 | 548363.158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563097.9217 | 576124.0429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097726.9841 | 1139221.9646
RC | RC | Reliability compliance | 3995373.2806 | 3988095.6945 | 3977003.5642 | 3964708.4171 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 4000000 | 4095257.6126 | 4189993.0391 | 4282797.8539 | 4376296.2584 | 4473932.8784 | 4585781.2003 | 4700425.7303 | 4817936.3736 | 4938384.7829 | 5120338.1768 | 39696704.7416 | 45581143.9063
SL | SL001 | Streetlighting growth | 1747975.8103 | 1744791.8664 | 1739939.0593 | 1734559.9325 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 1750000 | 1791675.2055 | 1833121.9546 | 1873724.0611 | 1914629.6131 | 1957345.6343 | 2006279.2751 | 2056436.257 | 2107847.1634 | 2160543.3425 | 2240147.9523 | 17367308.3245 | 19941750.459
SL | SL002 | Streetlighting refurbishment | 2996529.9605 | 2991071.7709 | 2982752.6732 | 2973531.3129 | 2965728.5678 | 2965728.5678 | 2965728.5678 | 2965728.5678 | 2965728.5678 | 3000000 | 3071443.2095 | 3142494.7793 | 3212098.3904 | 3282222.1938 | 3355449.6588 | 3439335.9002 | 3525319.2978 | 3613452.2802 | 3703788.5872 | 3840253.6326 | 29772528.5562 | 34185857.9298
SP | SP | Essential spares | 998843.3202 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 1023814.4032 | 1047498.2598 | 1070699.4635 | 1094074.0646 | 1118483.2196 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 9924176.1854 | 11395285.9766
TM | TM012 | Sub-transmission pole replacement | 3715697.151 | 3708928.9959 | 3698613.3147 | 3687178.8279 | 4863794.8511 | 5476712.0885 | 5476712.0885 | 5476712.0885 | 5476712.0885 | 5540000 | 3808589.5797 | 3896693.5263 | 3983002.0041 | 4069955.5203 | 5502937.4404 | 6351306.9625 | 6510089.6365 | 6672841.8774 | 6839662.9244 | 7091668.3748 | 47121061.4946 | 54726747.8465
TM | TM014 | Renewal of 33kV and 66kV gas and oil filled cables | 0 | 0 | 0 | 0 | 0 | 0 | 2224296.4258 | 2224296.4258 | 2224296.4258 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 2643989.4733 | 2710089.2101 | 2777841.4404 | 2880190.2244 | 8922889.2775 | 11012110.3483
TM | TM015 | Subtransmission tower replacement | 958889.5873 | 957142.9667 | 954480.8554 | 951530.0201 | 949033.1417 | 1898066.2834 | 1898066.2834 | 1898066.2834 | 1898066.2834 | 1920000 | 982861.827 | 1005598.3294 | 1027871.4849 | 1050311.102 | 1073743.8908 | 2201174.9762 | 2256204.3506 | 2312609.4593 | 2370424.6958 | 2457762.3249 | 14283341.7047 | 16738562.4409
TM | TM028 | 132kV oil cable replacement | 0 | 0 | 0 | 0 | 0 | 10083477.1304 | 9786904.2736 | 9786904.2736 | 10083477.1304 | 10200000 | 0 | 0 | 0 | 0 | 0 | 11693742.0608 | 11633553.6826 | 11924392.5247 | 12592881.1965 | 13056862.3508 | 49940762.8081 | 60901431.8154
TM | TM030 | Feeder 7028 replacement | 1598149.3122 | 1595238.2778 | 1590801.4257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1638103.045 | 1675997.2156 | 1713119.1416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4784189.0157 | 5027219.4022
TM | TM031 | Steel tower asbestos removal | 2808942.1907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879165.7455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808942.1907 | 2879165.7455
TM | TM033 | Pole top structure/hardware refurbishment (TR) | 1346111.1773 | 1343659.2312 | 1339922.0983 | 1335779.6481 | 1332274.473 | 1332274.473 | 1332274.473 | 1332274.473 | 1332274.473 | 1347670 | 1379763.9567 | 1411681.9797 | 1442949.5459 | 1474450.7946 | 1507346.2805 | 1545029.9376 | 1583655.686 | 1623247.0782 | 1663828.2551 | 1725131.5377 | 13374514.5198 | 15357085.0521
TM | TM132 | Sub-transmission pilot cable renewal program | 0 | 0 | 0 | 0 | 0 | 0 | 1102262.451 | 1102262.451 | 1102262.451 | 1115000 | 0 | 0 | 0 | 0 | 0 | 0 | 1310243.6723 | 1342999.7641 | 1376574.7582 | 1427294.2668 | 4421787.3531 | 5457112.4615
TM | TM134 | Wollongong - Port Kembla pilot cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 1645979.3551 | 1645979.3551 | 1645979.3551 | 1665000 | 0 | 0 | 0 | 0 | 0 | 0 | 1956552.2103 | 2005466.0155 | 2055602.6659 | 2131340.7661 | 6602938.0653 | 8148961.6577
TM | TM135 | Optical fibre protection and communication upgrades in the Blue Mountains | 0 | 0 | 0 | 0 | 0 | 0 | 917398.7036 | 917398.7036 | 917398.7036 | 928000 | 0 | 0 | 0 | 0 | 0 | 0 | 1090498.7694 | 1117761.2387 | 1145705.2696 | 1187918.457 | 3680196.1109 | 4541883.7348
TM | TM137 | Optical fibre protection and communication upgrades in the Macarthur area | 0 | 0 | 0 | 0 | 0 | 0 | 897627.1798 | 897627.1798 | 897627.1798 | 908000 | 0 | 0 | 0 | 0 | 0 | 0 | 1066996.6408 | 1093671.5568 | 1121013.3457 | 1162316.7661 | 3600881.5395 | 4443998.3095
TM | TM171 | Replacement of corroded earthwires | 0 | 0 | 0 | 0 | 136423.5141 | 886752.8418 | 886752.8418 | 886752.8418 | 886752.8418 | 897000 | 0 | 0 | 0 | 0 | 154350.6843 | 1028361.4342 | 1054070.47 | 1080422.2318 | 1107432.7876 | 1148235.8361 | 4580434.8812 | 5572873.444
TM | TM172 | Earthwire replacement due to fault rating | 0 | 997023.9236 | 994250.8911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1047498.2598 | 1070699.4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1991274.8147 | 2118197.7232
TM | TM174 | Hardex earthwire replacement | 0 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 0 | 1047498.2598 | 1070699.4635 | 1094074.0646 | 1118483.2196 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 8925332.8653 | 10371471.5734
TM | TM302 | Oil filled cable auxiliary equipment refurbishment | 0 | 71785.7225 | 0 | 0 | 0 | 0 | 71177.4856 | 0 | 0 | 0 | 0 | 75419.8747 | 0 | 0 | 0 | 0 | 84607.6631 | 0 | 0 | 0 | 142963.2081 | 160027.5378
TM | TM303 | Guilford and Camellia 132kV cables oil testing and flushing | 0 | 89732.1531 | 0 | 0 | 0 | 0 | 88971.857 | 0 | 0 | 0 | 0 | 94274.8434 | 0 | 0 | 0 | 0 | 105759.5789 | 0 | 0 | 0 | 178704.0102 | 200034.4223
TM | TM419 | Future sub-transmission feeder refurbishment works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4448592.8517 | 9193758.5601 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5420178.4203 | 11481744.6203 | 19201268.1629 | 28642351.4117 | 36103191.2036
TM | TM801 | Steel tower painting program | 0 | 0 | 0 | 0 | 0 | 790860.9514 | 790860.9514 | 790860.9514 | 790860.9514 | 800000 | 0 | 0 | 0 | 0 | 0 | 917156.2401 | 940085.1461 | 963587.2747 | 987676.9566 | 1024067.6354 | 3963443.8056 | 4832573.2528
TM | TM803 | Steel tower below ground rectification work | 0 | 1495535.8854 | 1491376.3366 | 1486765.6564 | 1482864.2839 | 1482864.2839 | 1482864.2839 | 1186291.4271 | 741432.1419 | 750000 | 0 | 1571247.3896 | 1606049.1952 | 1641111.0969 | 1677724.8294 | 1719667.9501 | 1762659.6489 | 1445380.9121 | 925947.1468 | 960063.4081 | 11599994.2992 | 13309851.5772
TM | TM805 | Earthing refurbishment of lines 940/941 | 279676.1296 | 279166.6986 | 278390.2495 | 277529.5892 | 19771.5238 | 19771.5238 | 19771.5238 | 19771.5238 | 19771.5238 | 20000 | 286668.0329 | 293299.5127 | 299795.8498 | 306340.7381 | 22369.6644 | 22928.906 | 23502.1287 | 24089.6819 | 24691.9239 | 25601.6909 | 1233620.2859 | 1329288.1292
TM | TM809 | Subtransmission line earthing refurbishment | 0 | 598214.3542 | 596550.5346 | 594706.2626 | 593145.7136 | 593145.7136 | 593145.7136 | 593145.7136 | 593145.7136 | 600000 | 0 | 628498.9559 | 642419.6781 | 656444.4388 | 671089.9318 | 687867.18 | 705063.8596 | 722690.456 | 740757.7174 | 768050.7265 | 5355199.7192 | 6222882.9441
TS | TS004 | 132kV circuit breaker replacement | 0 | 0 | 0 | 358806.1118 | 357864.5805 | 357864.5805 | 357864.5805 | 357864.5805 | 357864.5805 | 362000 | 0 | 0 | 0 | 396054.8114 | 404890.9255 | 415013.1986 | 425388.5286 | 436023.2418 | 446923.8229 | 463390.605 | 2510129.0143 | 2987685.1338
TS | TS005 | 33kV circuit breaker replacement | 0 | 0 | 0 | 763206.3703 | 761203.6657 | 1170474.2081 | 1170474.2081 | 1170474.2081 | 1170474.2081 | 1184000 | 0 | 0 | 0 | 842437.0297 | 861232.0791 | 1357391.2353 | 1391326.0162 | 1426109.1666 | 1461761.8957 | 1515620.1003 | 7390306.8683 | 8855877.523
TS | TS007 | 11kV circuit breaker replacement | 0 | 348958.3733 | 347987.8119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366624.3909 | 374744.8122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696946.1851 | 741369.2031
TS | TS008 | Battery replacement | 519398.5265 | 518452.4403 | 517010.4633 | 515412.0942 | 514059.6184 | 1028119.2368 | 1028119.2368 | 1028119.2368 | 1028119.2368 | 1040000 | 532383.4896 | 544699.0951 | 556763.721 | 568918.5136 | 581611.2742 | 1192303.1121 | 1222110.6899 | 1252663.4571 | 1283980.0436 | 1331287.926 | 7736810.0901 | 9066721.3221
TS | TS009 | Auxiliary switchgear replacement | 0 | 0 | 0 | 279511.9434 | 0 | 278778.4854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308528.8862 | 0 | 323297.5746 | 0 | 0 | 0 | 0 | 558290.4288 | 631826.4608
TS | TS015 | Replacement of surge arrester in zone and sub-transmission substations | 36957.2028 | 117648.823 | 117321.6051 | 116958.8983 | 49428.8095 | 49428.8095 | 49428.8095 | 49428.8095 | 49428.8095 | 50000 | 37881.1329 | 123604.7947 | 126342.5367 | 129100.7396 | 55924.161 | 57322.265 | 58755.3216 | 60224.2047 | 61729.8098 | 64004.2272 | 686030.5766 | 774889.1932
TS | TS016 | VT and CT replacement | 0 | 0 | 0 | 691841.6188 | 690026.1801 | 690026.1801 | 690026.1801 | 690026.1801 | 690026.1801 | 698000 | 0 | 0 | 0 | 763663.6971 | 780701.2873 | 800218.8195 | 820224.2899 | 840729.8972 | 861748.1446 | 893499.0118 | 4839972.5193 | 5760785.1474
TS | TS024 | Building and amenities refurbishment | 1498264.9802 | 1495535.8854 | 1491376.3366 | 1486765.6564 | 1482864.2839 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 2000000 | 1535721.6047 | 1571247.3896 | 1606049.1952 | 1641111.0969 | 1677724.8294 | 2292890.6002 | 2350212.8652 | 2408968.1868 | 2469192.3915 | 2560169.0884 | 17363416.6566 | 20113287.2479
TS | TS025 | Asbestos and other hazardous material reporting, management and removal | 88897.0555 | 448660.7656 | 447412.901 | 513429.74 | 514059.6184 | 532842.566 | 444859.2852 | 444859.2852 | 512082.466 | 520000 | 91119.4819 | 471374.2169 | 481814.7586 | 566730.3655 | 581611.2742 | 617934.0167 | 528797.8947 | 542017.842 | 639520.8294 | 665643.963 | 4467103.6829 | 5186564.6428
TS | TS026 | Noise attenuation in ZS and TS | 0 | 0 | 994250.8911 | 0 | 988576.1893 | 0 | 988576.1893 | 0 | 988576.1893 | 0 | 0 | 0 | 1070699.4635 | 0 | 1118483.2196 | 0 | 1175106.4326 | 0 | 1234596.1957 | 0 | 3959979.4588 | 4598885.3114
TS | TS027 | Substation switchyard lighting improvement | 109872.7652 | 109672.6316 | 109367.598 | 109029.4815 | 108743.3808 | 108743.3808 | 108743.3808 | 108743.3808 | 108743.3808 | 110000 | 112619.5843 | 115224.8086 | 117776.941 | 120348.1471 | 123033.1542 | 126108.983 | 129261.7076 | 132493.2503 | 135805.5815 | 140809.2999 | 1091659.3804 | 1253481.4574
TS | TS031 | Substation safety fence upgrade program | 99884.332 | 99702.3924 | 99425.0891 | 99117.7104 | 98857.6189 | 98857.6189 | 98857.6189 | 98857.6189 | 98857.6189 | 100000 | 102381.4403 | 104749.826 | 107069.9463 | 109407.4065 | 111848.322 | 114644.53 | 117510.6433 | 120448.4093 | 123459.6196 | 128008.4544 | 992417.6185 | 1139528.5977
TS | TS032 | Substation security systems | 149826.498 | 149553.5885 | 149137.6337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153572.1605 | 157124.739 | 160604.9195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448517.7202 | 471301.819
TS | TS033 | Substation fire hydrant installations | 199768.664 | 199404.7847 | 198850.1782 | 198235.4209 | 197715.2379 | 197715.2379 | 197715.2379 | 197715.2379 | 197715.2379 | 200000 | 204762.8806 | 209499.652 | 214139.8927 | 218814.8129 | 223696.6439 | 229289.06 | 235021.2865 | 240896.8187 | 246919.2391 | 256016.9088 | 1984835.2371 | 2279057.1953
TS | TS034 | Substation deluge showers and fire blankets | 159814.9312 | 159523.8278 | 159080.1426 | 158588.3367 | 158172.1903 | 158172.1903 | 158172.1903 | 158172.1903 | 158172.1903 | 160000 | 163810.3045 | 167599.7216 | 171311.9142 | 175051.8503 | 178957.3151 | 183431.248 | 188017.0292 | 192717.4549 | 197535.3913 | 204813.5271 | 1587868.1897 | 1823245.7563
TS | TS035 | Substation oil containment program - bund walls | 69919.0324 | 69791.6747 | 69597.5624 | 69382.3973 | 69200.3332 | 69200.3332 | 69200.3332 | 69200.3332 | 69200.3332 | 70000 | 71667.0082 | 73324.8782 | 74948.9624 | 76585.1845 | 78293.8254 | 80251.171 | 82257.4503 | 84313.8865 | 86421.7337 | 89605.9181 | 694692.333 | 797670.0184
TS | TS036 | Substation earthing | 339606.7289 | 406785.7608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348096.8971 | 427379.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 746392.4897 | 775476.1871
TS | TS049 | Tunnelboard refurbishment | 0 | 0 | 0 | 44602.9697 | 44485.9285 | 0 | 0 | 0 | 44485.9285 | 45000 | 0 | 0 | 0 | 49233.3329 | 50331.7449 | 0 | 0 | 0 | 55556.8288 | 57603.8045 | 178574.8267 | 212725.7111
TS | TS055 | 66kV circuit breaker replacement | 257701.5766 | 257232.1723 | 0 | 0 | 0 | 255052.6568 | 255052.6568 | 255052.6568 | 255052.6568 | 258000 | 264144.116 | 270254.551 | 0 | 0 | 0 | 295782.8874 | 303177.4596 | 310756.8961 | 318525.8185 | 330261.8124 | 1793144.3762 | 2092903.5411
TS | TS086 | Busbar support and isolator replacement | 0 | 94218.7608 | 93956.7092 | 93666.2364 | 93420.4499 | 93420.4499 | 93420.4499 | 93420.4499 | 93420.4499 | 94500 | 0 | 98988.5855 | 101181.0993 | 103389.9991 | 105696.6643 | 108339.0809 | 111047.5579 | 113823.7468 | 116669.3405 | 120967.9894 | 843443.9558 | 980104.0637
TS | TS116 | Roof refurbishment for control and switch rooms | 1498264.9802 | 1495535.8854 | 1491376.3366 | 1486765.6564 | 1482864.2839 | 1482864.2839 | 1482864.2839 | 1482864.2839 | 1482864.2839 | 1500000 | 1535721.6047 | 1571247.3896 | 1606049.1952 | 1641111.0969 | 1677724.8294 | 1719667.9501 | 1762659.6489 | 1806726.1401 | 1851894.2936 | 1920126.8163 | 14886264.2781 | 17092928.9649
TS | TS144 | Substation fire stopping measures | 65923.6591 | 65803.579 | 65620.5588 | 65417.6889 | 65246.0285 | 65246.0285 | 65246.0285 | 65246.0285 | 65246.0285 | 66000 | 67571.7506 | 69134.8851 | 70666.1646 | 72208.8883 | 73819.8925 | 75665.3898 | 77557.0246 | 79495.9502 | 81483.3489 | 84485.5799 | 654995.6282 | 752088.8745
TS | TS146 | Marayong Zone Substation renewal | 8195387.583 | 1823633.5272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8400272.2725 | 1915954.9745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10019021.1101 | 10316227.247
TS | TS155 | Sussex Inlet Zone Substation - stage 2 renewal | 1676614.4481 | 37233.8584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1718529.8093 | 39118.8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1713848.3065 | 1757648.6318
TS | TS167 | Carlingford Transmission Substation control building replacement | 0 | 4486607.6563 | 4474129.0097 | 4460296.9693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4713742.1689 | 4818147.5856 | 4923333.2907 | 0 | 0 | 0 | 0 | 0 | 0 | 13421033.6354 | 14455223.0453
TS | TS173 | 11kV switchboard truck replacement program | 3643780.4319 | 3637143.2734 | 3627027.2506 | 2902166.5613 | 2894551.0821 | 2894551.0821 | 2894551.0821 | 2894551.0821 | 0 | 0 | 3734874.9427 | 3821273.6516 | 3905911.6428 | 3203448.8612 | 3274918.867 | 3356791.8386 | 3440711.6346 | 3526729.4255 | 0 | 0 | 25388321.8458 | 28264660.8639
TS | TS177 | Substation battery duplication | 0 | 915267.9619 | 760601.9317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 961603.4025 | 819085.0896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675869.8935 | 1780688.492
TS | TS180 | Transformer fire wall installation | 0 | 598214.3542 | 596550.5346 | 594706.2626 | 593145.7136 | 593145.7136 | 593145.7136 | 593145.7136 | 593145.7136 | 600000 | 0 | 628498.9559 | 642419.6781 | 656444.4388 | 671089.9318 | 687867.18 | 705063.8596 | 722690.456 | 740757.7174 | 768050.7265 | 5355199.7192 | 6222882.9441
TS | TS199 | Future sub-transmission substation renewal programs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4448592.8517 | 9193758.5601 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5420178.4203 | 11481744.6203 | 19201268.1629 | 28642351.4117 | 36103191.2036
TS | TS600 | Power transformer replacement | 1698033.6443 | 11565477.5141 | 7456881.6829 | 10902948.1471 | 10973195.7007 | 12554917.6036 | 12554917.6036 | 12554917.6036 | 12554917.6036 | 12700000 | 1740484.4854 | 12150979.8132 | 8030245.9761 | 12034814.7106 | 12415163.7375 | 14559855.3111 | 14923851.6938 | 15296947.9862 | 15679371.6858 | 16257073.7113 | 105516207.1034 | 123088789.1109
TS | TS616 | Camellia TS transformer replacement and 33kV busbar rearrangement | 332257.2397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340563.6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332257.2397 | 340563.6707
TS | TS617 | Prospect ZS transformer replacement | 29234.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29234.1463 | 29965
TS | TS618 | Albion Park ZS transformer replacement | 1575436.614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1614822.5293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575436.614 | 1614822.5293
TS | TS620 | Minto 66/11kV No 1 transformer replacement | 1079313.1346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1106295.9629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079313.1346 | 1106295.9629
TS | TS700 | 11kV zone substation switchboard replacement | 0 | 3988095.6945 | 3977003.5642 | 7929416.8343 | 11862914.2711 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 4000000 | 0 | 4189993.0391 | 4282797.8539 | 8752592.5168 | 13421798.6351 | 4585781.2003 | 4700425.7303 | 4817936.3736 | 4938384.7829 | 5120338.1768 | 47574649.3922 | 54810048.3089
TS | TS701 | North Rocks ZS 11kV switchboard replacement | 776646.6282 | 36061.3583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 796062.7939 | 37886.9646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812707.9865 | 833949.7585
TS | TS702 | Kellyville ZS 11kV switchboard replacement | 952068.4863 | 264576.2505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975870.1985 | 277970.4232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1216644.7368 | 1253840.6217
TS | TS703 | Horsley Park ZS 11kV switchboard replacement | 423899.1166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434496.5946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423899.1166 | 434496.5946
TS | TS704 | Port Central ZS 11kV switchboard replacement | 488086.7861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500288.9557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488086.7861 | 500288.9557
UR | UR | Underground residential | 21633998.4122 | 14557232.2464 | 11691183.4582 | 10959043.8153 | 10680249.93 | 10680249.93 | 10680249.93 | 10680249.93 | 10680249.93 | 10803669 | 22174848.3725 | 15294192.1288 | 12590125.8613 | 12096733.8323 | 12083722.4865 | 12385815.5487 | 12695460.9374 | 13012847.4609 | 13338168.6474 | 13829609.7075 | 123046376.5821 | 139501524.9833
| SW | Network Switching | 6283900.8865 | 6382175.5445 | 6686467.7532 | 6495126.3573 | 6714861.5396 | 7423719.2767 | 7683873.5145 | 7944102.7058 | 8085985.7683 | 8183178.6979 | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | 10475160.5735 | 71883392.0442 | 83109035.6151
| OH | Capitalised Overheads | 73106139.0812 | 73273110.1037 | 73775204.5564 | 73462071.757 | 73820942.4206 | 76860996.0999 | 77233408.4879 | 77593252.7624 | 77784338.9426 | 78058962.8601 | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | 99922071.8932 | 754968427.0719 | 868519522.4252
|  | Total | 309741694.3046 | 305374259.576 | 312015229.0639 | 330954575.9922 | 328459632.2638 | 333790143.9881 | 343457170.0069 | 371391699.4738 | 392030259.9135 | 407936515.558 | 317485236.6622 | 320833831.4671 | 336006275.0361 | 365311927.1915 | 371621925.5463 | 387094233.0473 | 408262644.9824 | 452504722.75 | 489592074.7049 | 522193228.5791 | 3435151180.1408 | 3970906099.967
|  | Check | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK

## Division Lvl (excl. Esc)
ID | Description | Division | FY19 (R) | FY20 (R) | FY21 (R) | FY22 (R) | FY23 (R) | FY24 (R) | FY25 (R) | FY26 (R) | FY27 (R) | FY28 (R) | FY29 (R) | FY19 (N) | FY20 (N) | FY21 (N) | FY22 (N) | FY23 (N) | FY24 (N) | FY25 (N) | FY26 (N) | FY27 (N) | FY28 (N) | FY29 (N) | Reg Tot (R) | SAMP Tot (R) | Reg Tot (N) | SAMP Tot (N) | Rank | Wgt Rank | Percentage | Code | Plantname | Category | Type | Classification | RAB Category
AG | Automation - operational/capacity risk | Program - Short Term Need | 300000 | 299652.996 | 299107.1771 | 298275.2673 | 297353.1313 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 300000 | 0 | 307144.3209 | 314249.4779 | 321209.839 | 328222.2194 | 335544.9659 | 343933.59 | 352531.9298 | 361345.228 | 370378.8587 | 384025.3633 | 1490961.4285 | 2977252.8556 | 1606370.8232 | 3418585.793 | 190 | 2850 | 66.13% | AG | AGs | Augex | Std | Std | Substations
AR | Asset relocation | Program - Short Term Need | 1674562.9105 | 1621771.9568 | 1559196.86 | 1533617.0857 | 1521457.8463 | 1515555.5099 | 1515555.5099 | 1515555.5099 | 1515555.5099 | 1515555.5099 | 1533069 | 1670000 | 1662316.2557 | 1638131.201 | 1651537.8619 | 1679404.7832 | 1714711.951 | 1757579.7498 | 1801519.2435 | 1846557.2246 | 1892721.1552 | 1962457.9321 | 7751599.2586 | 15346890.2981 | 8346102.0528 | 17606937.358 | 140 | 2100 | 78.3% | AR | ARs | Connections | Std | Std | Distribution lines and cables
AU002 | Transmission substation SCADA upgrade | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | AU | AU002s | Repex | Std | Unallocated | Unallocated
AU004 | Substation SCADA RTU replacement | Program - Short Term Need | 1044144 | 2177478.4379 | 2173512.1535 | 2167466.9425 | 2160766.0873 | 2155096.0926 | 2155096.0926 | 2155096.0926 | 2155096.0926 | 2155096.0926 | 2180000 | 714162 | 2231915.3989 | 2283546.2063 | 2334124.8304 | 2385081.4608 | 2438293.4187 | 2499250.7542 | 2561732.023 | 2625775.3236 | 2691419.7067 | 2790584.3063 | 10834319.7139 | 21634704.0842 | 11672961.3151 | 24841723.429 | 220 | 3300 | 54.33% | AU | AU004s | Repex | Std | Std | Substations
AU008 | Western Sydney Ramtel SCADA upgrades | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | AU | AU008s | Repex | Std | Unallocated | Unallocated
AU013 | SCADA master station development software | Program - Short Term Need | 1000000 | 1108716.0854 | 1106696.5552 | 2097869.3801 | 2091383.69 | 1097319.5701 | 1097319.5701 | 1097319.5701 | 2085895.7593 | 2085895.7593 | 1110000 | 978004 | 1136433.9875 | 1162723.0683 | 2259175.8679 | 2308496.2763 | 1241516.3737 | 1272554.2831 | 1304368.1402 | 2541461.4371 | 2604997.973 | 1420893.8441 | 7501985.2808 | 14978415.9396 | 8108345.5738 | 17252621.2512 | 310 | 4650 | 21% | AU | AU013s | Repex | Std | Std | Substations
AU014 | SCADA substation refurbishments | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | AU | AU014s | Repex | Std | Unallocated | Unallocated
AU016 | PM121 (MD1000) MD3 to DNP3 conversion | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2250 | 70.87% | AU | AU016s | Repex | Std | Std | Substations
AU017 | AFIC availability and SCADA control | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | AU | AU017s | Repex | Std | Unallocated | Unallocated
CC002 | Communications development SCADA | Program - Short Term Need | 750000 | 624277.0751 | 523437.5599 | 521981.7178 | 520367.9797 | 519002.4994 | 444859.2852 | 444859.2852 | 444859.2852 | 444859.2852 | 450000 | 515765.25 | 639884.002 | 549936.5864 | 562117.2183 | 574388.8839 | 587203.6903 | 515900.385 | 528797.8947 | 542017.842 | 555568.2881 | 576038.0449 | 2709066.8319 | 4938503.9726 | 2913530.3809 | 5631852.8356 | 150 | 2250 | 70.87% | CC | CC002s | Repex | Std | Std | Communications
CC007 | SCADA radio repeaters | Program - Short Term Need | 870000 | 878982.1217 | 837500.0958 | 845113.2574 | 683912.202 | 632688.7611 | 731546.38 | 612917.2373 | 603031.4754 | 583259.9517 | 490000 | 692279.51 | 900956.6748 | 879898.5382 | 910094.544 | 754911.1046 | 715829.2605 | 848369.5221 | 728565.9882 | 734735.297 | 728411.7555 | 627241.4267 | 3878196.4381 | 6898951.4826 | 4161690.122 | 7829014.1114 | 270 | 4050 | 37.22% | CC | CC007s | Repex | Std | Std | Communications
CC020 | Microwave refurbishment and extension | Program - Short Term Need | 550000 | 669225.0245 | 668006.0288 | 487182.9366 | 426206.1548 | 276801.333 | 929261.6179 | 1532293.0933 | 1215948.7128 | 1502635.8077 | 930000 | 418230.73 | 685955.6501 | 701823.834 | 524642.7371 | 470451.8478 | 313175.3015 | 1077658.5821 | 1821414.9705 | 1481515.4349 | 1876586.2175 | 1190478.6261 | 2527421.4778 | 8637560.7095 | 2696049.3705 | 10143703.2016 | 230 | 3450 | 51.3% | CC | CC020s | Repex | Std | Std | Communications
DS002 | Pole substation refurbishment | Program - Short Term Need | 735000 | 699190.3241 | 697916.7465 | 695975.6237 | 743382.8282 | 790860.9514 | 790860.9514 | 790860.9514 | 790860.9514 | 790860.9514 | 800000 | 740000 | 716670.0822 | 733248.7818 | 749489.6244 | 820555.5485 | 894786.5757 | 917156.2401 | 940085.1461 | 963587.2747 | 987676.9566 | 1024067.6354 | 3627326.474 | 7590770.2796 | 3914750.6126 | 8747323.8654 | 280 | 4200 | 36.29% | DS | DS002s | Repex | Std | Std | Transformers
DS003 | Distribution substation refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | DS | DS003s | Repex | Std | Std | Substations
DS004 | Distribution mains refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | DS | DS004s | Repex | Std | Std | Distribution lines and cables
DS005 | Distribution pole replacement | Program - Short Term Need | 10800000 | 11316894.8173 | 12063989.4759 | 12796008.9679 | 13519655.7024 | 14245382.8872 | 15006586.5529 | 16528993.8844 | 17290197.5501 | 17290197.5501 | 17490000 | 10800000 | 11599817.1877 | 12674728.9431 | 13779902.0949 | 14923170.2412 | 16117343.1943 | 17403039.6553 | 19647779.5528 | 21066426.7936 | 21593087.4634 | 22388678.678 | 63941931.8507 | 147547907.3882 | 69094961.6613 | 171193973.8043 | 310 | 4650 | 21% | DS | DS005s | Repex | Std | Std | Distribution lines and cables
DS006 | LV CONSAC cable replacement | Program - Short Term Need | 6000000 | 6742192.411 | 7477679.4272 | 9693946.1878 | 9663976.7668 | 11121482.1291 | 11121482.1291 | 11121482.1291 | 11121482.1291 | 11121482.1291 | 11250000 | 6053654 | 6910747.2213 | 7856236.9482 | 10439319.7689 | 10667222.1299 | 12582936.2204 | 12897509.6259 | 13219947.3666 | 13550446.0507 | 13889207.202 | 14400951.1222 | 44699276.9219 | 100435205.4385 | 48456462.2887 | 116414523.6562 | 230 | 3450 | 51.3% | DS | DS006s | Repex | Std | Std | Distribution lines and cables
DS006 | LV CONSAC cable replacement | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 741432.1419 | 741432.1419 | 741432.1419 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 881329.8244 | 903363.07 | 925947.1468 | 960063.4081 | 0 | 2974296.4258 | 0 | 3670703.4494 | 230 | 2300 | 69.76% | DS | DS006m | Repex | Std | Std | Distribution lines and cables
DS006 | LV CONSAC cable replacement | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741432.1419 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925947.1468 | 960063.4081 | 0 | 1491432.1419 | 0 | 1886010.5549 | 230 | 1150 | 94.49% | DS | DS006l | Repex | Std | Std | Distribution lines and cables
DS007 | Service wire replacement program | Program - Short Term Need | 9167401 | 9189358.5454 | 9272322.4897 | 9246533.2868 | 9366623.6355 | 9688046.6547 | 9688046.6547 | 9688046.6547 | 9688046.6547 | 9688046.6547 | 9800000 | 4489678.5 | 9419092.509 | 9741733.8158 | 9957505.0103 | 10338999.9105 | 10961135.552 | 11235163.9408 | 11516043.0393 | 11803944.1153 | 12099042.7182 | 12544828.5331 | 46762884.6122 | 95315071.231 | 50418466.7976 | 109617489.1444 | 300 | 4500 | 25.55% | DS | DS007s | Repex | Std | Std | Low Voltage lines and cables
DS007 | Service wire replacement program | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 494288.0946 | 494288.0946 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 587553.2163 | 602242.0467 | 617298.0979 | 640042.2721 | 0 | 1982864.2839 | 0 | 2447135.633 | 300 | 3000 | 58.53% | DS | DS007m | Repex | Std | Std | Low Voltage lines and cables
DS007 | Service wire replacement program | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617298.0979 | 640042.2721 | 0 | 994288.0946 | 0 | 1257340.37 | 300 | 1500 | 92.19% | DS | DS007l | Repex | Std | Std | Low Voltage lines and cables
DS008 | Traffic black spot remediation | Program - Short Term Need | 1700000 | 998843.3202 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 917955.5 | 1023814.4032 | 1047498.2598 | 1070699.4635 | 1094074.0646 | 1118483.2196 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 4969871.4284 | 9924176.1854 | 5354569.4106 | 11395285.9766 | 150 | 2250 | 70.87% | DS | DS008s | Repex | Std | Std | Distribution lines and cables
DS009 | Reliability focused distribution mains renewal | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | DS | DS009s | Repex | Std | Std | Distribution lines and cables
DS011 | HV distribution steel mains replacement | Program - Short Term Need | 4800000 | 3691724.9113 | 4299167.1587 | 5205897.6656 | 5342444.5921 | 5937388.5927 | 5937388.5927 | 5937388.5927 | 5937388.5927 | 5937388.5927 | 6006000 | 4367566 | 3784018.0341 | 4516812.4961 | 5606182.3908 | 5897059.2082 | 6717610.2169 | 6885550.4723 | 7057689.2341 | 7234131.465 | 7414984.7516 | 7688187.7724 | 24476622.9203 | 54232177.291 | 26521682.346 | 62802226.0414 | 280 | 4200 | 36.29% | DS | DS011s | Repex | Std | Std | Distribution lines and cables
DS012 | HV porcelain expulsion drop-out fuse replacement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3383.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4800 | 12.56% | DS | DS012s | Repex | Std | Std | Distribution lines and cables
DS014 | LV cable network renewal | Program - Short Term Need | 0 | 0 | 1296131.1007 | 1292526.1584 | 1288530.2356 | 1285149.046 | 1285149.046 | 1285149.046 | 1285149.046 | 1285149.046 | 1300000 | 213.75 | 0 | 1361747.7377 | 1391909.3025 | 1422296.284 | 1454028.1855 | 1490378.8901 | 1527638.3624 | 1565829.3214 | 1604975.0545 | 1664109.9075 | 5162336.5407 | 11602932.7248 | 5629981.5097 | 13482913.0455 | 230 | 3450 | 51.3% | DS | DS014s | Repex | Std | Std | Low Voltage lines and cables
DS301 | Ground substation refurbishment program | Program - Short Term Need | 510000 | 509410.0933 | 508482.2011 | 507067.9544 | 505500.3232 | 504173.8565 | 504173.8565 | 504173.8565 | 504173.8565 | 504173.8565 | 510000 | 504882.99 | 522145.3456 | 534224.1125 | 546056.7264 | 557977.7729 | 570426.442 | 584687.103 | 599304.2806 | 614286.8876 | 629644.0598 | 652843.1175 | 2534634.4285 | 5061329.8546 | 2730830.3994 | 5811595.8481 | 240 | 3600 | 42.68% | DS | DS301s | Repex | Std | Std | Substations
DS301 | Ground substation refurbishment program | Program - Medium Term Need |  | 0 | 0 | 338045.303 | 337000.2155 | 504173.8565 | 504173.8565 | 504173.8565 | 504173.8565 | 504173.8565 | 510000 | 0 | 0 | 0 | 364037.8176 | 371985.182 | 570426.442 | 584687.103 | 599304.2806 | 614286.8876 | 629644.0598 | 652843.1175 | 1179219.3749 | 3705914.801 | 1306449.4415 | 4387214.8902 | 240 | 2400 | 69.76% | DS | DS301m | Repex | Std | Std | Substations
DS301 | Ground substation refurbishment program | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 252086.9283 | 252086.9283 | 252086.9283 | 252086.9283 | 255000 | 0 | 0 | 0 | 0 | 0 | 0 | 292343.5515 | 299652.1403 | 307143.4438 | 314822.0299 | 326421.5588 | 0 | 1263347.713 | 0 | 1540382.7243 | 240 | 1200 | 94.49% | DS | DS301l | Repex | Std | Std | Substations
DS302 | Distribution transformer replacement program | Program - Short Term Need | 1170000 | 1123698.7352 | 1121651.9141 | 1118532.2524 | 1424817.0874 | 1421078.2721 | 1421078.2721 | 1421078.2721 | 1421078.2721 | 1421078.2721 | 1437500 | 1169485.63 | 1151791.2035 | 1178435.5422 | 1204536.8964 | 1572731.4679 | 1607819.6282 | 1648015.1189 | 1689215.4968 | 1731445.8843 | 1774732.0314 | 1840121.5323 | 6209778.2612 | 13331591.3494 | 6715314.7382 | 15398844.8018 | 270 | 4050 | 37.22% | DS | DS302s | Repex | Std | Std | Substations
DS302 | Distribution transformer replacement program | Program - Medium Term Need |  | 124855.415 | 124627.9905 | 124281.3614 | 123897.138 | 123572.0237 | 123572.0237 | 123572.0237 | 123572.0237 | 123572.0237 | 125000 | 0 | 127976.8004 | 130937.2825 | 133837.4329 | 136759.2581 | 139810.4024 | 143305.6625 | 146888.3041 | 150560.5117 | 154324.5245 | 160010.568 | 621233.9285 | 1240522.0232 | 669321.1763 | 1424410.7471 | 270 | 2700 | 66.49% | DS | DS302m | Repex | Std | Std | Substations
DS302 | Distribution transformer replacement program | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123572.0237 | 123572.0237 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150560.5117 | 154324.5245 | 160010.568 | 0 | 372144.0473 | 0 | 464895.6042 | 270 | 1350 | 92.19% | DS | DS302l | Repex | Std | Std | Substations
DS305 | Compact LV switchgear replacement | Program - Short Term Need | 508400 | 299652.996 | 299107.1771 | 298275.2673 | 297353.1313 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 300000 | 387187.91 | 307144.3209 | 314249.4779 | 321209.839 | 328222.2194 | 335544.9659 | 343933.59 | 352531.9298 | 361345.228 | 370378.8587 | 384025.3633 | 1490961.4285 | 2977252.8556 | 1606370.8232 | 3418585.793 | 240 | 3600 | 42.68% | DS | DS305s | Repex | Std | Std | Substations
DS305 | Compact LV switchgear replacement | Program - Medium Term Need |  | 199768.664 | 199404.7847 | 198850.1782 | 198235.4209 | 197715.2379 | 197715.2379 | 197715.2379 | 197715.2379 | 197715.2379 | 200000 | 0 | 204762.8806 | 209499.652 | 214139.8927 | 218814.8129 | 223696.6439 | 229289.06 | 235021.2865 | 240896.8187 | 246919.2391 | 256016.9088 | 993974.2857 | 1984835.2371 | 1070913.8821 | 2279057.1953 | 240 | 2400 | 69.76% | DS | DS305m | Repex | Std | Std | Substations
DS307 | Holec MD4 epoxy switchgear replacement | Program - Short Term Need | 4035224.6688 | 5943117.7549 | 5583333.9723 | 5915792.8018 | 5897503.7705 | 5882028.3261 | 5882028.3261 | 5882028.3261 | 5882028.3261 | 5882028.3261 | 5950000 | 2360741.09 | 6091695.6988 | 5865990.2547 | 6370661.8077 | 6509740.6844 | 6654975.1566 | 6821349.5355 | 6991883.2739 | 7166680.3557 | 7345847.3646 | 7616503.038 | 29221776.6256 | 58699889.9299 | 31493063.6021 | 67435327.1698 | 280 | 4200 | 36.29% | DS | DS307s | Repex | Std | Std | Substations
DS307 | Holec MD4 epoxy switchgear replacement | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056436.257 | 2107847.1634 | 2160543.3425 | 2240147.9523 | 0 | 6940024.9936 | 0 | 8564974.7154 | 280 | 2800 | 66.41% | DS | DS307m | Repex | Std | Std | Substations
DS307 | Holec MD4 epoxy switchgear replacement | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730008.3312 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160543.3425 | 2240147.9523 | 0 | 3480008.3312 | 0 | 4400691.2949 | 280 | 1400 | 92.19% | DS | DS307l | Repex | Std | Std | Substations
DS308 | HV RGB12 switchgear replacement | Program - Short Term Need | 598000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4200 | 36.29% | DS | DS308s | Repex | Std | Std | Substations
DS312 | Miscellaneous substation renewal expenditure | Program - Short Term Need | 750000 | 1498264.9802 | 1495535.8854 | 1491376.3366 | 1486765.6564 | 1482864.2839 | 1482864.2839 | 1482864.2839 | 1482864.2839 | 1482864.2839 | 1500000 | 877711.92 | 1535721.6047 | 1571247.3896 | 1606049.1952 | 1641111.0969 | 1677724.8294 | 1719667.9501 | 1762659.6489 | 1806726.1401 | 1851894.2936 | 1920126.8163 | 7454807.1426 | 14886264.2781 | 8031854.1159 | 17092928.9649 | 230 | 3450 | 51.3% | DS | DS312s | Repex | Std | Std | Substations
DS312 | Miscellaneous substation renewal expenditure | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 494288.0946 | 494288.0946 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 587553.2163 | 602242.0467 | 617298.0979 | 640042.2721 | 0 | 1982864.2839 | 0 | 2447135.633 | 230 | 2300 | 69.76% | DS | DS312m | Repex | Std | Std | Substations
DS312 | Miscellaneous substation renewal expenditure | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617298.0979 | 640042.2721 | 0 | 994288.0946 | 0 | 1257340.37 | 230 | 1150 | 94.49% | DS | DS312l | Repex | Std | Std | Substations
DS313 | Padmount substation fire risk mitigation | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61797.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.33% | DS | DS313s | Repex | Std | Std | Substations
DS315 | Low voltage switchgear replacement | Program - Short Term Need | 354000 | 530385.803 | 529419.7034 | 527947.2232 | 526315.0424 | 524933.9565 | 524933.9565 | 524933.9565 | 524933.9565 | 524933.9565 | 531000 | 263730.92 | 543645.4481 | 556221.5759 | 568541.4151 | 580953.3283 | 593914.5896 | 608762.4543 | 623981.5157 | 639581.0536 | 655570.5799 | 679724.893 | 2639001.7285 | 5269737.5544 | 2843276.357 | 6050896.8536 | 280 | 4200 | 36.29% | DS | DS315s | Repex | Std | Std | Substations
DS315 | Low voltage switchgear replacement | Program - Medium Term Need |  | 176795.2677 | 176473.2345 | 175982.4077 | 175438.3475 | 174977.9855 | 174977.9855 | 174977.9855 | 174977.9855 | 174977.9855 | 177000 | 0 | 181215.1494 | 185407.192 | 189513.805 | 193651.1094 | 197971.5299 | 202920.8181 | 207993.8386 | 213193.6845 | 218523.5266 | 226574.9643 | 879667.2428 | 1756579.1848 | 947758.7857 | 2016965.6179 | 280 | 2800 | 66.41% | DS | DS315m | Repex | Std | Std | Substations
DS316 | HV oil switchgear replacement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17102.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | DS | DS316s | Repex | Std | Std | Substations
DS317 | Future distribution substation renewals | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460016.6624 | 7414321.4194 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4215694.3269 | 9259471.468 | 15361014.5304 | 0 | 22874338.0818 | 0 | 28836180.3253 | 180 | 2700 | 66.49% | DS | DS317s | Repex | Std | Unallocated | Unallocated
DS317 | Future distribution substation renewals | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 889718.5703 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602242.0467 | 1111136.5762 | 1920126.8163 | 0 | 2884006.665 | 0 | 3633505.4392 | 180 | 1800 | 82.37% | DS | DS317m | Repex | Std | Unallocated | Unallocated
DS317 | Future distribution substation renewals | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 889718.5703 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602242.0467 | 1111136.5762 | 1920126.8163 | 0 | 2884006.665 | 0 | 3633505.4392 | 180 | 900 | 97.4% | DS | DS317l | Repex | Std | Unallocated | Unallocated
DS318 | Distribution substation earthing refurbishment | Program - Short Term Need | 676000 | 179791.7976 | 179464.3063 | 178965.1604 | 178411.8788 | 177943.7141 | 177943.7141 | 177943.7141 | 177943.7141 | 177943.7141 | 180000 | 0 | 184286.5926 | 188549.6868 | 192725.9034 | 196933.3316 | 201326.9795 | 206360.154 | 211519.1579 | 216807.1368 | 222227.3152 | 230415.218 | 894576.8571 | 1786351.7134 | 963822.4939 | 2051151.4758 | 340 | 5100 | 9.284% | DS | DS318s | Repex | Std | Std | Substations
DS318 | Distribution substation earthing refurbishment | Program - Medium Term Need |  | 89895.8988 | 89732.1531 | 89482.5802 | 89205.9394 | 88971.857 | 88971.857 | 88971.857 | 88971.857 | 88971.857 | 90000 | 0 | 92143.2963 | 94274.8434 | 96362.9517 | 98466.6658 | 100663.4898 | 103180.077 | 105759.5789 | 108403.5684 | 111113.6576 | 115207.609 | 447288.4286 | 893175.8567 | 481911.247 | 1025575.7379 | 340 | 3400 | 51.33% | DS | DS318m | Repex | Std | Std | Substations
DS404 | Cast iron UGOH replacement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | DS | DS404s | Repex | Std | Std | Distribution lines and cables
DS405 | Air break switch replacement program | Program - Short Term Need | 6146400.5487 | 3635789.6853 | 3629167.082 | 3619073.2434 | 3607884.6596 | 3598417.3289 | 3598417.3289 | 3598417.3289 | 3598417.3289 | 3598417.3289 | 3640000 | 7304354.42 | 3726684.4275 | 3812893.6655 | 3897346.0471 | 3982429.5952 | 4071278.9193 | 4173060.8923 | 4277387.4146 | 4384322.1 | 4493930.1525 | 4659507.7409 | 18090331.9993 | 36124001.3149 | 19490632.6545 | 41478840.9548 | 280 | 4200 | 36.29% | DS | DS405s | Repex | Std | Std | Distribution lines and cables
DS409 | Miscellaneous mains renewal expenditure | Program - Short Term Need | 750000 | 1093733.4356 | 1091741.1964 | 1088704.7257 | 1085338.9292 | 1082490.9272 | 1186291.4271 | 1186291.4271 | 1186291.4271 | 1186291.4271 | 1200000 | 2087412.32 | 1121076.7715 | 1147010.5944 | 1172415.9125 | 1198011.1007 | 1224739.1255 | 1375734.3601 | 1410127.7191 | 1445380.9121 | 1481515.4349 | 1536101.453 | 5442009.2141 | 11387174.9225 | 5863253.5046 | 13112113.3838 | 290 | 4350 | 29.29% | DS | DS409s | Repex | Std | Std | Distribution lines and cables
DS410 | Capital works for compliance to NSW Maritime Waterways - crossing codes | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.33% | DS | DS410s | Repex | Std | Std | Distribution lines and cables
DS411 | Capital works for compliance to NSW Maritime Waterways - signage replacement and drawings update | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.33% | DS | DS411s | Repex | Std | Std | Distribution lines and cables
DS413 | Low mains remediation | Program - Short Term Need | 1800000 | 1623120.3952 | 1620163.8759 | 1615657.698 | 1610662.7945 | 1606436.3075 | 963861.7845 | 963861.7845 | 963861.7845 | 963861.7845 | 975000 | 2293431.29 | 1663698.4051 | 1702184.6721 | 1739886.6281 | 1777870.355 | 1817535.2318 | 1117784.1676 | 1145728.7718 | 1174371.9911 | 1203731.2908 | 1248082.4306 | 8076041.0711 | 12906488.2092 | 8701175.2922 | 14590873.9441 | 230 | 3450 | 51.3% | DS | DS413s | Repex | Std | Std | Distribution lines and cables
DS414 | Copper distribution mains replacement | Program - Short Term Need | 5600000 | 0 | 957142.9667 | 954480.8554 | 951530.0201 | 949033.1417 | 949033.1417 | 949033.1417 | 949033.1417 | 949033.1417 | 960000 | 4779336 | 0 | 1005598.3294 | 1027871.4849 | 1050311.102 | 1073743.8908 | 1100587.4881 | 1128102.1753 | 1156304.7297 | 1185212.3479 | 1228881.1624 | 3812186.9839 | 8568319.5506 | 4157524.8071 | 9956612.7105 | 260 | 3900 | 38.54% | DS | DS414s | Repex | Std | Std | Distribution lines and cables
DS414 | Copper distribution mains replacement | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 237258.2854 | 474516.5708 | 474516.5708 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282025.5438 | 578152.3648 | 592606.174 | 614440.5812 | 0 | 1666291.4271 | 0 | 2067224.6638 | 260 | 2600 | 66.72% | DS | DS414m | Repex | Std | Std | Distribution lines and cables
DS414 | Copper distribution mains replacement | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237258.2854 | 474516.5708 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289076.1824 | 592606.174 | 614440.5812 | 0 | 1191774.8563 | 0 | 1496122.9376 | 260 | 1300 | 92.19% | DS | DS414l | Repex | Std | Std | Distribution lines and cables
DS415 | LV mains replacement | Program - Short Term Need | 550000 | 964882.6473 | 963125.1102 | 960446.3608 | 957477.0827 | 954964.5988 | 949033.1417 | 949033.1417 | 949033.1417 | 949033.1417 | 960000 | 0 | 989004.7134 | 1011883.3189 | 1034295.6817 | 1056875.5464 | 1080454.7901 | 1100587.4881 | 1128102.1753 | 1156304.7297 | 1185212.3479 | 1228881.1624 | 4800895.7998 | 9557028.3666 | 5172514.0506 | 10971601.954 | 190 | 2850 | 66.13% | DS | DS415s | Repex | Std | Std | Distribution lines and cables
DS415 | LV mains replacement | Program - Medium Term Need |  | 133845.0049 | 133601.2058 | 133229.6194 | 132817.732 | 132469.2094 | 133457.7855 | 133457.7855 | 133457.7855 | 133457.7855 | 135000 | 0 | 137191.13 | 140364.7668 | 143473.7281 | 146605.9247 | 149876.7514 | 154770.1155 | 158639.3684 | 162605.3526 | 166670.4864 | 172811.4135 | 665962.7714 | 1334793.9136 | 717512.301 | 1533009.0374 | 190 | 1900 | 80.7% | DS | DS415m | Repex | Std | Std | Distribution lines and cables
DS416 | Asbestos service fuse replacement | Program - Short Term Need | 261000 | 260698.1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86000 | 267215.5592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260698.1066 | 260698.1066 | 267215.5592 | 267215.5592 | 200 | 3000 | 58.53% | DS | DS416s | Repex | Std | Std | Customer metering & load control
DS417 | Distribution access track reconstruction | Program - Short Term Need | 500000 | 439491.0609 | 1403809.6845 | 524964.4705 | 523341.5111 | 608962.9326 | 608962.9326 | 608962.9326 | 608962.9326 | 608962.9326 | 616000 | 500000 | 450478.3374 | 1474877.5497 | 565329.3167 | 577671.1061 | 688985.6633 | 706210.3049 | 723865.5625 | 741962.2015 | 760511.2566 | 788532.0792 | 3500569.6595 | 6552421.3898 | 3757341.9732 | 7478423.3779 | 290 | 4350 | 29.29% | DS | DS417s | Repex | Std | Std | Distribution lines and cables
DS417 | Distribution access track reconstruction | Program - Medium Term Need |  | 0 | 0 | 699952.6273 | 697788.6814 | 695957.6372 | 695957.6372 | 695957.6372 | 695957.6372 | 695957.6372 | 704000 | 0 | 0 | 0 | 753772.4223 | 770228.1415 | 787412.1866 | 807097.4913 | 827274.9285 | 847956.8018 | 869155.7218 | 901179.5191 | 2093698.946 | 5581529.4949 | 2311412.7504 | 6564077.2128 | 290 | 2900 | 59.76% | DS | DS417m | Repex | Std | Std | Distribution lines and cables
DS417 | Distribution access track reconstruction | Program - Long Term Need |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217486.7616 | 217486.7616 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264986.5005 | 271611.1631 | 281618.5997 | 0 | 654973.5233 | 0 | 818216.2633 | 290 | 1450 | 92.19% | DS | DS417l | Repex | Std | Std | Distribution lines and cables
DS418 | Pole top structure/hardware refurbishment (LV) | Program - Short Term Need | 5000000 | 2606631.4704 | 2601883.4823 | 2594646.8378 | 2586625.3302 | 2579837.8523 | 2579837.8523 | 2579837.8523 | 2579837.8523 | 2579837.8523 | 2609650 | 3923342.5 | 2671797.2572 | 2733603.8336 | 2794150.8549 | 2855150.3827 | 2918849.734 | 2991820.9774 | 3066616.5018 | 3143281.9143 | 3221863.9622 | 3340572.6308 | 12969624.9731 | 25898626.3822 | 13973552.0623 | 29737708.0488 | 330 | 4950 | 12.56% | DS | DS418s | Repex | Std | Std | Distribution lines and cables
DS420 | Future distribution feeder refurbishment works | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460016.6624 | 7414321.4194 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4215694.3269 | 9259471.468 | 15361014.5304 | 0 | 22874338.0818 | 0 | 28836180.3253 | 180 | 2700 | 66.49% | DS | DS420s | Repex | Std | Unallocated | Unallocated
DS420 | Future distribution feeder refurbishment works | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 889718.5703 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602242.0467 | 1111136.5762 | 1920126.8163 | 0 | 2884006.665 | 0 | 3633505.4392 | 180 | 1800 | 82.37% | DS | DS420m | Repex | Std | Unallocated | Unallocated
DS420 | Future distribution feeder refurbishment works | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 889718.5703 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602242.0467 | 1111136.5762 | 1920126.8163 | 0 | 2884006.665 | 0 | 3633505.4392 | 180 | 900 | 97.4% | DS | DS420l | Repex | Std | Unallocated | Unallocated
DS421 | Pole top structure/hardware refurbishment (HV) | Program - Short Term Need |  | 3244672.6065 | 3238762.4242 | 3229754.422 | 3219769.4409 | 3211320.5505 | 3211320.5505 | 3211320.5505 | 3211320.5505 | 3211320.5505 | 3248430 | 3793027.469 | 3325789.4216 | 3402724.772 | 3478092.2581 | 3554023.0137 | 3633314.445 | 3724147.3061 | 3817250.9888 | 3912682.2635 | 4010499.3201 | 4158265.0359 | 16144279.4441 | 32237991.6459 | 17393943.9104 | 37016788.8249 | 330 | 4950 | 12.56% | DS | DS421s | Repex | Std | Std | Distribution lines and cables
DU | Duct installation RMS road works | Program - Short Term Need | 1955226.0176 | 2150240.9794 | 2199982.1417 | 2248710.1656 | 2297801.2779 | 2349066.6038 | 2349066.6038 | 2349066.6038 | 2349066.6038 | 2349066.6038 | 2558920 | 700000 | 2203997.0039 | 2311356.2376 | 2421614.8956 | 2536342.6706 | 2657753.2482 | 2724197.0794 | 2792302.0064 | 2862109.5565 | 2933662.2955 | 3275633.9418 | 11245801.1684 | 23200987.5837 | 12131064.056 | 26718968.9356 | 170 | 2550 | 68.69% | DU | DUs | Connections | Std | Std | Distribution lines and cables
EF001 | Distribution management system | Program - Short Term Need | 12000000 | 8575435.4802 | 3606130.8443 | 92326.1377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11928177.61 | 8789821.3672 | 3788691.2182 | 99425.1522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12273892.4621 | 12273892.4621 | 12677937.7376 | 12677937.7376 | 260 | 3900 | 38.54% | EF | EF001s | Other | Std | Std | Communications
EF002 | Technology pilots | Program - Short Term Need | 552599 | 499421.6601 | 498511.9618 | 1988501.7821 | 1982354.2086 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 1977152.3785 | 2000000 | 505504.11 | 511907.2016 | 523749.1299 | 2141398.927 | 2188148.1292 | 2236966.4392 | 2292890.6002 | 2350212.8652 | 2408968.1868 | 2469192.3915 | 2560169.0884 | 6945941.9911 | 16854551.5051 | 7602169.8268 | 19683602.9588 | 230 | 3450 | 51.3% | EF | EF002s | Other | Std | Std | Distribution lines and cables
EF003 | Battery energy storage system pilot | Program - Short Term Need | 1692215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1639952.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.3% | EF | EF003s | Other | Std | Std | Substations
EH | Dist environmental enhancement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 2850 | 66.13% | EH | EHs | Other | Std | Std | Distribution lines and cables
HVW | HV development works | Program - Short Term Need | 7057544 | 6792977.6008 | 7081923.742 | 6609151.5572 | 6219682.9147 | 5879158.4894 | 5931457.1355 | 5931457.1355 | 5931457.1355 | 5931457.1355 | 6000000 | 8536573.1465 | 6962802.0408 | 7440446.1315 | 7117333.3511 | 6865366.1769 | 6651728.1998 | 6878671.8005 | 7050638.5955 | 7226904.5604 | 7407577.1744 | 7680507.2652 | 32582894.3041 | 62308722.8463 | 35037675.9001 | 71281975.2961 | 350 | 5250 | 4.712% | HV | HVWs | Augex | Std | Std | Distribution lines and cables
IC | Industrial & commercial | Program - Short Term Need | 10000000 | 7492767.2309 | 5316679.9239 | 4557732.5844 | 4283219.2149 | 4197052.606 | 4197052.606 | 4197052.606 | 4197052.606 | 4197052.606 | 4245553 | 10000000 | 7680086.4117 | 5585836.8451 | 4908179.4914 | 4727872.5828 | 4748579.7884 | 4867294.2831 | 4988976.6402 | 5113701.0562 | 5241543.5826 | 5434666.7769 | 25847451.5602 | 46881214.9843 | 27650555.1193 | 53296737.4583 | 200 | 3000 | 58.53% | IC | ICs | Connections | Std | Std | Distribution lines and cables
LV001 | Overloaded distribution sub uprates | Program - Short Term Need | 120000 | 79907.4656 | 79761.9139 | 79540.0713 | 79294.1683 | 79086.0951 | 79086.0951 | 79086.0951 | 79086.0951 | 79086.0951 | 80000 | 120000 | 81905.1523 | 83799.8608 | 85655.9571 | 87525.9252 | 89478.6576 | 91715.624 | 94008.5146 | 96358.7275 | 98767.6957 | 102406.7635 | 397589.7143 | 793934.0948 | 428365.5528 | 911622.8781 | 330 | 4950 | 12.56% | LV | LV001s | Augex | Std | Std | Low Voltage lines and cables
LV002 | Quality of supply reactive projects | Program - Short Term Need | 500000 | 499421.6601 | 498511.9618 | 497125.4455 | 495588.5521 | 494288.0946 | 494288.0946 | 494288.0946 | 494288.0946 | 494288.0946 | 500000 | 499406.74 | 511907.2016 | 523749.1299 | 535349.7317 | 547037.0323 | 559241.6098 | 573222.65 | 587553.2163 | 602242.0467 | 617298.0979 | 640042.2721 | 2484935.7142 | 4962088.0927 | 2677284.7053 | 5697642.9883 | 300 | 4500 | 25.55% | LV | LV002s | Other | Std | Std | Low Voltage lines and cables
LV003 | LV planning reactive projects | Program - Short Term Need | 1000000 | 849016.8221 | 847470.3351 | 845113.2574 | 842500.5386 | 840289.7609 | 840289.7609 | 840289.7609 | 840289.7609 | 840289.7609 | 850000 | 998030.36 | 870242.2427 | 890373.5208 | 910094.544 | 929962.9549 | 950710.7367 | 974478.5051 | 998840.4677 | 1023811.4794 | 1049406.7664 | 1088071.8626 | 4224390.7141 | 8435549.7576 | 4551383.999 | 9685993.0801 | 300 | 4500 | 25.55% | LV | LV003s | Other | Std | Std | Low Voltage lines and cables
LV003 | LV planning reactive projects | Program - Medium Term Need |  | 149826.498 | 149553.5885 | 149137.6337 | 148676.5656 | 148286.4284 | 148286.4284 | 148286.4284 | 148286.4284 | 148286.4284 | 150000 | 998030.36 | 153572.1605 | 157124.739 | 160604.9195 | 164111.1097 | 167772.4829 | 171966.795 | 176265.9649 | 180672.614 | 185189.4294 | 192012.6816 | 745480.7143 | 1488626.4278 | 803185.4116 | 1709292.8965 | 300 | 3000 | 58.53% | LV | LV003m | Other | Std | Std | Low Voltage lines and cables
LV004 | Low voltage system augmentations | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2498.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1200 | 94.49% | LV | LV004s | Other | Std | Std | Low Voltage lines and cables
LV005 | Dsub monitoring & LV feeder monitoring for solar PV | Program - Short Term Need | 250000 | 249710.83 | 249255.9809 | 248562.7228 | 247794.2761 | 247144.0473 | 247144.0473 | 247144.0473 | 247144.0473 | 247144.0473 | 250000 | 232429.45 | 255953.6008 | 261874.5649 | 267674.8659 | 273518.5162 | 279620.8049 | 286611.325 | 293776.6081 | 301121.0233 | 308649.0489 | 320021.136 | 1242467.8571 | 2481044.0464 | 1338642.3526 | 2848821.4941 | 250 | 3750 | 38.64% | LV | LV005s | Other | Std | Std | Low Voltage lines and cables
MC101 | Meters - Growth | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1050 | 95.93% | MC | MC101s | Other | Alt | Alt | Metering & Load control
MC102 | Relays - growth | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2847.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1050 | 95.93% | MC | MC102s | Other | Std | Std | Customer metering & load control
MC104 | Meters - renewal | Program - Short Term Need | 25000 | 59930.5992 | 59821.4354 | 9942.5089 | 9911.771 | 9885.7619 | 9885.7619 | 9885.7619 | 9885.7619 | 9885.7619 | 10000 | 25000 | 61428.8642 | 62849.8956 | 10706.9946 | 10940.7406 | 11184.8322 | 11464.453 | 11751.0643 | 12044.8409 | 12345.962 | 12800.8454 | 149492.0765 | 199035.124 | 157111.3273 | 217518.4929 | 50 | 750 | 99.19% | MC | MC104s | Other | Alt | Alt | Metering & Load control
MC105 | Relays - renewal | Program - Short Term Need | 300000 | 399537.3281 | 398809.5695 | 397700.3564 | 396470.8417 | 395430.4757 | 395430.4757 | 395430.4757 | 395430.4757 | 395430.4757 | 400000 | 100000 | 409525.7613 | 418999.3039 | 428279.7854 | 437629.6258 | 447393.2878 | 458578.12 | 470042.573 | 481793.6374 | 493838.4783 | 512033.8177 | 1987948.5714 | 3969670.4742 | 2141827.7642 | 4558114.3906 | 100 | 1500 | 92.19% | MC | MC105s | Other | Std | Std | Customer metering & load control
MC105 | Relays - renewal | Program - Medium Term Need |  | 556939.0538 | 505675.5787 | 454159.8875 | 402800.4987 | 351920.2719 | 302097.0205 | 252273.7692 | 202450.5178 | 152627.2664 | 103992 | 100000 | 570862.5302 | 531275.4049 | 489080.5251 | 444616.3828 | 398165.4859 | 350339.9264 | 299874.2354 | 246666.2975 | 190610.5413 | 133118.5519 | 2271495.2906 | 3284935.8646 | 2434000.3289 | 3654609.8813 | 100 | 1000 | 97.4% | MC | MC105m | Other | Std | Std | Customer metering & load control
MC106 | Labour (meter/relay renewal) | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | MC | MC106s | Other | Alt | Alt | Metering & load control
MC107 | Test equipment | Program - Short Term Need | 80000 | 119861.1984 | 79761.9139 | 119310.1069 | 79294.1683 | 118629.1427 | 84028.9761 | 118629.1427 | 84028.9761 | 118629.1427 | 85000 | 80000 | 122857.7284 | 83799.8608 | 128483.9356 | 87525.9252 | 134217.9864 | 97447.8505 | 141012.7719 | 102381.1479 | 148151.5435 | 108807.1863 | 516856.5303 | 1007172.7679 | 556885.4363 | 1154685.9364 | 50 | 750 | 99.19% | MC | MC107s | Other | Alt | Alt | Metering & Load control
MC108 | Smart metering pilot | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | MC | MC108s | Other | Alt | Unallocated | Unallocated
MC109 | Demand management technology | Program - Short Term Need | 500000 | 1398380.6482 | 747767.9427 | 745688.1683 | 743382.8282 | 741432.1419 | 741432.1419 | 741432.1419 | 741432.1419 | 741432.1419 | 750000 | 508000 | 1433340.1644 | 785623.6948 | 803024.5976 | 820555.5485 | 838862.4147 | 859833.9751 | 881329.8244 | 903363.07 | 925947.1468 | 960063.4081 | 4376651.7294 | 8092380.2971 | 4681406.42 | 9211943.8445 | 80 | 1200 | 94.49% | MC | MC109s | Other | Std | Std | Distribution lines and cables
MC110 | Labour meter renewal | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | MC | MC110s | Other | Alt | Alt | Metering & load control
MC111 | Labour relay renewal | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | MC | MC111s | Other | Std | Unallocated | Unallocated
MC112 | Neutral integrity monitoring | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3600 | 42.68% | MC | MC112s | Other | Std | Std | Customer metering & load control
NU | Non urban extension | Program - Short Term Need | 850000 | 1018160.95 | 740910.4122 | 658001.2052 | 626120.6297 | 612340.8974 | 612340.8974 | 612340.8974 | 612340.8974 | 612340.8974 | 619417 | 850000 | 1043614.9737 | 778419.0018 | 708595.3291 | 691120.0222 | 692807.5204 | 710127.7084 | 727880.9012 | 746077.9237 | 764729.8718 | 792906.1281 | 3655534.0945 | 6724314.6842 | 3914556.8472 | 7656279.3804 | 120 | 1800 | 82.37% | NU | NUs | Connections | Std | Std | Distribution lines and cables
OFP | Overloaded feeders (compliance) | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.33% | OF | OFPs | Augex | Std | Std | Distribution lines and cables
PF | Power factor | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PF | PFs | Other | Std | Unallocated | Unallocated
PQ001 | Permanent power quality monitoring | Program - Short Term Need | 615000 | 99884.332 | 99702.3924 | 99425.0891 | 99117.7104 | 98857.6189 | 98857.6189 | 98857.6189 | 98857.6189 | 98857.6189 | 100000 | 428055.67 | 102381.4403 | 104749.826 | 107069.9463 | 109407.4065 | 111848.322 | 114644.53 | 117510.6433 | 120448.4093 | 123459.6196 | 128008.4544 | 496987.1428 | 992417.6185 | 535456.9411 | 1139528.5977 | 300 | 4500 | 25.55% | PQ | PQ001s | Other | Std | Std | Substations
PQ003 | PQ surveying | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3600 | 42.68% | PQ | PQ003s | Other | Std | Std | Substations
PQ004 | Power quality monitoring replacement | Program - Short Term Need | 400000 | 342003.9528 | 615861.6776 | 868279.3032 | 939239.424 | 1348949.7761 | 1284714.0725 | 1413185.4798 | 1413185.4798 | 1156242.6653 | 1169604 | 363621.62 | 350554.0516 | 647039.6751 | 935041.8415 | 1036744.5836 | 1526212.8555 | 1489874.4542 | 1679833.4471 | 1721829.2833 | 1443988.6489 | 1497192.0032 | 4114334.1338 | 10551265.8311 | 4495593.0073 | 12328310.8439 | 200 | 3000 | 58.53% | PQ | PQ004s | Other | Std | Std | Substations
PR017 | Werrington ZS rebuild to 132kV | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR017 | Augex | Std | Unallocated | Unallocated
PR035 | Baulkham Hills TS 11kV supply | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR035 | Augex | Std | Unallocated | Unallocated
PR044 | West Liverpool ZS (Hoxton Park ZS rebuild) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6450 | 0% | PR | PR044 | Augex | Std | Std | Substations
PR052 | Penrith TS transformer and busbar augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6150 | 0% | PR | PR052 | Augex | Std | Std | Substations
PR054 | Quakers Hill ZS augment (132kV bar + 1st 132/11kV tfr) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR054 | Augex | Std | Std | Sub-transmission lines and cables
PR059 | ELTS 132kV busbar & substation works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR059 | Augex | Std | Std | Substations
PR060 | WLTS-ELTS first 132kV cable links | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR060 | Augex | Std | Std | Sub-transmission lines and cables
PR061 | Russell Vale ZS augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5325 | 1.975% | PR | PR061 | Augex | Std | Std | Substations
PR070 | Caddens ZS establishment and feeders | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR070 | Augex | Std | Std | Substations
PR073 | Campbelltown 66kV busbar & line to Ambarvale | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR073 | Augex | Std | Unallocated | Unallocated
PR081 | Collimore Park ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4147274.8292 | 12441824.4875 | 11187200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5053051.6686 | 15538133.881 | 14320561.8128 | 0 | 27776299.3167 | 0 | 34911747.3625 | 210 | 1050 | 95.93% | PR | PR081 | Augex | Std | Unallocated | Unallocated
PR090 | Doonside 132kV/11kV ZS rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6750 | 0% | PR | PR090 | Augex | Std | Std | Substations
PR091 | West Parramatta CBD 132kV/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5850 | 1.673% | PR | PR091 | Augex | Std | Std | Substations
PR096 | Berry ZS LDC CT's | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR096 | Augex | Std | Unallocated | Unallocated
PR102 | Kemps Creek/Luddenham capacity uprate | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4500 | 25.55% | PR | PR102 | Augex | Std | Std | Sub-transmission lines and cables
PR110 | Edmondson Park ZS establishment | Major Project - Committed Project | 2187000 | 1763811.4723 | 5095.7893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3153918 | 1807906.7591 | 5353.7636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768907.2615 | 1768907.2615 | 1813260.5227 | 1813260.5227 | 170 | 2550 | 68.69% | PR | PR110 | Augex | Std | Std | Substations
PR113 | Augment feeder 308 Nepean to Douglas Park | Major Project - Committed Project | 518000 | 1311730.9902 | 3928025.0031 | 3481866.6205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99996 | 1344524.2649 | 4126881.2689 | 3749589.5211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8721622.6138 | 8721622.6138 | 9220995.0549 | 9220995.0549 | 340 | 5100 | 9.284% | PR | PR113 | Augex | Std | Std | Sub-transmission lines and cables
PR123 | Connection works associated with Tomerong/Bamarang BSP | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR123 | Augex | Std | Std | Sub-transmission lines and cables
PR126 | Chipping Norton 33/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR126 | Augex | Std | Std | Substations
PR128 | Nepean ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PR | PR128 | Augex | Std | Std | Substations
PR144 | Sherwood ZS augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR144 | Augex | Std | Std | Substations
PR148 | Dapto ZS 3rd transformer & 33kV bus section CB's | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR148 | Augex | Std | Std | Transformers
PR149 | Gerringong ZS augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR149 | Augex | Std | Std | Substations
PR157 | Richmond ZS rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6450 | 0% | PR | PR157 | Augex | Std | Std | Substations
PR170 | Holsworthy 33/11kV ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4154392.5777 | 8308785.1555 | 8404800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5061723.9541 | 10376534.1059 | 10758854.5771 | 0 | 20867977.7332 | 0 | 26197112.6371 | 40 | 200 | 100% | PR | PR170 | Augex | Std | Std | Substations
PR172 | Parklea ZS 3rd transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR172 | Augex | Std | Std | Transformers
PR176 | Cheriton Av 132/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR176 | Augex | Std | Std | Substations
PR183 | Schofields ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR183 | Augex | Std | Unallocated | Unallocated
PR184 | Box Hill 22kV conversion | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PR | PR184 | Augex | Std | Std | Substations
PR186 | Glenorie ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR186 | Augex | Std | Std | Substations
PR190 | Eschol Park ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4378601.6575 | 8757203.3149 | 8757203.3149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204781.4112 | 10669801.893 | 10936546.9403 | 0 | 0 | 21893008.2873 | 0 | 26811130.2445 | 80 | 400 | 99.71% | PR | PR190 | Augex | Std | Std | Distribution lines and cables
PR192 | Feeder 7158 augment from Albion Park to Warilla | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR192 | Augex | Std | Unallocated | Unallocated
PR200 | Cordeaux/Figtree 33/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR200 | Augex | Std | Std | Substations
PR204 | Canley Vale subtransmission network upgrade | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5400 | 1.975% | PR | PR204 | Augex | Std | Std | Sub-transmission lines and cables
PR206 | Cawdor 66/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR206 | Augex | Std | Std | Substations
PR208 | Abbotsbury 132/11kV ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5700 | 1.673% | PR | PR208 | Augex | Std | Std | Substations
PR244 | Bellavista ZS establishment with two 132kV cable links | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR244 | Augex | Std | Unallocated | Unallocated
PR248 | Penrith Lakes ZS site acquisition | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 296572.8568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343933.59 | 0 | 0 | 0 | 0 | 0 | 296572.8568 | 0 | 343933.59 | 140 | 700 | 99.19% | PRL | PR248 | Augex | Std | Std | Land
PR249 | Establish Penrith Lakes 33/11kV Zone Substation | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 1553054.1819 | 6212216.7276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801066.7129 | 7384373.5228 | 0 | 0 | 0 | 0 | 7765270.9095 | 0 | 9185440.2357 | 140 | 700 | 99.19% | PR | PR249 | Augex | Std | Std | Substations
PR255 | Line works associated with Oran Park | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.33% | PR | PR255 | Augex | Std | Std | Sub-transmission lines and cables
PR257 | Menangle Park 66/11kV ZS site purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3150 | 54.88% | PRL | PR257 | Augex | Std | Std | Land
PR258 | Menangle Park 66/11kV ZS establishment | Major Project - Committed Project | 3800000 | 4481997.7601 | 8540.5069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295852.71 | 4594047.7041 | 8972.8701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4490538.267 | 4490538.267 | 4603020.5742 | 4603020.5742 | 170 | 2550 | 68.69% | PR | PR258 | Augex | Std | Std | Substations
PR261 | Huntingwood ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR261 | Augex | Std | Std | Substations
PR278 | Kemps Creek new BSP associated works | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1263400.3699 | 1263400.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1539330.6714 | 1577813.9381 | 0 | 0 | 2526800.7397 | 0 | 3117144.6095 | 20 | 100 | 100% | PR | PR278 | Augex | Std | Std | Sub-transmission lines and cables
PR280 | Wilton Park 66/11kV ZS establishment & 66kV line works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR280 | Augex | Std | Std | Substations
PR288 | Holroyd 330/132kV BSP associated works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR288 | Augex | Std | Std | Sub-transmission lines and cables
PR291 | Marsden Park Zone Substation site acquisition | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR291 | Augex | Std | Unallocated | Unallocated
PR292 | South Marsden Park (industrial) 132/11kV ZS establishment | Major Project - Committed Project | 14500000 | 1213606.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14082714.11 | 1243946.7856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213606.6201 | 1213606.6201 | 1243946.7856 | 1243946.7856 | 210 | 3150 | 54.88% | PR | PR292 | Augex | Std | Std | Substations
PR303 | Mittagong ZS transformer augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR303 | Augex | Std | Std | Transformers
PR308 | Granville ZS & Camellia TS rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3900 | 38.54% | PR | PR308 | Augex | Std | Std | Substations
PR311 | Quakers Hill ZS 2nd 132kV feeder | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR311 | Augex | Std | Unallocated | Unallocated
PR326 | Casula 33/11kV ZS establishment with link to LTS or WLTS | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR326 | Augex | Std | Std | Substations
PR329 | Box Hill site purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PRL | PR329 | Augex | Std | Std | Land
PR339 | North Eastern Creek ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR339 | Augex | Std | Std | Substations
PR342 | Jordan Springs establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.33% | PR | PR342 | Augex | Std | Std | Substations
PR343 | Wetherill Park ZS augmentation | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR343 | Augex | Std | Unallocated | Unallocated
PR353 | Shoalhaven Feeder 7510/7511 Augment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR353 | Augex | Std | Std | Sub-transmission lines and cables
PR384 | Glossodia ZS transformer augments | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR384 | Augex | Std | Std | Substations
PR406 | Tomerong ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4350 | 29.29% | PR | PR406 | Augex | Std | Std | Substations
PR408 | Oran Park (permanent) ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.53% | PR | PR408 | Augex | Std | Std | Substations
PR413 | Windsor transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.33% | PR | PR413 | Augex | Std | Std | Transformers
PR423 | Maryland ZS establishment | Major Project - Prior to Approval | 0 | 0 | 4114438.5661 | 8205990.0743 | 8180620.7596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4322732.0185 | 8836953.7798 | 9029874.6477 | 0 | 0 | 0 | 0 | 0 | 0 | 20501049.4 | 20501049.4 | 22189560.4461 | 22189560.4461 | 80 | 800 | 99.13% | PR | PR423 | Augex | Std | Std | Substations
PR424 | Austral ZS site purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1520855.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.33% | PRL | PR424 | Augex | Std | Std | Land
PR425 | Austral ZS establishment (interim initially) | Major Project - Prior to Approval | 0 | 0 | 3545417.0724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3724903.8117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3545417.0724 | 3545417.0724 | 3724903.8117 | 3724903.8117 | 160 | 1600 | 91.19% | PR | PR425 | Augex | Std | Std | Substations
PR426 | Leppington North ZS site purchase (strategic) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR426 | Augex | Std | Std | Land
PR427 | Leppington North ZS establishment | Major Project - Committed Project | 10000000 | 1753878.9743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9689043 | 1797725.9486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753878.9743 | 1753878.9743 | 1797725.9486 | 1797725.9486 | 210 | 3150 | 54.88% | PR | PR427 | Augex | Std | Std | Substations
PR429 | Leppington South ZS establishment (interim initially) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3675 | 38.64% | PR | PR429 | Augex | Std | Std | Substations
PR430 | North Rossmore ZS site purchase | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 2973531.3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3282222.1938 | 0 | 0 | 0 | 0 | 0 | 0 | 2973531.3129 | 2973531.3129 | 3282222.1938 | 3282222.1938 | 40 | 400 | 99.71% | PRL | PR430 | Augex | Std | Std | Land
PR432 | Rossmore ZS site purchase | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 0 | 2965728.5678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3355449.6588 | 0 | 0 | 0 | 0 | 0 | 2965728.5678 | 2965728.5678 | 3355449.6588 | 3355449.6588 | 40 | 400 | 99.71% | PRL | PR432 | Augex | Std | Std | Land
PR433 | Rossmore ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12800845.442 | 0 | 10000000 | 0 | 12800845.442 | 160 | 800 | 99.13% | PR | PR433 | Augex | Std | Unallocated | Unallocated
PR434 | Catherine Fields North land purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR434 | Augex | Std | Unallocated | Unallocated
PR435 | Catherine Fields North ZS establishment (interim) | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4242178.1433 | 8484356.2867 | 8582400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5168682.1416 | 10595798.3903 | 10986197.5921 | 0 | 21308934.43 | 0 | 26750678.124 | 140 | 700 | 99.19% | PR | PR435 | Augex | Std | Std | Substations
PR436 | Catherine Fields ZS site purchase | Major Project - Committed Project | 0 | 652268.6603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668575.3768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652268.6603 | 652268.6603 | 668575.3768 | 668575.3768 | 240 | 3600 | 42.68% | PRL | PR436 | Augex | Std | Std | Land
PR437 | Catherine Fields 11kV feeder works | Major Project - Committed Project | 530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2400 | 69.76% | PR | PR437 | Augex | Std | Std | Substations
PR438 | North Bringelly ZS site purchase | Major Project - Prior to Approval | 0 | 0 | 0 | 3479878.1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747448.1222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3479878.1187 | 3479878.1187 | 3747448.1222 | 3747448.1222 | 20 | 200 | 100% | PRL | PR438 | Augex | Std | Std | Land
PR439 | North Bringelly ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4369506.7565 | 8739013.513 | 8739013.513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193970.432 | 10647639.3857 | 10913830.3703 | 0 | 0 | 21847533.7826 | 0 | 26755440.188 | 40 | 200 | 100% | PR | PR439 | Augex | Std | Unallocated | Unallocated
PR440 | Feeder 443 and 458/1 augmentation and Cattai rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4800 | 12.56% | PR | PR440 | Augex | Std | Std | Sub-transmission lines and cables
PR444 | Culburra Beach development (33kV fdr and single transformer ZS) | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3788718.2453 | 1894359.1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4503595.4029 | 2308092.644 | 0 | 0 | 0 | 5683077.368 | 0 | 6811688.0469 | 110 | 550 | 99.19% | PR | PR444 | Augex | Std | Std | Substations
PR479 | Far South Coast 132kV voltage constraints | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12266.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4800 | 12.56% | PR | PR479 | Augex | Std | Std | Transformers
PR487 | Connection works associated with Macarthur BSP | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14791.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4050 | 37.22% | PR | PR487 | Augex | Std | Std | Sub-transmission lines and cables
PR499 | Southpipe (Oakdale Estate) ZS 132/11kV establishment | Major Project - Committed Project | 0 | 6339858.3217 | 12656620.4961 | 12621418.5114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 6498354.7797 | 13297361.9087 | 13591887.2691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31617897.3292 | 31617897.3292 | 33387603.9576 | 33387603.9576 | 140 | 2100 | 78.3% | PR | PR499 | Augex | Std | Std | Substations
PR517 | Installation of OPGW on Feeders 98W and 98F | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3825 | 38.54% | PR | PR517 | Augex | Std | Std | Sub-transmission lines and cables
PR521 | Culburra ZS fdr duplication & provision for rural ZS's | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3150 | 54.88% | PR | PR521 | Augex | Std | Std | Sub-transmission lines and cables
PR559 | Mamre ZS transformer augment and 11kV busbar extension | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PR | PR559 | Augex | Std | Std | Substations
PR563 | Shoalhaven TS 132kV capacitor install | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR563 | Augex | Std | Unallocated | Unallocated
PR595 | The Oaks ZS establishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR595 | Augex | Std | Unallocated | Unallocated
PR596 | Marsden Park (residential) 132/11kV ZS establishment - stage 1 | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179571.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4050 | 37.22% | PR | PR596 | Augex | Std | Std | Substations
PR599 | Penrith CBD ZS site purchase | Major Project - Committed Project | 3720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3367600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2100 | 78.3% | PRL | PR599 | Augex | Std | Std | Land
PR602 | Riverstone West site purchase | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4942880.9463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6022420.467 | 0 | 0 | 0 | 4942880.9463 | 0 | 6022420.467 | 70 | 350 | 99.71% | PRL | PR602 | Augex | Std | Std | Land
PR603 | Eschol Park ZS site purchase | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400422.721 | 0 | 5000000 | 0 | 6400422.721 | 100 | 500 | 99.19% | PRL | PR603 | Augex | Std | Std | Land
PR620 | West Dapto ZS establishment | Major Project - Prior to Approval | 0 | 0 | 0 | 4062111.4405 | 8099106.3545 | 4617837.0953 | 3460016.6624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4374449.728 | 8939897.9967 | 5224658.8154 | 4012558.5503 | 0 | 0 | 0 | 0 | 16779054.8903 | 20239071.5527 | 18539006.54 | 22551565.0903 | 110 | 1100 | 95.93% | PR | PR620 | Augex | Std | Std | Substations
PR632 | Mt Druitt TS automation scheme | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR632 | Augex | Std | Unallocated | Unallocated
PR642 | Auxiliary transformer at Shoalhaven TS | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR642 | Augex | Std | Unallocated | Unallocated
PR643 | Fibre works at Carlingford TS for Ausgrid | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR643 | Augex | Std | Std | Substations
PR652 | Purchase of additional land Lawson TS | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR652 | Augex | Std | Unallocated | Unallocated
PR653 | Avondale (South West Dapto) 132/11kV ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4942880.9463 | 4942880.9463 | 4942880.9463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5875532.1629 | 6022420.467 | 6172980.9787 | 0 | 0 | 14828642.8388 | 0 | 18070933.6086 | 110 | 550 | 99.19% | PR | PR653 | Augex | Std | Unallocated | Unallocated
PR656 | Leppington South ZS establishment (permanent) | Major Project - Committed Project | 10900000 | 13550952.7351 | 3516197.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7152455 | 13889726.5535 | 3694204.7802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17067150.0274 | 17067150.0274 | 17583931.3337 | 17583931.3337 | 230 | 3450 | 51.3% | PR | PR656 | Augex | Std | Std | Substations
PR657 | Calderwood ZS establishment (interim initially) | Major Project - Committed Project | 200000 | 1474792.1622 | 1472105.8232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46912.52 | 1511661.9663 | 1546631.1805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2946897.9854 | 2946897.9854 | 3058293.1468 | 3058293.1468 | 170 | 2550 | 68.69% | PR | PR657 | Augex | Std | Std | Substations
PR659 | Avondale (South West Dapto) 132/11kV Zone Substation establishment site purchase | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 2471440.4731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2866113.2502 | 0 | 0 | 0 | 0 | 0 | 2471440.4731 | 0 | 2866113.2502 | 60 | 300 | 99.71% | PRL | PR659 | Augex | Std | Std | Land
PR660 | Install 66kV iso Douglas Pk/Appin/Wcliff | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR660 | Augex | Std | Unallocated | Unallocated
PR673 | Liverpool ZS 11kV switchboard extension & distribution works | Major Project - Committed Project | 950000 | 292344.4595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1625842 | 299653.071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292344.4595 | 292344.4595 | 299653.071 | 299653.071 | 360 | 5400 | 1.975% | PR | PR673 | Augex | Std | Std | Substations
PR674 | South Marsden Park (stage 1) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5100 | 9.284% | PR | PR674 | Augex | Std | Std | Substations
PR677 | South Penrith Zone Substation | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 5774597.8096 | 11518889.7572 | 11518889.7572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6374075.5004 | 13032566.4747 | 13358380.6366 | 0 | 0 | 0 | 0 | 17293487.5668 | 28812377.324 | 19406641.9751 | 32765022.6116 | 210 | 2100 | 78.3% | PR | PR677 | Augex | Std | Std | Substations
PR698 | Marsden Park (residential) 132/11kV ZS - stage 2 | Major Project - Prior to Approval | 0 | 3060455.9329 | 3054881.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3136967.3313 | 3209534.6679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6115337.2349 | 6115337.2349 | 6346501.9992 | 6346501.9992 | 200 | 2000 | 80.62% | PR | PR698 | Augex | Std | Std | Substations
PR700 | Riverstone east ZS establishment | Major Project - Prior to Approval | 0 | 0 | 0 | 4062111.4405 | 8099106.3545 | 4617837.0953 | 3460016.6624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4374449.728 | 8939897.9967 | 5224658.8154 | 4012558.5503 | 0 | 0 | 0 | 0 | 16779054.8903 | 20239071.5527 | 18539006.54 | 22551565.0903 | 120 | 1200 | 94.49% | PR | PR700 | Augex | Std | Std | Substations
PR701 | Dapto 33kV feeder constraints | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2400 | 69.76% | PR | PR701 | Augex | Std | Std | Sub-transmission lines and cables
PR702 | Penrith ZS 11kV transformer cable constraints | Major Project - Committed Project | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | PR | PR702 | Augex | Std | Std | Transformers
PR703 | Riverstone East site purchase | Major Project - Prior to Approval | 0 | 5993059.9209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6142886.4189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5993059.9209 | 5993059.9209 | 6142886.4189 | 6142886.4189 | 120 | 1200 | 94.49% | PRL | PR703 | Augex | Std | Std | Land
PR704 | Oakdale (Southpipe) site purchase | Major Project - Committed Project | 300000 | 194896.3063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128559 | 199768.714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194896.3063 | 194896.3063 | 199768.714 | 199768.714 | 160 | 2400 | 69.76% | PRL | PR704 | Augex | Std | Std | Land
PR707 | 132kV ducts Bringelly Rd | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850291.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2850 | 66.13% | PR | PR707 | Augex | Std | Std | Sub-transmission lines and cables
PR709 | Feeder 230 undergrounding | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.33% | PR | PR709 | Augex | Std | Std | Sub-transmission lines and cables
PR710 | Feeder 868 rebuild & rearrangement South32 | Major Project - Committed Project | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1050 | 95.93% | PR | PR710 | Augex | Std | Std | Sub-transmission lines and cables
PR713 | Box Hill 132/22kV ZS establishment | Major Project - Prior to Approval | 0 | 7161307.0682 | 14296525.4457 | 14256762.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7340339.7449 | 15020287.0464 | 15352973.7467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35714594.8909 | 35714594.8909 | 37713600.5379 | 37713600.5379 | 170 | 1700 | 88.93% | PR | PR713 | Augex | Std | Std | Substations
PR715 | Nepean TS constraints | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR715 | Augex | Std | Std | Substations
PR716 | Box Hill ZS - 132kV ducts Old Pitt Town | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR716 | Augex | Std | Std | Sub-transmission lines and cables
PR717 | Acquire improved site for West Dapto ZS | Major Project - Committed Project | 0 | 1997686.6403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 2047628.8063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1997686.6403 | 1997686.6403 | 2047628.8063 | 2047628.8063 | 140 | 2100 | 78.3% | PRL | PR717 | Augex | Std | Std | Land
PR722 | Camellia TS connection works for Ausgrid | Major Project - Committed Project | 187082 | 274654.9443 | 104676.5447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1247859 | 281521.3179 | 109975.7948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379331.489 | 379331.489 | 391497.1127 | 391497.1127 | 170 | 2550 | 68.69% | PR | PR722 | Augex | Std | Std | Substations
PR723 | Supply to Luddenham Science Park | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 8540973.1076 | 17037122.0456 | 17037122.0456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9427636.2147 | 19275939.8065 | 19757838.3016 | 0 | 0 | 0 | 0 | 25578095.1533 | 42615217.1989 | 28703576.0211 | 48461414.3228 | 210 | 2100 | 78.3% | PR | PR723 | Augex | Std | Std | Substations
PR724 | Establish Mt Gilead ZS | Major Project - Prior to Approval | 0 | 0 | 0 | 4021347.154 | 8017829.832 | 4536773.8477 | 3460016.6624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4330551.05 | 8850183.9234 | 5132943.1914 | 4012558.5503 | 0 | 0 | 0 | 0 | 16575950.8337 | 20035967.4961 | 18313678.1647 | 22326236.715 | 200 | 2000 | 80.62% | PR | PR724 | Augex | Std | Std | Substations
PR727 | Luddenham ZS site purchase | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PRL | PR727 | Augex | Std | Std | Land
PR728 | Western Sydney Employment Lands ZS | Major Project - Prior to Approval | 0 | 0 | 0 | 4491031.2749 | 8954293.9601 | 8930797.2937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4836349.4765 | 9883865.0996 | 10104377.4058 | 0 | 0 | 0 | 0 | 0 | 22376122.5287 | 22376122.5287 | 24824591.9819 | 24824591.9819 | 160 | 1600 | 91.19% | PR | PR728 | Augex | Std | Std | Substations
PR729 | Cheriton Avenue 3rd transformer | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7066066.684 | 0 | 5520000 | 0 | 7066066.684 | 210 | 1050 | 95.93% | PR | PR729 | Augex | Std | Unallocated | Unallocated
PR732 | Feeder 214/215 contraints | Major Project - Committed Project | 0 | 5134054.6656 | 5124702.9675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5262406.0322 | 5384141.0552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10258757.633 | 10258757.633 | 10646547.0874 | 10646547.0874 | 220 | 3300 | 54.33% | PR | PR732 | Augex | Std | Std | Sub-transmission lines and cables
PR733 | Bringelly ZS augmentation | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 4215288.871 | 8430577.742 | 8430577.742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4888442.7596 | 10021307.6571 | 10271840.3485 | 0 | 0 | 0 | 21076444.3549 | 0 | 25181590.7651 | 140 | 700 | 99.19% | PR | PR733 | Augex | Std | Unallocated | Unallocated
PR735 | Termeil area distribution works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1131110.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PR | PR735 | Augex | Std | Std | Distribution lines and cables
PR739 | South Gilead (South Campbelltown) | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 3998395.2551 | 7996790.5101 | 7996790.5101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4636912.6607 | 9505670.9545 | 9743312.7283 | 0 | 0 | 0 | 19991976.2753 | 0 | 23885896.3435 | 110 | 550 | 99.19% | PR | PR739 | Augex | Std | Std | Substations
PR740 | AFIC upgrade Minto, Prospect, Kingswood | Major Project - Committed Project | 1900000 | 310803.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2242841 | 318573.1611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310803.084 | 310803.084 | 318573.1611 | 318573.1611 | 150 | 2250 | 70.87% | PR | PR740 | Augex | Std | Std | Substations
PR741 | Western Sydney Airport 132kV supply | Major Project - Prior to Approval | 0 | 0 | 0 | 7814812.0037 | 15581304.0794 | 15540417.6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8415697.7829 | 17198844.2955 | 17582556.212 | 0 | 0 | 0 | 0 | 0 | 38936533.7782 | 38936533.7782 | 43197098.2905 | 43197098.2905 | 170 | 1700 | 88.93% | PR | PR741 | Augex | Cont | Std | Sub-transmission lines and cables
PR742 | North Bomaderry ZS establishment | Major Project - Prior to Approval | 0 | 0 | 0 | 3662024.8819 | 7301407.021 | 3822230.9781 | 3460016.6624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3943600.2639 | 8059387.1895 | 4324503.5202 | 4012558.5503 | 0 | 0 | 0 | 0 | 14785662.8811 | 18245679.5435 | 16327490.9736 | 20340049.5239 | 100 | 1000 | 97.4% | PR | PR742 | Augex | Std | Std | Substations
PR744 | Termeil ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 3935274.6654 | 3935274.6654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4563712.1283 | 4677804.9315 | 0 | 0 | 0 | 0 | 7870549.3308 | 0 | 9241517.0598 | 270 | 1350 | 92.19% | PR | PR744 | Augex | Std | Std | Substations
PR745 | Austral Permanent ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 10398338.6467 | 10398338.6467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12058884.8889 | 12360357.0111 | 0 | 0 | 0 | 0 | 20796677.2934 | 0 | 24419241.9001 | 160 | 800 | 99.13% | PR | PR745 | Augex | Std | Unallocated | Unallocated
PR746 | Sydney University - Western Sydney Employment Lands ZS establishment | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12115989.7755 | 12115989.7755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14762157.0487 | 15131210.9749 | 0 | 0 | 24231979.5511 | 0 | 29893368.0236 | 80 | 400 | 99.71% | PR | PR746 | Augex | Std | Unallocated | Unallocated
PR748 | Establish permanent Catherine Park ZS | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 0 | 1878294.7596 | 3756589.5192 | 3756589.5192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125118.1172 | 4356492.1403 | 4465404.4438 | 0 | 0 | 0 | 1878294.7596 | 9391473.7979 | 2125118.1172 | 10947014.7014 | 240 | 2400 | 69.76% | PR | PR748 | Augex | Std | Std | Substations
PR749 | Nepean ZS augmentation | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3558874.2813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4230383.1573 | 0 | 0 | 0 | 0 | 3558874.2813 | 0 | 4230383.1573 | 250 | 1250 | 92.19% | PR | PR749 | Augex | Std | Unallocated | Unallocated
PR750 | Feeder 512 augmentation | Major Project - Committed Project | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2300 | 69.76% | PR | PR750 | Augex | Std | Std | Sub-transmission lines and cables
PR751 | Parklea ZS to Bella Vista ZS load transfer | Major Project - Prior to Approval | 0 | 0 | 997023.9236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1047498.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997023.9236 | 997023.9236 | 1047498.2598 | 1047498.2598 | 360 | 3600 | 42.68% | PR | PR751 | Augex | Std | Std | Substations
PR752 | Kemps Creek 132kV conversion | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8898000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11390192.2743 | 0 | 8898000 | 0 | 11390192.2743 | 340 | 1700 | 88.93% | PR | PR752 | Augex | Std | Unallocated | Unallocated
PR754 | Augment Westmead Zone Substation | Major Project - Prior to Approval | 0 | 0 | 0 | 0 | 5081269.4251 | 5067935.8342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5608770.6922 | 5733904.2252 | 0 | 0 | 0 | 0 | 0 | 10149205.2593 | 10149205.2593 | 11342674.9174 | 11342674.9174 | 360 | 3600 | 42.68% | PR | PR754 | Augex | Std | Std | Substations
PR755 | Narellan ZS busbar augmentation | Major Project - Future/Planning Stage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7196834.6578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8554774.8292 | 0 | 0 | 0 | 0 | 7196834.6578 | 0 | 8554774.8292 | 360 | 1800 | 82.37% | PR | PR755 | Augex | Std | Unallocated | Unallocated
PR761 | Glenfield Zone Substation site acquisition | Major Project - Prior to Approval |  | 0 | 2991071.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3142494.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2991071.7709 | 2991071.7709 | 3142494.7793 | 3142494.7793 | 170 | 1700 | 88.93% | PRL | PR761 | Augex | Std | Std | Substations
PR765 | Minto 66kV Reconfiguration | Major Project - Prior to Approval |  | 299652.996 | 398809.5695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307144.3209 | 418999.3039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698462.5655 | 698462.5655 | 726143.6249 | 726143.6249 | 180 | 1800 | 82.37% | PR | PR765 | Augex | Std | Std | Substations
PR766 | Baulkham Hills 132kV bus section CB | Major Project - Prior to Approval |  | 0 | 348958.3733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366624.3909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348958.3733 | 348958.3733 | 366624.3909 | 366624.3909 | 180 | 1800 | 82.37% | PR | PR766 | Augex | Std | Std | Substations
PR767 | Mt Terry 132kV bus section CB | Major Project - Prior to Approval |  | 0 | 0 | 397700.3564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428279.7854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397700.3564 | 397700.3564 | 428279.7854 | 428279.7854 | 180 | 1800 | 82.37% | PR | PR767 | Augex | Std | Std | Substations
PR768 | Establish Glenfield 66/11kV Zone Substation | Major Project - Future/Planning Stage |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6148943.8972 | 12297887.7944 | 12440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7491891.0609 | 15358376.6749 | 15924251.7298 | 0 | 30886831.6915 | 0 | 38774519.4657 | 170 | 850 | 97.4% | PR | PR768 | Augex | Std | Unallocated | Unallocated
PR769 | Nepean TS 132kV bus section CB | Major Project - Prior to Approval |  | 299652.996 | 299107.1771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307144.3209 | 314249.4779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598760.1731 | 598760.1731 | 621393.7989 | 621393.7989 | 180 | 1800 | 82.37% | PR | PR769 | Augex | Std | Std | Substations
PS002 | Replacement of ASEA RI O/C relays | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8296.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PS | PS002s | Repex | Std | Std | Substations
PS004 | Underfrequency load shed program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | PS | PS004s | Repex | Std | Unallocated | Unallocated
PS008 | Substation protection relay refurbishment | Program - Short Term Need | 3600000 | 4369939.5257 | 4486607.6563 | 4474129.0097 | 4460296.9693 | 4448592.8517 | 4695736.899 | 4695736.899 | 4695736.899 | 4695736.899 | 4750000 | 4598385 | 4479188.0138 | 4713742.1689 | 4818147.5856 | 4923333.2907 | 5033174.4882 | 5445615.1754 | 5581755.5548 | 5721299.4436 | 5864331.9297 | 6080401.5849 | 22239566.0127 | 45772513.6085 | 23967585.5472 | 52660989.2357 | 240 | 3600 | 42.68% | PS | PS008s | Repex | Std | Std | Substations
PS009 | Installation of SEF relays | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2850 | 66.13% | PS | PS009s | Repex | Std | Std | Substations
PS010 | Protection refurbishment (interfacing feeders) | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2550 | 68.69% | PS | PS010s | Repex | Std | Std | Substations
PS011 | Protection refurbishment (miscellaneous) | Program - Short Term Need | 895000 | 699190.3241 | 697916.7465 | 695975.6237 | 693823.973 | 692003.3325 | 692003.3325 | 692003.3325 | 692003.3325 | 692003.3325 | 700000 | 1259449.92 | 716670.0822 | 733248.7818 | 749489.6244 | 765851.8452 | 782938.2537 | 802511.7101 | 822574.5028 | 843138.8654 | 864217.337 | 896059.1809 | 3478909.9999 | 6946923.3298 | 3748198.5874 | 7976700.1836 | 150 | 2250 | 70.87% | PS | PS011s | Repex | Std | Std | Substations
PS012 | Distribution feeder safety improvement | Program - Short Term Need | 4615800 | 3096414.2925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2633018.75 | 3173824.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3096414.2925 | 3096414.2925 | 3173824.6498 | 3173824.6498 | 310 | 4650 | 21% | PS | PS012s | Repex | Std | Std | Substations
PS013 | Feeder differential relay replacement | Program - Short Term Need | 330000 | 0 | 329017.8948 | 328102.794 | 327088.4444 | 326230.1425 | 326230.1425 | 326230.1425 | 326230.1425 | 326230.1425 | 330000 | 0 | 0 | 345674.4257 | 353330.8229 | 361044.4413 | 369099.4625 | 378326.949 | 387785.1228 | 397479.7508 | 407416.7446 | 422427.8996 | 1310439.2757 | 2945359.8455 | 1429149.1525 | 3422585.6192 | 240 | 3600 | 42.68% | PS | PS013s | Repex | Std | Std | Substations
PS014 | Under frequency load shedding | Program - Short Term Need | 500000 | 549363.8261 | 548363.158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313232.73 | 563097.9217 | 576124.0429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097726.9841 | 1097726.9841 | 1139221.9646 | 1139221.9646 | 170 | 2550 | 68.69% | PS | PS014s | Repex | Std | Std | Substations
RC | Reliability compliance | Program - Short Term Need | 4000000 | 3995373.2806 | 3988095.6945 | 3977003.5642 | 3964708.4171 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 4000000 | 3685231.26 | 4095257.6126 | 4189993.0391 | 4282797.8539 | 4376296.2584 | 4473932.8784 | 4585781.2003 | 4700425.7303 | 4817936.3736 | 4938384.7829 | 5120338.1768 | 19879485.7135 | 39696704.7416 | 21418277.6424 | 45581143.9063 | 400 | 6000 | 1.673% | RC | RCs | Reliability | Std | Std | Distribution lines and cables
RI | Reliability enhancement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359985.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6000 | 1.673% | RI | RIs | Reliability | Std | Std | Distribution lines and cables
SG001 | Smart grid fibre rollout & trial | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | SG | SG001s | Other | Std | Unallocated | Unallocated
SG002 | Smart meter rollout | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | SG | SG002s | Other | Std | Unallocated | Unallocated
SL001 | Streetlighting growth | Program - Short Term Need | 1400000 | 1747975.8103 | 1744791.8664 | 1739939.0593 | 1734559.9325 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 1750000 | 1100000 | 1791675.2055 | 1833121.9546 | 1873724.0611 | 1914629.6131 | 1957345.6343 | 2006279.2751 | 2056436.257 | 2107847.1634 | 2160543.3425 | 2240147.9523 | 8697274.9997 | 17367308.3245 | 9370496.4685 | 19941750.459 | 100 | 1500 | 92.19% | SL | SL001s | Other | Alt | Alt | Public lighting
SL002 | Streetlighting refurbishment | Program - Short Term Need | 3000000 | 2996529.9605 | 2991071.7709 | 2982752.6732 | 2973531.3129 | 2965728.5678 | 2965728.5678 | 2965728.5678 | 2965728.5678 | 2965728.5678 | 3000000 | 1900000 | 3071443.2095 | 3142494.7793 | 3212098.3904 | 3282222.1938 | 3355449.6588 | 3439335.9002 | 3525319.2978 | 3613452.2802 | 3703788.5872 | 3840253.6326 | 14909614.2851 | 29772528.5562 | 16063708.2318 | 34185857.9298 | 220 | 3300 | 54.33% | SL | SL002s | Other | Alt | Alt | Public lighting
SP | Essential spares | Program - Short Term Need | 1239026 | 998843.3202 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 1423626.78 | 1023814.4032 | 1047498.2598 | 1070699.4635 | 1094074.0646 | 1118483.2196 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 4969871.4284 | 9924176.1854 | 5354569.4106 | 11395285.9766 | 160 | 2400 | 69.76% | SP | SPs | Repex | Std | Std | Emergency Spares (Major Plant, Excludes Inventory)
TM004 | 66 & 33kV line refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM004s | Repex | Std | Unallocated | Unallocated
TM008 | 132kV tower refurb/safety upgrade | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM008s | Repex | Std | Std | Sub-transmission lines and cables
TM012 | Sub-transmission pole replacement | Program - Short Term Need | 2500000 | 2756807.5636 | 2751786.0292 | 2744132.4593 | 2735648.8078 | 3914761.7095 | 4221220.3281 | 4221220.3281 | 4221220.3281 | 4221220.3281 | 4270000 | 2499999.99 | 2825727.7527 | 2891095.1969 | 2955130.5192 | 3019644.4183 | 4429193.5496 | 4895321.4314 | 5017704.4671 | 5143147.0788 | 5271725.7558 | 5465961.0037 | 14903136.5694 | 36058017.8819 | 16120791.4367 | 41914651.1735 | 310 | 4650 | 21% | TM | TM012s | Repex | Std | Std | Sub-transmission lines and cables
TM012 | Sub-transmission pole replacement | Program - Medium Term Need |  | 958889.5873 | 957142.9667 | 954480.8554 | 951530.0201 | 949033.1417 | 1255491.7604 | 1255491.7604 | 1255491.7604 | 1255491.7604 | 1270000 | 0 | 982861.827 | 1005598.3294 | 1027871.4849 | 1050311.102 | 1073743.8908 | 1455985.5311 | 1492385.1694 | 1529694.7986 | 1567937.1686 | 1625707.3711 | 4771076.5712 | 11063043.6127 | 5140386.6342 | 12812096.673 | 310 | 3100 | 55.28% | TM | TM012m | Repex | Std | Std | Sub-transmission lines and cables
TM013 | Underground pilots | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM013s | Repex | Std | Unallocated | Unallocated
TM014 | Renewal of 33kV and 66kV gas and oil filled cables | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2700 | 66.49% | TM | TM014s | Repex | Std | Std | Sub-transmission lines and cables
TM014 | Renewal of 33kV and 66kV gas and oil filled cables | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2224296.4258 | 2224296.4258 | 2224296.4258 | 2250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2643989.4733 | 2710089.2101 | 2777841.4404 | 2880190.2244 | 0 | 8922889.2775 | 0 | 11012110.3483 | 180 | 1800 | 82.37% | TM | TM014m | Repex | Std | Std | Sub-transmission lines and cables
TM015 | Subtransmission tower replacement | Program - Short Term Need | 1600000 | 958889.5873 | 957142.9667 | 954480.8554 | 951530.0201 | 949033.1417 | 1898066.2834 | 1898066.2834 | 1898066.2834 | 1898066.2834 | 1920000 | 0 | 982861.827 | 1005598.3294 | 1027871.4849 | 1050311.102 | 1073743.8908 | 2201174.9762 | 2256204.3506 | 2312609.4593 | 2370424.6958 | 2457762.3249 | 4771076.5712 | 14283341.7047 | 5140386.6342 | 16738562.4409 | 310 | 4650 | 21% | TM | TM015s | Repex | Std | Std | Sub-transmission lines and cables
TM016 | Cast iron UGOH replacement within zone substations | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | TM | TM016s | Repex | Std | Std | Sub-transmission lines and cables
TM017 | Installation of overhead earthwire | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM017s | Repex | Std | Unallocated | Unallocated
TM019 | Access track reconstruction | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4500 | 25.55% | TM | TM019s | Repex | Std | Std | Sub-transmission lines and cables
TM020 | Traffic blackspot remediation - transmission | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM020 | Repex | Std | Unallocated | Unallocated
TM021 | Capital works for compliance to NSW Maritime Waterways | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TM | TM021 | Repex | Std | Std | Sub-transmission lines and cables
TM023 | Renewal of 132kV cable 233 | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | TM | TM023 | Repex | Std | Std | Sub-transmission lines and cables
TM027 | Steel tower asbestos removal | Major Project - Committed Project | 3013000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3900 | 38.54% | TM | TM027 | Repex | Std | Std | Sub-transmission lines and cables
TM028 | 132kV oil cable replacement | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 10083477.1304 | 9786904.2736 | 9786904.2736 | 10083477.1304 | 10200000 | 0 | 0 | 0 | 0 | 0 | 0 | 11693742.0608 | 11633553.6826 | 11924392.5247 | 12592881.1965 | 13056862.3508 | 0 | 49940762.8081 | 0 | 60901431.8154 | 260 | 1300 | 92.19% | TM | TM028l | Repex | Std | Std | Sub-transmission lines and cables
TM029 | Installation of aerial marker malls on high spans | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122585.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2100 | 78.3% | TM | TM029s | Repex | Std | Std | Sub-transmission lines and cables
TM030 | Feeder 7028 replacement | Major Project - Prior to Approval | 500000 | 1598149.3122 | 1595238.2778 | 1590801.4257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1638103.045 | 1675997.2156 | 1713119.1416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4784189.0157 | 4784189.0157 | 5027219.4022 | 5027219.4022 | 200 | 2000 | 80.62% | TM | TM030 | Repex | Std | Std | Sub-transmission lines and cables
TM031 | Steel tower asbestos removal | Program - Short Term Need |  | 12180.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112125 | 12485.4166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12180.8943 | 12180.8943 | 12485.4166 | 12485.4166 | 260 | 3900 | 38.54% | TM | TM031s | Repex | Std | Std | Sub-transmission lines and cables
TM031 | Steel tower asbestos removal | Program - Medium Term Need |  | 2796761.2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2866680.3288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2796761.2964 | 2796761.2964 | 2866680.3288 | 2866680.3288 | 260 | 2600 | 66.72% | TM | TM031m | Repex | Std | Std | Sub-transmission lines and cables
TM033 | Pole top structure/hardware refurbishment (TR) | Program - Short Term Need |  | 1346111.1773 | 1343659.2312 | 1339922.0983 | 1335779.6481 | 1332274.473 | 1332274.473 | 1332274.473 | 1332274.473 | 1332274.473 | 1347670 | 734759.36 | 1379763.9567 | 1411681.9797 | 1442949.5459 | 1474450.7946 | 1507346.2805 | 1545029.9376 | 1583655.686 | 1623247.0782 | 1663828.2551 | 1725131.5377 | 6697746.6279 | 13374514.5198 | 7216192.5576 | 15357085.0521 | 330 | 4950 | 12.56% | TM | TM033s | Repex | Std | Std | Sub-transmission lines and cables
TM131 | Underground pilots replacement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1950 | 80.62% | TM | TM131s | Repex | Std | Std | Sub-transmission lines and cables
TM132 | Sub-transmission pilot cable renewal program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102262.451 | 1102262.451 | 1102262.451 | 1115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1310243.6723 | 1342999.7641 | 1376574.7582 | 1427294.2668 | 0 | 4421787.3531 | 0 | 5457112.4615 | 160 | 2400 | 69.76% | TM | TM132s | Repex | Std | Std | Sub-transmission lines and cables
TM133 | Hardex pilot cable renewal | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3300 | 54.33% | TM | TM133s | Repex | Std | Std | Sub-transmission lines and cables
TM134 | Wollongong - Port Kembla pilot cable replacement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1645979.3551 | 1645979.3551 | 1645979.3551 | 1665000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1956552.2103 | 2005466.0155 | 2055602.6659 | 2131340.7661 | 0 | 6602938.0653 | 0 | 8148961.6577 | 110 | 1650 | 88.96% | TM | TM134s | Repex | Std | Std | Sub-transmission lines and cables
TM135 | Optical fibre protection and communication upgrades in the Blue Mountains | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917398.7036 | 917398.7036 | 917398.7036 | 928000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1090498.7694 | 1117761.2387 | 1145705.2696 | 1187918.457 | 0 | 3680196.1109 | 0 | 4541883.7348 | 110 | 1650 | 88.96% | TM | TM135s | Repex | Std | Std | Sub-transmission lines and cables
TM137 | Optical fibre protection and communication upgrades in the Macarthur area | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897627.1798 | 897627.1798 | 897627.1798 | 908000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066996.6408 | 1093671.5568 | 1121013.3457 | 1162316.7661 | 0 | 3600881.5395 | 0 | 4443998.3095 | 110 | 1650 | 88.96% | TM | TM137s | Repex | Std | Std | Sub-transmission lines and cables
TM138 | 132kV optical fibre ring completion | Major Project - Committed Project | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1650 | 88.96% | TM | TM138 | Repex | Std | Std | Sub-transmission lines and cables
TM171 | Replacement of corroded earthwires | Program - Short Term Need | 2000000 | 0 | 0 | 0 | 0 | 136423.5141 | 886752.8418 | 886752.8418 | 886752.8418 | 886752.8418 | 897000 | 3545011.83 | 0 | 0 | 0 | 0 | 154350.6843 | 1028361.4342 | 1054070.47 | 1080422.2318 | 1107432.7876 | 1148235.8361 | 136423.5141 | 4580434.8812 | 154350.6843 | 5572873.444 | 270 | 4050 | 37.22% | TM | TM171s | Repex | Std | Std | Sub-transmission lines and cables
TM172 | Earthwire replacement due to fault rating | Program - Short Term Need | 0 | 0 | 997023.9236 | 994250.8911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1047498.2598 | 1070699.4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1991274.8147 | 1991274.8147 | 2118197.7232 | 2118197.7232 | 170 | 2550 | 68.69% | TM | TM172s | Repex | Std | Std | Sub-transmission lines and cables
TM174 | Hardex earthwire replacement | Program - Short Term Need | 0 | 0 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 0 | 0 | 1047498.2598 | 1070699.4635 | 1094074.0646 | 1118483.2196 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 3971028.1082 | 8925332.8653 | 4330755.0074 | 10371471.5734 | 240 | 3600 | 42.68% | TM | TM174s | Repex | Std | Std | Sub-transmission lines and cables
TM302 | Oil filled cable auxiliary equipment refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.53% | TM | TM302s | Repex | Std | Std | Sub-transmission lines and cables
TM302 | Oil filled cable auxiliary equipment refurbishment | Program - Medium Term Need | 0 | 0 | 71785.7225 | 0 | 0 | 0 | 0 | 71177.4856 | 0 | 0 | 0 | 0 | 0 | 75419.8747 | 0 | 0 | 0 | 0 | 84607.6631 | 0 | 0 | 0 | 71785.7225 | 142963.2081 | 75419.8747 | 160027.5378 | 200 | 2000 | 80.62% | TM | TM302m | Repex | Std | Std | Sub-transmission lines and cables
TM303 | Guilford and Camellia 132kV cables oil testing and flushing | Program - Short Term Need | 465136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3900 | 38.54% | TM | TM303s | Repex | Std | Std | Sub-transmission lines and cables
TM303 | Guilford and Camellia 132kV cables oil testing and flushing | Program - Medium Term Need |  | 0 | 89732.1531 | 0 | 0 | 0 | 0 | 88971.857 | 0 | 0 | 0 | 0 | 0 | 94274.8434 | 0 | 0 | 0 | 0 | 105759.5789 | 0 | 0 | 0 | 89732.1531 | 178704.0102 | 94274.8434 | 200034.4223 | 260 | 2600 | 66.72% | TM | TM303m | Repex | Std | Std | Sub-transmission lines and cables
TM401 | South Coast 33kV overhead line refurbishment | Program - Short Term Need | 998000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932355.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3600 | 42.68% | TM | TM401s | Repex | Std | Std | Sub-transmission lines and cables
TM404 | Avon/Nepean Dam feeder refurbishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5250 | 4.712% | TM | TM404 | Repex | Std | Std | Sub-transmission lines and cables
TM408 | Ringwood Feeder 7906 Refurbishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3200 | 54.33% | TM | TM408 | Repex | Std | Std | Sub-transmission lines and cables
TM410 | Hazelbook ZS to Springwood ZS Feeder 808 refurbishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4350 | 29.29% | TM | TM410 | Repex | Std | Std | Sub-transmission lines and cables
TM419 | Future sub-transmission feeder refurbishment works | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460016.6624 | 7414321.4194 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4215694.3269 | 9259471.468 | 15361014.5304 | 0 | 22874338.0818 | 0 | 28836180.3253 | 150 | 2250 | 70.87% | TM | TM419s | Repex | Std | Std | Sub-transmission lines and cables
TM419 | Future sub-transmission feeder refurbishment works | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 889718.5703 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602242.0467 | 1111136.5762 | 1920126.8163 | 0 | 2884006.665 | 0 | 3633505.4392 | 150 | 1500 | 92.19% | TM | TM419m | Repex | Std | Std | Sub-transmission lines and cables
TM419 | Future sub-transmission feeder refurbishment works | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 889718.5703 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602242.0467 | 1111136.5762 | 1920126.8163 | 0 | 2884006.665 | 0 | 3633505.4392 | 150 | 750 | 99.19% | TM | TM419l | Repex | Std | Std | Sub-transmission lines and cables
TM801 | Steel tower painting program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 790860.9514 | 790860.9514 | 790860.9514 | 790860.9514 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 917156.2401 | 940085.1461 | 963587.2747 | 987676.9566 | 1024067.6354 | 0 | 3963443.8056 | 0 | 4832573.2528 | 170 | 2550 | 68.69% | TM | TM801s | Repex | Std | Std | Sub-transmission lines and cables
TM803 | Steel tower below ground rectification work | Program - Short Term Need | 2599999.92 | 0 | 1495535.8854 | 1491376.3366 | 1486765.6564 | 1482864.2839 | 1482864.2839 | 1482864.2839 | 1186291.4271 | 741432.1419 | 750000 | 4408559.12 | 0 | 1571247.3896 | 1606049.1952 | 1641111.0969 | 1677724.8294 | 1719667.9501 | 1762659.6489 | 1445380.9121 | 925947.1468 | 960063.4081 | 5956542.1623 | 11599994.2992 | 6496132.5111 | 13309851.5772 | 310 | 4650 | 21% | TM | TM803s | Repex | Std | Std | Sub-transmission lines and cables
TM805 | Earthing refurbishment of lines 940/941 | Program - Short Term Need | 178388.89 | 199768.664 | 199404.7847 | 198850.1782 | 198235.4209 | 19771.5238 | 19771.5238 | 19771.5238 | 19771.5238 | 19771.5238 | 20000 | 46970 | 204762.8806 | 209499.652 | 214139.8927 | 218814.8129 | 22369.6644 | 22928.906 | 23502.1287 | 24089.6819 | 24691.9239 | 25601.6909 | 816030.5716 | 915116.6667 | 869586.9026 | 990401.2339 | 270 | 4050 | 37.22% | TM | TM805s | Repex | Std | Std | Sub-transmission lines and cables
TM805 | Earthing refurbishment of lines 940/941 | Program - Medium Term Need |  | 79907.4656 | 79761.9139 | 79540.0713 | 79294.1683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81905.1523 | 83799.8608 | 85655.9571 | 87525.9252 | 0 | 0 | 0 | 0 | 0 | 0 | 318503.6191 | 318503.6191 | 338886.8953 | 338886.8953 | 270 | 2700 | 66.49% | TM | TM805m | Repex | Std | Std | Sub-transmission lines and cables
TM809 | Subtransmission line earthing refurbishment | Program - Short Term Need | 0 | 0 | 299107.1771 | 298275.2673 | 297353.1313 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 300000 | 0 | 0 | 314249.4779 | 321209.839 | 328222.2194 | 335544.9659 | 343933.59 | 352531.9298 | 361345.228 | 370378.8587 | 384025.3633 | 1191308.4325 | 2677599.8596 | 1299226.5022 | 3111441.472 | 150 | 2250 | 70.87% | TM | TM809s | Repex | Std | Std | Sub-transmission lines and cables
TM809 | Subtransmission line earthing refurbishment | Program - Medium Term Need | 0 | 0 | 299107.1771 | 298275.2673 | 297353.1313 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 296572.8568 | 300000 | 0 | 0 | 314249.4779 | 321209.839 | 328222.2194 | 335544.9659 | 343933.59 | 352531.9298 | 361345.228 | 370378.8587 | 384025.3633 | 1191308.4325 | 2677599.8596 | 1299226.5022 | 3111441.472 | 150 | 1500 | 92.19% | TM | TM809m | Repex | Std | Std | Sub-transmission lines and cables
TS001 | Power transformer replacement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS001s | Repex | Std | Unallocated | Unallocated
TS004 | 132kV circuit breaker replacement | Program - Short Term Need | 903000 | 0 | 0 | 0 | 358806.1118 | 357864.5805 | 357864.5805 | 357864.5805 | 357864.5805 | 357864.5805 | 362000 | 100000 | 0 | 0 | 0 | 396054.8114 | 404890.9255 | 415013.1986 | 425388.5286 | 436023.2418 | 446923.8229 | 463390.605 | 716670.6923 | 2510129.0143 | 800945.7369 | 2987685.1338 | 240 | 3600 | 42.68% | TS | TS004s | Repex | Std | Std | Substations
TS005 | 33kV circuit breaker replacement | Program - Short Term Need | 3410000 | 0 | 0 | 0 | 763206.3703 | 761203.6657 | 1170474.2081 | 1170474.2081 | 1170474.2081 | 1170474.2081 | 1184000 | 1522311.51 | 0 | 0 | 0 | 842437.0297 | 861232.0791 | 1357391.2353 | 1391326.0162 | 1426109.1666 | 1461761.8957 | 1515620.1003 | 1524410.036 | 7390306.8683 | 1703669.1088 | 8855877.523 | 240 | 3600 | 42.68% | TS | TS005s | Repex | Std | Std | Substations
TS007 | 11kV circuit breaker replacement | Program - Short Term Need | 0 | 0 | 348958.3733 | 347987.8119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.59 | 0 | 366624.3909 | 374744.8122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696946.1851 | 696946.1851 | 741369.2031 | 741369.2031 | 230 | 3450 | 51.3% | TS | TS007s | Repex | Std | Std | Substations
TS008 | Battery replacement | Program - Short Term Need | 1253792 | 519398.5265 | 518452.4403 | 517010.4633 | 515412.0942 | 514059.6184 | 514059.6184 | 514059.6184 | 514059.6184 | 514059.6184 | 520000 | 1300326.84 | 532383.4896 | 544699.0951 | 556763.721 | 568918.5136 | 581611.2742 | 596151.556 | 611055.3449 | 626331.7286 | 641990.0218 | 665643.963 | 2584333.1428 | 5160571.6164 | 2784376.0935 | 5925548.7078 | 370 | 5550 | 1.951% | TS | TS008s | Repex | Std | Std | Substations
TS008 | Battery replacement | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 514059.6184 | 514059.6184 | 514059.6184 | 514059.6184 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 596151.556 | 611055.3449 | 626331.7286 | 641990.0218 | 665643.963 | 0 | 2576238.4737 | 0 | 3141172.6143 | 370 | 3700 | 38.64% | TS | TS008m | Repex | Std | Std | Substations
TS009 | Auxiliary switchgear replacement | Program - Short Term Need | 817000 | 0 | 0 | 0 | 279511.9434 | 0 | 278778.4854 | 0 | 0 | 0 | 0 | 647392 | 0 | 0 | 0 | 308528.8862 | 0 | 323297.5746 | 0 | 0 | 0 | 0 | 279511.9434 | 558290.4288 | 308528.8862 | 631826.4608 | 190 | 2850 | 66.13% | TS | TS009s | Repex | Std | Std | Substations
TS011 | Freq injection replacement/augmentation | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS011s | Repex | Std | Unallocated | Unallocated
TS015 | Replacement of surge arrester in zone and sub-transmission substations | Program - Short Term Need | 132000 | 36957.2028 | 49851.1962 | 49712.5446 | 49558.8552 | 24714.4047 | 49428.8095 | 49428.8095 | 49428.8095 | 49428.8095 | 50000 | 57400 | 37881.1329 | 52374.913 | 53534.9732 | 54703.7032 | 27962.0805 | 57322.265 | 58755.3216 | 60224.2047 | 61729.8098 | 64004.2272 | 210794.2035 | 458509.4414 | 226456.8028 | 528492.6311 | 190 | 2850 | 66.13% | TS | TS015s | Repex | Std | Std | Substations
TS015 | Replacement of surge arrester in zone and sub-transmission substations | Program - Medium Term Need |  | 0 | 67797.6268 | 67609.0606 | 67400.0431 | 24714.4047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71229.8817 | 72807.5635 | 74397.0364 | 27962.0805 | 0 | 0 | 0 | 0 | 0 | 227521.1352 | 227521.1352 | 246396.5621 | 246396.5621 | 190 | 1900 | 80.7% | TS | TS015m | Repex | Std | Std | Substations
TS016 | VT and CT replacement | Program - Short Term Need | 1095000 | 0 | 0 | 0 | 691841.6188 | 690026.1801 | 690026.1801 | 690026.1801 | 690026.1801 | 690026.1801 | 698000 | 1131559.16 | 0 | 0 | 0 | 763663.6971 | 780701.2873 | 800218.8195 | 820224.2899 | 840729.8972 | 861748.1446 | 893499.0118 | 1381867.7989 | 4839972.5193 | 1544364.9844 | 5760785.1474 | 240 | 3600 | 42.68% | TS | TS016s | Repex | Std | Std | Substations
TS017 | Power transformer refurbishment | Program - Short Term Need | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2100 | 78.3% | TS | TS017s | Repex | Std | Std | Transformers
TS020 | Portable earthing set cabinets | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1350 | 92.19% | TS | TS020s | Repex | Std | Std | Substations
TS024 | Building and amenities refurbishment | Program - Short Term Need | 500000 | 1498264.9802 | 1495535.8854 | 1491376.3366 | 1486765.6564 | 1482864.2839 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 740909.15 | 1535721.6047 | 1571247.3896 | 1606049.1952 | 1641111.0969 | 1677724.8294 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 7454807.1426 | 12409111.8996 | 8031854.1159 | 14072570.6819 | 200 | 3000 | 58.53% | TS | TS024s | Repex | Std | Std | Substations
TS024 | Building and amenities refurbishment | Program - Medium Term Need |  | 0 | 0 | 0 | 0 | 0 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 0 | 4954304.757 | 0 | 6040716.566 | 200 | 2000 | 80.62% | TS | TS024m | Repex | Std | Std | Substations
TS025 | Asbestos and other hazardous material reporting, management and removal | Program - Short Term Need | 650000 | 88897.0555 | 448660.7656 | 447412.901 | 513429.74 | 514059.6184 | 532842.566 | 444859.2852 | 444859.2852 | 512082.466 | 520000 | 641743.65 | 91119.4819 | 471374.2169 | 481814.7586 | 566730.3655 | 581611.2742 | 617934.0167 | 528797.8947 | 542017.842 | 639520.8294 | 665643.963 | 2012460.0805 | 4467103.6829 | 2192650.097 | 5186564.6428 | 160 | 2400 | 69.76% | TS | TS025s | Repex | Std | Std | Substations
TS026 | Noise attenuation in ZS and TS | Program - Short Term Need | 0 | 0 | 0 | 994250.8911 | 0 | 988576.1893 | 0 | 988576.1893 | 0 | 988576.1893 | 0 | 0 | 0 | 0 | 1070699.4635 | 0 | 1118483.2196 | 0 | 1175106.4326 | 0 | 1234596.1957 | 0 | 1982827.0803 | 3959979.4588 | 2189182.6831 | 4598885.3114 | 210 | 3150 | 54.88% | TS | TS026s | Repex | Std | Std | Substations
TS027 | Substation switchyard lighting improvement | Program - Short Term Need | 0 | 109872.7652 | 109672.6316 | 109367.598 | 109029.4815 | 108743.3808 | 108743.3808 | 108743.3808 | 108743.3808 | 108743.3808 | 110000 | 0 | 112619.5843 | 115224.8086 | 117776.941 | 120348.1471 | 123033.1542 | 126108.983 | 129261.7076 | 132493.2503 | 135805.5815 | 140809.2999 | 546685.8571 | 1091659.3804 | 589002.6352 | 1253481.4574 | 140 | 2100 | 78.3% | TS | TS027s | Repex | Std | Std | Substations
TS028 | Control cable trench and cover refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 600 | 99.19% | TS | TS028s | Repex | Std | Std | Substations
TS029 | Substation control room temperature reduction initiatives | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1500 | 92.19% | TS | TS029s | Repex | Std | Std | Substations
TS031 | Substation safety fence upgrade program | Program - Short Term Need | 300000 | 99884.332 | 99702.3924 | 99425.0891 | 99117.7104 | 98857.6189 | 98857.6189 | 98857.6189 | 98857.6189 | 98857.6189 | 100000 | 646105.78 | 102381.4403 | 104749.826 | 107069.9463 | 109407.4065 | 111848.322 | 114644.53 | 117510.6433 | 120448.4093 | 123459.6196 | 128008.4544 | 496987.1428 | 992417.6185 | 535456.9411 | 1139528.5977 | 230 | 3450 | 51.3% | TS | TS031s | Repex | Std | Std | Substations
TS032 | Substation security systems | Program - Short Term Need | 0 | 149826.498 | 149553.5885 | 149137.6337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153572.1605 | 157124.739 | 160604.9195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448517.7202 | 448517.7202 | 471301.819 | 471301.819 | 150 | 2250 | 70.87% | TS | TS032s | Repex | Std | Std | Substations
TS033 | Substation fire hydrant installations | Program - Short Term Need | 200000 | 199768.664 | 199404.7847 | 198850.1782 | 198235.4209 | 197715.2379 | 197715.2379 | 197715.2379 | 197715.2379 | 197715.2379 | 200000 | 191793 | 204762.8806 | 209499.652 | 214139.8927 | 218814.8129 | 223696.6439 | 229289.06 | 235021.2865 | 240896.8187 | 246919.2391 | 256016.9088 | 993974.2857 | 1984835.2371 | 1070913.8821 | 2279057.1953 | 160 | 2400 | 69.76% | TS | TS033s | Repex | Std | Std | Substations
TS034 | Substation deluge showers and fire blankets | Program - Short Term Need | 160000 | 159814.9312 | 159523.8278 | 159080.1426 | 158588.3367 | 158172.1903 | 158172.1903 | 158172.1903 | 158172.1903 | 158172.1903 | 160000 | 152066.08 | 163810.3045 | 167599.7216 | 171311.9142 | 175051.8503 | 178957.3151 | 183431.248 | 188017.0292 | 192717.4549 | 197535.3913 | 204813.5271 | 795179.4285 | 1587868.1897 | 856731.1057 | 1823245.7563 | 120 | 1800 | 82.37% | TS | TS034s | Repex | Std | Std | Substations
TS035 | Substation oil containment program - bund walls | Program - Short Term Need | 210000 | 69919.0324 | 69791.6747 | 69597.5624 | 69382.3973 | 69200.3332 | 69200.3332 | 69200.3332 | 69200.3332 | 69200.3332 | 70000 | 198616 | 71667.0082 | 73324.8782 | 74948.9624 | 76585.1845 | 78293.8254 | 80251.171 | 82257.4503 | 84313.8865 | 86421.7337 | 89605.9181 | 347891 | 694692.333 | 374819.8587 | 797670.0184 | 110 | 1650 | 88.96% | TS | TS035s | Repex | Std | Std | Substations
TS036 | Substation earthing | Program - Short Term Need | 998483 | 339606.7289 | 406785.7608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 755210 | 348096.8971 | 427379.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 746392.4897 | 746392.4897 | 775476.1871 | 775476.1871 | 370 | 5550 | 1.951% | TS | TS036s | Repex | Std | Std | Substations
TS047 | Equipment labelling in TS & ZS | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS047s | Repex | Std | Unallocated | Unallocated
TS048 | Substation oil containment program - separators | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000 | 97.4% | TS | TS048s | Repex | Std | Std | Substations
TS049 | Tunnelboard refurbishment | Program - Short Term Need | 0 | 0 | 0 | 0 | 44602.9697 | 44485.9285 | 0 | 0 | 0 | 44485.9285 | 45000 | 0 | 0 | 0 | 0 | 49233.3329 | 50331.7449 | 0 | 0 | 0 | 55556.8288 | 57603.8045 | 89088.8982 | 178574.8267 | 99565.0778 | 212725.7111 | 150 | 2250 | 70.87% | TS | TS049s | Repex | Std | Std | Substations
TS050 | POW switching for capacitors | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2250 | 70.87% | TS | TS050s | Repex | Std | Std | Substations
TS055 | 66kV circuit breaker replacement | Program - Short Term Need | 258000 | 257701.5766 | 257232.1723 | 0 | 0 | 0 | 255052.6568 | 255052.6568 | 255052.6568 | 255052.6568 | 258000 | 0 | 264144.116 | 270254.551 | 0 | 0 | 0 | 295782.8874 | 303177.4596 | 310756.8961 | 318525.8185 | 330261.8124 | 514933.7489 | 1793144.3762 | 534398.667 | 2092903.5411 | 240 | 3600 | 42.68% | TS | TS055s | Repex | Std | Std | Substations
TS057 | Substation insulation co-ordination | Program - Short Term Need | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2400 | 69.76% | TS | TS057s | Repex | Std | Std | Substations
TS060 | Lawson TS rebuild | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS060 | Repex | Std | Unallocated | Unallocated
TS067 | Rosehill ZS renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS067 | Repex | Std | Std | Substations
TS072 | Holroyd ZS renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS072 | Repex | Std | Std | Substations
TS086 | Busbar support and isolator replacement | Program - Short Term Need | 325000 | 0 | 94218.7608 | 93956.7092 | 93666.2364 | 93420.4499 | 93420.4499 | 93420.4499 | 93420.4499 | 93420.4499 | 94500 | 197917 | 0 | 98988.5855 | 101181.0993 | 103389.9991 | 105696.6643 | 108339.0809 | 111047.5579 | 113823.7468 | 116669.3405 | 120967.9894 | 375262.1562 | 843443.9558 | 409256.3482 | 980104.0637 | 200 | 3000 | 58.53% | TS | TS086s | Repex | Std | Std | Substations
TS092 | Jasper Rd 11kV CB renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS092 | Repex | Std | Std | Substations
TS099 | Substation power outlet installation | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 750 | 99.19% | TS | TS099s | Repex | Std | Std | Substations
TS100 | Substation internal fence replacement | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1350 | 92.19% | TS | TS100s | Repex | Std | Std | Substations
TS102 | Rydalmere Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.3% | TS | TS102 | Repex | Std | Std | Substations
TS111 | Blackheath ZS 11kV switchyard renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS111 | Repex | Std | Std | Substations
TS116 | Roof refurbishment for control and switch rooms | Program - Short Term Need | 500000 | 998843.3202 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 988576.1893 | 1000000 | 556587.42 | 1023814.4032 | 1047498.2598 | 1070699.4635 | 1094074.0646 | 1118483.2196 | 1146445.3001 | 1175106.4326 | 1204484.0934 | 1234596.1957 | 1280084.5442 | 4969871.4284 | 9924176.1854 | 5354569.4106 | 11395285.9766 | 280 | 4200 | 36.29% | TS | TS116s | Repex | Std | Std | Substations
TS116 | Roof refurbishment for control and switch rooms | Program - Medium Term Need |  | 499421.6601 | 498511.9618 | 497125.4455 | 495588.5521 | 494288.0946 | 494288.0946 | 494288.0946 | 494288.0946 | 494288.0946 | 500000 | 0 | 511907.2016 | 523749.1299 | 535349.7317 | 547037.0323 | 559241.6098 | 573222.65 | 587553.2163 | 602242.0467 | 617298.0979 | 640042.2721 | 2484935.7142 | 4962088.0927 | 2677284.7053 | 5697642.9883 | 280 | 2800 | 66.41% | TS | TS116m | Repex | Std | Std | Substations
TS118 | Smithfield Zone Substation rebuilding | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS118 | Repex | Std | Unallocated | Unallocated
TS119 | Bomaderry ZS redevelopment (fmr PR403) | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS119 | Repex | Std | Std | Substations
TS120 | Canley Vale ZS redevelopment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS120 | Repex | Std | Std | Substations
TS121 | Port Kembla ZS | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4200 | 36.29% | TS | TS121 | Repex | Std | Std | Substations
TS122 | Leabons Lane Zone Substation renewal | Major Project - Committed Project | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.3% | TS | TS122 | Repex | Std | Std | Substations
TS123 | St Marys Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.3% | TS | TS123 | Repex | Std | Std | Substations
TS124 | Substation control building fire alarm systems | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.53% | TS | TS124s | Repex | Std | Std | Substations
TS125 | Guildford Transmission Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6300 | 0% | TS | TS125 | Repex | Std | Std | Substations
TS126 | Comalco HVC renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS126 | Repex | Std | Std | Substations
TS127 | Castle Hill Zone Substation renewal | Major Project - Committed Project | 163333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.3% | TS | TS127 | Repex | Std | Std | Substations
TS128 | Capacitor bank refurbishment | Program - Short Term Need | 1270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1372467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4200 | 36.29% | TS | TS128s | Repex | Std | Std | Substations
TS130 | Northmead Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4500 | 25.55% | TS | TS130 | Repex | Std | Std | Substations
TS131 | Bulli Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4125 | 36.29% | TS | TS131 | Repex | Std | Std | Substations
TS133 | Corrimal ZS redevelopment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4575 | 21% | TS | TS133 | Repex | Std | Std | Substations
TS134 | South Granville Zone Substation renewal | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.3% | TS | TS134 | Repex | Std | Std | Substations
TS135 | Ringwood ZS redevelopment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS135 | Repex | Std | Std | Substations
TS136 | Kandos ZS redevelopment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS136 | Repex | Std | Std | Substations
TS137 | Power transformer oil temperature indicator | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS137s | Repex | Std | Unallocated | Unallocated
TS138 | Baulkham Hills switchgear rearrangement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS138 | Repex | Std | Std | Substations
TS139 | Oakdale ZS swgr rearrangement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS139 | Repex | Std | Std | Substations
TS143 | Westmead Zone Substation renewal and augmentation | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5700 | 1.673% | TS | TS143 | Repex | Std | Std | Substations
TS144 | Substation fire stopping measures | Program - Short Term Need | 198000 | 65923.6591 | 65803.579 | 65620.5588 | 65417.6889 | 65246.0285 | 65246.0285 | 65246.0285 | 65246.0285 | 65246.0285 | 66000 | 186676 | 67571.7506 | 69134.8851 | 70666.1646 | 72208.8883 | 73819.8925 | 75665.3898 | 77557.0246 | 79495.9502 | 81483.3489 | 84485.5799 | 328011.5143 | 654995.6282 | 353401.5811 | 752088.8745 | 160 | 2400 | 69.76% | TS | TS144s | Repex | Std | Std | Substations
TS146 | Marayong Zone Substation renewal | Major Project - Committed Project | 13051000 | 8195387.583 | 1823633.5272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2558031 | 8400272.2725 | 1915954.9745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10019021.1101 | 10019021.1101 | 10316227.247 | 10316227.247 | 230 | 3450 | 51.3% | TS | TS146 | Repex | Std | Std | Substations
TS149 | South Windsor ZS refurbishment | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS149 | Repex | Std | Std | Substations
TS155 | Sussex Inlet Zone Substation - stage 2 renewal | Major Project - Committed Project | 2400000 | 1676614.4481 | 37233.8584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3841000.34 | 1718529.8093 | 39118.8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1713848.3065 | 1713848.3065 | 1757648.6318 | 1757648.6318 | 210 | 3150 | 54.88% | TS | TS155 | Repex | Std | Std | Substations
TS156 | Lawson TS - RailCorp connections works | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3975 | 37.22% | TS | TS156 | Repex | Std | Std | Substations
TS167 | Carlingford Transmission Substation control building replacement | Major Project - Prior to Approval | 0 | 0 | 4486607.6563 | 4474129.0097 | 4460296.9693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4713742.1689 | 4818147.5856 | 4923333.2907 | 0 | 0 | 0 | 0 | 0 | 0 | 13421033.6354 | 13421033.6354 | 14455223.0453 | 14455223.0453 | 180 | 1800 | 82.37% | TS | TS167 | Repex | Std | Std | Substations
TS168 | Carramar Zone Substation switchgear replacement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3750 | 38.64% | TS | TS168 | Repex | Std | Std | Substations
TS173 | 11kV switchboard truck replacement program | Program - Short Term Need | 2894255 | 3643780.4319 | 3637143.2734 | 3627027.2506 | 2902166.5613 | 2894551.0821 | 2894551.0821 | 2894551.0821 | 2894551.0821 | 0 | 0 | 1841138 | 3734874.9427 | 3821273.6516 | 3905911.6428 | 3203448.8612 | 3274918.867 | 3356791.8386 | 3440711.6346 | 3526729.4255 | 0 | 0 | 16704668.5994 | 25388321.8458 | 17940427.9652 | 28264660.8639 | 290 | 4350 | 29.29% | TS | TS173s | Repex | Std | Std | Substations
TS175 | Defective CT replacement program | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2100 | 78.3% | TS | TS175s | Repex | Std | Std | Substations
TS177 | Substation battery duplication | Program - Short Term Need | 1582100 | 0 | 915267.9619 | 760601.9317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2245214.8 | 0 | 961603.4025 | 819085.0896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1675869.8935 | 1675869.8935 | 1780688.492 | 1780688.492 | 330 | 4950 | 12.56% | TS | TS177s | Repex | Std | Std | Substations
TS178 | Jerrara SS steel support structures | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.53% | TS | TS178 | Repex | Std | Std | Substations
TS179 | 33kV wall bushing replacement | Program - Short Term Need | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237836.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3150 | 54.88% | TS | TS179s | Repex | Std | Std | Substations
TS180 | Transformer fire wall installation | Program - Short Term Need | 200000 | 0 | 598214.3542 | 596550.5346 | 594706.2626 | 593145.7136 | 593145.7136 | 593145.7136 | 593145.7136 | 593145.7136 | 600000 | 0 | 0 | 628498.9559 | 642419.6781 | 656444.4388 | 671089.9318 | 687867.18 | 705063.8596 | 722690.456 | 740757.7174 | 768050.7265 | 2382616.8649 | 5355199.7192 | 2598453.0045 | 6222882.9441 | 140 | 2100 | 78.3% | TS | TS180s | Repex | Std | Std | Substations
TS181 | 11kV capacitor bank refurbishment | Program - Short Term Need | 887526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4050 | 37.22% | TS | TS181s | Repex | Std | Std | Substations
TS182 | Substation civil capital works scoping | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.3% | TS | TS182s | Repex | Std | Std | Substations
TS183 | Carlingford TS/Dundas ZS Redevelopment | Major Project - Committed Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS183 | Repex | Std | Std | Substations
TS184 | Blaxland Zone Substation reinstatement | Major Project - Committed Project | 691500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 946244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4500 | 25.55% | TS | TS184 | Repex | Std | Std | Substations
TS185 | Penrith TS civil development | Major Project - Committed Project | 2101666.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2086556.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3450 | 51.3% | TS | TS185 | Repex | Std | Std | Substations
TS187 | Mobile substation No 2 refurbishment | Program - Short Term Need | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2850 | 66.13% | TS | TS187s | Repex | Std | Std | Substations
TS188 | Bossley Park ZS civil refurbishment | Major Project - Committed Project | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3000 | 58.53% | TS | TS188 | Repex | Std | Std | Substations
TS199 | Future sub-transmission substation renewal programs | Program - Short Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460016.6624 | 7414321.4194 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4215694.3269 | 9259471.468 | 15361014.5304 | 0 | 22874338.0818 | 0 | 28836180.3253 | 180 | 2700 | 66.49% | TS | TS199s | Repex | Std | Std | Substations
TS199 | Future sub-transmission substation renewal programs | Program - Medium Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 889718.5703 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602242.0467 | 1111136.5762 | 1920126.8163 | 0 | 2884006.665 | 0 | 3633505.4392 | 180 | 1800 | 82.37% | TS | TS199m | Repex | Std | Std | Substations
TS199 | Future sub-transmission substation renewal programs | Program - Long Term Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494288.0946 | 889718.5703 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602242.0467 | 1111136.5762 | 1920126.8163 | 0 | 2884006.665 | 0 | 3633505.4392 | 180 | 900 | 97.4% | TS | TS199l | Repex | Std | Std | Substations
TS600 | Power transformer replacement | Program - Short Term Need | 0 | 1698033.6443 | 11565477.5141 | 7456881.6829 | 10902948.1471 | 10973195.7007 | 12554917.6036 | 12554917.6036 | 12554917.6036 | 12554917.6036 | 12700000 | 0 | 1740484.4854 | 12150979.8132 | 8030245.9761 | 12034814.7106 | 12415163.7375 | 14559855.3111 | 14923851.6938 | 15296947.9862 | 15679371.6858 | 16257073.7113 | 42596536.6891 | 105516207.1034 | 46371688.7228 | 123088789.1109 | 340 | 5100 | 9.284% | TS | TS600s | Repex | Std | Std | Transformers
TS601 | Cranebrook ZS 33kV No 3 - transformer replacement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS601 | Repex | Std | Std | Transformers
TS602 | Prospect ZS 33kV No3 transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS602 | Repex | Std | Std | Transformers
TS603 | Kingwood ZS 33kV No 3 - transformer replacement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS603 | Repex | Std | Unallocated | Unallocated
TS604 | Liverpool TS 132kV No 3 - transformer replacement | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS604 | Repex | Std | Std | Transformers
TS605 | West Liverpool 132 kV No 3 transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4950 | 12.56% | TS | TS605 | Repex | Std | Std | Substations
TS615 | Gerringong ZS 33kV No 2 transformer replacement | Major Project - Committed Project | 6894.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15251.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5100 | 9.284% | TS | TS615 | Repex | Std | Std | Transformers
TS616 | Camellia TS transformer replacement and 33kV busbar rearrangement | Major Project - Committed Project | 2608611 | 332257.2397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2660563 | 340563.6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332257.2397 | 332257.2397 | 340563.6707 | 340563.6707 | 340 | 5100 | 9.284% | TS | TS616 | Repex | Std | Std | Transformers
TS617 | Prospect ZS transformer replacement | Major Project - Committed Project | 2449406 | 29234.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2449406 | 29965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29234.1463 | 29234.1463 | 29965 | 29965 | 340 | 5100 | 9.284% | TS | TS617 | Repex | Std | Std | Transformers
TS618 | Albion Park ZS transformer replacement | Major Project - Committed Project | 2457614 | 1575436.614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248155.45 | 1614822.5293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1575436.614 | 1575436.614 | 1614822.5293 | 1614822.5293 | 340 | 5100 | 9.284% | TS | TS618 | Repex | Std | Std | Transformers
TS619 | Dundas ZS 66kV No 2 transformer | Major Project - Committed Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5100 | 9.284% | TS | TS619 | Repex | Std | Std | Transformers
TS620 | Minto 66/11kV No 1 transformer replacement | Major Project - Committed Project |  | 1079313.1346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662423 | 1106295.9629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079313.1346 | 1079313.1346 | 1106295.9629 | 1106295.9629 | 340 | 4950 | 12.56% | TS | TS620 | Repex | Std | Std | Transformers
TS700 | 11kV zone substation switchboard replacement | Program - Short Term Need | 0 | 0 | 3988095.6945 | 3977003.5642 | 3964708.4171 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 4000000 | 0 | 0 | 4189993.0391 | 4282797.8539 | 4376296.2584 | 4473932.8784 | 4585781.2003 | 4700425.7303 | 4817936.3736 | 4938384.7829 | 5120338.1768 | 15884112.4329 | 35701331.461 | 17323020.0297 | 41485886.2937 | 290 | 4350 | 29.29% | TS | TS700s | Repex | Std | Std | Substations
TS700 | 11kV zone substation switchboard replacement | Program - Medium Term Need | 0 | 0 | 0 | 0 | 3964708.4171 | 7908609.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4376296.2584 | 8947865.7567 | 0 | 0 | 0 | 0 | 0 | 11873317.9312 | 11873317.9312 | 13324162.0152 | 13324162.0152 | 290 | 2900 | 59.76% | TS | TS700m | Repex | Std | Std | Substations
TS701 | North Rocks ZS 11kV switchboard replacement | Major Project - Committed Project | 2100000 | 776646.6282 | 36061.3583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1453893 | 796062.7939 | 37886.9646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812707.9865 | 812707.9865 | 833949.7585 | 833949.7585 | 290 | 4350 | 29.29% | TS | TS701 | Repex | Std | Std | Substations
TS702 | Kellyville ZS 11kV switchboard replacement | Major Project - Committed Project | 1890000 | 952068.4863 | 264576.2505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573638 | 975870.1985 | 277970.4232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1216644.7368 | 1216644.7368 | 1253840.6217 | 1253840.6217 | 290 | 4350 | 29.29% | TS | TS702 | Repex | Std | Std | Substations
TS703 | Horsley Park ZS 11kV switchboard replacement | Major Project - Committed Project | 2610000 | 423899.1166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1941242 | 434496.5946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423899.1166 | 423899.1166 | 434496.5946 | 434496.5946 | 290 | 4350 | 29.29% | TS | TS703 | Repex | Std | Std | Substations
TS704 | Port Central ZS 11kV switchboard replacement | Major Project - Committed Project | 1740000 | 488086.7861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1583396.03 | 500288.9557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488086.7861 | 488086.7861 | 500288.9557 | 500288.9557 | 290 | 4350 | 29.29% | TS | TS704 | Repex | Std | Std | Substations
UR | Underground residential | Program - Short Term Need | 33939845.5741 | 21633998.4122 | 14557232.2464 | 11691183.4582 | 10959043.8153 | 10680249.93 | 10680249.93 | 10680249.93 | 10680249.93 | 10680249.93 | 10803669 | 27120000.008 | 22174848.3725 | 15294192.1288 | 12590125.8613 | 12096733.8323 | 12083722.4865 | 12385815.5487 | 12695460.9374 | 13012847.4609 | 13338168.6474 | 13829609.7075 | 69521707.8621 | 123046376.5821 | 74239622.6815 | 139501524.9833 | 190 | 2850 | 66.13% | UR | URs | Connections | Std | Std | Distribution lines and cables
SW | Network Switching | Overheads | 3277485.76 | 6283900.8865 | 6382175.5445 | 6686467.7532 | 6495126.3573 | 6714861.5396 | 7423719.2767 | 7683873.5145 | 7944102.7058 | 8085985.7683 | 8183178.6979 | 3277485.76 | 6440998.4086 | 6705273.1814 | 7200594.4377 | 7169404.1994 | 7597249.4943 | 8609238.3838 | 9133710.9797 | 9679117.7549 | 10098288.2016 | 10475160.5735 | [9 empty] | Overheads |  | Std | Overheads
OH | Capitalised Overheads | Overheads | 66922514.26 | 73106139.0812 | 73273110.1037 | 73775204.5564 | 73462071.757 | 73820942.4206 | 76860996.0999 | 77233408.4879 | 77593252.7624 | 77784338.9426 | 78058962.8601 | 66922514.26 | 74933792.5582 | 76982561.3027 | 79447826.1443 | 81088381.7774 | 83521620.538 | 89135191.2943 | 91806252.3768 | 94539843.993 | 97141980.5473 | 99922071.8932 | [9 empty] | Overheads |  | Std | Overheads
|  | Total - Exc SWOH | 278268576.2497 | 230351654.3369 | 225718973.9278 | 231553556.7543 | 250997377.8779 | 247923828.3036 | 249505428.6115 | 258539888.0045 | 285854344.0055 | 306159935.2026 | 321694374 | 246955911.5435 | 236110445.6954 | 237145996.9829 | 249357854.4541 | 277054141.2147 | 280503055.514 | 289349803.3692 | 307322681.6259 | 348285761.0021 | 382351805.9561 | 411795996.1123
|  | Total - Inc SWOH | 348468576.2697 | 309741694.3046 | 305374259.576 | 312015229.0639 | 330954575.9922 | 328459632.2638 | 333790143.9881 | 343457170.0069 | 371391699.4738 | 392030259.9135 | 407936515.558 | 317155911.5635 | 317485236.6622 | 320833831.4671 | 336006275.0361 | 365311927.1915 | 371621925.5463 | 387094233.0473 | 408262644.9824 | 452504722.75 | 489592074.7049 | 522193228.5791
|  |  | FY19 (R) | FY20 (R) | FY21 (R) | FY22 (R) | FY23 (R) | FY24 (R) | FY25 (R) | FY26 (R) | FY27 (R) | FY28 (R) | FY28 (R) | FY19 (N) | FY20 (N) | FY21 (N) | FY22 (N) | FY23 (N) | FY24 (N) | FY25 (N) | FY26 (N) | FY27 (N) | FY28 (N) | FY28 (N)
|  | Augex | 57522026 | 64734004.7727 | 64322990.4567 | 69729209.1459 | 77619066.1512 | 71248264.7159 | 79328149.009 | 75272320.4431 | 84083001.7755 | 83658457.7311 | 76412400 | 57478433.0865 | 66352354.892 | 67579341.8486 | 75090731.6178 | 85676925.776 | 80610871.8538 | 91996332.2848 | 89475134.9563 | 102446972.9947 | 104477949.9833 | 97814332.2249
|  | Repex | 146012101.7474 | 109161460.9207 | 119941187.3726 | 118105323.4094 | 123049433.8172 | 126358572.7905 | 135549365.622 | 148526405.2584 | 167114603.345 | 188116904.4858 | 210402750 | 123680707.799 | 111890497.4437 | 126013209.9833 | 127186515.5422 | 135823551.2315 | 142963127.0243 | 157195707.1548 | 176551221.9742 | 203612916.9318 | 234932236.0334 | 269333308.3314
|  | Connections | 48419634.5023 | 33916939.5292 | 24374001.5841 | 20689244.4991 | 19687642.7841 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19760628 | 40340000.008 | 34764863.0174 | 25607935.4143 | 22280053.4394 | 21731473.8911 | 21897574.9945 | 22445014.3694 | 23006139.7286 | 23581293.2218 | 24170825.5524 | 25295274.4864
|  | Reliability | 4000000 | 3995373.2806 | 3988095.6945 | 3977003.5642 | 3964708.4171 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 4000000 | 4045216.63 | 4095257.6126 | 4189993.0391 | 4282797.8539 | 4376296.2584 | 4473932.8784 | 4585781.2003 | 4700425.7303 | 4817936.3736 | 4938384.7829 | 5120338.1768
|  | Other | 17809814 | 13619578.2654 | 8217251.8333 | 6386019.7837 | 6297925.4441 | 6643750.9943 | 6529692.0393 | 6608340.1952 | 6558516.9438 | 6251750.878 | 6273596 | 18306554.02 | 13960067.7221 | 8633250.2073 | 6877044.8361 | 6951731.2894 | 7516794.4394 | 7572440.881 | 7855239.8454 | 7990916.0477 | 7807580.1688 | 8030733.2761
|  | Overheads | 70200000.02 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 86242141.558 | 70200000.02 | 81374790.9669 | 83687834.4841 | 86648420.582 | 88257785.9769 | 91118870.0324 | 97744429.6781 | 100939963.3565 | 104218961.7479 | 107240268.7488 | 110397232.4667
|  | Contingent | 0 | 0 | 0 | 7814812.0037 | 15581304.0794 | 15540417.6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8415697.7829 | 17198844.2955 | 17582556.212 | 0 | 0 | 0 | 0 | 0
|  | Alternate Control | 4505000 | 4924297.5683 | 4875446.9865 | 4851944.3483 | 4797297.1847 | 4824251.8036 | 4789651.6369 | 4824251.8036 | 4789651.6369 | 4824251.8036 | 4845000 | 3105000 | 5047405.0076 | 5122266.4902 | 5225013.3818 | 5295318.4727 | 5458198.1116 | 5554527.4789 | 5734519.391 | 5835725.4325 | 6024829.4352 | 6202009.6166

## RIN Cat Summary (excl. Esc)
RIN / Submission Categories
RIN Categories:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 48419634.5023 | 33916939.5292 | 24374001.5841 | 20689244.4991 | 19687642.7841 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 118022093.9437
| Augex | 57522026 | 64734004.7727 | 64322990.4567 | 77544021.1495 | 93200370.2306 | 86788682.411 | 79328149.009 | 75272320.4431 | 84083001.7755 | 83658457.7311 | 386590069.0206
| Repex | 150012101.7474 | 113156834.2013 | 123929283.0671 | 122082326.9736 | 127014142.2343 | 130312877.5476 | 129420193.2487 | 142693805.7418 | 161282003.8284 | 181987732.1124 | 616495464.0239
| Other | 17809814 | 13619578.2654 | 8217251.8333 | 6386019.7837 | 6297925.4441 | 6643750.9943 | 6529692.0393 | 6608340.1952 | 6558516.9438 | 6251750.878 | 41164526.3209
| Overheads | 70200000.02 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Total System | 343963576.2697 | 304817396.7363 | 300498812.5895 | 307163284.7155 | 326157278.8075 | 323635380.4602 | 318917015.2207 | 328846013.9297 | 356815143.5632 | 377122530.9795 | 1562272153.309
| Non System | 53120118.5878 | 49686736.0244 | 35108941.55 | 31713950.6162 | 30022401.5922 | 23558369.2171 |  |  |  |  | 170090399
| Total Capex | 397083694.8576 | 354504132.7607 | 335607754.1395 | 338877235.3317 | 356179680.3997 | 347193749.6774 |  |  |  |  | 1732362552.309
Submission Categories:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 48419634.5023 | 33916939.5292 | 24374001.5841 | 20689244.4991 | 19687642.7841 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 118022093.9437
| Augex | 57522026 | 64734004.7727 | 64322990.4567 | 77544021.1495 | 93200370.2306 | 86788682.411 | 79328149.009 | 75272320.4431 | 84083001.7755 | 83658457.7311 | 386590069.0206
| Repex | 146012101.7474 | 109161460.9207 | 119941187.3726 | 118105323.4094 | 123049433.8172 | 126358572.7905 | 125465888.4916 | 138739500.9848 | 157327699.0714 | 178033427.3553 | 596615978.3104
| Reliability | 4000000 | 3995373.2806 | 3988095.6945 | 3977003.5642 | 3964708.4171 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 19879485.7135
| Other | 17809814 | 13619578.2654 | 8217251.8333 | 6386019.7837 | 6297925.4441 | 6643750.9943 | 6529692.0393 | 6608340.1952 | 6558516.9438 | 6251750.878 | 41164526.3209
| Overheads | 70200000.02 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Total System | 343963576.2697 | 304817396.7363 | 300498812.5895 | 307163284.7155 | 326157278.8075 | 323635380.4602 | 318917015.2207 | 328846013.9297 | 356815143.5632 | 377122530.9795 | 1562272153.309
| Non System | 53120118.5878 | 49686736.0244 | 35108941.55 | 31713950.6162 | 30022401.5922 | 23558369.2171 |  |  |  |  | 170090399
| Total Capex | 397083694.8576 | 354504132.7607 | 335607754.1395 | 338877235.3317 | 356179680.3997 | 347193749.6774 |  |  |  |  | 1732362552.309
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Calculation
Pivot RIN Categories:
| Row Labels | Sum of FY19 (R) | Sum of FY20 (R) | Sum of FY21 (R) | Sum of FY22 (R) | Sum of FY23 (R) | Sum of FY24 (R) | Sum of FY25 (R) | Sum of FY26 (R) | Sum of FY27 (R) | Sum of FY28 (R) | RCP
| Augex | 57522026 | 64734004.7727 | 64322990.4567 | 77544021.1495 | 93200370.2306 | 86788682.411 | 79328149.009 | 75272320.4431 | 84083001.7755 | 83658457.7311 | 386590069.0206
| Connections | 48419634.5023 | 33916939.5292 | 24374001.5841 | 20689244.4991 | 19687642.7841 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 118022093.9437
| Other | 22314814 | 18543875.8338 | 13092698.8198 | 11237964.132 | 11095222.6289 | 11468002.7979 | 11319343.6763 | 11432591.9988 | 11348168.5808 | 11076002.6815 | 65437764.2124
| Overheads | 70200000.02 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Reliability | 4000000 | 3995373.2806 | 3988095.6945 | 3977003.5642 | 3964708.4171 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 19879485.7135
| Repex | 146012101.7474 | 109161460.9207 | 119941187.3726 | 118105323.4094 | 123049433.8172 | 126358572.7905 | 135549365.622 | 148526405.2584 | 167114603.345 | 188116904.4858 | 596615978.3104
| Grand Total | 348468576.2697 | 309741694.3046 | 305374259.576 | 312015229.0639 | 330954575.9922 | 328459632.2638 | 333790143.9881 | 343457170.0069 | 371391699.4738 | 392030259.9135 | 1586545391.2006
Adjustments
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP | Comment | RIN Category
[12 empty] | 0 | Contingent |  | PR741 (Western Sydney Airport 132kV supply) removed from exclusion list
TM028 | 132kV oil cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 10083477.1304 | 9786904.2736 | 9786904.2736 | 10083477.1304 | 0 | Remove | Std
MC101 | Meters - Growth | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Alt | Alt
MC104 | Meters - renewal | 25000 | 59930.5992 | 59821.4354 | 9942.5089 | 9911.771 | 9885.7619 | 9885.7619 | 9885.7619 | 9885.7619 | 9885.7619 | 149492.0765 | Alt | Alt
MC106 | Labour (meter/relay renewal) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Alt | Alt
MC107 | Test equipment | 80000 | 119861.1984 | 79761.9139 | 119310.1069 | 79294.1683 | 118629.1427 | 84028.9761 | 118629.1427 | 84028.9761 | 118629.1427 | 516856.5303 | Alt | Alt
MC110 | Labour meter renewal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Alt | Alt
SL001 | Streetlighting growth | 1400000 | 1747975.8103 | 1744791.8664 | 1739939.0593 | 1734559.9325 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 1730008.3312 | 8697274.9997 | Alt | Alt
SL002 | Streetlighting refurbishment | 3000000 | 2996529.9605 | 2991071.7709 | 2982752.6732 | 2973531.3129 | 2965728.5678 | 2965728.5678 | 2965728.5678 | 2965728.5678 | 2965728.5678 | 14909614.2851 | Alt | Alt

## RAB Cat Summary (excl. Esc)
RAB Category
RAB Categories:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | 18443731.342 | 23194209.6669 | 28827749.9119 | 31482068.7378 | 32994561.8453 | 34488730.1983 | 150987320.3602
| Distribution lines and cables | 130889621.0935 | 112358925.1914 | 105000856.7249 | 105847422.6011 | 102653745.8444 | 105995808.8018 | 531856759.1637
| Substations | 144454423.5593 | 117567128.2826 | 122865644.5516 | 132188620.5425 | 150090645.6598 | 142311613.2157 | 665023652.2522
| Transformers | 11192145.4748 | 7319956.0321 | 16686635.396 | 11046495.8919 | 15428653.022 | 15661339.2964 | 66143079.6385
| Low Voltage lines and cables | 13867673.6061 | 14897246.8085 | 16862998.2091 | 16744871.2117 | 16518506.81 | 17016900.5968 | 82040523.6362
| Customer metering and Load control | 704854.7836 | 1645833.781 | 1230720.7587 | 1154205.2475 | 1058846.7911 | 994938.5639 | 6084545.1422
| Communication | 17803551.307 | 14533075.9793 | 7667570.0131 | 2637499.0789 | 2160011.4231 | 1901734.0574 | 28899890.5518
| Land | 5050831.0694 | 11950409.3164 | 0 | 4714967.7587 | 3939230.5588 | 3948236.7974 | 24552844.4313
| Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1556744.034 | 1350611.678 | 1356637.0241 | 1347133.6454 | 1313076.8529 | 1316078.9325 | 6683538.1328
| Total System | 343963576.2697 | 304817396.7363 | 300498812.5895 | 307163284.7155 | 326157278.8075 | 323635380.4602 | 1562272153.309
| Information & Communication Technology | 41064345.6181 | 30637169 | 16816254 | 16519250 | 14143911 | 13073815 | 91190399
| Furniture, fittings, plant and equipment | 3584421.6116 | 4776208.7856 | 4672381.6498 | 2888212.8897 | 3190649.8926 | 3172546.7823 | 18700000
| Motor Vehicles | 4745572.2745 | 6873358.2388 | 4120305.9002 | 4406487.7265 | 5087840.6997 | 1612007.4348 | 22100000
| Buildings | 3725779.0836 | 7400000 | 9500000 | 7900000 | 7600000 | 5700000 | 38100000
| Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Capex | 397083694.8576 | 354504132.7607 | 335607754.1395 | 338877235.3317 | 356179680.3997 | 347193749.6774 | 1732362552.309
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live PTRM (Net Capex + Disposals):
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | [6 empty] | 0
| Distribution lines and cables | [6 empty] | 0
| Substations | [6 empty] | 0
| Transformers | [6 empty] | 0
| Low Voltage lines and cables | [6 empty] | 0
| Customer metering and Load control | [6 empty] | 0
| Communication | [6 empty] | 0
| Land | [6 empty] | 0
| Easements | [6 empty] | 0
| Emergency Spares (Major Plant, Excludes Inventory) | [6 empty] | 0
| Total System | [6 empty] | 0
| Information & Communication Technology | [6 empty] | 0
| Furniture, fittings, plant and equipment | [6 empty] | 0
| Motor Vehicles | [6 empty] | 0
| Buildings | [6 empty] | 0
| Land (non-system) | [6 empty] | 0
| Other non system assets | [6 empty] | 0
| Total Capex | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variance:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | [6 empty] | 0
| Distribution lines and cables | [6 empty] | 0
| Substations | [6 empty] | 0
| Transformers | [6 empty] | 0
| Low Voltage lines and cables | [6 empty] | 0
| Customer metering and Load control | [6 empty] | 0
| Communication | [6 empty] | 0
| Land | [6 empty] | 0
| Easements | [6 empty] | 0
| Emergency Spares (Major Plant, Excludes Inventory) | [6 empty] | 0
| Total System | [6 empty] | 0
| Information & Communication Technology | [6 empty] | 0
| Furniture, fittings, plant and equipment | [6 empty] | 0
| Motor Vehicles | [6 empty] | 0
| Buildings | [6 empty] | 0
| Land (non-system) | [6 empty] | 0
| Other non system assets | [6 empty] | 0
| Total Capex | 397083694.8576 | 354504132.7607 | 335607754.1395 | 338877235.3317 | 356179680.3997 | 347193749.6774 | 1732362552.309
Calculation
Pivot RAB Categories:
| Row Labels | Sum of FY19 (R) | Sum of FY20 (R) | Sum of FY21 (R) | Sum of FY22 (R) | Sum of FY23 (R) | Sum of FY24 (R) | RCP | Comment
| Communications | 14170000 | 10747919.7015 | 5635074.5288 | 1946604.0496 | 1630486.3365 | 1428492.5935 | 21388577.2099
| Customer metering & load control | 561000 | 1217174.4884 | 904485.1482 | 851860.2439 | 799271.3404 | 747350.7476 | 4520141.9685
| Distribution lines and cables | 104176178.051 | 83094914.4847 | 77167557.9386 | 78120604.1435 | 77488261.5 | 79619033.5984 | 395490371.6653
| Emergency Spares (Major Plant, Excludes Inventory) | 1239026 | 998843.3202 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 4969871.4284
| Land | 4020000 | 8837911.5278 | 0 | 3479878.1187 | 2973531.3129 | 2965728.5678 | 18257049.5271
| Low Voltage lines and cables | 11037401 | 11017241.8213 | 12393007.3707 | 12358538.5758 | 12469007.9719 | 12782290.1271 | 61020085.8668
| Metering & Load control | 105000 | 179791.7976 | 139583.3493 | 129252.6158 | 89205.9394 | 128514.9046 | 666348.6068 | Alt
| Overheads | 70200000.02 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 400000000
| Public lighting | 4400000 | 4744505.7707 | 4735863.6372 | 4722691.7325 | 4708091.2454 | 4695736.899 | 23606889.2848 | Alt
| Substations | 114972521.2988 | 86946635.1179 | 90296803.6674 | 97561703.8555 | 113296042.9638 | 106897746.6388 | 494998932.2434
| Sub-transmission lines and cables | 14679524.81 | 17153251.2039 | 21186180.1032 | 23235315.2212 | 24905971.188 | 25906301.3855 | 112387019.1019
| Transformers | 8907925.09 | 5413465.1029 | 12263394.2606 | 8152857.3067 | 11646330.9753 | 11764056.6522 | 49240104.2977
| Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Check Zero
| Grand Total | 348468576.2697 | 309741694.3046 | 305374259.576 | 312015229.0639 | 330954575.9922 | 328459632.2638 | 1586545391.2006
| Check: | 0 | 0 | 0 | 0 | 0 | 0
Adjustments
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP | Comment | RAB Category
0
[8 empty] | 0 | Contingent |  | PR741 (Western Sydney Airport 132kV supply) removed from exclusion list
TM028 | 132kV oil cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Remove | Std
| Total (Remove Alt & Adjustments) | 343963576.2697 | 304817396.7363 | 300498812.5895 | 307163284.7155 | 326157278.8075 | 323635380.4602 | 1562272153.309
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0
RAB Categories (PTRM Order / Overheads Not Allocated):
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | 14679524.81 | 17153251.2039 | 21186180.1032 | 23235315.2212 | 24905971.188 | 25906301.3855 | 112387019.1019
| Distribution lines and cables | 104176178.051 | 83094914.4847 | 77167557.9386 | 78120604.1435 | 77488261.5 | 79619033.5984 | 395490371.6653
| Substations | 114972521.2988 | 86946635.1179 | 90296803.6674 | 97561703.8555 | 113296042.9638 | 106897746.6388 | 494998932.2434
| Transformers | 8907925.09 | 5413465.1029 | 12263394.2606 | 8152857.3067 | 11646330.9753 | 11764056.6522 | 49240104.2977
| Low Voltage lines and cables | 11037401 | 11017241.8213 | 12393007.3707 | 12358538.5758 | 12469007.9719 | 12782290.1271 | 61020085.8668
| Customer metering and Load control | 561000 | 1217174.4884 | 904485.1482 | 851860.2439 | 799271.3404 | 747350.7476 | 4520141.9685
| Communication | 14170000 | 10747919.7015 | 5635074.5288 | 1946604.0496 | 1630486.3365 | 1428492.5935 | 21388577.2099
| Land | 4020000 | 8837911.5278 | 0 | 3479878.1187 | 2973531.3129 | 2965728.5678 | 18257049.5271
| Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1239026 | 998843.3202 | 997023.9236 | 994250.8911 | 991177.1043 | 988576.1893 | 4969871.4284
| Overheads | 70200000.02 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 400000000
| Total | 343963576.2697 | 304817396.7363 | 300498812.5895 | 307163284.7155 | 326157278.8075 | 323635380.4602 | 1562272153.309
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0

## RAB Cat Summary ($N)(excl. Esc)
RAB Category
RAB Categories:
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | 18443731.342 | 23194209.6669 | 28827749.9119 | 31482068.7378 | 32994561.8453 | 34488730.1983 | 150987320.3602
| Distribution lines and cables | 130889621.0935 | 112358925.1914 | 105000856.7249 | 105847422.6011 | 102653745.8444 | 105995808.8018 | 531856759.1637
| Substations | 144454423.5593 | 117567128.2826 | 122865644.5516 | 132188620.5425 | 150090645.6598 | 142311613.2157 | 665023652.2522
| Transformers | 11192145.4748 | 7319956.0321 | 16686635.396 | 11046495.8919 | 15428653.022 | 15661339.2964 | 66143079.6385
| Low Voltage lines and cables | 13867673.6061 | 14897246.8085 | 16862998.2091 | 16744871.2117 | 16518506.81 | 17016900.5968 | 82040523.6362
| Customer metering and Load control | 704854.7836 | 1645833.781 | 1230720.7587 | 1154205.2475 | 1058846.7911 | 994938.5639 | 6084545.1422
| Communication | 17803551.307 | 14533075.9793 | 7667570.0131 | 2637499.0789 | 2160011.4231 | 1901734.0574 | 28899890.5518
| Land | 5050831.0694 | 11950409.3164 | 0 | 4714967.7587 | 3939230.5588 | 3948236.7974 | 24552844.4313
| Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1556744.034 | 1350611.678 | 1356637.0241 | 1347133.6454 | 1313076.8529 | 1316078.9325 | 6683538.1328
| Total System | 343963576.2697 | 304817396.7363 | 300498812.5895 | 307163284.7155 | 326157278.8075 | 323635380.4602 | 1562272153.309
| Information & Communication Technology | 41064345.6181 | 30637169 | 16816254 | 16519250 | 14143911 | 13073815 | 91190399
| Furniture, fittings, plant and equipment | 3584421.6116 | 4776208.7856 | 4672381.6498 | 2888212.8897 | 3190649.8926 | 3172546.7823 | 18700000
| Motor Vehicles | 4745572.2745 | 6873358.2388 | 4120305.9002 | 4406487.7265 | 5087840.6997 | 1612007.4348 | 22100000
| Buildings | 3725779.0836 | 7400000 | 9500000 | 7900000 | 7600000 | 5700000 | 38100000
| Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Capex | 397083694.8576 | 354504132.7607 | 335607754.1395 | 338877235.3317 | 356179680.3997 | 347193749.6774 | 1732362552.309
| Check: | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPI Index
|  | FY19 | FY20 | FY21 | FY22 | FY23 | FY24
| Dec-Dec sum of 4 quarters (Lagged - Pricing) | 1.949% | 1.964% | 1.932% | 2.456% | 2.5% | 2.5%
| Index (Real 18/19) | 1 | 1.0196 | 1.0393 | 1.0649 | 1.0915 | 1.1188
RAB Categories:
| $Nominal | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | RCP
| Sub-transmission lines and cables | 18266614.0758 | 23420852.3474 | 29676422.8208 | 33119850.4119 | 35571250.4124 | 38111657.4799 | 159900033.4724
| Distribution lines and cables | 129632673.0585 | 113456842.6609 | 108092023.4925 | 111353889.4863 | 110670422.4875 | 117130318.6907 | 560703496.8179
| Substations | 143067211.1714 | 118715937.812 | 126482740.7273 | 139065427.2114 | 161811875.7378 | 157260978.5026 | 703336959.991
| Transformers | 11084666.0189 | 7391483.1279 | 17177880.6525 | 11621164.2431 | 16633543.5138 | 17306511.3012 | 70130582.8386
| Low Voltage lines and cables | 13734500.7469 | 15042815.5516 | 17359435.4887 | 17615984.3344 | 17808508.7152 | 18804469.8424 | 86631213.9323
| Customer metering and Load control | 698085.9823 | 1661916.0785 | 1266952.4927 | 1214250.1009 | 1141536.7336 | 1099453.5764 | 6384108.9821
| Communication | 17632581.763 | 14675086.2199 | 7893299.0057 | 2774708.8567 | 2328696.0919 | 2101504.9437 | 29773295.1181
| Land | 5002327.3597 | 12067182.9784 | 0 | 4960253.0306 | 4246862.1737 | 4362986.0423 | 25637284.2251
| Easements | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1541794.4426 | 1363809.2069 | 1396575.6628 | 1417215.1516 | 1415620.7246 | 1454328.6808 | 7047549.4266
| Total System | 340660454.6191 | 307795925.9836 | 309345330.343 | 323142742.8268 | 351628316.5907 | 357632209.06 | 1649544524.8041
| Information & Communication Technology | 40670000 | 30936540.7055 | 17311315.1561 | 17378625.7019 | 15248470.4101 | 14447176.1173 | 95322128.0909
| Furniture, fittings, plant and equipment | 3550000 | 4822879.6046 | 4809933.9645 | 3038465.4726 | 3439821.5936 | 3505812.3512 | 19616912.9864
| Motor Vehicles | 4700000 | 6940521.3954 | 4241605.4121 | 4635725.0395 | 5485172.2667 | 1781343.4956 | 23084367.6093
| Buildings | 3690000 | 7472309.247 | 9779674.7113 | 8310979.1937 | 8193516.9924 | 6298766.1879 | 40055246.3322
| Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Capex | 393270454.6191 | 357968176.9361 | 345487859.5869 | 356506538.2345 | 383995297.8535 | 383665307.212 | 1827623179.823

## Impact of Escalator
RIN / Submission Categories
RIN Categories:
Inclusive of Escalator
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 48419634.5023 | 33956216 | 24446757 | 20808877 | 19862891 | 19577920 | 19577920 | 19577920 | 19577920 | 19577920 | 118652661
| Augex | 57522026 | 64808968 | 64514992 | 77992408 | 94029987 | 87791597 | 80244851 | 76142154 | 85054650 | 84625200 | 389137952
| Repex | 150012101.7474 | 113287872 | 124299207 | 122788250 | 128144750 | 131818750 | 130915750 | 144342750 | 163145750 | 184090750 | 620338829
| Other | 17809814 | 13635350 | 8241780 | 6422946 | 6353986 | 6720525 | 6605148 | 6684705 | 6634306 | 6323995 | 41374587
| Overheads | 76532785.0026 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Total System | 350296361.2523 | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 | 321628384.3766 | 331664811.0024 | 359949981.4683 | 380488189.7109 | 1569504029
| Non System | 53120118.5878 | 49686736.0244 | 35108941.55 | 31713950.6162 | 30022401.5922 | 23558369.2171 |  |  |  |  | 170090399
| Total Capex | 403416479.8402 | 354765181.9921 | 336266963.1982 | 340188103.9258 | 358371213.7066 | 350002965.1774 |  |  |  |  | 1739594428
Exclusive of Escalator
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 48419634.5023 | 33916939.5292 | 24374001.5841 | 20689244.4991 | 19687642.7841 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 118022093.9437
| Augex | 57522026 | 64734004.7727 | 64322990.4567 | 77544021.1495 | 93200370.2306 | 86788682.411 | 79328149.009 | 75272320.4431 | 84083001.7755 | 83658457.7311 | 386590069.0206
| Repex | 150012101.7474 | 113156834.2013 | 123929283.0671 | 122082326.9736 | 127014142.2343 | 130312877.5476 | 129420193.2487 | 142693805.7418 | 161282003.8284 | 181987732.1124 | 616495464.0239
| Other | 17809814 | 13619578.2654 | 8217251.8333 | 6386019.7837 | 6297925.4441 | 6643750.9943 | 6529692.0393 | 6608340.1952 | 6558516.9438 | 6251750.878 | 41164526.3209
| Overheads | 70200000.02 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Total System | 343963576.2697 | 304817396.7363 | 300498812.5895 | 307163284.7155 | 326157278.8075 | 323635380.4602 | 318917015.2207 | 328846013.9297 | 356815143.5632 | 377122530.9795 | 1562272153.309
| Non System | 53120118.5878 | 49686736.0244 | 35108941.55 | 31713950.6162 | 30022401.5922 | 23558369.2171 |  |  |  |  | 170090399
| Total Capex | 397083694.8576 | 354504132.7607 | 335607754.1395 | 338877235.3317 | 356179680.3997 | 347193749.6774 |  |  |  |  | 1732362552.309
Impact of Escalator
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 0 | 39276.4708 | 72755.4159 | 119632.5009 | 175248.2159 | 223654.4528 | 223654.4528 | 223654.4528 | 223654.4528 | 223654.4528 | 630567.0563
| Augex | 0 | 74963.2273 | 192001.5433 | 448386.8505 | 829616.7694 | 1002914.589 | 916701.991 | 869833.5569 | 971648.2245 | 966742.2689 | 2547882.9794
| Repex | 0 | 131037.7987 | 369923.9329 | 705923.0264 | 1130607.7657 | 1505872.4524 | 1495556.7513 | 1648944.2582 | 1863746.1716 | 2103017.8876 | 3843364.9761
| Other | 0 | 15771.7346 | 24528.1667 | 36926.2163 | 56060.5559 | 76774.0057 | 75455.9607 | 76364.8048 | 75789.0562 | 72244.122 | 210060.6791
| Overheads | 6332784.9826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total System | 6332784.9826 | 261049.2314 | 659209.0587 | 1310868.594 | 2191533.3069 | 2809215.5 | 2711369.1558 | 2818797.0727 | 3134837.9051 | 3365658.7314 | 7231875.691
| Non System | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Total Capex | 6332784.9826 | 261049.2314 | 659209.0587 | 1310868.594 | 2191533.3069 | 2809215.5 |  |  |  |  | 7231875.691
Submission Categories:
Inclusive of Escalator
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 48419634.5023 | 33956216 | 24446757 | 20808877 | 19862891 | 19577920 | 19577920 | 19577920 | 19577920 | 19577920 | 118652661
| Augex | 57522026 | 64808968 | 64514992 | 77992408 | 94029987 | 87791597 | 80244851 | 76142154 | 85054650 | 84625200 | 389137952
| Repex | 146012101.7474 | 109287872 | 120299207 | 118788250 | 124144750 | 127818750 | 126915750 | 140342750 | 159145750 | 180090750 | 600338829
| Reliability | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 20000000
| Other | 17809814 | 13635350 | 8241780 | 6422946 | 6353986 | 6720525 | 6605148 | 6684705 | 6634306 | 6323995 | 41374587
| Overheads | 76532785.0026 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Total System | 350296361.2523 | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 | 321628384.3766 | 331664811.0024 | 359949981.4683 | 380488189.7109 | 1569504029
| Non System | 53120118.5878 | 49686736.0244 | 35108941.55 | 31713950.6162 | 30022401.5922 | 23558369.2171 |  |  |  |  | 170090399
| Total Capex | 403416479.8402 | 354765181.9921 | 336266963.1982 | 340188103.9258 | 358371213.7066 | 350002965.1774 |  |  |  |  | 1739594428
Exclusive of Escalator
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 48419634.5023 | 33916939.5292 | 24374001.5841 | 20689244.4991 | 19687642.7841 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 19354265.5472 | 118022093.9437
| Augex | 57522026 | 64734004.7727 | 64322990.4567 | 77544021.1495 | 93200370.2306 | 86788682.411 | 79328149.009 | 75272320.4431 | 84083001.7755 | 83658457.7311 | 386590069.0206
| Repex | 146012101.7474 | 109161460.9207 | 119941187.3726 | 118105323.4094 | 123049433.8172 | 126358572.7905 | 125465888.4916 | 138739500.9848 | 157327699.0714 | 178033427.3553 | 596615978.3104
| Reliability | 4000000 | 3995373.2806 | 3988095.6945 | 3977003.5642 | 3964708.4171 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 3954304.757 | 19879485.7135
| Other | 17809814 | 13619578.2654 | 8217251.8333 | 6386019.7837 | 6297925.4441 | 6643750.9943 | 6529692.0393 | 6608340.1952 | 6558516.9438 | 6251750.878 | 41164526.3209
| Overheads | 70200000.02 | 79390039.9677 | 79655285.6482 | 80461672.3096 | 79957198.1143 | 80535803.9602 | 84284715.3766 | 84917282.0024 | 85537355.4683 | 85870324.7109 | 400000000
| Total System | 343963576.2697 | 304817396.7363 | 300498812.5895 | 307163284.7155 | 326157278.8075 | 323635380.4602 | 318917015.2207 | 328846013.9297 | 356815143.5632 | 377122530.9795 | 1562272153.309
| Non System | 53120118.5878 | 49686736.0244 | 35108941.55 | 31713950.6162 | 30022401.5922 | 23558369.2171 |  |  |  |  | 170090399
| Total Capex | 397083694.8576 | 354504132.7607 | 335607754.1395 | 338877235.3317 | 356179680.3997 | 347193749.6774 |  |  |  |  | 1732362552.309
Impact of Escalator
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | RCP
| Customer Connection | 0 | 39276.4708 | 72755.4159 | 119632.5009 | 175248.2159 | 223654.4528 | 223654.4528 | 223654.4528 | 223654.4528 | 223654.4528 | 630567.0563
| Augex | 0 | 74963.2273 | 192001.5433 | 448386.8505 | 829616.7694 | 1002914.589 | 916701.991 | 869833.5569 | 971648.2245 | 966742.2689 | 2547882.9794
| Repex | 0 | 126411.0793 | 358019.6274 | 682926.5906 | 1095316.1828 | 1460177.2095 | 1449861.5084 | 1603249.0152 | 1818050.9286 | 2057322.6447 | 3722850.6896
| Reliability | 0 | 4626.7194 | 11904.3055 | 22996.4358 | 35291.5829 | 45695.243 | 45695.243 | 45695.243 | 45695.243 | 45695.243 | 120514.2865
| Other | 0 | 15771.7346 | 24528.1667 | 36926.2163 | 56060.5559 | 76774.0057 | 75455.9607 | 76364.8048 | 75789.0562 | 72244.122 | 210060.6791
| Overheads | 6332784.9826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total System | 6332784.9826 | 261049.2314 | 659209.0587 | 1310868.594 | 2191533.3069 | 2809215.5 | 2711369.1558 | 2818797.0727 | 3134837.9051 | 3365658.7314 | 7231875.691
| Non System | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Total Capex | 6332784.9826 | 261049.2314 | 659209.0587 | 1310868.594 | 2191533.3069 | 2809215.5 |  |  |  |  | 7231875.691
RAB Category
RAB Categories:
Inclusive of Escalator
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 |  |  |  |  | RCP
| Sub-transmission lines and cables | 18783302.718 | 23214073.463 | 28890989.8087 | 31616423.5166 | 33216260.6573 | 34788098.8127 |  |  |  |  | 151725846.2583
| Distribution lines and cables | 133299457.146 | 112455150.7067 | 105231198.7863 | 106299143.4576 | 103343502.3445 | 106915872.2034 |  |  |  |  | 534244867.4984
| Substations | 147114004.0128 | 117667814.1647 | 123135176.8842 | 132752756.687 | 151099142.696 | 143546904.577 |  |  |  |  | 668201795.0088
| Transformers | 11398206.3943 | 7326224.9292 | 16723241.1354 | 11093638.5852 | 15532322.0467 | 15797282.6442 |  |  |  |  | 66472709.3408
| Low Voltage lines and cables | 14122994.2308 | 14910004.9872 | 16899990.8384 | 16816332.6359 | 16629498.8381 | 17164610.4697 |  |  |  |  | 82420437.7694
| Customer metering and Load control | 717832.0117 | 1647243.2926 | 1233420.6105 | 1159131.0035 | 1065961.4507 | 1003574.8163 |  |  |  |  | 6109331.1737
| Communication | 18131336.1951 | 14545522.2778 | 7684390.4843 | 2648755.0293 | 2174525.0865 | 1918241.4639 |  |  |  |  | 28971434.3419
| Land | 5143822.9714 | 11960643.7886 | 0 | 4735089.64 | 3965699.246 | 3982508.2296 |  |  |  |  | 24643940.9042
| Easements | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1585405.5724 | 1351768.3579 | 1359613.1004 | 1352882.7543 | 1321899.7487 | 1327502.7432 |  |  |  |  | 6713666.7045
| Total System | 350296361.2523 | 305078445.9677 | 301158021.6482 | 308474153.3096 | 328348812.1143 | 326444595.9602 |  |  |  |  | 1569504029
| Information & Communication Technology | 41064345.6181 | 30637169 | 16816254 | 16519250 | 14143911 | 13073815 |  |  |  |  | 91190399
| Furniture, fittings, plant and equipment | 3584421.6116 | 4776208.7856 | 4672381.6498 | 2888212.8897 | 3190649.8926 | 3172546.7823 |  |  |  |  | 18700000
| Motor Vehicles | 4745572.2745 | 6873358.2388 | 4120305.9002 | 4406487.7265 | 5087840.6997 | 1612007.4348 |  |  |  |  | 22100000
| Buildings | 3725779.0836 | 7400000 | 9500000 | 7900000 | 7600000 | 5700000 |  |  |  |  | 38100000
| Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Total Capex | 403416479.8402 | 354765181.9921 | 336266963.1982 | 340188103.9258 | 358371213.7066 | 350002965.1774 |  |  |  |  | 1739594428
Exclusive of Escalator
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 |  |  |  |  | RCP
| Sub-transmission lines and cables | 18443731.342 | 23194209.6669 | 28827749.9119 | 31482068.7378 | 32994561.8453 | 34488730.1983 |  |  |  |  | 150987320.3602
| Distribution lines and cables | 130889621.0935 | 112358925.1914 | 105000856.7249 | 105847422.6011 | 102653745.8444 | 105995808.8018 |  |  |  |  | 531856759.1637
| Substations | 144454423.5593 | 117567128.2826 | 122865644.5516 | 132188620.5425 | 150090645.6598 | 142311613.2157 |  |  |  |  | 665023652.2522
| Transformers | 11192145.4748 | 7319956.0321 | 16686635.396 | 11046495.8919 | 15428653.022 | 15661339.2964 |  |  |  |  | 66143079.6385
| Low Voltage lines and cables | 13867673.6061 | 14897246.8085 | 16862998.2091 | 16744871.2117 | 16518506.81 | 17016900.5968 |  |  |  |  | 82040523.6362
| Customer metering and Load control | 704854.7836 | 1645833.781 | 1230720.7587 | 1154205.2475 | 1058846.7911 | 994938.5639 |  |  |  |  | 6084545.1422
| Communication | 17803551.307 | 14533075.9793 | 7667570.0131 | 2637499.0789 | 2160011.4231 | 1901734.0574 |  |  |  |  | 28899890.5518
| Land | 5050831.0694 | 11950409.3164 | 0 | 4714967.7587 | 3939230.5588 | 3948236.7974 |  |  |  |  | 24552844.4313
| Easements | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 1556744.034 | 1350611.678 | 1356637.0241 | 1347133.6454 | 1313076.8529 | 1316078.9325 |  |  |  |  | 6683538.1328
| Total System | 343963576.2697 | 304817396.7363 | 300498812.5895 | 307163284.7155 | 326157278.8075 | 323635380.4602 |  |  |  |  | 1562272153.309
| Information & Communication Technology | 41064345.6181 | 30637169 | 16816254 | 16519250 | 14143911 | 13073815 |  |  |  |  | 91190399
| Furniture, fittings, plant and equipment | 3584421.6116 | 4776208.7856 | 4672381.6498 | 2888212.8897 | 3190649.8926 | 3172546.7823 |  |  |  |  | 18700000
| Motor Vehicles | 4745572.2745 | 6873358.2388 | 4120305.9002 | 4406487.7265 | 5087840.6997 | 1612007.4348 |  |  |  |  | 22100000
| Buildings | 3725779.0836 | 7400000 | 9500000 | 7900000 | 7600000 | 5700000 |  |  |  |  | 38100000
| Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Total Capex | 397083694.8576 | 354504132.7607 | 335607754.1395 | 338877235.3317 | 356179680.3997 | 347193749.6774 |  |  |  |  | 1732362552.309
Impact of Escalator
| $Real FY19 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 |  |  |  |  | RCP
| Sub-transmission lines and cables | 339571.3759 | 19863.7961 | 63239.8968 | 134354.7788 | 221698.812 | 299368.6145 |  |  |  |  | 738525.8981
| Distribution lines and cables | 2409836.0525 | 96225.5153 | 230342.0614 | 451720.8565 | 689756.5 | 920063.4016 |  |  |  |  | 2388108.3347
| Substations | 2659580.4536 | 100685.8821 | 269532.3326 | 564136.1445 | 1008497.0362 | 1235291.3612 |  |  |  |  | 3178142.7566
| Transformers | 206060.9195 | 6268.8971 | 36605.7394 | 47142.6933 | 103669.0247 | 135943.3478 |  |  |  |  | 329629.7023
| Low Voltage lines and cables | 255320.6247 | 12758.1787 | 36992.6293 | 71461.4242 | 110992.0281 | 147709.8729 |  |  |  |  | 379914.1332
| Customer metering and Load control | 12977.2281 | 1409.5116 | 2699.8518 | 4925.7561 | 7114.6596 | 8636.2524 |  |  |  |  | 24786.0315
| Communication | 327784.8881 | 12446.2985 | 16820.4712 | 11255.9504 | 14513.6635 | 16507.4065 |  |  |  |  | 71543.7901
| Land | 92991.9019 | 10234.4722 | 0 | 20121.8813 | 26468.6871 | 34271.4322 |  |  |  |  | 91096.4729
| Easements | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Emergency Spares (Major Plant, Excludes Inventory) | 28661.5384 | 1156.6798 | 2976.0764 | 5749.1089 | 8822.8957 | 11423.8107 |  |  |  |  | 30128.5716
| Total System | 6332784.9826 | 261049.2314 | 659209.0587 | 1310868.594 | 2191533.3069 | 2809215.5 |  |  |  |  | 7231875.691
| Information & Communication Technology | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Furniture, fittings, plant and equipment | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Motor Vehicles | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Buildings | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Land (non-system) | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Other non system assets | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Total Capex | 6332784.9826 | 261049.2314 | 659209.0587 | 1310868.594 | 2191533.3069 | 2809215.5 |  |  |  |  | 7231875.691