## STANDARD TIMEFRAMES (hidden)
FY 20/21 |  | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01
Albury Depot Roof and Improvement Works | Stage 6 - Construction | 2020-08-01: 6 - Construction; 2020-09-01: 6 - Construction; 2020-10-01: 6 - Construction
Balranald Depot Improvement Works | Stage 4 - Design/DA |  | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Berrigan Depot Imporvements Works | Stage 4 - Design/DA | 2020-09-01: 4 - Design and DA; 2020-10-01: 4 - Design and DA; 2020-11-01: 4 - Design and DA; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 5 - Tender; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction
Braidwood Depot Retaining Wall | Stage 6 - Construction | 2020-09-01: 6 - Construction; 2020-10-01: 6 - Construction
Canowindra Depot Improvement Works | Stage 4 - Design/DA |  | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Dubbo Depot Hydraulic Study and Works | Stage 1 - Inception |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Eulomogo Zone Substation Bund Works | Stage 1 - Inception |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Inverell Depot Welding Workshop Enclosure | Stage 3 - Business Case |  | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Kempsey Depot Fire Hydrant Upgrade | Stage 3 - Business Case |  | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Lismore Depot Tier 2 Store Works | Stage 1 - Inception |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | Stage 4 | Stage 4 | Stage 4 | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Leeton Depot Improvement Works - Fire Hydrant and Hardstand Works | Stage 4 - Design/DA | 2020-09-01: 4 - Design and DA; 2020-10-01: 4 - Design and DA; 2020-11-01: 4 - Design and DA; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 5 - Tender; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction
Moruya Depot Transformer Storage | Stage 5 - Tender | 2020-09-01: 5 - Tender; 2020-10-01: 5 - Tender; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 6 - Construction; 2021-02-01: 6 - Construction; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction
Port Macquarie Depot Improvements | Stage 5 - Tender | 2020-09-01: 5 - Tender; 2020-10-01: 5 - Tender; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 6 - Construction; 2021-02-01: 6 - Construction; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction
Tamworth Depot Gantry Crane Installation | Stage 4 - Design/DA | 2020-09-01: 4 - Design and DA; 2020-10-01: 4 - Design and DA; 2020-11-01: 4 - Design and DA; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 5 - Tender; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction
Temora Depot Improvement Works | Stage 2 - Concept Design |  | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Tweed Heads EWP Storange Review | Stage 1 - Inception |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Wagga Wagga Warehouse Extension and Tier 2 Store | Stage 4 - Design/DA | 2020-09-01: 4 - Design and DA; 2020-10-01: 4 - Design and DA; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction
Walgett Depot Improvement Works | Stage 5 - Tender | 2020-09-01: 5 - Tender; 2020-10-01: 5 - Tender; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 6 - Construction; 2021-02-01: 6 - Construction; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction
Warren Depot Upgrade | Stage 5 - Tender | 2020-09-01: 5 - Tender; 2020-10-01: 5 - Tender; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 6 - Construction; 2021-02-01: 6 - Construction; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction
West Wyalong Shed and Storage Upgrades | Stage 4 - Design/DA |  | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Young Depot Upgrade Works | Stage 4 - Design/DA | 2020-09-01: 4 - Design and DA; 2020-10-01: 4 - Design and DA; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction
FY 21/22
Ballina Depot Stage 2 Hardstand Works | Stage 4 - Design/DA | 2021-07-01: 4 - Design and DA; 2021-08-01: 5 - Tender; 2021-09-01: 5 - Tender; 2021-10-01: 5 - Tender; 2021-11-01: 5 - Tender; 2021-12-01: 6 - Construction; 2022-01-01: 6 - Construction; 2022-02-01: 6 - Construction; 2022-03-01: 6 - Construction
Balranald Depot Improvement Works | Stage 4 - Design/DA | [7 empty] | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Barham Depot Improvement Works | Stage 1 - Inception |  |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Bourke Depot Hardstand Works | Stage 1 - Inception |  |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Broken Hill Water Office Improvement Works | Stage 1 - Inception |  |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Canowindra Depot Improvement Works | Continuation from FY20/21
Condobolin Depot Improvement Works | Stage 3 - Business Case |  |  | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Cooma Depot Hardstand and Drainage Works | Stage 1 - Inception |  |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Dubbo Depot Warehouse Storage | Stage 4 - Design/DA | [7 empty] | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Griffith Depot Hardstand Works | Stage 1 - Inception |  |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Hay Depot Hardstand Upgrade | Stage 2 - Concept Design
Inverell Depot Hardstand Works | Stage 1 - Inception |  |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Leeton Depot Improvement Works | Stage 1 - Inception |  |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Parkes Depot Improvement Works | Stage 2 - Concept Design |  |  |  |  | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Tamworth Depot New Entrance | Stage 1 - Inception |  |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Taree Depot Improvement Works | Stage 5 - Tender | 2021-08-01: 5 - Tender; 2021-09-01: 5 - Tender; 2021-10-01: 5 - Tender; 2021-11-01: 5 - Tender; 2021-12-01: 6 - Construction; 2022-01-01: 6 - Construction; 2022-02-01: 6 - Construction; 2022-03-01: 6 - Construction
Wagga Wagga Warehouse Extension and Tier 2 Store | Continuation from FY20/21
Warialda Depot Internal and External Improvement Works | Stage 1 - Inception |  |  |  | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
| DAYS | 2020-08-01: MONTHS
Stage 1 | 24 | 2020-08-01: 1.2
Stage 2 | 61 | 2020-08-01: 3.05
Stage 3 | 55 | 2020-08-01: 2.75
Stage 4 | 142 | 2020-08-01: 7.1
Stage 5 | 78 | 2020-08-01: 3.9
Stage 6 | 76 | 2020-08-01: 3.8
Stage 7

## September 2020 (hidden)
| FY 20/21 | PO number | Stage | Sub stage | Action | Resource | Stage 1-3 | Stage 4-7 | Variation | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01
A | Albury Depot Roof and Improvement Works | 737612 | Stage 6 - Construction | 6B Monitoring | [5 empty] | 2020-08-01: 6 - Construction; 2020-09-01: 6 - Construction; 2020-10-01: 6 - Construction; 2020-11-01: 7 - Construction
[6 empty] | Shelley | 0 | 7508 |  | 2020-09-01: 3754
B | Balranald Depot Improvement Works | 740147 | Stage 4 - Design/DA | 4A Detailed Design | Urgent |  |  |  |  | 2020-09-01: 4 - Design and DA+O4I4:I4:Q4; 2020-10-01: 4 - Design and DA; 2020-11-01: 4 - Design and DA; 2020-12-01: 4 - Design and DA; 2021-01-01: 4 - Design and DA; 2021-02-01: 5 - Tender; 2021-03-01: 5 - Tender; 2021-04-01: 5 - Tender; 2021-05-01: 5 - Tender; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction; 2021-08-01: 6 - Construction
C | Berrigan Depot Improvements Works | 757469 | Stage 4 - Design/DA | 4B DA submission | Urgent |  |  |  |  | 2020-09-01: 4 - Design and DA; 2020-10-01: 4 - Design and DA; 2020-11-01: 4 - Design and DA; 2020-12-01: 4 - Design and DA; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 5 - Tender; 2021-04-01: 5 - Tender; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction; 2021-08-01: 6 - Construction
D | Braidwood Depot Retaining Wall | 740047 | Stage 6 - Construction | 6B Monitoring |  |  |  |  | 0 | 2020-09-01: 6 - Construction; 2020-10-01: 6 - Construction
[6 empty] | Andy | 0 | 2818 |  | 2020-09-01: 1700; 2020-10-01: 1118
E | Canowindra Depot Improvement Works | 739923 | Stage 4 - Design/DA | 4D Construction Design | Urgent |  |  |  |  | 2020-09-01: DELAY; 2020-10-01: DELAY; 2020-11-01: 4 - Design and DA; 2020-12-01: 4 - Design and DA; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 5 - Tender; 2021-04-01: 5 - Tender; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction; 2021-08-01: 6 - Construction
[6 empty] | Shelley | 17 | 8601.5 | 11921 | 2020-09-01: 0; 2020-11-01: 600; 2021-01-01: 2980; 2021-02-01: 2980; 2021-03-01: 2980; 2021-04-01: 2980; 2021-05-01: 2150.37; 2021-06-01: 2150.37; 2021-07-01: 2150.37; 2021-08-01: 2150.37
F | Dubbo Depot Hydraulic Study and Works | 739917 | Stage 1 - Inception | 1A Feasibility Proposal | [7 empty] | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
[6 empty] | Tom | 11880 | 20000 | 0 | 2020-12-01: 3960
G | Eulomogo Zone Substation Bund Works |  | Stage 1 - Inception | 1A Feasibility Proposal | [7 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
[6 empty] | Tom | 11880 | 7692.31 | 0 | 2020-10-01: 1320; 2020-11-01: 2805; 2021-01-01: 2805; 2021-02-01: 2475; 2021-04-01: 2475
H | Inverell Depot Welding Workshop Enclosure | 766089 | Stage 3 - Business Case | 3B Business Case | [5 empty] | 2020-09-01: 5 - Tender; 2020-10-01: 5 - Tender; 2020-11-01: 3 - Business Case; 2020-12-01: 3 - Business Case; 2021-01-01: 4 - Design and DA; 2021-02-01: 4 - Design and DA; 2021-03-01: 4 - Design and DA; 2021-04-01: 4 - Design and DA; 2021-05-01: 4 - Design and DA; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction
[6 empty] | Shelley |  | 5510 |  | 2020-09-01: 928; 2020-10-01: 464; 2020-11-01: 946.5; 2020-12-01: 946.5; 2021-04-01: 290; 2021-05-01: 290; 2021-06-01: 1305; 2021-07-01: 1305
I | Kempsey Depot Fire Hydrant Upgrade | 763426 | Stage 3 - Business Case | 3B Business Case/ 5A Tender Finalisation | [5 empty] | 2020-09-01: 5 - Tender; 2020-10-01: 5 - Tender; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 6 - Construction; 2021-02-01: 7 - Construction; 2021-03-01: 6 - Construction; 2021-04-01: 7 - Construction
[6 empty] | Shelley | 0 | 22005 | 0 | 2020-09-01: 5901; 2020-10-01: 5388; 2020-11-01: 1796; 2021-01-01: 2373.33; 2021-02-01: 2373.33; 2021-03-01: 2373.33; 2021-04-01: 1800
J | Lismore Depot Tier 2 Store Works |  | Stage 1 - Inception | 1A Feasibility Proposal | [7 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction | 7 - DLP | 7 - DLP | 7 - DLP | 7 - DLP
[6 empty] | Tom | 11880 | 15384.62 | 0 | 2020-10-01: 1320; 2020-11-01: 2805; 2021-01-01: 2805; 2021-02-01: 2475; 2021-04-01: 2475
K | Leeton Depot Improvement Works - Fire Hydrant and Hardstand Works | 739031 | Stage 4 - Design/DA | 4D Construction Design | Urgent |  |  |  |  | 2020-10-01: 4 - Design and DA; 2020-11-01: 4 - Design and DA; 2020-12-01: 4 - Design and DA; 2021-01-01: 4 - Design and DA; 2021-02-01: 5 - Tender; 2021-03-01: 5 - Tender; 2021-04-01: 5 - Tender; 2021-05-01: 5 - Tender; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction; 2021-08-01: 6 - Construction; 2021-09-01: 6 - Construction
[6 empty] | Andy | 0 | 7591 | 20989.12 | 2020-10-01: 2623.64; 2020-11-01: 2623.64; 2020-12-01: 2623.64; 2021-01-01: 2623.64; 2021-02-01: 2623.64; 2021-03-01: 2623.64; 2021-04-01: 2623.64; 2021-05-01: 2623.64; 2021-06-01: 1897.75; 2021-07-01: 1897.75; 2021-08-01: 1897.75; 2021-09-01: 1897.75
L | Moruya Depot Transformer Storage | 737949 | Stage 5 - Tender | 5A Tender Finalisation | [5 empty] | 2020-09-01: DELAY; 2020-10-01: DELAY; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction
[6 empty] | Unallocated |  | 2949.06 | 4423.58 | 2020-11-01: 1105.9; 2020-12-01: 1105.9; 2021-01-01: 1105.9; 2021-02-01: 1105.9; 2021-03-01: 983.02; 2021-04-01: 983.02; 2021-05-01: 983.02
M | Port Macquarie Depot Improvements | 737951 | Stage 5 - Tender | 5B Tender Period | [5 empty] | 2020-09-01: 5 - Tender; 2020-10-01: 5 - Tender; 2020-11-01: 6 - Tender; 2020-12-01: 6 - Construction; 2021-01-01: 6 - Construction; 2021-02-01: 6 - Construction; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction
[6 empty] | Shelley | 0 | 21264.17 | 0 | 2020-09-01: 3479.7; 2020-10-01: 3479.7; 2020-12-01: 3221.84; 2021-01-01: 1610.92; 2021-02-01: 1610.92; 2021-03-01: 1610.92; 2021-04-01: 1610.92
N | Tamworth Depot Gantry Crane Installation |  | Stage 4 - Design/DA | 4C Tender Preparation | [5 empty] | 2020-10-01: 5 - Tender; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 6 - Construction; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction
[6 empty] | Amy |  | 21000 |  | 2020-10-01: 3000; 2020-12-01: 3000; 2021-01-01: 3000; 2021-02-01: 3000; 2021-03-01: 2000; 2021-04-01: 2500; 2021-05-01: 3000
O | Temora Depot Improvement Works | 737946 | Stage 2 - Concept Design | 2A Scope of Work Development | [6 empty] | DELAY | DELAY | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
[6 empty] | Unallocated |  | 4867.9 | 11727 |  |  |  | 2805 |  | 2805 | 2475 |  | 2475 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 553.17 | 553.17 | 553.17 | 553.17
P | Tweed Heads EWP Storage Review |  | Stage 1 - Inception | 1A Feasibility Proposal | [7 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
[7 empty] | Removed | Removed | Removed
Q | Wagga Wagga Warehouse Extension and Tier 2 Store | 739918 | Stage 4 - Design/DA | 4B DA Submission | Urgent |  |  |  |  | 2020-09-01: 4 - Design and DA; 2020-10-01: 4 - Design and DA; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 6 - Construction; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction
[6 empty] | Shelley | 0 | 22024.7 | 1500 | 2020-09-01: 1006.48; 2020-10-01: 1200; 2020-11-01: 4037.03; 2020-12-01: 4037.03; 2021-01-01: 4037.03; 2021-02-01: 2018.52; 2021-03-01: 2018.52; 2021-04-01: 2018.52; 2021-05-01: 2018.52
R | Walgett Depot Improvement Works | 739920 | Stage 5 - Tender | 5A Tender Finalisation | [5 empty] | 2020-09-01: DELAY; 2020-10-01: DELAY; 2020-11-01: 4 - Design and DA; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction
[6 empty] | Unallocated | 0 | 22024.7 | 1500 | 2020-12-01: 512.2033; 2021-01-01: 512.2033; 2021-02-01: 512.2033; 2021-03-01: 5122.02; 2021-04-01: 5122.02; 2021-05-01: 5122.02; 2021-06-01: 5122.02
S | Warren Depot Upgrade | 737609 | Stage 5 - Tender | 5A Tender Finalisation | [5 empty] | 2020-09-01: DELAY; 2020-10-01: DELAY; 2020-11-01: 5 - Tender; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 6 - Construction; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction
[6 empty] | Unallocated | 0 | 4229.91 | 0 | 2020-11-01: 328.18; 2020-12-01: 328.18; 2021-01-01: 328.18; 2021-02-01: 328.18; 2021-03-01: 729.29; 2021-04-01: 729.29; 2021-05-01: 729.29; 2021-06-01: 729.29
T | West Wyalong Shed and Storage Upgrades | 740024 | Stage 4 - Design/DA | 4B DA submission | Urgent |  |  |  |  | 2020-09-01: 4 - Design and DA; 2020-10-01: 4 - Design and DA; 2020-11-01: 4 - Design and DA; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 5 - Tender; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction
[6 empty] | Andy | 0 | 11781 |  | 2021-01-01: 2062; 2021-02-01: 2062; 2021-03-01: 2062; 2021-04-01: 883.25; 2021-05-01: 883.25; 2021-06-01: 883.25; 2021-07-01: 883.25
U | Young Depot Upgrade Works | 739919 | Stage 4 - Design/DA | 4D Construction Design | Urgent |  |  |  |  | 2020-09-01: 4 - Design and DA; 2020-10-01: 4 - Design and DA; 2020-11-01: 4 - Design and DA; 2020-12-01: 5 - Tender; 2021-01-01: 5 - Tender; 2021-02-01: 5 - Tender; 2021-03-01: 5 - Tender; 2021-04-01: 6 - Construction; 2021-05-01: 6 - Construction; 2021-06-01: 6 - Construction; 2021-07-01: 6 - Construction; 2021-08-01: 6 - Construction
[6 empty] | Shelley |  | 46238.4 | 1350 | 2020-10-01: 600; 2020-11-01: 750; 2020-12-01: 1586.8; 2021-02-01: 1586.8; 2021-03-01: 1586.8; 2021-04-01: 8295.6; 2021-05-01: 8295.6; 2021-06-01: 8295.6; 2021-07-01: 8295.6; 2021-08-01: 8295.6
V | Condobolin Depot Improvement Works | 740026 | Stage 3 - Business Case | [6 empty] | 2020-10-01: 3 - Business Case; 2020-11-01: 3 - Business Case; 2020-12-01: 3 - Business Case; 2021-01-01: 4 - Design and DA; 2021-02-01: 4 - Design and DA; 2021-03-01: 5 - Tender; 2021-04-01: 5 - Tender; 2021-05-01: 5 - Tender; 2021-06-01: 5 - Tender; 2021-07-01: 6 - Construction; 2021-08-01: 6 - Construction; 2021-09-01: 6 - Construction; 2021-10-01: 6 - Construction
[6 empty] | Shelley | 4465 | 4714.17 | 49178.14 | 2020-10-01: 1488.33; 2020-11-01: 1488.33; 2020-12-01: 1488.33; 2021-01-01: 5389.23; 2021-02-01: 5389.23; 2021-03-01: 5389.23; 2021-04-01: 5389.23; 2021-05-01: 5389.23; 2021-06-01: 5389.23; 2021-07-01: 5389.23; 2021-08-01: 5389.23; 2021-09-01: 5389.23; 2021-10-01: 5389.23
[7 empty] | 40122 | 258204.44 | 102588.84
[11 empty] | 16769.18 | 22001.67 | 22090.58 | 22810.4233 | 34437.4333 | 33015.7233 | 29478.77 | 42650.49 | 32551.03 | 26838.6 | 20987.29 | 18799.04 | 8353.07 | 6455.32 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 553.17 | 553.17 | 553.17 | 553.17
[9 empty] | Rebecca (3 projects) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Shelley (9 projects) |  | 15069.18 | 12620.03 | 9617.86 | 11280.5 | 16390.51 | 15958.8 | 15958.8 | 22384.27 | 18143.72 | 17140.2 | 17140.2 | 15835.2 | 5389.23 | 5389.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Amy (1 projects) |  | 0 | 3000 | 0 | 3000 | 3000 | 3000 | 2000 | 2500 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Andy (2 project) |  | 1700 | 3741.64 | 2623.64 | 2623.64 | 4685.64 | 4685.64 | 4685.64 | 3506.89 | 3506.89 | 2781 | 2781 | 1897.75 | 1897.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Tom (3 projects) |  | 0 | 2640 | 5610 | 3960 | 5610 | 4950 | 0 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Unallocated |  | 0 | 0 | 4239.08 | 1946.2833 | 4751.2833 | 4421.2833 | 6834.33 | 9309.33 | 7900.42 | 6917.4 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 1066.09 | 553.17 | 553.17 | 553.17 | 553.17
|  |  | DAYS | MONTHS
|  | Stage 1 | 24 | 1.2
|  | Stage 2 | 61 | 3.05
|  | Stage 3 | 55 | 2.75
|  | Stage 4 | 142 | 7.1
|  | Stage 5 | 78 | 3.9
|  | Stage 6 | 76 | 3.8
Stage 7

## 2021-2022 (hidden)
| FY21/22 | MASTT | PO number | Stage | Sub stage | Resource | Feasibility | Delivery | Variation | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01
AA | Ballina Depot Stage 2 Hardstand Works | Done |  | Stage 4 - Design/DA | 4C Tender Preparation |  |  |  |  | 2021-07-01: 4 - Design and DA; 2021-08-01: 5 - Tender; 2021-09-01: 5 - Tender; 2021-10-01: 5 - Tender; 2021-11-01: 5 - Tender; 2021-12-01: 6 - Construction; 2022-01-01: 6 - Construction
Unallocated
AB | Balranald Depot Improvement Works |  |  | Continuation from FY20/21
Unallocated
AC | Barham Depot Improvement Works | Done |  | Stage 1 - Inception | 1A Feasibility Proposal | [6 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AD | Bourke Depot Hardstand Works |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [9 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AE | Broken Hill Water Office Improvement Works |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [7 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AF | Canowindra Depot Improvement Works |  |  | Continuation from FY20/21
Unallocated
AG | Cooma Depot Hardstand and Drainage Works |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [8 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AH | Dubbo Depot Warehouse Storage |  |  | Stage 4 - Design/DA | [12 empty] | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AI | Griffith Depot Hardstand Works |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [10 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AJ | Hay Depot Hardstand Upgrade |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [13 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AK | Inverell Depot Hardstand Works |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [11 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AL | Leeton Depot Improvement Works |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [6 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AM | Parkes Depot Improvement Works |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [9 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
Unallocated
AN | Tamworth Depot New Entrance |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [7 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction
Unallocated
AO | Taree Depot Improvement Works |  |  | Stage 5 - Tender | 5A Tender Finalisation |  |  |  |  | 2021-08-01: 5 - Tender; 2021-09-01: 5 - Tender; 2021-10-01: 5 - Tender; 2021-11-01: 5 - Tender; 2021-12-01: 6 - Construction; 2022-01-01: 6 - Construction; 2022-02-01: 6 - Construction; 2022-03-01: 6 - Construction
Unallocated
AP | Wagga Wagga Warehouse Extension and Tier 2 Store |  |  | Continuation from FY20/21
Unallocated
AQ | Warialda Depot Internal and External Improvement Works |  |  | Stage 1 - Inception | 1A Feasibility Proposal | [6 empty] | 1 - Inception | 2 - Concept Design | 2 - Concept Design | 2 - Concept Design | 3 - Business Case | 3 - Business Case | 3 - Business Case | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 4 - Design and DA | 5 - Tender | 5 - Tender | 5 - Tender | 5 - Tender | 6 - Construction | 6 - Construction | 6 - Construction | 6 - Construction
[6 empty] | Unallocated |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Rebecca (4 projects) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Shelley (9 projects) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DAYS | MONTHS |  |  |  | Amy (3 projects) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stage 1 |  |  | 24 | 1.2 |  |  |  | Andy (1 project) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stage 2 |  |  | 61 | 3.05 |  |  |  | Unallocated |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stage 3 |  |  | 55 | 2.75
| Stage 4 |  |  | 142 | 7.1
| Stage 5 |  |  | 78 | 3.9
| Stage 6 |  |  | 76 | 3.8
Stage 7

## Property Capex Summary
Property AER Capex Model - Summary FY24-29
Workstreams | FY25 | FY26 | FY27 | FY28 | FY29 | TOTAL
Security | 2150910.7159 | 2161402.9633 | 2171946.3924 | 2182541.2528 | 2193187.7955 | 10859989.1199
Compliance | 417088.6866 | 417088.6866 | 417088.6866 | 417088.6866 | 417088.6866 | 2085443.4329
Asset Renewals | 979358.6459 | 2075775.1137 | 510653.5143 | 525423.4198 | 1420928.3832 | 5512139.0769
Major Capital Works | 25607972.5059 | 13825217.1099 | 13825217.1099 | 13825217.1099 | 13825217.1099 | 80908840.9456
Total (Real FY24$) | 29155330.5543 | 18479483.8735 | 16924905.7032 | 16950270.4691 | 17856421.9752 | 99366412.5753
Workstream | Definition
Security | Capital expenditure related to electronic security and barriers including fencing upgrades, CCTV and card readers
Compliance | Capital expenditure allowance related to compliance works to property portfolio
Asset Renewals | Minor capital works prioritised based on sites with a Critical Infrastructure rating of 4 or 5 and all building elements with a rating of 'poor'
Major Capital Works | Major capital works prioritised and filtered for all proposed (business improvement or property maintenance) projects with a rating greater than 5
Forecast capex subject to ongoing site risk assessments which will determine final year on year forecast

## Security
Security Capital Expenditure - Workstream Overview
Security workstreams | FY25 | FY26 | FY27 | FY28 | FY29 | TOTAL | Commentary
Electronic Security | 895117 | 921970.51 | 949629.6253 | 978118.5141 | 1007462.0695 | 4752297.7188 | Ongoing Security Uplift Program eg CCTV, readers. Continuation of FY19-24 planned activity based on site criticality and risk
Physical Security Barriers | 1079000 | 1111370 | 1144711.1 | 1179052.433 | 1214424.006 | 5728557.539 | Fencing & gate replacement - based on Critical Infrastructure (CI) rating 1-3 plus end of life/replacement
Technical Security Support | 88668 | 91328.04 | 94067.8812 | 96889.9176 | 99796.6152 | 470750.454 | Security project 3rd party resources eg Project Manager, Technical Consultants
0
Total (FY22$) | 2062785 | 2124668.55 | 2188408.6065 | 2254060.8647 | 2321682.6906 | 10951605.7118 | Forecast capex subject to ongoing site risk assessments which will determine final year on year forecast
Inflation adjusted | 2167084.5666 | 2232097.1036 | 2299060.0167 | 2368031.8172 | 2439072.7717
FY24$ Real | 2114228.8454 | 2124542.1569 | 2134905.7771 | 2145319.9517 | 2155784.927
Adjusted for end of year $ | 2150910.7159 | 2161402.9633 | 2171946.3924 | 2182541.2528 | 2193187.7955
Total (Real FY24$) | 2150910.7159 | 2161402.9633 | 2171946.3924 | 2182541.2528 | 2193187.7955 | 10859989.1199 | Forecast capex subject to ongoing site risk assessments which will determine final year on year forecast
Original planning based on FY22$ with 2.5% inflation
Inflated and converted to Real FY24$
FY24$ Conversion | 1.025 | 1.0506 | 1.0769 | 1.1038 | 1.1314

## Compliance
Compliance Capital Expenditure - Workstream Overview
Compliance workstream | FY25 | FY26 | FY27 | FY28 | FY29 | TOTAL | Commentary
Compliance | 400000 | 410000 | 420250 | 430756.25 | 441525.1562 | 2102531.4062 | Compliance works allowance (non planned capex to meet compliance requirements)
0
Total (FY22$) | 400000 | 410000 | 420250 | 430756.25 | 441525.1562 | 2102531.4062
Inflation adjusted | 420225 | 430730.625 | 441498.8906 | 452536.3629 | 463849.772
FY24$ Real | 409975.6098 | 409975.6098 | 409975.6098 | 409975.6098 | 409975.6098
Adjusted for end of year $ | 417088.6866 | 417088.6866 | 417088.6866 | 417088.6866 | 417088.6866
Total (Real FY24$) | 417088.6866 | 417088.6866 | 417088.6866 | 417088.6866 | 417088.6866 | 2085443.4329 | Forecast capex subject to ongoing site risk assessments which will determine final year on year forecast
Original planning based on FY22$ with 2.5% inflation
Inflated and converted to Real FY24$
FY24$ Conversion | 1.025 | 1.0506 | 1.0769 | 1.1038 | 1.1314

## Asset Renewals
Asset Renewals (Minor Works) Capital Expenditure - Workstream Overview
Asset Renewal workstreams | FY25 | FY26 | FY27 | FY28 | FY29 | TOTAL | Commentary
Site Criticality 5 | 601268 | 1639206 | 478881 | 346465 | 1266966 | 4332786 | Asset renewal investment prioritised on assets with a Site Critical Infrastructure (CI) rating of 4 and 5
Site Criticality 4 | 1539 | 76571 | 35643 | 133939 | 106945 | 354637 | Asset renewal investment prioritised on assets with a Site Critical Infrastructure (CI) rating of 4 and 6
Condition Description 'Poor' | 336426 | 324719 | 0 | 62237 | 130267 | 853649 | Asset renewal investment prioritised on assets with an asset Condition Description rating of 'Poor'
0
Total (FY22$) | 939233 | 2040496 | 514524 | 542641 | 1504178 | 5541072
Inflation adjusted | 986722.9686 | 2143668.579 | 540539.6197 | 570078.2856 | 1580233.0001
FY24$ Real | 962656.5547 | 2040374.6142 | 501944.7725 | 516462.7904 | 1396695.7126
Adjusted for end of year $ | 979358.6459 | 2075775.1137 | 510653.5143 | 525423.4198 | 1420928.3832
Total (Real FY24$) | 979358.6459 | 2075775.1137 | 510653.5143 | 525423.4198 | 1420928.3832 | 5512139.0769 | Forecast capex subject to ongoing site risk assessments which will determine final year on year forecast
Original planning based on FY22$ with 2.5% inflation
Inflated and converted to Real FY24$
Refer to 'Asset Renewals - Data inputs' tab for key inputs to asset renewal (minor works) forecast
FY24$ Conversion | 1.025 | 1.0506 | 1.0769 | 1.1038 | 1.1314

## Major Capital Works
Major Capital Works Capital Expenditure - Workstream Overview
MCW workstream | FY25 | FY26 | FY27 | FY28 | FY29 | TOTAL | Commentary
Major Capital Works (FY22$) | 24558779.3 | 13590248.7825 | 13930005.0021 | 14278255.1271 | 14635211.5053 | 80992499.717 | Prioritised Major Capital Works forecast to be evenly spread over regulatory period
Inflation adjusted | 25800532.5784 | 14277405.7366 | 14634340.88 | 15000199.402 | 15375204.387
FY24$ Real | 25171251.296 | 13589440.3203 | 13589440.3203 | 13589440.3203 | 13589440.3203
Adjusted for end of year $ | 25607972.5059 | 13825217.1099 | 13825217.1099 | 13825217.1099 | 13825217.1099
Total (Real FY24$) | 25607972.5059 | 13825217.1099 | 13825217.1099 | 13825217.1099 | 13825217.1099 | 80908840.9456 | Forecast capex subject to ongoing site risk assessments which will determine final year on year forecast
Original planning based on FY22$ with 2.5% inflation
Inflated and converted to Real FY24$
FY24$ Conversion | 1.025 | 1.0506 | 1.0769 | 1.1038 | 1.1314