## DMIA Spend Summary
Essential Energy - DMIA Project Summary | [6 empty] | 2014-05-28 18:52
Total expenditure ie. Opex + capex
DMIA projected (based on latest information on project progress) | 2009/10 (Actual) | 2010/11 (Actual) | 2011/12 (Actual) | 2012/13 (Actual) | 2013/14 (Estimated) | Total 2009-14 | Status
Grid Interactive Inverter program 20kVA based |  |  |  | 58612.35 | 13495 | 72107.35 | In progress
Grid Interactive Inverter program 5kVA based |  |  |  | 120260.6 | 26945 | 147205.6 | In progress
Conservation Voltage Reduction through low voltage regulators |  |  |  | 142355.3 | 131013 | 273368.3 | In progress
Capacitor Package Development |  |  |  | 24763.36 | 28452 | 53215.36 | In progress
Energy and Network Capacity cost evaluation |  |  |  | 205023.96 | 0 | 205023.96 | Complete
Energy and Demand Audits |  |  |  | 43907.13 | 35855 | 79762.13 | In progress
Switched Reactors |  |  |  |  | 104879 | 104879 | In progress
Program Facilitation |  |  | 208564.5319 | 381677.24 | 185260 | 775501.7719 | In progress
Grid Interactive Inverters (60kVA Statcom) |  |  | 168964.6 |  |  | 168964.6 | Complete
Grid Interactive Inverters (20kVA Energy Storage) |  |  | 107219.11 |  |  | 107219.11 | Complete
Grid Interactive Inverters (60kVA, energy storage and solar) |  |  | 120976.8255 |  |  | 120976.8255 | Complete
Grid Interactive Inverters (20kVA statcom) |  |  | 99466.7345 |  |  | 99466.7345 | Complete
Integration of Solar, Wind and Storage Systems into Distribution Grids for Network Support - Study |  |  | 50000 |  |  | 50000 | Complete
Grid Interactive Inverter Project | 312885.3558 | 245014.46 |  |  |  | 557899.8158 | Complete
Total Essential Energy DMIA projected expenditure | 312885.3558 | 245014.46 | 755191.8019 | 976599.94 | 525899 | 2815590.5576

## DMIA Carryover calculation
Essential Energy - DMIA carryover calculation | [9 empty] | 2014-05-28 18:52
Total expenditure ie. Opex + capex
Expenditure Profile
| Year | Allowance | Expenditure | [5 empty] | Carry over amount
|  | Rt | At | Rt - At | (1+i)t | (1+i*)1 | (1+i*)2 | (1+i*)2 * (1+i*)1 | Ct |  | Annual
| 1 | 0.6 | 0.31289 | 0.28711 | 1.1002 | 1.612 | 1.1844 | 1.9092 | -0.49824 |  | -0.49824
| 2 | 0.6 | 0.24501 | 0.35499 | 1.2104 | 1.612 | 1.1844 | 1.9092 | -1.0582 |  | -0.55992
| 3 | 0.6 | 0.75519 | -0.15519 | 1.3317 | 1.612 | 1.1844 | 1.9092 | -0.83567 |  | 0.22249
| 4 | 0.6 | 0.9766 | -0.3766 | 1.4652 | 1.612 | 1.1844 | 1.9092 | -0.34493 |  | 0.49074
| 5 | 0.6 | 0.5259 | 0.074101 | 1.612 | 1.612 | 1.1844 | 1.9092 | -0.43269 |  | -0.087765
| Total | 3 | 2.8156 | [5 empty] | 2.5673
Indicative numbers
|  | Real | Nominal
| Wacc |  | 10.02%
| New wacc |  | 8.83%
Inflation
|  | NPV Neutral test (must equal zero) = |  |  | 0

## Notes
Source: | Demand management incentive scheme for the ACT and NSW 2009 distribution determinations
November 2008