## Run Extract (hidden)
[12 empty] | 1 | 2 | 3 | 4 | 5 | 6
[12 empty] | Option 1 | Option 2 | Option 3 | Option 4 | Option 5 | Option 6
[10 empty] | Address | Value Metric | Replace LV structures based on condition ($7M Repex model cap) | Replace LV structures based on condition (top down capital constraint) | Replace LV structures based on condition. | Replace LV structures upon failure and capitalise
[11 empty] | UARM - Environment and Community - Fire Risk | 4264617.1323 | 4896552.211 | 5182603.1558 | -9755576.3119
[11 empty] | UARM - Safety & People - Worker | 0 | 0 | 0 | 0
Notes | [10 empty] | UARM - Network Performance Risk | 2887096.3361 | 3314909.0591 | 3508562.223 | -6604412.0548
Need to open the .xlsm Investment Summary report from Copperleaf in the Trusted folder Save in the preferred location as an .xlsx Need to test environment - other and when two of the same value models have been selected with a different name | [10 empty] | UARM - Environment and Community - Other Risk | 0 | 0 | 0 | 0
[11 empty] | UARM - Financial Risk | 13336084.73 | 15312238.5841 | 16206761.9806 | -30507121.4631
[11 empty] | UARM - Safety & People - Public | 156812.0103 | 180048.582 | 190566.8234 | -358717.2121
[11 empty] | Terminal Value | 13872740.9921 | 11373787.2838 | 15859414.8739 | 33558036.1342
[11 empty] | Total Investment Cost | 28700117.5395 | 33039562.7025 | 34373805.5896 | 55550878.421
Options
| Option | 2025 | 2026 | 2027 | 2028 | 2029
| Baseline | 795214.17 | 910403.48 | 1037465.19 | 1176762.43 | 1328494.64
| Replace LV structures based on condition ($7M Repex model cap) | 713463.85 | 753035.55 | 795808.4 | 842424.57 | 891818.74
| Replace LV structures based on condition (top down capital constraint) | 656632.73 | 642608.18 | 635430.14 | 633545.01 | 636926.57
| Replace LV structures based on condition. | 642568.05 | 618246.18 | 599668.39 | 590500.87 | 586217.15
| Replace LV structures upon failure and capitalise | 4393977.79 | 4699294.53 | 4980010.45 | 5230574.5 | 5446840
Option Breakdown | [7 empty] | Folder and File Paths
| Option 1 |  |  |  |  | Greater 0 | (Multiple Items)
| Recommended Option - Value | [6 empty] | This File Path | \\TNAD.tasnetworks.com.au\user$\user_folders\BahramabadiM\My Documents\Trusted\InvestmentTemplate.xlsm
| Value Function Measure | Value | Value in % | Greater 0 |  | Row Labels | Sum of Value in % | Folder Path | H:\RPSAM\SAM\R24 IES\final draft\
Option 1 | UARM - Environment and Community - Fire Risk | 4264.6171 | 6.75% | 1 | K20 | Terminal Value | 21.94% | File Name | InvestmentSummary_R24_D_OH_RELSA_LV_Crossarms.xlsx
Option 1 | UARM - Safety & People - Worker | 0 | 0% | 1 | K21 | Total Investment Cost | 45.4% | File Path | H:\RPSAM\SAM\R24 IES\final draft\InvestmentSummary_R24_D_OH_RELSA_LV_Crossarms.xlsx
Option 1 | UARM - Network Performance Risk | 2887.0963 | 4.57% | 1 | K22 | UARM - Environment and Community - Fire Risk | 6.75%
Option 1 | UARM - Environment and Community - Other Risk | 0 | 0% | 1 | K23 | UARM - Environment and Community - Other Risk | 0%
Option 1 | UARM - Financial Risk | 13336.0847 | 21.1% | 1 | K24 | UARM - Financial Risk | 21.1%
Option 1 | UARM - Safety & People - Public | 156.812 | 0.25% | 1 | K25 | UARM - Network Performance Risk | 4.57%
Option 1 | Terminal Value | 13872.741 | 21.94% | 1 | K26 | UARM - Safety & People - Public | 0.25%
Option 1 | Total Investment Cost | -28700.1175 | 45.4% | 1 | K27 | UARM - Safety & People - Worker | 0%
Option 1 |  |  |  | 0 | K28
Option 1 |  |  |  | 0 | K29
Option 1 |  |  |  | 0 | K30 |  |  | 1 | InvestmentSummary_R24_D_ND_PRHVR_Augment_HV_Fdr_TRIP.xlsx
Option 1 |  |  |  | 0 | K31 |  |  | 2 | InvestmentSummary_R24_D_OH_REPOL_Basic Fleet Pole Replacement.xlsx
Option 1 |  |  |  | 0 | K32 |  |  | 3 | InvestmentSummary_R24_T_ND_AUGSB_W Coast Reliability Improvement.xlsx
Option 1 |  |  |  | 0 | K33 |  |  | 4 | InvestmentSummary_R24_T_ND_AUGSB_Upper Derwent 110 kV Losses.xlsx
| Total | 5817.2337 | 100% |  |  |  |  | 5 | InvestmentSummary_R24_D_OH_SIWES_Bird_Mitigation.xlsx
[8 empty] | 6 | InvestmentSummary_R24_D_SB_REGMS_GMS_Replacement of GMS.xlsx
[8 empty] | 7 | InvestmentSummary_R24_D_OH_REPOL_Complex Design.xlsx
Start | Option 1 |  |  |  |  | Greater 0 | 1 | 8 | InvestmentSummary_R24_D_PQ_PQTXV_Power_Quality_LV_Tformers.xlsx
| Value Function Measure | Value | Value in % | Greater 0 |  |  |  | 9 | InvestmentSummary_R24_D_ND_PQLVV_Aug_HV_LV_Conductor.xlsx
Option 1 | UARM - Environment and Community - Fire Risk | 4264.6171 | 6.75% | 1 | K20 | Row Labels | Sum of Value in % | 10 | InvestmentSummary_R24_D_CA_SOLCP_Crossover_Extension_OH.xlsx
Option 1 | UARM - Safety & People - Worker | 0 | 0% | 1 | K21 | Terminal Value | 21.94% | 11 | InvestmentSummary_R24_D_CI_SOIRR_Irrigation_Supply.xlsx
Option 1 | UARM - Network Performance Risk | 2887.0963 | 4.57% | 1 | K22 | Total Investment Cost | 45.4% | 12 | InvestmentSummary_R24_D_AMIPD_AM Improvement Program.xlsx
Option 1 | UARM - Environment and Community - Other Risk | 0 | 0% | 1 | K23 | UARM - Environment and Community - Fire Risk | 6.75% | 13 | InvestmentSummary_R24_D_CI_SOPOR_Permanent_Residence_OH.xlsx
Option 1 | UARM - Financial Risk | 13336.0847 | 21.1% | 1 | K24 | UARM - Environment and Community - Other Risk | 0% | 14 | InvestmentSummary_R24_D_CI_SUPOR_Permanent_Residence_UG.xlsx
Option 1 | UARM - Safety & People - Public | 156.812 | 0.25% | 1 | K25 | UARM - Financial Risk | 21.1% | 15 | InvestmentSummary_R24_D_CI_SOGSI_General_Supply_OH.xlsx
Option 1 | Terminal Value | 13872.741 | 21.94% | 1 | K26 | UARM - Network Performance Risk | 4.57% | 16 | InvestmentSummary_R24_D_CI_SUGSI_General_Supply_UG.xlsx
Option 1 | Total Investment Cost | -28700.1175 | 45.4% | 1 | K27 | UARM - Safety & People - Public | 0.25% | 17 | InvestmentSummary_R24_D_CI_SUSBD_Subdivision_UG.xlsx
Option 1 |  |  |  | 0 | K28 | UARM - Safety & People - Worker | 0% | 18 | InvestmentSummary_R24_D_CI_SOSDI_Subdivision_OH.xlsx
Option 1 |  |  |  | 0 | K29 |  |  | 19 | InvestmentSummary_R24_D_CI_SUSUB_Augment_Dist_Substations.xlsx
Option 1 |  |  |  | 0 | K30 |  |  | 20 | InvestmentSummary_R24_T_ND_LAEMP_SELA.xlsx
Option 1 |  |  |  | 0 | K31 |  |  | 21 | InvestmentSummary_R24_D_CA_DESDB_Prelim_Drive_by_Design.xlsx
Option 1 |  |  |  | 0 | K32 |  |  | 22 | InvestmentSummary_R24_D_CI_SUMPR_Major_Commercial.xlsx
Option 1 |  |  |  | 0 | K33 |  |  | 23 | InvestmentSummary_R24_D_CI_EASEN_Easements_Non_Major_Comm.xlsx
| Total | 5817.2337 | 100% |  |  |  |  | 24 | InvestmentSummary_R24_D_ND_PRHVR_Rosebery_Supply_Improve.xlsx
[8 empty] | 25 | InvestmentSummary_R24_D_ND_CAHVF_Huonville_Supply_Improvement.xlsx
[8 empty] | 26 | InvestmentSummary_R24_D_ND_CAHVF_Aug_Fdr_Network_Access.xlsx
[8 empty] | 27 | InvestmentSummary_R24_D_ND_PRHVR_Deloraine_Supply_Improve.xlsx
| Option 2 |  |  |  |  | Greater 0 | 1 | 28 | InvestmentSummary_R24_D_ND_CALVF_Augment_LV_Fdr_Capacity.xlsx
| Value Function Measure | Value | Value in % | Greater 0 |  |  |  | 29 | InvestmentSummary_R24_D_ND_CAHVF_Augment_HV_Fdr_Trunk.xlsx
Option 2 | UARM - Environment and Community - Fire Risk | 4896.5522 | 7.19% | 1 | K20 | Row Labels | Sum of Value in % | 30 | InvestmentSummary_R24_D_ND_CAHVF_Aug_Pole_Mtd_Regulator.xlsx
Option 2 | UARM - Safety & People - Worker | 0 | 0% | 1 | K21 | Terminal Value | 16.7% | 31 | InvestmentSummary_R24_D_ND_CAHVF_Aug_Grnd_Mtd_Regulator.xlsx
Option 2 | UARM - Network Performance Risk | 3314.9091 | 4.87% | 1 | K22 | Total Investment Cost | 48.5% | 32 | InvestmentSummary_R24_D_ND_CAHVF_22kV_Emu_Bay_Feeders.xlsx
Option 2 | UARM - Environment and Community - Other Risk | 0 | 0% | 1 | K23 | UARM - Environment and Community - Fire Risk | 7.19% | 33 | InvestmentSummary_R24_D_ND_CAHVF_Augment_HV_Fdr_Capacity.xlsx
Option 2 | UARM - Financial Risk | 15312.2386 | 22.48% | 1 | K24 | UARM - Environment and Community - Other Risk | 0% | 34 | InvestmentSummary_R24_D_ND_CAHVF_Aug_SubStd_Cond_Capacity.xlsx
Option 2 | UARM - Safety & People - Public | 180.0486 | 0.26% | 1 | K25 | UARM - Financial Risk | 22.48% | 35 | InvestmentSummary_R24_D_ND_LANDZ_LandAcq_ZoneSubs.xlsx
Option 2 | Terminal Value | 11373.7873 | 16.7% | 1 | K26 | UARM - Network Performance Risk | 4.87% | 36 | InvestmentSummary_R24_D_ND_CATXU_Aug_Dist_Sub.xlsx
Option 2 | Total Investment Cost | -33039.5627 | 48.5% | 1 | K27 | UARM - Safety & People - Public | 0.26% | 37
Option 2 |  |  |  | 0 | K28 | UARM - Safety & People - Worker | 0% | 38
Option 2 |  |  |  | 0 | K29 |  |  | 39
Option 2 |  |  |  | 0 | K30 |  |  | 40
Option 2 |  |  |  | 0 | K31 |  |  | 41
Option 2 |  |  |  | 0 | K32 |  |  | 42
Option 2 |  |  |  | 0 | K33 |  |  | 43
| Total | 2037.973 | 100%
| Option 3 |  |  |  |  | Greater 0 | 1
| Value Function Measure | Value | Value in % | Greater 0
Option 3 | UARM - Environment and Community - Fire Risk | 5182.6032 | 6.88% | 1 | K20 | Row Labels | Sum of Value in %
Option 3 | UARM - Safety & People - Worker | 0 | 0% | 1 | K21 | Terminal Value | 21.06%
Option 3 | UARM - Network Performance Risk | 3508.5622 | 4.66% | 1 | K22 | Total Investment Cost | 45.64%
Option 3 | UARM - Environment and Community - Other Risk | 0 | 0% | 1 | K23 | UARM - Environment and Community - Fire Risk | 6.88%
Option 3 | UARM - Financial Risk | 16206.762 | 21.52% | 1 | K24 | UARM - Environment and Community - Other Risk | 0%
Option 3 | UARM - Safety & People - Public | 190.5668 | 0.25% | 1 | K25 | UARM - Financial Risk | 21.52%
Option 3 | Terminal Value | 15859.4149 | 21.06% | 1 | K26 | UARM - Network Performance Risk | 4.66%
Option 3 | Total Investment Cost | -34373.8056 | 45.64% | 1 | K27 | UARM - Safety & People - Public | 0.25%
Option 3 |  |  |  | 0 | K28 | UARM - Safety & People - Worker | 0%
Option 3 |  |  |  | 0 | K29
Option 3 |  |  |  | 0 | K30
Option 3 |  |  |  | 0 | K31
Option 3 |  |  |  | 0 | K32
Option 3 |  |  |  | 0 | K33
| Total | 6574.1035 | 100%
| Option 4 |  |  |  |  | Greater 0 | 1
| Value Function Measure | Value | Value in % | Greater 0
Option 4 | UARM - Environment and Community - Fire Risk | -9755.5763 | 7.16% | 1 | K20 | Row Labels | Sum of Value in %
Option 4 | UARM - Safety & People - Worker | 0 | 0% | 1 | K21 | Terminal Value | 24.61%
Option 4 | UARM - Network Performance Risk | -6604.4121 | 4.84% | 1 | K22 | Total Investment Cost | 40.75%
Option 4 | UARM - Environment and Community - Other Risk | 0 | 0% | 1 | K23 | UARM - Environment and Community - Fire Risk | 7.16%
Option 4 | UARM - Financial Risk | -30507.1215 | 22.38% | 1 | K24 | UARM - Environment and Community - Other Risk | 0%
Option 4 | UARM - Safety & People - Public | -358.7172 | 0.26% | 1 | K25 | UARM - Financial Risk | 22.38%
Option 4 | Terminal Value | 33558.0361 | 24.61% | 1 | K26 | UARM - Network Performance Risk | 4.84%
Option 4 | Total Investment Cost | -55550.8784 | 40.75% | 1 | K27 | UARM - Safety & People - Public | 0.26%
Option 4 |  |  |  | 0 | K28 | UARM - Safety & People - Worker | 0%
Option 4 |  |  |  | 0 | K29
Option 4 |  |  |  | 0 | K30
Option 4 |  |  |  | 0 | K31
Option 4 |  |  |  | 0 | K32
Option 4 |  |  |  | 0 | K33
| Total | -69218.6693 | 100%
| Option 5 |  |  |  |  | Greater 0 | 0
| Value Function Measure | Value | Value in % | Greater 0
Option 5 |  |  |  | 0 | K20 | Row Labels | Sum of Value in %
Option 5 |  |  |  | 0 | K21 |  | 0%
Option 5 |  |  |  | 0 | K22
Option 5 |  |  |  | 0 | K23
Option 5 |  |  |  | 0 | K24
Option 5 |  |  |  | 0 | K25
Option 5 |  |  |  | 0 | K26
Option 5 |  |  |  | 0 | K27
Option 5 |  |  |  | 0 | K28
Option 5 |  |  |  | 0 | K29
Option 5 |  |  |  | 0 | K30
Option 5 |  |  |  | 0 | K31
Option 5 |  |  |  | 0 | K32
Option 5 |  |  |  | 0 | K33
| Total | 0 | 0%
| Option 6 |  |  |  |  | Greater 0 | 0
| Value Function Measure | Value | Value in % | Greater 0
Option 6 |  |  |  | 0 | K20 | Row Labels | Sum of Value in %
Option 6 |  |  |  | 0 | K21 |  | 0%
Option 6 |  |  |  | 0 | K22
Option 6 |  |  |  | 0 | K23
Option 6 |  |  |  | 0 | K24
Option 6 |  |  |  | 0 | K25
Option 6 |  |  |  | 0 | K26
Option 6 |  |  |  | 0 | K27
Option 6 |  |  |  | 0 | K28
Option 6 |  |  |  | 0 | K29
Option 6 |  |  |  | 0 | K30
Option 6 |  |  |  | 0 | K31
Option 6 |  |  |  | 0 | K32
Option 6 |  |  |  | 0 | K33
| Total | 0 | 0%

## Summary
Investment Evaluation Summary |  |  |  | Investment Code |  | Report Start Year |  | NPV Period | Base Fiscal Year | Currency Scale
|  |  |  | PRJ000617 |  | 2025 |  | 25 | FY23 | Literal
|  |  |  | Investment Name | [5 empty] | Scenario
|  |  |  | R24_D_OH_RELSA_LV_Crossarms | [5 empty] | Approved
Value Function |  | TasNetworks Value Function |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Investment Description
Description |  | To manage asset risk associated with low voltage crossarms and other low voltage pole top structures. | [9 empty] | TRUE
Functional Area |  | RELSA |  |  | Department |  |  | Asset Strategy
Works Initiator |  |  |  |  | Portfolio |  |  | Dx - Renewal
Investment Category |  | Standard Control - Reliability & Quality Maintained |  |  | Needs Item Reference
Investment Type |  | Network Project |  |  | Document No.
Investment Stage |  | Gate 2 – Investment Evaluation Summary |  |  | Project Zone Location
PPM ID |  |  |  |  | Regulatory Test Required |  |  | No
Investment Summary
Problem Definition |  | TasNetworks accounting data shows that the cost to replace a crossarm following failure is 179 per cent of the cost of doing the same job in a planned way. This is due to the: - high cost of on-call labour compared to day-rates; - unplanned crossarm replacements aren’t optimised with other jobs (where planned work is combined to reduce travel, traffic management, site supervision etc); and - materials can’t be organised in advance and must be sourced ad-hoc. Outage duration and frequency (since many crossarms can be replaced live) is also significantly higher for unplanned crossarm replacement. There are also risks associated with allowing these assets to fail such as: - risk of injury to public from electric shock or mechanical injury by a fallen LV conductor; - risk to property including agricultural livestock contacting low hanging LV conductors (there is approximately one event per year where a fallen LV conductor causes the death of a domestic animal); and - although rare with the current failure rate, TasNetworks has recently recorded a ground fire start from failed crossarms causing conductor clashing. | [9 empty] | TRUE
Recommendation |  | Option 1, Replace LV structures based on condition ($7M Repex model cap) is recommended for approval as it best satisfies the customer and business needs. | [9 empty] | TRUE
Alternative Spend Profile
Name |  | Status | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV | Alternative Start Date
Replace LV structures based on condition ($7M Repex model cap) |  | Recommended | 1335386.12 | 1360948.8 | 1388579.37 | 1418692.66 | 1450600.5 | 6954207.45 | 40433215.69 | -8055507.33 | 4547400%
Replace LV structures based on condition (top down capital constraint) |  | Candidate | 2175920 | 2162672 | 2158716 | 2162202 | 2170597 | 10830107 | 45792918 | -9335814.27 | 4547400%
Replace LV structures based on condition. |  | Candidate | 2375433.8 | 2375433.8 | 2352214.35 | 2335779.49 | 2331566.26 | 11770427.7 | 47356283.79 | -9285311.41 | 4547400%
Replace LV structures upon failure and capitalise |  | Candidate | 518798.2 | 637875.5 | 780168.9 | 949432.2 | 1149905 | 4036179.8 | 87316840.8 | -102776705.46 | 4547400%
0
0
Leader Endorsement
Name |  |  | Governance |  | Signature |  |  | Comments |  |  | Date
|  |  | Submission | [7 empty] | 4486800%
|  |  | Endorsement | [7 empty] | 4486800%
|  |  | Approval | [7 empty] | 4486800%
Investment Attachments
Date | Attachment Name |  | Description

## Investment Overview
Investment Evaluation Summary |  | Copperleaf Investment Code |  | Report Start Year | NPV Period | Base Fiscal Year | Currency Scale
|  | PRJ000617 |  | 2025 | 25 | FY23 | Literal
|  | Investment Name |  |  |  |  | Scenario
|  | R24_D_OH_RELSA_LV_Crossarms |  |  |  |  | Approved
Value Function | TasNetworks Value Function | Version |  | 0.1 | Date |  | 2022-11-03
Functional Area | RELSA |  | Department |  | Asset Strategy
Works Initiator |  |  | Portfolio |  | Dx - Renewal
Investment Category | Standard Control - Reliability & Quality Maintained |  | Needs Item Reference
Investment Type | Network Project |  | Document No.
Investment Stage | Gate 2 – Investment Evaluation Summary |  | Project Zone Location
PPM ID |  |  | Regulatory Test Required |  | No
Investment Overview
01. Overview | Background |  | Low voltage (LV) crossarms are used to connect the insulators which hold the LV open wire conductors to the support structures (poles) and provide adequate clearance between the conductors and to earth. TasNetworks' LV crossarms are predominantly manufactured from sawn timber as this material is cost effective and offers insulation qualities to allow live line activities to be performed safely. There are approximately 97,000 wooden LV crossarms in the distribution network. Wooden LV crossarms have an asset life of approximately 30 years. TasNetworks also has fibreglass (FRP) crossarms as part of the LV crossarm fleet. Fibreglass crossarms currently make up a small percentage of the LV crossarm population, with approximately 4.3% of the total number installed. Fibreglass (FRP) crossarms are included in this investment evaluation summary (IES), as the preferred replacement material to the earlier sawn timber LV cross arms. The transition to replacement with FRP crossarms has occurred in the last 5 years due to their longer service life and are unlikely to require any replacements within the next regulatory period. LV aerial bundled conductor (LVABC) is the preferred alternative design technology to LV open wire. However, it is only used to replace LV open wire configurations where a significant amount of the network is being replaced such that a design change is economically viable. Otherwise, the cost to install outweighs the benefits to transition to aerial bundled conductor. Hence, TasNetworks will be required to continue replacement of LV crossarms to ensure adequate isolation of the conductor, until alternative technologies are cost effective. TasNetworks does not keep detailed records of its pole top hardware (including LV crossarms). However, as LV pole top hardware is installed new whenever a pole is replaced, and the asset life is known, the age distribution can be calculated (refer asset management plan). Age, design, construction methods, fault currents, and environmental considerations such as proximity to coastlines will all impact the service life of the pole top components including crossarms. Crossarm failures results in a customer outages, as well as the bushfire, property and safety risks associated with downed live conductors, until they can be replaced. Crossarm condition can be determined visually by looking for splits, general degradation, and signs of rot. They are inspected during 5-yearly ground-based pole inspections and aerial pole-top imagery. The required replacement rate to maintain the network at a steady condition, without increasing the failure rate, can be calculated by looking at the total population of crossarm structures, historic crossarm replacement rates, and the expected crossarm life. This number is the adjusted with the volume of LVABC installed (where open wire is removed) and the incidental replacement of crossarms on other programs (e.g. pole replacements). The final number is cross-checked against the number of incoming notifications and historical replacement volumes to confirm it reflects a sustaining replacement volume. Incoming notifications are audited to ensure the asset inspectors are raising defects on the right asset conditions and some failed crossarms are investigated to drive program improvements. This is a continuation of an existing program to proactively rectify wooden LV crossarm defects and failures in the overhead system. A condition based replacement strategy is appropriate as the condition of timber crossarms can be easily visually assessed. |  |  |  |  | TRUE
| Problem Definition |  | TasNetworks accounting data shows that the cost to replace a crossarm following failure is 179 per cent of the cost of doing the same job in a planned way. This is due to the: - high cost of on-call labour compared to day-rates; - unplanned crossarm replacements aren’t optimised with other jobs (where planned work is combined to reduce travel, traffic management, site supervision etc); and - materials can’t be organised in advance and must be sourced ad-hoc. Outage duration and frequency (since many crossarms can be replaced live) is also significantly higher for unplanned crossarm replacement. There are also risks associated with allowing these assets to fail such as: - risk of injury to public from electric shock or mechanical injury by a fallen LV conductor; - risk to property including agricultural livestock contacting low hanging LV conductors (there is approximately one event per year where a fallen LV conductor causes the death of a domestic animal); and - although rare with the current failure rate, TasNetworks has recently recorded a ground fire start from failed crossarms causing conductor clashing. |  |  |  |  | FALSE
02. Customer Needs and Impact | Customer Needs and impact |  | TasNetworks has a customer and stakeholder engagement strategy to inform the existing program of work and the upcoming revenue submission. The feedback obtained informs the approach taken by TasNetworks to align our investments with customer needs and impacts. Customer needs addressed by this investment include: - affordability; - supply reliability and safety of the current network; - resilience to future impacts including climate change; and - investment in future networks to unlock community benefits in renewable energy products and services. |  |  |  |  | TRUE

## Objectives and Analysis
Investment Evaluation Summary |  | Copperleaf Investment Code |  | Report Start Year | NPV Period | Base Fiscal Year | Currency Scale
|  | PRJ000617 |  | 2025 | 25 | FY23 | Literal
|  | Investment Name |  |  |  |  | Scenario
|  | R24_D_OH_RELSA_LV_Crossarms |  |  |  |  | Approved
Value Function | TasNetworks Value Function | Version |  | 0.1 | Date |  | 2022-11-03
Functional Area | RELSA |  | Department |  | Asset Strategy
Works Initiator |  |  | Portfolio |  | Dx - Renewal
Investment Category | Standard Control - Reliability & Quality Maintained |  | Needs Item Reference
Investment Type | Network Project |  | Document No.
Investment Stage | Gate 2 – Investment Evaluation Summary |  | Project Zone Location
PPM ID |  |  | Regulatory Test Required |  | No
Objectives and Analysis
03. Business Performance Objectives | Safety and Wellbeing |  | TasNetworks Business Plan 2020-21: Our services reflect our customers’ needs and expectations. Investment will reduce the likelihood of in-service failure and therefore likelihood of incident. |  |  |  |  | TRUE
| Our Customers |  | TasNetworks Business Plan 2020-21: Our services reflect our customers’ needs and expectations. The proposed plan is based around a model of constant and sustainable maintenance spend on the network. Investment will reduce the likelihood of in-service failure and customer outage. |  |  |  |  | FALSE
| Our People |  | TasNetworks' Corporate plan: Employee engagement. Investment will help our employees will feel that our asset management practices sufficiently manage our risks and that we are empowered to have a positive effect on our risks. |  |  |  |  | FALSE
| Our Business - Sustained Cost Management |  | TasNetworks Business Plan: Define and efficiently deliver our work. The better the ratio between planned, condition based replacements and unplanned replacements, the more efficient and cost effective the program of work will be. Investment reduces our total cost when compared to run-to-failure. |  |  |  |  | FALSE
| Our Business - Network Service |  | TasNetworks Business Plan 2020-21: Our services reflect our customers’ needs and expectations. Investment would reduce unserved energy by 44MWh when compared to run-to-failure. It’s more likely that some residual failures will continue to occur. |  |  |  |  | FALSE
04. Business Risks | Death or Injury (Employee) | [6 empty] | FALSE
| Death or Injury (Public) |  | Public contact with live conductors directly or indirectly after they fall to ground or reduce their clearance to ground following crossarm failure. |  |  |  |  | FALSE
| Sustainable and Predictable Pricing |  | If a sustainable proactive program is not implemented, increased failure rates will result in a large increase in the program of work and ultimately increase power price to customer. |  |  |  |  | FALSE
| Widespread Power Disruption |  | 80 failures occur per year currently. A program aims to reduce this number and limit risk exposure. A run-to-failure strategy would increase this failure rate and risk exposure approximately ten-fold. |  |  |  |  | FALSE
| Bushfire Start |  | TasNetworks has recorded a ground fire start from a poor condition LV crossarm snapping and the conductors clashing. TasNetworks data suggests this is unlikely for the current failure rate. |  |  |  |  | FALSE
| Loss of Major Industrial | [6 empty] | FALSE
| Customer Focus |  | Customers have an expectation of consistent and reliable power supply which these assets provide. |  |  |  |  | FALSE
| Business Continuity Management | [6 empty] | FALSE
| Cyber Security | [6 empty] | FALSE
| Private Assets | [6 empty] | FALSE
Energy Policy and Regulation
Project Marinus (D&A)
Tasmanian Power System Complexity
| Emerging Complexity of the NEM | [6 empty] | FALSE
05. Strategic Objectives | Strategic Objectives |  | The strategic objective is to manage the risk to customers by developing a risk based strategic plan. This includes a condition/risk-based approach to manage the assets to maintain reliability and security of the network and effectively manage the safety risk associated with maintaining the asset. |  |  |  |  | FALSE
| Strategic Document #1 |  | Towards 2030 |  |  |  |  | FALSE
| Strategic Document #2 |  | Balanced Business Plan 2021-22 |  |  |  |  | FALSE
| Strategic Document #3 |  | NER 5A Distribution |  |  |  |  | FALSE
| Strategic Document #4 |  | Poletop Structures Asset Management Plan - R0002286926 |  |  |  |  | FALSE
| Strategic Document #5 | [6 empty] | FALSE
06. Project Objectives | Project Objectives |  | The implemented program will aim to avoid the high cost of asset replacement under unplanned longer duration outages to the customer and to avoid unnecessary safety risk exposure. LV crossarm failure rates, incidents, and fault capitalisation will continue to be tracked as key performance indicators of the program. LV crossarm replacement is standard control capex. |  |  |  |  | FALSE
07. Options Analysis | Benchmarking |  | All other Australian network service providers conduct planned crossarm replacement programs and generally favour fibreglass crossarms. Pole top structures are included in AER RIN reporting and REPEX modelling. |  |  |  |  | TRUE
| Expert Findings |  | Improvements to inspection practices have been made based on findings from engineering investigations into high consequence failure and consultation with other network service providers. |  |  |  |  | FALSE
08. Investment Timing | Investment Timing |  | The program will continue for the whole regulatory period and beyond at a constant but slightly decreasing rate of approximately 700 structures per year (it will be adjusted based on network condition). The replacement rate will slowly reduce in the long term since: - the population of open wire LV will slowly reduce in the network at a rate of approximately 1% of the population per year as more LV ABC is installed; and - eventually timber crossarms will be replaced with FRP material, which have a longer MTBF. FRP crossarms are being installed at a rate of approximately 2.5% of the population per year and forecast to not impact replacement rate until 2050. |  |  |  |  | TRUE
09. Expected Outcomes and Benefits | Expected Outcomes and Benefits |  | The benefits to TasNetworks from implementation of the selected option will be: - improved unit rate for LV crossarm replacements as in-service failures decrease; - decrease in risk to public, property, reliability and fire starts; and - decrease in number of customer outages and their duration. |  |  |  |  | TRUE
10. Assumptions | Assumptions |  | - Assume that the time to inspect crossarms is negligible compared to pole testing and other aerial asset inspection - therefore maintenance inspection cost of pole inspections not included in this IES. - Unserved energy was determined from TasNetworks outage impact recording system and SAP. Events where object part was listed as LV crossarm or brace were counted. - Accounting data from planned and failed-in-service jobs were compared from the TasNetworks asset management system. This comparison found that the cost of unplanned jobs are 179% compared to planned replacement due to the high cost of on-call labour and other inefficiencies. - It is assumed that unserved energy increases proportionally to the number of unplanned failures. - Pole-top structures are not tracked as separate assets but the failure distribution can be determined by using the pole age at the time of pole-top structure failure since it is assumed the structure was installed at the same time as the pole. - Only TasNetworks assets were considered in calculation as private LV crossarms are not considered as part of this IES. - The required replacement rate to maintain the network at a steady condition without increasing the failure rate can be calculated by looking at the total population of cross-arm structures and the expected MTBF. This number is the adjusted with the volume of LVABC installed (where open wire is removed) and the incidental replacement of cross-arms on other programs (e.g. pole replacements). |  |  |  |  | TRUE
11. Regulatory Considerations | Regulatory Investment Test |  | A RIT-D is not required because this is a high volume, low cost, program with separate sites where assets have failed a serviceability test during inspection.
| Meet or manage the expected demand for Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | No
| Comply with all applicable regulatory obligations associated with the provision of Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | No
| Maintain the quality, reliability and security of supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | No
| Maintain the reliability and security of the system through the supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | Yes
| Maintain the safety of the system through the supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). |  | Yes
12. Recommendation | Recommendation |  | Option 1, Replace LV structures based on condition ($7M Repex model cap) is recommended for approval as it best satisfies the customer and business needs. |  |  |  |  | TRUE

## Economic Analysis
alternative
| Investment Evaluation Summary |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[5 empty] | PRJ000617 |  | 2025 |  | 25 | FY23 | Literal
[5 empty] | Investment Name | [5 empty] | Scenario
[5 empty] | R24_D_OH_RELSA_LV_Crossarms | [5 empty] | Approved
autofit | Value Function |  |  | TasNetworks Value Function | Version |  | 0.1 |  | Date |  | 2022-11-03
Economic Analysis
| Parameter |  |  |  | Value | Unit | Source of Values
75679 | NPV Period |  |  |  | 25 | Years | TasNetworks requirement
autofit | First Fiscal Year of Forecast |  |  |  | FY23 | - | TasNetworks requirement
| Weighted Average Cost of Capital (WACC) |  |  |  | 2.82 | % | 2019-24 Revenue determination and ISP 2022 draft data
| Voluntary load shedding assumed? |  |  |  | No | - | N/A
| Reduction in system losses considered? |  |  |  | No | - | N/A
| Value of Customer Reliability applied |  |  | Very large business customer - Services | 10.93 | $/kWh | AER - Values of Customer Reliability - Annual adjustment summary - December 2021
|  |  |  | Residential | 17.08 | $/kWh
|  |  |  | Very large business customer - Metals | 20.6 | $/kWh
|  |  |  | Very large business customer - Transmission | 27.43 | $/kWh
|  |  |  | Very large business customer - Mines | 36.47 | $/kWh
|  |  |  | Business customer - Agricultural | 39.28 | $/kWh
|  |  |  | Business customer - Commercial | 46.18 | $/kWh
|  |  |  | Very large business customer - Distribution | 58.8 | $/kWh
|  |  |  | Business customer - Industrial | 66.16 | $/kWh
autofit |  |  |  | Very large business customer - Industrial | 122.39 | $/kWh
Sensitivity to Project Timing
|  | 1 | Navigate to Copperleaf Portfolio and search for your Investment
|  | 2 | Navigate to the Value Comparison Page for your Investment through the breadcrumb menu
|  | 3 | Once on the Value Comparison Page, select "Value by Start Date" in the drop-down menu in the top-left corner of the page
|  | 4 | This screen will show the value change over time for each option in your investment
|  | 5 | With the snipping tool on your PC, take a screenshot of the chart and copy + paste it in this section of the report
Options Considered
| Options Summary |  |  |  | R24 Expenditure ($M) | NPV ($M) | Preferred Option | Reason for selection/rejection
| Replace LV structures based on condition ($7M Repex model cap) |  |  |  | 6.9542 | -8.0555 | Yes | This option has been selected following portfolio optimisation to assess risk and expenditure across the whole asset fleet. This option manages asset risk and network performance within an acceptable range compared to other asset portfolios.
| Replace LV structures based on condition (top down capital constraint) |  |  |  | 10.8301 | -9.3358 | No | This option has been rejected following portfolio optimisation to assess risk and expenditure across the whole asset fleet. This option manages asset risk and network performance within an acceptable range compared to other asset portfolios but has a lower NPV compared to the selected option.
| Replace LV structures based on condition. |  |  |  | 11.7704 | -9.2853 | No | Whilst this option has the most positive NPV outcome, it has been rejected following portfolio optimisation to assess risk and expenditure across the whole asset fleet.
| Replace LV structures upon failure and capitalise |  |  |  | 4.0362 | -102.7767 | No | This option has been rejected as it does not manage risk nor network performance to an acceptable level and does not meet the business objectives. It requires the highest capital expenditure over the longer term with the lowest NPV outcome.
0
0
NPV Components

## Needs Assessment (hidden)
Needs Assessment Form |  | Copperleaf Investment Code |  | Report Start Year | NPV Period | Base Fiscal Year | Currency Scale
|  | PRJ000617 |  | 2025 | 25 | FY23 | Literal
|  | Investment Name |  |  |  |  | Scenario
|  | R24_D_OH_RELSA_LV_Crossarms |  |  |  |  | Approved
Value Function | TasNetworks Value Function | Version |  | 0.1 | Date |  | 2022-11-03
Functional Area | RELSA |  | Department |  | Asset Strategy
Works Initiator |  |  | Portfolio |  | Dx - Renewal
Investment Category | Standard Control - Reliability & Quality Maintained |  | Needs Item Reference
Investment Type | Network Project |  | Document No.
Investment Stage | Gate 2 – Investment Evaluation Summary |  | Project Zone Location
PPM ID |  |  | Regulatory Test Required |  | No
Investment Overview
01. Overview | Background |  | Low voltage (LV) crossarms are used to connect the insulators which hold the LV open wire conductors to the support structures (poles) and provide adequate clearance between the conductors and to earth. TasNetworks' LV crossarms are predominantly manufactured from sawn timber as this material is cost effective and offers insulation qualities to allow live line activities to be performed safely. There are approximately 97,000 wooden LV crossarms in the distribution network. Wooden LV crossarms have an asset life of approximately 30 years. TasNetworks also has fibreglass (FRP) crossarms as part of the LV crossarm fleet. Fibreglass crossarms currently make up a small percentage of the LV crossarm population, with approximately 4.3% of the total number installed. Fibreglass (FRP) crossarms are included in this investment evaluation summary (IES), as the preferred replacement material to the earlier sawn timber LV cross arms. The transition to replacement with FRP crossarms has occurred in the last 5 years due to their longer service life and are unlikely to require any replacements within the next regulatory period. LV aerial bundled conductor (LVABC) is the preferred alternative design technology to LV open wire. However, it is only used to replace LV open wire configurations where a significant amount of the network is being replaced such that a design change is economically viable. Otherwise, the cost to install outweighs the benefits to transition to aerial bundled conductor. Hence, TasNetworks will be required to continue replacement of LV crossarms to ensure adequate isolation of the conductor, until alternative technologies are cost effective. TasNetworks does not keep detailed records of its pole top hardware (including LV crossarms). However, as LV pole top hardware is installed new whenever a pole is replaced, and the asset life is known, the age distribution can be calculated (refer asset management plan). Age, design, construction methods, fault currents, and environmental considerations such as proximity to coastlines will all impact the service life of the pole top components including crossarms. Crossarm failures results in a customer outages, as well as the bushfire, property and safety risks associated with downed live conductors, until they can be replaced. Crossarm condition can be determined visually by looking for splits, general degradation, and signs of rot. They are inspected during 5-yearly ground-based pole inspections and aerial pole-top imagery. The required replacement rate to maintain the network at a steady condition, without increasing the failure rate, can be calculated by looking at the total population of crossarm structures, historic crossarm replacement rates, and the expected crossarm life. This number is the adjusted with the volume of LVABC installed (where open wire is removed) and the incidental replacement of crossarms on other programs (e.g. pole replacements). The final number is cross-checked against the number of incoming notifications and historical replacement volumes to confirm it reflects a sustaining replacement volume. Incoming notifications are audited to ensure the asset inspectors are raising defects on the right asset conditions and some failed crossarms are investigated to drive program improvements. This is a continuation of an existing program to proactively rectify wooden LV crossarm defects and failures in the overhead system. A condition based replacement strategy is appropriate as the condition of timber crossarms can be easily visually assessed. |  |  |  |  | TRUE
| Problem Definition |  | TasNetworks accounting data shows that the cost to replace a crossarm following failure is 179 per cent of the cost of doing the same job in a planned way. This is due to the: - high cost of on-call labour compared to day-rates; - unplanned crossarm replacements aren’t optimised with other jobs (where planned work is combined to reduce travel, traffic management, site supervision etc); and - materials can’t be organised in advance and must be sourced ad-hoc. Outage duration and frequency (since many crossarms can be replaced live) is also significantly higher for unplanned crossarm replacement. There are also risks associated with allowing these assets to fail such as: - risk of injury to public from electric shock or mechanical injury by a fallen LV conductor; - risk to property including agricultural livestock contacting low hanging LV conductors (there is approximately one event per year where a fallen LV conductor causes the death of a domestic animal); and - although rare with the current failure rate, TasNetworks has recently recorded a ground fire start from failed crossarms causing conductor clashing. |  |  |  |  | FALSE
02. Customer Needs and Impact | Customer Needs and impact |  | TasNetworks has a customer and stakeholder engagement strategy to inform the existing program of work and the upcoming revenue submission. The feedback obtained informs the approach taken by TasNetworks to align our investments with customer needs and impacts. Customer needs addressed by this investment include: - affordability; - supply reliability and safety of the current network; - resilience to future impacts including climate change; and - investment in future networks to unlock community benefits in renewable energy products and services. |  |  |  |  | TRUE
03. Business Objectives | Business Objectives
04. Project Objectives | Project Objectives |  | The implemented program will aim to avoid the high cost of asset replacement under unplanned longer duration outages to the customer and to avoid unnecessary safety risk exposure. LV crossarm failure rates, incidents, and fault capitalisation will continue to be tracked as key performance indicators of the program. LV crossarm replacement is standard control capex. |  |  |  |  | FALSE
05. Risk Objective | Risk if not progressed | [6 empty] | TRUE
06. Investment Timing | Investment Timing |  | The program will continue for the whole regulatory period and beyond at a constant but slightly decreasing rate of approximately 700 structures per year (it will be adjusted based on network condition). The replacement rate will slowly reduce in the long term since: - the population of open wire LV will slowly reduce in the network at a rate of approximately 1% of the population per year as more LV ABC is installed; and - eventually timber crossarms will be replaced with FRP material, which have a longer MTBF. FRP crossarms are being installed at a rate of approximately 2.5% of the population per year and forecast to not impact replacement rate until 2050. |  |  |  |  | TRUE
07. Business Consulatation | Business Consulatation | [6 empty] | TRUE

## Option 1
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000617 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_D_OH_RELSA_LV_Crossarms | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name |  | Replace LV structures based on condition ($7M Repex model cap)
autofit | Description |  | Proactive asset renewal program to replace LV structures based on condition and limited by the $7M Repex model cap.
autofit | Alternative Status |  | Recommended
autofit | Alternative Start Date |  | 4547400%
| Reason for selection/rejection |  | This option has been selected following portfolio optimisation to assess risk and expenditure across the whole asset fleet. This option manages asset risk and network performance within an acceptable range compared to other asset portfolios.
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
| Replace LV structures based on condition ($7M Repex model cap) |  | Capex |  |  | 1335386.12 | 1360948.8 | 1388579.37 | 1418692.66 | 1450600.5 | 6954207.45 | 40433215.69 | -8055507.33
|  |  | Opex |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | UARM - Environment and Community - Fire Risk |  |  | 4264.6171 | 6.75%
[9 empty] | UARM - Safety & People - Worker |  |  | 0 | 0%
[9 empty] | UARM - Network Performance Risk |  |  | 2887.0963 | 4.57%
[9 empty] | UARM - Environment and Community - Other Risk |  |  | 0 | 0%
[9 empty] | UARM - Financial Risk |  |  | 13336.0847 | 21.1%
[9 empty] | UARM - Safety & People - Public |  |  | 156.812 | 0.25%
[9 empty] | Terminal Value |  |  | 13872.741 | 21.94%
[9 empty] | Total Investment Cost |  |  | -28700.1175 | 45.4%
[9 empty] | Total |  |  | 5817.2337
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE | Investment Cost | CAPEX Cost |  | Outcome | 2024 | 0 | Dollar | 1335386.12 | 1360948.8 | 1388579.37 | 1418692.66 | 1450600.5
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE | Investment Cost | Total Investment Cost |  | Outcome | 2024 | -28700.1175 | Dollar | 1335386.12 | 1360948.8 | 1388579.37 | 1418692.66 | 1450600.5
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE | Terminal Value | Terminal Value |  | Outcome | 2048 | 13872.741 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Baseline |  | 0 | Dollar | 164269.7 | 188064.69 | 214312.2 | 243087.24 | 274431
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Outcome | 2024 | 4264.6171 | Dollar | 147382.3 | 155556.74 | 164392.45 | 174022.09 | 184225.59
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Baseline |  | 0 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Outcome | 2024 | 0 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE | UARM - PA to Investment | UARM - Network Performance Risk |  | Baseline |  | 0 | Dollar | 111208.68 | 127317.62 | 145086.87 | 164567.24 | 185786.6
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE | UARM - PA to Investment | UARM - Network Performance Risk |  | Outcome | 2024 | 2887.0963 | Dollar | 99776.11 | 105310.11 | 111291.79 | 117810.94 | 124718.59
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE | UARM - PA to Investment | UARM - Environment and Community - Other Risk |  | Baseline |  | 0 | Dollar | 0 | 0 | 0 | 0 | 0
| UARM - PA to Investment | UARM - Environment and Community - Other Risk |  | Outcome | 2024 | 0 | Dollar | 0 | 0 | 0 | 0 | 0
| UARM - PA to Investment | UARM - Financial Risk |  | Baseline |  | 0 | Dollar | 513695.51 | 588105.94 | 670185.76 | 760169.52 | 858186.08
| UARM - PA to Investment | UARM - Financial Risk |  | Outcome | 2024 | 13336.0847 | Dollar | 460886.12 | 486448.8 | 514079.37 | 544192.66 | 576100.5
| UARM - PA to Investment | UARM - Safety & People - Public |  | Baseline |  | 0 | Dollar | 6040.28 | 6915.23 | 7880.36 | 8938.43 | 10090.96
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE | UARM - PA to Investment | UARM - Safety & People - Public |  | Outcome | 2024 | 156.812 | Dollar | 5419.32 | 5719.9 | 6044.79 | 6398.88 | 6774.06
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 795214.17 | 910403.48 | 1037465.19 | 1176762.43 | 1328494.64
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 713463.85 | 753035.55 | 795808.4 | 842424.57 | 891818.74
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 2
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000617 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_D_OH_RELSA_LV_Crossarms | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name |  | Replace LV structures based on condition (top down capital constraint)
autofit | Description |  | Proactive asset renewal program to replace LV structures based on condition and limited by a top down expenditure constraint.
autofit | Alternative Status |  | Candidate
autofit | Alternative Start Date |  | 4547400%
| Reason for selection/rejection |  | This option has been rejected following portfolio optimisation to assess risk and expenditure across the whole asset fleet. This option manages asset risk and network performance within an acceptable range compared to other asset portfolios but has a lower NPV compared to the selected option.
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
| Replace LV structures based on condition (top down capital constraint) |  | Capex |  |  | 1699500 | 1699500 | 1699500 | 1699500 | 1699500 | 8497500 | 45792918 | -9335814.27
|  |  | Opex |  |  | 476420 | 463172 | 459216 | 462702 | 471097 | 2332607
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | UARM - Environment and Community - Fire Risk |  |  | 4896.5522 | 7.19%
[9 empty] | UARM - Safety & People - Worker |  |  | 0 | 0%
[9 empty] | UARM - Network Performance Risk |  |  | 3314.9091 | 4.87%
[9 empty] | UARM - Environment and Community - Other Risk |  |  | 0 | 0%
[9 empty] | UARM - Financial Risk |  |  | 15312.2386 | 22.48%
[9 empty] | UARM - Safety & People - Public |  |  | 180.0486 | 0.26%
[9 empty] | Terminal Value |  |  | 11373.7873 | 16.7%
[9 empty] | Total Investment Cost |  |  | -33039.5627 | 48.5%
[9 empty] | Total |  |  | 2037.973
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE | Investment Cost | CAPEX Cost |  | Outcome | 2024 | 0 | Dollar | 1699500 | 1699500 | 1699500 | 1699500 | 1699500
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE | Investment Cost | OPEX Cost |  | Outcome | 2024 | 0 | Dollar | 476420 | 463172 | 459216 | 462702 | 471097
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE | Investment Cost | Total Investment Cost |  | Outcome | 2024 | -33039.5627 | Dollar | 2175920 | 2162672 | 2158716 | 2162202 | 2170597
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE | Terminal Value | Terminal Value |  | Outcome | 2048 | 11373.7873 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Baseline |  | 0 | Dollar | 164269.7 | 188064.69 | 214312.2 | 243087.24 | 274431
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Outcome | 2024 | 4896.5522 | Dollar | 135642.53 | 132745.44 | 131262.65 | 130873.23 | 131571.77
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Baseline |  | 0 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Outcome | 2024 | 0 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE | UARM - PA to Investment | UARM - Network Performance Risk |  | Baseline |  | 0 | Dollar | 111208.68 | 127317.62 | 145086.87 | 164567.24 | 185786.6
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE | UARM - PA to Investment | UARM - Network Performance Risk |  | Outcome | 2024 | 3314.9091 | Dollar | 91828.42 | 89867.12 | 88863.29 | 88599.66 | 89072.56
| UARM - PA to Investment | UARM - Environment and Community - Other Risk |  | Baseline |  | 0 | Dollar | 0 | 0 | 0 | 0 | 0
| UARM - PA to Investment | UARM - Environment and Community - Other Risk |  | Outcome | 2024 | 0 | Dollar | 0 | 0 | 0 | 0 | 0
| UARM - PA to Investment | UARM - Financial Risk |  | Baseline |  | 0 | Dollar | 513695.51 | 588105.94 | 670185.76 | 760169.52 | 858186.08
| UARM - PA to Investment | UARM - Financial Risk |  | Outcome | 2024 | 15312.2386 | Dollar | 424174.14 | 415114.51 | 410477.61 | 409259.85 | 411444.28
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE | UARM - PA to Investment | UARM - Safety & People - Public |  | Baseline |  | 0 | Dollar | 6040.28 | 6915.23 | 7880.36 | 8938.43 | 10090.96
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE | UARM - PA to Investment | UARM - Safety & People - Public |  | Outcome | 2024 | 180.0486 | Dollar | 4987.64 | 4881.11 | 4826.59 | 4812.27 | 4837.96
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 795214.17 | 910403.48 | 1037465.19 | 1176762.43 | 1328494.64
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 656632.73 | 642608.18 | 635430.14 | 633545.01 | 636926.57
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 3
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000617 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_D_OH_RELSA_LV_Crossarms | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name |  | Replace LV structures based on condition.
autofit | Description |  | Proactive asset renewal program to replace LV structures based on condition
autofit | Alternative Status |  | Candidate
autofit | Alternative Start Date |  | 4547400%
| Reason for selection/rejection |  | Whilst this option has the most positive NPV outcome, it has been rejected following portfolio optimisation to assess risk and expenditure across the whole asset fleet.
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
| Replace LV structures based on condition. |  | Capex |  |  | 2375433.8 | 2375433.8 | 2352214.35 | 2335779.49 | 2331566.26 | 11770427.7 | 47356283.79 | -9285311.41
|  |  | Opex |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | UARM - Environment and Community - Fire Risk |  |  | 5182.6032 | 6.88%
[9 empty] | UARM - Safety & People - Worker |  |  | 0 | 0%
[9 empty] | UARM - Network Performance Risk |  |  | 3508.5622 | 4.66%
[9 empty] | UARM - Environment and Community - Other Risk |  |  | 0 | 0%
[9 empty] | UARM - Financial Risk |  |  | 16206.762 | 21.52%
[9 empty] | UARM - Safety & People - Public |  |  | 190.5668 | 0.25%
[9 empty] | Terminal Value |  |  | 15859.4149 | 21.06%
[9 empty] | Total Investment Cost |  |  | -34373.8056 | 45.64%
[9 empty] | Total |  |  | 6574.1035
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE | Investment Cost | CAPEX Cost |  | Outcome | 2024 | 0 | Dollar | 2375433.8 | 2375433.8 | 2352214.35 | 2335779.49 | 2331566.26
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE | Investment Cost | Total Investment Cost |  | Outcome | 2024 | -34373.8056 | Dollar | 2375433.8 | 2375433.8 | 2352214.35 | 2335779.49 | 2331566.26
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE | Terminal Value | Terminal Value |  | Outcome | 2048 | 15859.4149 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Baseline |  | 0 | Dollar | 164269.7 | 188064.69 | 214312.2 | 243087.24 | 274431
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Outcome | 2024 | 5182.6032 | Dollar | 132737.15 | 127712.91 | 123875.24 | 121981.48 | 121096.58
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Baseline |  | 0 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Outcome | 2024 | 0 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE | UARM - PA to Investment | UARM - Network Performance Risk |  | Baseline |  | 0 | Dollar | 111208.68 | 127317.62 | 145086.87 | 164567.24 | 185786.6
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE | UARM - PA to Investment | UARM - Network Performance Risk |  | Outcome | 2024 | 3508.5622 | Dollar | 89861.51 | 86460.16 | 83862.1 | 82580.05 | 81980.98
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE | UARM - PA to Investment | UARM - Environment and Community - Other Risk |  | Baseline |  | 0 | Dollar | 0 | 0 | 0 | 0 | 0
| UARM - PA to Investment | UARM - Environment and Community - Other Risk |  | Outcome | 2024 | 0 | Dollar | 0 | 0 | 0 | 0 | 0
| UARM - PA to Investment | UARM - Financial Risk |  | Baseline |  | 0 | Dollar | 513695.51 | 588105.94 | 670185.76 | 760169.52 | 858186.08
| UARM - PA to Investment | UARM - Financial Risk |  | Outcome | 2024 | 16206.762 | Dollar | 415088.58 | 399377.05 | 387376.1 | 381454.02 | 378686.81
| UARM - PA to Investment | UARM - Safety & People - Public |  | Baseline |  | 0 | Dollar | 6040.28 | 6915.23 | 7880.36 | 8938.43 | 10090.96
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE | UARM - PA to Investment | UARM - Safety & People - Public |  | Outcome | 2024 | 190.5668 | Dollar | 4880.81 | 4696.06 | 4554.95 | 4485.32 | 4452.78
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 795214.17 | 910403.48 | 1037465.19 | 1176762.43 | 1328494.64
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 642568.05 | 618246.18 | 599668.39 | 590500.87 | 586217.15
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 4
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000617 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_D_OH_RELSA_LV_Crossarms | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name |  | Replace LV structures upon failure and capitalise
autofit | Description |  | Reactive renewal program to replace LV structures upon failure with no proactive replacement
autofit | Alternative Status |  | Candidate
autofit | Alternative Start Date |  | 4547400%
| Reason for selection/rejection |  | This option has been rejected as it does not manage risk nor network performance to an acceptable level and does not meet the business objectives. It requires the highest capital expenditure over the longer term with the lowest NPV outcome.
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
| Replace LV structures upon failure and capitalise |  | Capex |  |  | 518798.2 | 637875.5 | 780168.9 | 949432.2 | 1149905 | 4036179.8 | 87316840.8 | -102776705.46
|  |  | Opex |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | UARM - Environment and Community - Fire Risk |  |  | -9755.5763 | 7.16%
[9 empty] | UARM - Safety & People - Worker |  |  | 0 | 0%
[9 empty] | UARM - Network Performance Risk |  |  | -6604.4121 | 4.84%
[9 empty] | UARM - Environment and Community - Other Risk |  |  | 0 | 0%
[9 empty] | UARM - Financial Risk |  |  | -30507.1215 | 22.38%
[9 empty] | UARM - Safety & People - Public |  |  | -358.7172 | 0.26%
[9 empty] | Terminal Value |  |  | 33558.0361 | 24.61%
[9 empty] | Total Investment Cost |  |  | -55550.8784 | 40.75%
[9 empty] | Total |  |  | -69218.6693
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE | Investment Cost | CAPEX Cost |  | Outcome | 2024 | 0 | Dollar | 518798.2 | 637875.5 | 780168.9 | 949432.2 | 1149905
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE | Investment Cost | Total Investment Cost |  | Outcome | 2024 | -55550.8784 | Dollar | 518798.2 | 637875.5 | 780168.9 | 949432.2 | 1149905
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE | Terminal Value | Terminal Value |  | Outcome | 2048 | 33558.0361 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Baseline |  | 0 | Dollar | 164269.7 | 188064.69 | 214312.2 | 243087.24 | 274431
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE | UARM - PA to Investment | UARM - Environment and Community - Fire Risk |  | Outcome | 2024 | -9755.5763 | Dollar | 907676.76 | 970746.93 | 1028735.23 | 1080494.97 | 1125169.57
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Baseline |  | 0 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE | UARM - PA to Investment | UARM - Safety & People - Worker |  | Outcome | 2024 | 0 | Dollar | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE | UARM - PA to Investment | UARM - Network Performance Risk |  | Baseline |  | 0 | Dollar | 111208.68 | 127317.62 | 145086.87 | 164567.24 | 185786.6
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE | UARM - PA to Investment | UARM - Network Performance Risk |  | Outcome | 2024 | -6604.4121 | Dollar | 614486.64 | 657184.41 | 696441.82 | 731482.57 | 761726.75
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE | UARM - PA to Investment | UARM - Environment and Community - Other Risk |  | Baseline |  | 0 | Dollar | 0 | 0 | 0 | 0 | 0
| UARM - PA to Investment | UARM - Environment and Community - Other Risk |  | Outcome | 2024 | 0 | Dollar | 0 | 0 | 0 | 0 | 0
| UARM - PA to Investment | UARM - Financial Risk |  | Baseline |  | 0 | Dollar | 513695.51 | 588105.94 | 670185.76 | 760169.52 | 858186.08
| UARM - PA to Investment | UARM - Financial Risk |  | Outcome | 2024 | -30507.1215 | Dollar | 2838438.68 | 3035668.36 | 3217006.31 | 3378866.64 | 3518570.66
| UARM - PA to Investment | UARM - Safety & People - Public |  | Baseline |  | 0 | Dollar | 6040.28 | 6915.23 | 7880.36 | 8938.43 | 10090.96
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE | UARM - PA to Investment | UARM - Safety & People - Public |  | Outcome | 2024 | -358.7172 | Dollar | 33375.71 | 35694.83 | 37827.09 | 39730.32 | 41373.02
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 795214.17 | 910403.48 | 1037465.19 | 1176762.43 | 1328494.64
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 4393977.79 | 4699294.53 | 4980010.45 | 5230574.5 | 5446840
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 5 (hidden)
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000617 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_D_OH_RELSA_LV_Crossarms | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name
autofit | Description
autofit | Alternative Status
autofit | Alternative Start Date
Reason for selection/rejection
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
0
0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | Total |  |  | 0
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 0 | 0 | 0 | 0 | 0
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## Option 6 (hidden)
alternative
| Investment Evaluation Summary |  |  |  |  | Investment Code |  | Report Start Year |  | Number of Years | Base Fiscal Year | Currency Scale
[6 empty] | PRJ000617 |  | 2025 |  | 25 | FY23 | Literal
[6 empty] | Investment Name | [5 empty] | Scenario
[6 empty] | R24_D_OH_RELSA_LV_Crossarms | [5 empty] | Approved
autofit | Value Function |  | TasNetworks Value Function |  |  | Version |  | 0.1 |  | Date |  | 2022-11-03
Alternative Overview
75679 | Alternative Name
autofit | Description
autofit | Alternative Status
autofit | Alternative Start Date
Reason for selection/rejection
Alternative Spend Profile and Alternative Value
| Name |  | Account Type |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | R24 Expenditure | Total Expenditure | NPV
0
0
[9 empty] | Value Function Measure |  |  | Value | Value in %
[9 empty] | Total |  |  | 0
Alternative Value Details
| Value Model | Value Measure |  | Type | Impact Year | Value | Unit | 2025 | 2026 | 2027 | 2028 | 2029
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostCAPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostOPEX CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacInvestment CostInvestment CostTotal Investment CostFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacTerminal ValueTerminal ValueTerminal ValueFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Fire RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - WorkerFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Network Performance RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Environment and Community - Other RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskTRUE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Financial RiskFALSE
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicTRUE | [6 empty] | Baseline | 0 | 0 | 0 | 0 | 0
75679PRJ000652 / R24_D_OH_REPOL_Basic Fleet Pole ReplacUARM - PA to InvestmentUARM - PA to InvestmentUARM - Safety & People - PublicFALSE | [6 empty] | Outcome | 0 | 0 | 0 | 0 | 0
Note: Based on the characteristics of the value model, Financial Benefits & Costs was excluded from the chart above - please refer to the "Economic Analysis" sheet for the full breakdown of Investment Value.

## TextFormatting (hidden)
Index | 8
Column Width | 238
Font | Calibri
Font Size | 11
Font Colour
Text | Sheet | Group | Field | Row Height | Row Number
To manage asset risk associated with low voltage crossarms and other low voltage pole top structures. | Investment Summary | Header | Description | 15 | 9
Low voltage (LV) crossarms are used to connect the insulators which hold the LV open wire conductors to the support structures (poles) and provide adequate clearance between the conductors and to earth. TasNetworks' LV crossarms are predominantly manufactured from sawn timber as this material is cost effective and offers insulation qualities to allow live line activities to be performed safely. There are approximately 97,000 wooden LV crossarms in the distribution network. Wooden LV crossarms have an asset life of approximately 30 years. TasNetworks also has fibreglass (FRP) crossarms as part of the LV crossarm fleet. Fibreglass crossarms currently make up a small percentage of the LV crossarm population, with approximately 4.3% of the total number installed. Fibreglass (FRP) crossarms are included in this investment evaluation summary (IES), as the preferred replacement material to the earlier sawn timber LV cross arms. The transition to replacement with FRP crossarms has occurred in the last 5 years due to their longer service life and are unlikely to require any replacements within the next regulatory period. LV aerial bundled conductor (LVABC) is the preferred alternative design technology to LV open wire. However, it is only used to replace LV open wire configurations where a significant amount of the network is being replaced such that a design change is economically viable. Otherwise, the cost to install outweighs the benefits to transition to aerial bundled conductor. Hence, TasNetworks will be required to continue replacement of LV crossarms to ensure adequate isolation of the conductor, until alternative technologies are cost effective. TasNetworks does not keep detailed records of its pole top hardware (including LV crossarms). However, as LV pole top hardware is installed new whenever a pole is replaced, and the asset life is known, the age distribution can be calculated (refer asset management plan). Age, design, construction methods, fault currents, and environmental considerations such as proximity to coastlines will all impact the service life of the pole top components including crossarms. Crossarm failures results in a customer outages, as well as the bushfire, property and safety risks associated with downed live conductors, until they can be replaced. Crossarm condition can be determined visually by looking for splits, general degradation, and signs of rot. They are inspected during 5-yearly ground-based pole inspections and aerial pole-top imagery. The required replacement rate to maintain the network at a steady condition, without increasing the failure rate, can be calculated by looking at the total population of crossarm structures, historic crossarm replacement rates, and the expected crossarm life. This number is the adjusted with the volume of LVABC installed (where open wire is removed) and the incidental replacement of crossarms on other programs (e.g. pole replacements). The final number is cross-checked against the number of incoming notifications and historical replacement volumes to confirm it reflects a sustaining replacement volume. Incoming notifications are audited to ensure the asset inspectors are raising defects on the right asset conditions and some failed crossarms are investigated to drive program improvements. This is a continuation of an existing program to proactively rectify wooden LV crossarm defects and failures in the overhead system. A condition based replacement strategy is appropriate as the condition of timber crossarms can be easily visually assessed. | Investment Summary | 0.1 Overview | Background | 409.5 | 16
TasNetworks accounting data shows that the cost to replace a crossarm following failure is 179 per cent of the cost of doing the same job in a planned way. This is due to the: - high cost of on-call labour compared to day-rates; - unplanned crossarm replacements aren’t optimised with other jobs (where planned work is combined to reduce travel, traffic management, site supervision etc); and - materials can’t be organised in advance and must be sourced ad-hoc. Outage duration and frequency (since many crossarms can be replaced live) is also significantly higher for unplanned crossarm replacement. There are also risks associated with allowing these assets to fail such as: - risk of injury to public from electric shock or mechanical injury by a fallen LV conductor; - risk to property including agricultural livestock contacting low hanging LV conductors (there is approximately one event per year where a fallen LV conductor causes the death of a domestic animal); and - although rare with the current failure rate, TasNetworks has recently recorded a ground fire start from failed crossarms causing conductor clashing. | Investment Summary | 0.1 Overview | Problem Definition | 225 | 17
TasNetworks has a customer and stakeholder engagement strategy to inform the existing program of work and the upcoming revenue submission. The feedback obtained informs the approach taken by TasNetworks to align our investments with customer needs and impacts. Customer needs addressed by this investment include: - affordability; - supply reliability and safety of the current network; - resilience to future impacts including climate change; and - investment in future networks to unlock community benefits in renewable energy products and services. | Investment Summary | 02. Customer Needs and Impact | Customer Needs and impact | 135 | 18
TasNetworks Business Plan 2020-21: Our services reflect our customers’ needs and expectations. Investment will reduce the likelihood of in-service failure and therefore likelihood of incident. | Objectives and Analysis | 03. Business Performance Objectives | Safety and Wellbeing | 30 | 17
TasNetworks Business Plan 2020-21: Our services reflect our customers’ needs and expectations. The proposed plan is based around a model of constant and sustainable maintenance spend on the network. Investment will reduce the likelihood of in-service failure and customer outage. | Objectives and Analysis | 03. Business Performance Objectives | Our Customers | 45 | 18
TasNetworks' Corporate plan: Employee engagement. Investment will help our employees will feel that our asset management practices sufficiently manage our risks and that we are empowered to have a positive effect on our risks. | Objectives and Analysis | 03. Business Performance Objectives | Our People | 30 | 19
TasNetworks Business Plan: Define and efficiently deliver our work. The better the ratio between planned, condition based replacements and unplanned replacements, the more efficient and cost effective the program of work will be. Investment reduces our total cost when compared to run-to-failure. | Objectives and Analysis | 03. Business Performance Objectives | Our Business - Sustained Cost Management | 45 | 20
TasNetworks Business Plan 2020-21: Our services reflect our customers’ needs and expectations. Investment would reduce unserved energy by 44MWh when compared to run-to-failure. It’s more likely that some residual failures will continue to occur. | Objectives and Analysis | 03. Business Performance Objectives | Our Business - Network Service | 45 | 21
| Objectives and Analysis | 04. Business Risks | Death or Injury (Employee) | 15 | 23
Public contact with live conductors directly or indirectly after they fall to ground or reduce their clearance to ground following crossarm failure. | Objectives and Analysis | 04. Business Risks | Death or Injury (Public) | 30 | 24
If a sustainable proactive program is not implemented, increased failure rates will result in a large increase in the program of work and ultimately increase power price to customer. | Objectives and Analysis | 04. Business Risks | Sustainable and Predictable Pricing | 30 | 25
80 failures occur per year currently. A program aims to reduce this number and limit risk exposure. A run-to-failure strategy would increase this failure rate and risk exposure approximately ten-fold. | Objectives and Analysis | 04. Business Risks | Widespread Power Disruption | 30 | 26
TasNetworks has recorded a ground fire start from a poor condition LV crossarm snapping and the conductors clashing. TasNetworks data suggests this is unlikely for the current failure rate. | Objectives and Analysis | 04. Business Risks | Bushfire Start | 30 | 27
| Objectives and Analysis | 04. Business Risks | Loss of Major Industrial | 15 | 28
Customers have an expectation of consistent and reliable power supply which these assets provide. | Objectives and Analysis | 04. Business Risks | Customer Focus | 15 | 29
| Objectives and Analysis | 04. Business Risks | Business Continuity Management | 15 | 30
| Objectives and Analysis | 04. Business Risks | Cyber Security | 15 | 31
| Objectives and Analysis | 04. Business Risks | Private Assets | 15 | 32
| Objectives and Analysis | 04. Business Risks | Energy Policy and Regulation | 15 | 33
| Objectives and Analysis | 04. Business Risks | Project Marinus (D&A) | 15 | 34
| Objectives and Analysis | 04. Business Risks | Tasmanian Power System Complexity | 15 | 35
| Objectives and Analysis | 04. Business Risks | Emerging Complexity of the NEM | 15 | 36
The strategic objective is to manage the risk to customers by developing a risk based strategic plan. This includes a condition/risk-based approach to manage the assets to maintain reliability and security of the network and effectively manage the safety risk associated with maintaining the asset. | Objectives and Analysis | 05. Strategic Objectives | Strategic Objectives | 45 | 38
Towards 2030 | Objectives and Analysis | 05. Strategic Objectives | Strategic Document #1 | 15 | 39
Balanced Business Plan 2021-22 | Objectives and Analysis | 05. Strategic Objectives | Strategic Document #2 | 15 | 40
NER 5A Distribution | Objectives and Analysis | 05. Strategic Objectives | Strategic Document #3 | 15 | 41
Poletop Structures Asset Management Plan - R0002286926 | Objectives and Analysis | 05. Strategic Objectives | Strategic Document #4 | 15 | 42
| Objectives and Analysis | 05. Strategic Objectives | Strategic Document #5 | 15 | 43
The implemented program will aim to avoid the high cost of asset replacement under unplanned longer duration outages to the customer and to avoid unnecessary safety risk exposure. LV crossarm failure rates, incidents, and fault capitalisation will continue to be tracked as key performance indicators of the program. LV crossarm replacement is standard control capex. | Objectives and Analysis | 06. Project Objectives | Project Objectives | 75 | 44
All other Australian network service providers conduct planned crossarm replacement programs and generally favour fibreglass crossarms. Pole top structures are included in AER RIN reporting and REPEX modelling. | Objectives and Analysis | 07. Options Analysis | Benchmarking | 30 | 45
Improvements to inspection practices have been made based on findings from engineering investigations into high consequence failure and consultation with other network service providers. | Objectives and Analysis | 07. Options Analysis | Expert Findings | 30 | 46
The program will continue for the whole regulatory period and beyond at a constant but slightly decreasing rate of approximately 700 structures per year (it will be adjusted based on network condition). The replacement rate will slowly reduce in the long term since: - the population of open wire LV will slowly reduce in the network at a rate of approximately 1% of the population per year as more LV ABC is installed; and - eventually timber crossarms will be replaced with FRP material, which have a longer MTBF. FRP crossarms are being installed at a rate of approximately 2.5% of the population per year and forecast to not impact replacement rate until 2050. | Objectives and Analysis | 08. Investment Timing | Investment Timing | 105 | 47
The benefits to TasNetworks from implementation of the selected option will be: - improved unit rate for LV crossarm replacements as in-service failures decrease; - decrease in risk to public, property, reliability and fire starts; and - decrease in number of customer outages and their duration. | Objectives and Analysis | 09. Expected Outcomes and Benefits | Expected Outcomes and Benefits | 60 | 48
- Assume that the time to inspect crossarms is negligible compared to pole testing and other aerial asset inspection - therefore maintenance inspection cost of pole inspections not included in this IES. - Unserved energy was determined from TasNetworks outage impact recording system and SAP. Events where object part was listed as LV crossarm or brace were counted. - Accounting data from planned and failed-in-service jobs were compared from the TasNetworks asset management system. This comparison found that the cost of unplanned jobs are 179% compared to planned replacement due to the high cost of on-call labour and other inefficiencies. - It is assumed that unserved energy increases proportionally to the number of unplanned failures. - Pole-top structures are not tracked as separate assets but the failure distribution can be determined by using the pole age at the time of pole-top structure failure since it is assumed the structure was installed at the same time as the pole. - Only TasNetworks assets were considered in calculation as private LV crossarms are not considered as part of this IES. - The required replacement rate to maintain the network at a steady condition without increasing the failure rate can be calculated by looking at the total population of cross-arm structures and the expected MTBF. This number is the adjusted with the volume of LVABC installed (where open wire is removed) and the incidental replacement of cross-arms on other programs (e.g. pole replacements). | Objectives and Analysis | 10. Assumptions | Assumptions | 225 | 49
A RIT-D is not required because this is a high volume, low cost, program with separate sites where assets have failed a serviceability test during inspection. | Objectives and Analysis | 11. Regulatory Considerations | Regulatory Investment Test | 30 | 50
No | Objectives and Analysis | 11. Regulatory Considerations | Meet or manage the expected demand for Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 51
No | Objectives and Analysis | 11. Regulatory Considerations | Comply with all applicable regulatory obligations associated with the provision of Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 52
No | Objectives and Analysis | 11. Regulatory Considerations | Maintain the quality, reliability and security of supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 53
Yes | Objectives and Analysis | 11. Regulatory Considerations | Maintain the reliability and security of the system through the supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 54
Yes | Objectives and Analysis | 11. Regulatory Considerations | Maintain the safety of the system through the supply of Standard Control Services (Distribution)/Prescribed Services (Transmission). | 15 | 55
Option 1, Replace LV structures based on condition ($7M Repex model cap) is recommended for approval as it best satisfies the customer and business needs. | Objectives and Analysis | 12. Recommendation | Recommendation | 30 | 56
Proactive asset renewal program to replace LV structures based on condition and limited by the $7M Repex model cap. | Option 1 | Description |  | 15
This option has been selected following portfolio optimisation to assess risk and expenditure across the whole asset fleet. This option manages asset risk and network performance within an acceptable range compared to other asset portfolios. | Option 1 | Reason for selection/rejection |  | 15
Proactive asset renewal program to replace LV structures based on condition and limited by a top down expenditure constraint. | Option 2 | Description |  | 15
This option has been rejected following portfolio optimisation to assess risk and expenditure across the whole asset fleet. This option manages asset risk and network performance within an acceptable range compared to other asset portfolios but has a lower NPV compared to the selected option. | Option 2 | Reason for selection/rejection |  | 15
Proactive asset renewal program to replace LV structures based on condition | Option 3 | Description |  | 15
Whilst this option has the most positive NPV outcome, it has been rejected following portfolio optimisation to assess risk and expenditure across the whole asset fleet. | Option 3 | Reason for selection/rejection |  | 15
Reactive renewal program to replace LV structures upon failure with no proactive replacement | Option 4 | Description |  | 15
This option has been rejected as it does not manage risk nor network performance to an acceptable level and does not meet the business objectives. It requires the highest capital expenditure over the longer term with the lowest NPV outcome. | Option 4 | Reason for selection/rejection |  | 15
| Option 5 | Description
| Option 5 | Reason for selection/rejection
| Option 6 | Description
| Option 6 | Reason for selection/rejection