## inputs¦BandT
Portfolio Roadmap as updated June 2016 | Benefits provided to: |  |  | Cost
Project |  | Estimate Confidence* | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | Total Cost (FY16+)
2016/17
Remote Vehicle Comms - Journey Management | Transmission | H | 1701664.9551 | 26315 | 0 | 0 | 0 | 0 | 1727979.9551
Satellite Strategy | APA | H | 1127479.5001 | 1592834 | 0 | 0 | 0 | 0 | 2720313.5001
Enterprise Content Management | APA | M | 1616634.8357 | 4766127.9322 | 0 | 0 | 0 | 0 | 6382762.7679
APA Website Project | APA | H | 977996.8573 | 0 | 0 | 0 | 0 | 0 | 977996.8573
BI - Asset Datamart | APA | H | 99999.9945 | 0 | 0 | 0 | 0 | 0 | 99999.9945
APA Grid - Energy Components Upgrade | APA | M | 615933.7957 | 2548065 | 0 | 0 | 0 | 0 | 3163998.7957
Hyperion Upgrade to v 11-1-2-4 | APA | M | 136624 | 700397 | 0 | 0 | 0 | 0 | 837021
APA Grid Services Initiatives Program | Transmission | L | 201477.3618 | 738522.7165 | 0 | 0 | 0 | 0 | 940000.0783
APA Grid Extend | Transmission | L | 90000 | 7080567 | 1571587 | 0 | 0 | 0 | 8742154
Forecast
BI - Transmission Dashboard | APA | L | 79975.764 | 977526.446 | 0 | 0 | 0 | 0 | 1057502.21
HR Systems Refresh | APA | L | 0 | 880580.0001 | 4659928.8 | 58565.6 | 0 | 0 | 5599074.4
SharePoint Upgrade | APA | L | 0 | 1046427.4362 | 697320.5638 | 0 | 0 | 0 | 1743748
SQL Server Upgrade | APA | L | 0 | 930084.5333 | 60930.4667 | 0 | 0 | 0 | 991015
Upgrade Enterprise OSI PI Historian | Pipelines | L | 0 | 242399.2 | 3290.8 | 0 | 0 | 0 | 245690
Hazardous Area Platform | Pipelines | L | 0 | 269310.8 | 1557287.2 | 0 | 0 | 0 | 1826598
Form Digitisation Project | APA | L | 0 | 168732 | 1276736 | 0 | 0 | 0 | 1445468
Enterprise Asset Management Upgrade FY18 | Pipelines | L | 0 | 133163.8889 | 2728842.6986 | 0 | 0 | 0 | 2862006.5875
PPM Refresh | APA | L | 0 | 23940 | 839189.5 | 0 | 0 | 0 | 863129.5
BizTalk System Upgrade FY18 | APA | L | 0 | 0 | 791311.2 | 0 | 0 | 0 | 791311.2
Automated Testing Tool | APA | L | 0 | 0 | 421470 | 0 | 0 | 0 | 421470
Oracle eBS Upgrade to v12 2 | APA | L | 0 | 0 | 916998.7764 | 0 | 0 | 0 | 916998.7764
CRM Upgrade | Transmission | L | 0 | 0 | 594865.9 | 0 | 0 | 0 | 594865.9
X-Info Aware Version 2 | Transmission | L | 0 | 0 | 270771 | 0 | 0 | 0 | 270771
ID Procurement Data | Pipelines | L | 0 | 0 | 289762 | 15720.6 | 0 | 0 | 305482.6
Upgrade Enterprise OSI PI Historian 2017 | Pipelines | L | 0 | 17723.2 | 128386.8 | 0 | 0 | 0 | 146110
Supplier Qualification and Compliance | APA | L | 0 | 0 | 112070.8 | 123703.36 | 0 | 0 | 235774.16
BizTalk System Upgrade FY20 | APA | L | 0 | 0 | 0 | 0 | 201049.3361 | 0 | 201049.3361
Enterprise Asset Management Upgrade FY21 | Pipelines | L | 0 | 0 | 0 | 0 | 117290.3333 | 939791.6917 | 1057082.025
|  | Totals | 6647787.0641 | 22142716.1532 | 16920749.5053 | 197989.56 | 318339.6694 | 939791.6917 | 47167373.6437

## inputs¦Engineering
[24 empty] | MEJ |  | 0 | 150000 | 230000 | 50000 | 0 | 80000
[24 empty] | SIB |  | 15619000 | 23725000 | 14983000 | 6338000 | 7608000 | 8134000
PROJECT SUMMARY |  |  |  |  | FUNDING REQUEST DETAILS | [16 empty] | AMP ACCEPTANCE
Asset | Asset Group | SITE NAME | Function | PROJECT NAME | PROJECT TYPE | ISSUE DESCRIPTION | SCOPE SPECIFICS | ISSUE RAISED BY | FR BY | DATE RAISED | ALTERNATIVE OPTIONS | JUSTIFICATION / RISK IF DEFERRED | PRIORITY LEVEL | DRIVER CATEGORY | REF DOCUMENT / WORK ORDER | FEED Estimate | Delivery Estimate | Contingency? | Estimate Confidence 1 (best),2,3 (worst) | Estimate Basis | Total Estimate | In 5 Year Plan? | PROGRAM FREQUENCY | FUNDING TYPE | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | Business Case No. | AMP Ref | AA Commentary - Follow up | Value ($2015/16) | Asset Group | Asset | AA Asset Class | real year
QLD | Other |  | Electrical | ALARM RATIONALISATION | FEED | Currently underway for SWQP FY15 but expand; | [8 empty] | Update | [8 empty] | BAU | FY16: FY16-17; FY17: 50000 |  |  |  | 50000 | Other | QLD |  | $2015/16
RBP | Pipeline | RBP ALL | Lands | ANODE BED EASEMENTS PROGRAM | Lifecycle Program | First year include status of existing beds - provide plan for long-term including status of existing bed easements | TBC with outcomes of FY15 works |  | Jwo | Ongoing Program |  | Reference easement plan? | High | Compliance | [5 empty] | cost estimate per year at 9.6 sites per annum over 6 years with escalation | 1394000 |  |  | SIB | FY17 | 210000 | 215000 | 220000 | 225000 | 230000 | 235000 | AA-03 | 5.6 |  | 1335000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Station |  | Civil | BELLBIRD PARK STATION UPGRADE | Deliver | Upgrade station to include storage for emergency response and upgrade admin facilities to improve ops efficiency | Include subsidence and other upgrade | PT |  | 2016-01-06 | [11 empty] | No |  | SIB | FY18: 0 |  |  |  | 0 | Station | RBP |  | $2015/16
RBP | Pipeline |  | Lands | COMMISSION LEGAL ADVICE FOR ENCROACHMENT MANAGEMENT | FEED+Deliver | Understand legal obligations for APA notifications and development applications - CONFIRM OF MEJ or FEED study under internal opex in year 1 - placeholder for FY17 | [15 empty] | No |  | MEJ | [10 empty] | 0 | Pipeline | RBP |  | $2015/16
RBP | Pipeline |  | Integrity | Condamine River Strain Excavation | FEED+Deliver | >0.3 % magnitude strain event at Condamine river; prioritised on FY15 dig program but requires river diversion and major works; | Scope and plan excavation on the Condamine river | OM |  | 2014-12-01 |  |  | Medium | Integrity | [9 empty] | SIB | FY16: FY18; FY18: 200000 |  | 4.3.3 |  | 200000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Cathodic Protection | CP INTERFERENCE TESTING AND MITIGATION | Lifecycle Program | Upgrades of CPUs and re-registration of CPUs requires interference testing and mitigation of third party assets. | Annual program to be established to address all registration requirements and ensure interference being adequately managed | [6 empty] | Compliance | [9 empty] | MEJ | FY18: 100000; FY19: 100000; FY20: 50000 |  | 5.3 |  | 250000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Integrity | DN200 & 300 METRO ANNUAL EXCAVATION PROGRAM | Lifecycle Program | Forecast increase post FY18 ILI - include Lytton Road defect | 1 or 2 verification digs for Lytton Lateral | [5 empty] | High | Integrity | [7 empty] | No |  | MEJ | [10 empty] | 0 | Pipeline | RBP |  | $2015/16
RBP | Pipeline | RBP DN250 | Integrity | DN250 INTEGRITY UPGRADE PROGRAM | Lifecycle Program | Progressing integrity upgrade program based on ILI growth assessment and dent criticality; | Target 100 digs per year for budgeting |  |  | Ongoing Program |  |  | High | Integrity |  |  | 4000000 |  |  | $4M / year as a starting point -- dependent on outcome of Major Project | 4000000 |  |  | SIB | 3800000 | 4900000 | 5293000 | 5970000 | 3980000 | 3680000 | 4231000 | AA-03 | 5.1 |  | 28054000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Operations | DN250, DN300, DN200 Assessment of loss of cover and mitigation | FEED+Deliver | Some areas on RBP flagged as shallow depth of cover. Identified need to survey, assess and mitigate as required. Was $50k FY16 - but not used. | Consider operations survey to be completed as part of normal maintenance works to identify areas and document (in GIS); Allow budget in FY18 for mitigation as required; | JS |  |  |  |  | Low | Integrity | [6 empty] | 50000 |  |  | MEJ | FY16: 50000; FY18: 50000; FY19: 50000 |  | 4.2 |  | 100000 | Pipeline | RBP | Pipeline | $2015/16
QLD | Station |  | Electrical | Earthing and Lightning protection design review (Stations) | FEED | Some sites identified as an issue - needs assessment on whether SIB budget required | [15 empty] | No |  | BAU | [10 empty] | 0 | Station | QLD |  | $2015/16
RBP | Pipeline |  | Operations | EMERGENCY STOPPLE FITTINGS FOR DN250 EMERGENCIES | FEED+Deliver | DN250 emergency preparedness needs review - implement outcome of FEED works in FY15 | Include status of pipe - include pre-test | [14 empty] | No |  | SIB | FY18: 0 |  |  |  | 0 | Pipeline | RBP |  | $2015/16
QLD | Easement |  | Lands | Environmental Offset Strategy | FEED+Deliver |  |  | JWo |  | 42005 |  | Environmental compliance works program in place - refer Brynn / PK | [9 empty] | No |  | MEJ | [10 empty] | 0 | Easement | QLD |  | $2015/16
QLD | Pipeline |  | Lands | Files up to date on x-info | FEED+Deliver |  |  | JWo |  | 42005 | [11 empty] | No |  | MEJ | [10 empty] | 0 | Pipeline | QLD |  | $2015/16
RBP | Station | OAKEY, KOGAN | Electrical | Fire protection upgrades to RBP compressor stations (FM Global) | FEED+Deliver | FEED completed in FY15 flagged these sites for potential water mist system | Oakey and Kogan Water Mist System | RB |  |  |  |  | Low | Fire | QLD FM Global FEED | [5 empty] | n/a | No |  | SIB | FY18: 0 |  | 4.3.4 |  | 0 | Station | RBP |  | $2015/16
RBP | Station |  | Metering | Gas Measurement Upgrade - including shades | FEED |  | Should be evaluated as part of Meter performance FEED works in FY16. | RC | [15 empty] | SIB | FY16: FY18; FY20: 50000; FY21: 50000 |  | 5.2 |  | 100000 | Station | RBP | Regulators&Meters | $2015/16
RBP | Station |  | Electrical | GIBSON ISLAND E/I REVIEW FEED | FEED+Deliver | Incorporated in RTU upgrade works in FY16. this review is required to address Haz area, Flow computer and other component review. | Driven by Electrical, but with Mechanical components - undertake FEED to address compliance and flow computer performance - to present to Incitec | RB |  |  |  |  | Low | Reliability |  | 10000 | TBA |  |  |  | 10000 |  |  | SIB | FY17: 10000 |  | 7 |  | 10000 | Station | RBP | Regulators&Meters | $2015/16
RBP | Station |  | Mechanical | Gibson Island Pressure Vessel platforms | FEED+Deliver |  | past vessel defect, but defect assessment no concern; raised HSE issue of need for platform upgrade | CC | CC | 2015-12-01 |  |  | Low | Integrity | [9 empty] | SIB | FY20: 80000 |  | 7.1 |  | 80000 | Station | RBP | Regulators&Meters | $2015/16
QLD | Easement |  | Lands | Lands Property Database | FEED+Deliver |  |  | JWo |  | 42005 | [11 empty] | No |  | MEJ | [10 empty] | 0 | Easement | QLD |  | $2015/16
RBP | Pipeline | RBP ALL | Integrity | Laser Scanner for Feature Assessment | FEED+Deliver | Replacement of Laser Scanner for feature assessment; | Anticipate replacement / upgrade of laser scanner for feature assessment | [5 empty] | Low | Efficiency |  |  | 150000 |  | 2 | based on 2016 purchase cost | 150000 |  |  | SIB | FY21: 150000 | AA-03 |  |  | 150000 | Pipeline | RBP | Pipeline | $2015/16
QLD | Station |  | Operations | LOSS OF SUPPLY DESIGN REVIEW | FEED+Deliver | Critical sites for supply not fully understood | Undertake loss of supply review and provide recommendations - consider incorporating with HAZOP Assessment and SIS Review | [13 empty] | 15000 |  |  | BAU | FY16: FY17; FY17: 15000 |  |  |  | 15000 | Station | QLD |  | $2015/16
QLD | Station |  | Metering | METER PERFORMANCE PROGRAM FEED | FEED | Review status of existing meters and maintenance costs / process and assess for upgrading/replacing meters. - audits conducted on meter performance; | Continuation? 3 years time consider turbine meter upgrades (should send away 3 yearly); national policy on meter maintenance? Improved accuracy and reliabilty | Andrew Adams |  |  |  |  | Low | [10 empty] | BAU | FY16: FY18; FY18: 10000 |  | 5.2 |  | 10000 | Station | QLD | Regulators&Meters | $2015/16
RBP | Pipeline |  | Integrity | MP14 MLV Removal - study and implementation | FEED+Deliver | Moved to Fy16 - P4 item. | Raised from past issues list from MOP upgrade works | RG |  | 2012-12-01 | leave in situ | [10 empty] | No |  | BAU | [10 empty] | 0 | Pipeline | RBP |  | $2015/16
RBP | Pipeline |  | Operations | PEAT lateral cleaning pigging | Lifecycle Program | Liquids issue in Peat Lateral - also impacting CP isolation | Cleaning run to be established intermittently until liquids removal project established - budget for 2 x 3 mth runs then 1 x 6 mth | ND |  | 2014-11-01 | [9 empty] | $4k per run plus eng hrs data | 15000 |  |  | BAU | FY16: FY17; FY17: 15000 |  |  |  | 15000 | Pipeline | RBP |  | $2015/16
RBP | Pipeline | PEAT | Integrity | PEAT LATERAL ILI - DN250 | ILI SCHEDULE |  |  |  | OM |  |  | National Policy - non-strategic (10 yr target but extend if agreed) - subject to RLR and CP issues | Low | Integrity | ILI Pigging Strategy - National | [7 empty] | 10 yrs | SIB | FY16: 0; FY20: 140000 | AA-03 | 5.1 |  | 140000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Station | PEAT | Mechanical | PEAT LATERAL LIQUIDS REMOVAL | FEED+Deliver | Outcomes of FY14 works to be used - Implementation of liquids removal upgrade at Arubial, may need commercial input | Outcome of FY16 FEED | ND |  | mid 2014 |  |  | Medium | Reliability |  |  | xx |  |  | Liquids vessel at Scotia and Woodroyd? 100k vessel plus pipework | 300000 |  |  | SIB | FY18: 300000 | AA-05 | 4.3.5 |  | 300000 | Station | RBP | Pipeline | $2015/16
RBP | Pipeline | RBP | Integrity | PIPELINE REPAIR & EXCAVATION PROGRAM (unplanned) | Lifecycle Program | DN400 Excavations as required - include direct assessment of unpiggable lines, DCVG outcome, ILI repairs / corrosion rate re-assessment | maybe up to 4 digs per year managed adhoc by operations | OM |  |  |  |  | Medium | Integrity | [6 empty] | 100000 |  |  | SIB |  | 100000 | 100000 | 100000 | 100000 | 100000 |  |  | 5.1 |  | 500000 | Pipeline | RBP | Pipeline | $2015/16
QLD | Station | FACILITIES ALL | Mechanical | Portable Slug Catcher - DN400 | FEED+Deliver | Liquids issues in Peat Lateral and Wallumbilla from RBP reverse flow and BWP - more frequent cleaning pigging required. Need more efficient means of capturing liquids | Design transportable liquids drop out facility for DN400 (max) capability - similar to VIC design - Confirm CL rating (900 or 1500) | LB |  | 2015-12-01 |  |  | Medium | Efficiency |  |  |  |  | 2 | rough quotation from QPS | 250000 |  |  | SIB | FY17: 400000 | AA-05 | 4.3.5 |  | 400000 | Station | QLD | Pipeline | $2015/16
RBP | Tools |  | Integrity | PURCHASE 3D SCANNER TOOL | Deliver |  | Justification | OM | EV | [9 empty] | 2 | quotation | 180000 |  |  | SIB | FY16: 150000 |  |  |  | 0 | Tools | RBP |  | $2015/16
QLD | Facility | FACILITIES ALL | Operations | QLD OPERATIONS SIB FUNDING | Lifecycle Program | regular tools funding | Basis for funding to be scoped to confirm estimate - notional breakdown $70k per 3 systems; reduced from FY16 by $40k; |  | JS | Ongoing Program |  |  | Medium | Tool | [6 empty] | 70000 |  |  | SIB | 250000 | 210000 | 200000 | 200000 | 200000 | 200000 | 200000 |  | 7.1 |  | 1210000 | Facility | QLD | Other | $2015/16
QLD | Easement |  | Lands | QLD Tenure Audit | FEED+Deliver |  |  | JWo |  | 42005 | [11 empty] | No |  | MEJ | [10 empty] | 0 | Easement | QLD |  | $2015/16
RBP | Station |  | Operations | RBP - Security fencing upgrade for vent stacks | FEED+Deliver | Isolation plan, hazardous area and security | May be HA related, but limited background - discussion with Operations required to scope | AR |  | 2014-11-01 | [11 empty] | No |  | SIB | [10 empty] | 0 | Station | RBP |  | $2015/16
RBP | Station |  | Operations | RBP - Station painting program | Lifecycle Program | Part of an overall QLD painting program - $80k per year across all assets - designated across 5 years | FY16 - SEA, Caltex and BBP flagged for completion; | JS | [12 empty] | 80000 | moved to BAU |  | BAU | FY17 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 |  |  |  | 480000 | Station | RBP |  | $2015/16
RBP | Station | RBP DN250 | Mechanical | RBP - TYPE B GAS COMPLIANCE UPGRADES | Lifecycle Program | Ongoing program | Oakey and Kogan Remaining Works |  | CC |  |  |  | Medium | Non compliance - regulatory & reputation |  |  |  |  | 1 | followon from past works | 25000 |  |  | SIB | FY16: 50000; FY17: 25000; FY18: 110000; FY19: 110000 |  | 3.3.4 |  | 245000 | Station | RBP | Compressors | $2015/16
RBP | Station | RBP METRO | Mechanical | RBP & PEAT ISOLATION PLAN UPGRADES | FEED+Deliver | FEED in progress - Metro Vent stack redesign; consider actuating MLVs and new offtake for blowdown (include Peat Lateral) | 4 metro sites redesign vent stack; actuate key MLVs in metro; consider new offtake for blowdown, consider vent stack at Scotia and actuating Welsh MLV | PR | PR | 2015-12-01 |  | Isolation Plan outcomes | High | Compliance | Isolation Plan | 10000 | 100000 |  | 3 | 100k each for MLV actuation, additional blowdown | 100000 | Yes |  | SIB | FY16: 15000; FY17: 100000; FY18: 100000; FY19: 100000 |  | 4.3.2 |  | 300000 | Station | RBP | Pipeline | $2015/16
RBP | Pipeline | RBP ALL | Electrical | RBP- AS4853 ELECTRICAL HAZARD UPGRADES | Continuation | Review AS4853 Requirements for QLD assets; | Implement RBP FEED report recommendations - test points in metro area, update procedures | AB |  | 2015-04-01 | Deferral only | Low risk - however metro area exposure to test points will increase and is a safety & compliance risk | Low | Compliance | RBP FEED Report | $ - | consider allocating spend / yr or address in full by priority | nil | 2 | $900 per unit quote, approx 90 units - plus install across metro | 120000 |  |  | SIB | FY18: 120000 |  | 3.3.4 |  | 120000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline | RBP CE Lateral | Integrity | RBP CE Lateral ILI - DN400 | ILI SCHEDULE | DN400 Collinwood Park take off–Ellengrove - as per national pigging schedule | MFL4 + Geometry + Mapping XYZ |  | OM |  |  | Metro, AC risks | Medium | Integrity | ILI Pigging Strategy - National |  |  |  |  | Pig run calculator for GE - plus minor for internal costs |  |  | 7 yrs | SIB | FY16: -; FY19: 10000; FY20: 190000 | AA-03 | 5.2 |  | 200000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Integrity | RBP Cleaning Program (DN400) | Lifecycle Program | Liquids being captured in Wallumbilla in reverse flow | [13 empty] | $8k per session (2 sections, 2 runs each) | 16000 |  |  | BAU | FY16: FY17; FY17: 16000 |  |  |  | 16000 | Pipeline | RBP |  | $2015/16
RBP | Pipeline | RBP ALL | Electrical | RBP CP TELEMETRY UPGRADE | Lifecycle Program | 10 units per year - supply and install, dependent on outcomes of FY15 works - refer to CP plan - purchases in blocks of 10. | Delivery being managed through Electrical |  |  | Ongoing Program |  |  | Medium | Reliability | [6 empty] | 150000 |  |  | SIB | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 |  | AA-03 | 5.3 |  | 750000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline | RBP ALL | Cathodic Protection | RBP CP UPGRADE PROGRAM | Lifecycle Program | Ref CP upgrade 5 year plan | Include Peat Lateral CP Bed upgrades; Scope includes: - upgrade units to 80A; - re-shuffle of 40 A units to 25A sites; - 1 x infill site assumed ($150k) - bed upgrades and other misc items | ND | ND | Ongoing Program |  |  | High | Integrity | CP 5 year upgrade plan |  |  |  |  | CP Plan | 629000 |  |  | SIB | 500000 | 629000 | 642000 | 648000 | 648000 | 648000 | 648000 | AA-03 | 5.3 |  | 3863000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Integrity | RBP DN400 Supply Offtakes | FEED | New offtakes at existing stations off DN400 for supply reliability | Only potential points are Dably biorefinery, Oakey Sales station, Sandy Creek and Ellengrove sales station (if not already being done by ALARP works) - and Riverview most likely underground site | FC | [11 empty] | past works underground $400k - reduce for mostly above ground offtakes ($100k AG, $250k below ground) |  |  |  | SIB | FY19: 250000; FY21: 100000 |  | 4.4 |  | 350000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Station | RBP DN250 | Electrical | RBP HA RECTIFICATION | Lifecycle Program | Implementation of HA inspections to address compliance - ongoing program - Kogan and Oakey completion first up - $100k insufficient for full completion of station package, hence increase based on typical actuals | Updated in AMP or separate plan for 5 years; in past 2 years scope focus on fire and gas and aftercooler equipment; Oakey and Kogan sites require valve skid, fuel gas skid , aftecooler fan motor and compressor shed lights into 2017/18 |  | RB | Ongoing Program | Deferral or no upgrade | Increased risk of station outage due to degraded equipment; elevated risk of ignition in case of gas release. | Medium | Compliance |  |  | 50000 |  |  |  | 150000 |  |  | SIB | FY16: 150000; FY17: 150000; FY18: 50000; FY22: 100000 |  | 3.3 |  | 300000 | Station | RBP | Compressors | $2015/16
RBP | Pipeline |  | Integrity | RBP LOOPING ILI - DN400 | ILI SCHEDULE | DN400 Wallumbilla to Swanbank (Roma to Brisbane – “Looping”) - as per national pigging schedule |  |  | OM |  |  | frequency increased due to dents and feature numbers |  | Integrity | ILI Pigging Strategy - National | [7 empty] | 7 yrs | SIB | FY16: -; FY21: 1800000 | AA-03 | 5.1 |  | 1800000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Integrity | RBP LYTTON LATERAL ILI - DN200 | ILI SCHEDULE | DN200 Lytton Lateral from SEA block valve to Caltex Refinery - as per national pigging schedule - COMMISSIONED 2010 |  |  | OM |  |  | Strategic (7 yr first run) | Medium | Compliance | ILI Pigging Strategy - National | [7 empty] | 7 yrs | SIB | FY16: -; FY17: 5000; FY18: 140000 | AA-03 | 5.2 |  | 145000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Integrity | RBP MAINLINE ILI PROGRAM - DN250 | ILI SCHEDULE | FY19 for DN250 ILI & Verification digs; [Verification digs carryover from remaining 2015 ILI] | MFL4 + Geometry + Mapping for further Strain reports - Mapping module will be required - costs based on past work rather than vendor and incl verification |  | OM |  |  | ESD recommend 5 yr freq due to age, feature qty and dents |  | Integrity | ILI Pigging Strategy - National |  |  |  |  | Pig run calculator for GE - plus $400k total for other based on past project 32565 |  |  | 5 yrs | SIB | FY16: 100000; FY19: 1500000 | AA-03 | 5.1 |  | 1500000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Integrity | RBP METRO (ORIGINAL) ILI - DN200 | ILI SCHEDULE | DN200 “metro” from SEA block valve to Gibson Island - built 1970 - as per national pigging schedule |  |  | OM |  |  | Age and metro | Low | Integrity | ILI Pigging Strategy - National | [7 empty] | 7 yrs | SIB | FY16: -; FY18: 60000 | AA-03 | 5.1 |  | 60000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline | RBP METRO | Integrity | RBP METRO ILI - DN300 | ILI SCHEDULE | DN300 “metro” from Bellbird Park to SEA block valve via Ellengrove and Mount Gravatt - built 1970 - as per national pigging schedule | MFL4 + Geometry + Mapping for further Strain reports - Mapping module will be required |  | OM |  |  | ESD and RLR recommendation - metro (target CY16) | Medium | Integrity | ILI Pigging Strategy - National |  |  |  |  | Pig run calculator for GE - plus minor for internal costs |  |  | 5 yrs | SIB | FY17: 220000; FY22: 220000 | AA-03 | 5.1 |  | 440000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Integrity | RBP METRO LOOP ILI - DN400 | ILI SCHEDULE | As per national pigging strategy - commissioned 2013 - FY20 (strategic) or FY23 (non-strategic) TBC - $250k | MFL4 + Geometry + Mapping XYZ |  | OM |  |  | Strategic (7 yr first run) | Low | Compliance | ILI Pigging Strategy - National | [7 empty] | 7 yrs | SIB | FY16: 0; FY19: 120000 | AA-03 | 5.1 |  | 120000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Integrity | RBP REPLACEMENT SPOOLS FOR DN250 CHECK VALVES | Deliver | Removal of the DN250 check valves and their latching modifications from the RBP MLV sites. Replace with pipe spools. | Consider purchase of spools for replacement in shutdowns as available | NL | NL | 2014-12-01 | [10 empty] | 10000 |  |  | BAU | FY16: FY17; FY17: 10000 |  |  |  | 10000 | Pipeline | RBP |  | $2015/16
RBP | Pipeline | RBP ALL | Integrity | RBP RISK MITIGATION - FEED and IMPLEMENTATION | FEED+Deliver | ALARP study outcomes to be scoped and implemented | Mt Gravatt minor modifications; consider future compression in metro to meet capacity and address ALARP outcomes; Regulation on DN250 and DN400; Significant slabbing (10km) |  |  | 2015-12-01 |  |  | High | Risk |  | 15000 |  |  |  | $2M per station (x 4), plus $500k / km - up to 12km makes total $14M - allow for some carryover into FY18 | 14000000 |  |  | SIB | 120000 | 8000000 | 1650000 | 300000 | 300000 | 300000 | 300000 | AA-02 | 4.3 |  | 10850000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Station |  | Mechanical | RBP S20 Decommissioned Compressor Removal | Continuation | Remove compressor, turbines, condensate tanks, lube oil, etc | Yuleba, Condamine, Dalby, Gatton | PR | PR | 2015-11-01 |  |  | Low | Obsolence |  |  |  |  | 3 |  | 200000 | deferred |  | SIB | FY18: 100000; FY19: 100000 |  | 5.5 |  | 200000 | Station | RBP | Compressors | $2015/16
RBP | Pipeline |  | Integrity | RBP SCC EMAT ILI - DN300 | ILI SCHEDULE | Consider EMAT tool for inspection of Metro |  |  | OM |  |  | SCC mitigation | High | Integrity | SCC Management Plan | [8 empty] | SIB | FY16: 900000; FY22: 900000 | AA-03 | 4.3.3 |  | 900000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline | RBP DN250 | Integrity | RBP SCCMP EMAT ILI - DN250 | ILI SCHEDULE | SCC Managemennt Plan recommendations - timing within 4 years of identification - either hydrotesting or crack detection; Target FY17 start - FY18 complete | Dependent on tool availability for EMAT versus Hydro | EV |  | 2015-12-01 |  |  | Medium | Integrity |  |  | $2M per 3 sections |  | 3 | 600k per section, target 3 sections as first priority, followup with 2 sections | 3800000 |  |  | SIB | FY18: 1800000; FY19: 1200000 | AA-03 | 4.3.3 |  | 3000000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline | RBP ALL | Mechanical | RBP SCRAPER TRAP MODIFICATIONS | FEED+Deliver | Savings anticipated from minimising the number of ILI runs in the RBP - based on latest commercial proposal. Reduce to 4 sections per pipeline gives approx saving of $400-500k per pigging run. | Modify applicable Scraper Sites to reduce the runs in the DN250 and DN400 RBP: - DN400: mods to stations at Yuleba, Kogan and Gatton; - DN250: mods to stations at Condamine, Dalby and Gatton; - No DN400 mods at Condamine due to spec break in place; - No mods for either line at Oakey due to the current configuration (but may be looked at in future as an option) - No DN250 mods at Yuleba and Kogan due to inline filter preference to retain in place; - Retain existing DN100 bypass pipeline (between two scrapers currently) for venting/blowdown purposes (ie for DN400 mods at Yuleba and DN250 mods at Condamine) | [5 empty] | Medium | Efficiency | [9 empty] | SIB | FY18: 200000; FY19: 200000 | AA-03 | 5.1 |  | 400000 | Pipeline | RBP | Compressors | $2015/16
RBP | Station | BELLBIRD PARK | Electrical | RBP STATION FIRE SUPRESSION UPGRADES - BELLBIRD PARK | Deliver | Follow up from FEED works in FY15; Upgrade station control rooms that are identified as requiring fire suppression; Followup from FM Global FY15 recommendations to review adequacy. | Bellbird Park and Ellengrove nominated for potential fire suppression - Ellengrove first priority - BBP in FY17 but likely to cost more than Ellengrove | AB |  | 2015-01-01 | Deferral or no upgrade | Risk of fire escalation to full control room outage, leading to prolonged station control outage. | Medium | Fire | QLD Fire Suppression FEED | $ - | 75000 |  | 3 | FEED report | 75000 |  |  | SIB | FY20: 75000 |  | 4.3.4 |  | 75000 | Station | RBP | Regulators&Meters | $2015/16
RBP | Station | RBP DN250 | Mechanical | RBP STATION UPGRADES - HAZOP & Other | Continuation | Address all required HAZOP Actions - incorporating FEED in FY16 and implementation across FY17, 18, 19; Include some upgrade items associated with S20 decommissioning (pipe supports upgrade etc); - Redesign vent stacks at MLVs and Compressor Stations for safe pipeline blowdown (FY18); - Actuate key MLV's for remote operation from IOC (FY19) - Scraper Station Upgrades (FY19) | MP20, MP106, MP143 - Investigate Fire break adequacy /Fencing/Signage; SS Upgrade (Gat / Con); MS Design review (Wall and Red); -Dalby and Yuleba upgrades (100k) - include earthing of vent points while still isolating CP ($40k) - include DN250 MLV Station upgrade 14 sites for venting ($350k); - include DN250 MLV Actuation at key sites ($250k); Continue to include RBP Wallumbilla | PR | PR | 2015-11-01 |  |  | Medium | Risk |  | 7k | 160000 |  |  | potentially 550k in FY18 for MLV vents and Actuation - consider program spread to FY19 as well | 167000 | Yes |  | SIB |  | 160000 | 305000 | 305000 | 100000 | 100000 |  |  | 5.2 |  | 970000 | Station | RBP | Compressors | $2015/16
RBP |  |  | Operations | ROW Erosion Repairs - | FEED+Deliver | Erosion on ROW | TBC with outcomes of FY15 works | JS |  |  | Manage under provision in operational budget (typ $100k per year) | [10 empty] | Yes |  | MEJ | FY19: 80000; FY22: 80000 |  |  |  | 160000 | Easement | RBP | Pipeline | $2015/16
RBP | Station |  | Mechanical | SCOTIA / WOODROYD VENT EXTENSION | FEED+Deliver | Extend vent lines above roof | Carryover from FY16 works |  | SI |  |  |  | Medium | HSE |  | * | [7 empty] | SIB | FY16: 10000; FY18: 30000 |  | 7.1 |  | 30000 | Station | RBP | Regulators&Meters | $2015/16
QLD | Station |  | Electrical | SIS demand/test tracking system | FEED+Deliver | System and process for capturing trip tests and real system demands on the safety instrumented systems (SIS) across the sites. RBP will only pay a proportion of software costs. | 1) purchase software licence 2) configure key sites and test procedures, and Maximo interface (if applicable) 3) train people in use | WWP |  | 2015-11-09 | 1) instigate manual paper based processes 2) build something in Maximo | Manual paper based systems are a starting poing, but they are prone to duplication and cost more in the long run due to double handling, lack of analysis capabilities and resultant loss of opportunity to improve safety/availability,. | Low |  |  |  | 200000 |  |  | total software implementation cost - dependent on IT drivers; RBP proportion only | 200000 |  |  | SIB | FY16: FY18; FY18: 50000 |  | 5.2 |  | 50000 | Station | QLD | Compressors | $2015/16
QLD | Station |  | Electrical | SIS improvement program FEED and Implementation | FEED+Deliver | APA's process safety risks across QLD assets, as well as the safety instrumented system (SIS) installed to mitigate those risks can be refined. This means we have difficulty managing those safety functions, to ensure they are effective. | 1) Consolidate HAZOP/LOPA documentation for SIS across QLD sites. 2) Build master safety function and protective layer list. 3) Determine key safety requirements for each SIF 4) Identify where proof testing is lacking 5) Develop proof test procedures and implement in EAM 6) Gather scope items for full compliance with APA's functional safety management framework. Includes min two workshops | WWP |  | 2015-11-09 | Consider merging with HAZOP FEED and Loss of Supply FEED |  | Medium | Risk |  | 50000 | TBA |  | 2 |  | 50000 |  |  | BAU | FY16: FY17; FY17: 50000 |  |  |  | 50000 | Station | QLD |  | $2015/16
QLD | Pipeline |  | Integrity | SMS Reviews - QLD | Lifecycle Program | 5 yearly review required | SWQP: Incorporate scoping of HI sub-class near Wallumbilla and potential light wall pipe; PEAT & CGP also required in 2016 |  |  | Ongoing Program | [10 empty] | 10000 |  |  | BAU | FY16: FY17; FY17: 10000 |  |  |  | 10000 | Pipeline | QLD |  | $2015/16
QLD | Pipeline |  | Integrity | SMS, RLR, MEJ project review | Lifecycle Program | Review compliance register and include in the MEJ plan | Scope being included in other line items as MEJ, but keep in here until recap completed |  | JW | Ongoing Program | [11 empty] | No |  | BAU | [10 empty] | 0 | Pipeline | QLD |  | $2015/16
RBP | Station |  | Electrical | SOLAR S20 Unit Control Panel Upgrade FEED | FEED | SATURN 20 Panels Upgrade - may be driven out of nationals ESD requirements and operating philosophy. | Include analysis on hazardous area | [5 empty] | Low | Reliability | [7 empty] | No |  | BAU | [10 empty] | 0 | Station | RBP |  | $2015/16
RBP | Station |  | Mechanical | Station Remaining Life Review | [30 empty] | 0 | Station | RBP |  | $2015/16
RBP | Station | COLLINGWOOD | Mechanical | SWANBANK ISOLATION VALVE | Continuation | plan with shutdown works - bring procurement forward. Moved to Fy16 P4 item. FEED and procurement FY16. | Carryover from FY16 to FY17 for construction - Procurement in FY16 |  | PR | Access Arrangement |  | Isolation Plan outcome; manages risk of coal fire on swanbank lateral by enabling islation and maintaining brisbane supply through Ellengrove; | Medium | Supply Reliability & Availability |  |  |  |  | 3 | estimated carryover | 200000 |  |  | SIB | FY16: 665000; FY17: 50000 |  | 6.2 |  | 50000 | Station | RBP | Pipeline | $2015/16
RBP | Pipeline |  | Integrity | TOOWOOMBA DN250 RAIL CROSSING | FEED+Deliver | Design Life finish in 2017; Requires pigging to be re-run by 2019. | May be resolved by Nexus through TRSC project | [5 empty] | Medium | Integrity | [7 empty] | HOLD |  | SIB | FY16: FY18; FY18: 11000000; FY19: 3500000 | AA-06 | 4.3.1 |  | 14500000 | Pipeline | RBP | Pipeline | $2015/16
RBP | Pipeline | TOOWOOMBA | Civil | TOOWOOMBA RANGE SLOPE MONITORING WORKS | FEED+Deliver | Linked to road project and ongoing survey data; being investigated in 2015 (NL). Further monitoring measures to be implemented. . | Slope Management Plan outcomes to be implemented. Consider LIDAR surveys, Coffey stress state assessment, and strain guage install & measurement | FC | NL |  |  |  | Low | Integrity | Slope Management Plan |  |  |  | 3 | 15k per LIDAR; $400k Coffeys quote; $250k strain guage install and monitoring; | 800000 |  |  | SIB | FY17: 300000; FY18: 650000 | AA-06 | 4.3.1 |  | 950000 | Pipeline | RBP | Pipeline | $2015/16
RBP |  |  |  | Toowoomba Slope Management | [19 empty] | BAU | [10 empty] | 0 | Easement | RBP |  | $2015/16
RBP | Station | TOOWOOMBA | Electrical | TOOWOOMBA STATION HEATER INSTALLATION | FEED | Heater installation at Toowoomba MS. Recent upgrade project on Toowoomba Station | Outcome of FY16 FEED works to understand requirements and priority for a Heater at Toowoomba | RB |  | 2015-01-01 |  |  | Low |  | Toowoomba Range Station upgrade | 10000 | 250000 |  | 2 | $98k estimate for 130kW Heater and control panel (DN200) - plus additional for civils and pipework; | 250000 |  |  | SIB | FY16: FY18; FY18: 250000 |  | 7.1 |  | 250000 | Station | RBP | Regulators&Meters | $2015/16
RBP | Station | DALBY | Rotating | Turbine overhauls - Dalby | Lifecycle Program | 50,000hrs major overhaul as per EAM regime - intermittent usage up to 4000 hrs per year - currently at approx 20000hrs | Confirm EAM regimes - nothing identified over next 5 years for other assets; Dalby estimate $1.3M based on 2016 pricing, which includes the overhaul of gas producer, power turbine and auxiliary gear box |  | XL | Ongoing Program |  |  | Low | Reliability |  |  | 1300000 |  | 1 | 2016 Solar Schedule | 1300000 | No | outside 5 years, subject to 50,000hrs run time | SIB | FY22: 1300000 | AA-08 | 5.5 |  | 1300000 | Station | RBP | Compressors | $2015/16
RBP | Operations | FACILITIES ALL | Operations | VEHICLE PURCHASES | Deliver | Status of existing vehicles and purchase dates | 2 vehicles required for FY17 on CGP, providing for one purchase but preference to lease if possible on RBP - based on previous spend in FY16. Longterm vehicle plan still to be confirmed |  | LB |  |  | Many vehicles over due for renewal / replacement; Heavily modified or high spec vehicles on replacement program rather than lease. 5 outstanding vehicles up for renewal; | Medium | Pool |  |  |  |  | 1 | based on FY16 AFE | 220000 |  |  | SIB | FY17: 0 |  |  |  | 0 | Operations | RBP |  | $2015/16
RBP | Station |  | Mechanical | Wallumbilla MS Upgrade | FEED+Deliver | General site deterioration as per site visit and email pre-Christmas - poor wiring, PSVs without tail etc |  | BC |  | 2015-12-01 | [11 empty] | No |  | BAU | [10 empty] | 0 | Station | RBP |  | $2015/16
RBP | Pipeline |  | Integrity | WATER EASEMENT EMERGENCY PREPAREDNESS - FEED | FEED | Price and plan a FEED for water easement emergency preparedness, including risk based selection of water crossings - cost estimate of easement widening and other lands / licence costs; include additional purchases if required ie stopple fittings | Outcomes of FEED to be implemented | CB |  |  |  |  | Medium | Reliability | [5 empty] | 9 CP sites for $200k; similar approvals required but for extra land and longer lead - allow for $100k per annum for 2 years |  | HOLD |  | SIB | FY18: 10000; FY20: 100000; FY21: 100000 |  | 4.3.1 |  | 210000 | Pipeline | RBP |  | $2015/16
Note on V63: Ward, Jennifer: MEJ?
Note on AC40: Ward, Jennifer: defer pigging for inclusion with RBP Looping - include small amount for preparation and potentially scraper trap modification FEED

## inputs¦other
#VALUE!
inflation
cpi values | $2016/17 | CPI
$2014/15 | 0.96487 | 1.328%
$2015/16 | 0.97752 | 1.311%
$2016/17 | 1 | 2.3%
$2017/18 | 1.023 | 2.3%
$2018/19 | 1.0465 | 2.3%
$2019/20 | 1.0706 | 2.3%
$2020/21 | 1.0952 | 2.3%
$2021/22 | 1.1204 | 2.3%
Percent of group assets allocated to RBP
Asset | Type | Percent to RBP
APA | percent | 5.953%
QLD | percent | 55.81%
RBP | percent | 100%
Regulated | percent | 100%
Transmission | percent | 6.724%
Pipelines | percent | 5.953%
Asset Classes
Original Pipeline
Pipelines
Lytton lateral
Peat Lateral
Compressors
Regulators and meters
Easements
Communications
Other
Capitalised AA costs
Group IT
SIB Capex
PMA
Projects
Project code | Project name
AA-01 | Flooding Emergency Works
AA-02 | Urban Risk Reduction
AA-03 | Pipeline Integrity Management
AA-04 | Aquarium Passage
AA-05 | Liquids Removal
AA-06 | Toowoomba Crossing
AA-07 | Bi-directional flow
AA-08 | Dalby Turbine Overhaul
AA-09 | RBP Metro Looping FEED
AA-10 | SCADA Upgrade
RBP01 | Applications and Renewals
RBP02 | Infrastructure Renewals
Number of Assets in Assets class
Asset Class | Number of mechanical assets
Original Pipeline | 7
Pipelines | 7
Lytton lateral
Peat Lateral
Compressors | 3
Regulators and meters | 16
Easements
Communications
Capitalised AA costs
Group IT
SIB Capex
PMA
Total | 33
Historic Capex |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
Capex | $m nominal | 0 | 0 | 0 | 0 | 0
Inflation index | index | 0.9085 | 0.92329 | 0.9464 | 0.97412 | 0.98706 | 1
Forecast number of dig ups |  | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Metro | # | 27 | 33 | 36 | 15 | 11 | 7
Non Metro | # | 81 | 83 | 94 | 76 | 74 | 93
Total | # | 108 | 116 | 130 | 91 | 85 | 100
Application Upgrade Plan
Upgrade Projects | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22
Energy Components | X | bar: 2018; 2020
Historian | bar: 2017; 2019
SCADA | bar: 2017; 2019
Middleware | bar: 2017; 2019
DBYD | bar: 2017; 2019
Field Data / Mobility | X | bar: 2017 to 2020
GIS | bar: 2017; 2019
EAM | X | bar: 2018; 2020

## inputs│RIN
#VALUE!
Urban Risk Mitigation
Description | Labour | Material | Plant | Subcontract | Other | Cost Total
Project Management | 810658 | 0 | 0 | 0 | 76577 | 887235
Land & Approvals | 0 | 0 | 0 | 0 | 35500 | 35500
Design | 1450849 | 0 | 0 | 0 | 15000 | 1465849
Procurement | 74432 | 2377152 | 62500 | 52828 | 7500 | 2574412
Construction | 649344 | 55797 | 27240 | 3437978 | 204796 | 4375155
Commissioning & Handover | 119190 | 71060 | 0 | 0 | 58638 | 248888
Total | 3104473 | 2504009 | 89740 | 3490806 | 398011 | 9587039
Toowoomba Range
10"
Description | Labour | Material | Plant | Subcontract | Other | Cost Total
Project Management | 116215 |  |  |  | 23243 | 139458
Land & Approvals | 24225 |  |  | 6465 | 61510 | 92200
Design | 97960 |  |  | 181883 | 19592 | 299435
Procurement | 15643 | 544951 |  |  | 3129 | 563723
Construction | 317243 |  |  | 2928615 | 126897 | 3372755
Commissioning & Handover | 80150 | 396 |  |  | 17500 | 98046
Design Development | 4566 | 109575 |  | 342421 |  | 456562
Total = | 656002 | 654922 | 0 | 3459384 | 251871 | 5022179
16"
Description | Labour | Material | Plant | Subcontract | Other | Cost Total
Project Management | 116215 |  |  |  | 23243 | 139458
Land & Approvals | 24225 |  |  | 6465 | 61510 | 92200
Design | 97960 |  |  | 181883 | 19592 | 299435
Procurement | 15643 | 1094017 |  |  | 3129 | 1112789
Construction | 317243 |  |  | 5734782 | 126897 | 6178922
Commissioning & Handover | 80150 | 877 |  |  | 17500 | 98527
Design Development | 7921 | 190112 |  | 594100 |  | 792133
Total = | 659357 | 1285006 | 0 | 6517230 | 251871 | 8713464
Total
Project Management | 232430 | 0 | 0 | 0 | 46486 | 278916
Land & Approvals | 48450 | 0 | 0 | 12930 | 123020 | 184400
Design | 195920 | 0 | 0 | 363766 | 39184 | 598870
Procurement | 31286 | 1638968 | 0 | 0 | 6258 | 1676512
Construction | 634486 | 0 | 0 | 8663397 | 253794 | 9551677
Commissioning & Handover | 160300 | 1273 | 0 | 0 | 35000 | 196573
Design Development | 12487 | 299687 | 0 | 936521 | 0 | 1248695
Total = | 1315359 | 1939928 | 0 | 9976614 | 503742 | 13735643 |  | Check | TRUE
Energy Components
Cost Type | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
Internal Labour | 540 |  | 540 |  | 540 | 1620
External Labour | 1170 |  | 1170 |  | 1170 | 3510
Materials | 90 |  | 90 |  | 90 | 270
Total | 1800 |  | 1800 |  | 1800 | 5400
Historian
Cost Type | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
Internal Labour |  | 210 |  | 210 |  | 420
External Labour |  | 455 |  | 455 |  | 910
Materials |  | 35 |  | 35 |  | 70
Total |  | 700 |  | 700 |  | 1400
SCADA System
Cost Type | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
Internal Labour |  | 990 |  | 990 |  | 1980
External Labour |  | 2145 |  | 2145 |  | 4290
Materials |  | 165 |  | 165 |  | 330
Total |  | 3300 |  | 3300 |  | 6600
Middleware - Biztalk
Cost Type | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
Internal Labour |  | 234 |  | 234 |  | 468
External Labour |  | 507 |  | 507 |  | 1014
Materials |  | 39 |  | 39 |  | 78
Total |  | 780 |  | 780 |  | 1560
Dial Before You Dig
Cost Type | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
Internal Labour |  | 252 |  | 252 |  | 504
External Labour |  | 546 |  | 546 |  | 1092
Materials |  | 42 |  | 42 |  | 84
Total |  | 840 |  | 840 |  | 1680
Field Data – Mobility Systems
Cost Type | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
Internal Labour | 250 | 250 | 250 | 250 | 250 | 1250
External Labour | 100 | 100 | 100 | 100 | 100 | 500
Materials | 150 | 150 | 150 | 150 | 150 | 750
Total | 500 | 500 | 500 | 500 | 500 | 2500
Geospatial Information System
Cost Type | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
Internal Labour |  | 750 |  | 750 |  | 1500
External Labour |  | 1625 |  | 1625 |  | 3250
Materials |  | 125 |  | 125 |  | 250
Total |  | 2500 |  | 2500 |  | 5000
Enterprise Asset Management
Cost Type | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
Internal Labour | 1380 |  | 1380 |  | 1380 | 4140
External Labour | 2990 |  | 2990 |  | 2990 | 8970
Materials | 230 |  | 230 |  | 230 | 690
Total | 4600 |  | 4600 |  | 4600 | 13800
Infrastructure Renewal
Cost Type | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
Internal Labour | 675 | 225 | 225 | 225 |  | 1350
External Labour | 1463 | 488 | 488 | 488 |  | 2925
Materials | 113 | 38 | 38 | 38 |  | 225
Total | 2250 | 750 | 750 | 750 |  | 4500
Integrity Management Upgrade
| ILI | Excavations | Laser Scanner | CP Easement | CP Upgrades | CP Telemetry | TOTALS
Labour | 539825 | 6848592 | 5000 | 105000 | 347500 | 395842 | 8510559
Materials | 0 | 2020896 | 145000 | 0 | 2213000 | 234767 | 4613663
Contractors | 7632295 | 17795112 | 0 | 880000 | 1264000 | 108386 | 27560743
Other | 132880 | 1403400 | 0 | 350000 | 38500 | 11005 | 1786035
TOTAL | 8305000 | 28068000 | 150000 | 1335000 | 3863000 | 750000 | 42471000
Daldy Turbine Overhaul
[5 empty] | 2021/22 | Total
Labour | [6 empty] | 0
Materials | [6 empty] | 0
Contractors |  |  |  |  | 1329900 |  | 1329900
Other | [6 empty] | 0
TOTAL | 0 | 0 | 0 | 0 | 1329900 | 0 | 1329900

## calculation¦capex
aa asset class
|  | Financial Year | 17 | 18 | 19 | 20 | 21 | 22 | funding type | asset group | business case # | asset | aa driver | asset group | total value ($2015/16) | sumif function ($ value covered by business cases) | Original Pipeline | Pipelines | Compressors | Regulators and meters | Easements | Communications | Other | Capitalised AA costs | Group IT | SIB Capex | PMA | Total | Dollars
ALARM RATIONALISATION | QLD | Currently underway for SWQP FY15 but expand; | 50000 | 0 | 0 | 0 | 0 | 0 | BAU | Other | 0 | Other | Stay in Business | BAU | 50000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
ANODE BED EASEMENTS PROGRAM | RBP | First year include status of existing beds - provide plan for long-term including status of existing bed easements | 210000 | 215000 | 220000 | 225000 | 230000 | 235000 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 1335000 | AA | 50% | 50% | [9 empty] | 100% | $2015/16
BELLBIRD PARK STATION UPGRADE | RBP | Upgrade station to include storage for emergency response and upgrade admin facilities to improve ops efficiency | 0 | 0 | 0 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 0 | 0 |  |  |  | 100% | [7 empty] | 100% | $2015/16
COMMISSION LEGAL ADVICE FOR ENCROACHMENT MANAGEMENT | RBP | Understand legal obligations for APA notifications and development applications - CONFIRM OF MEJ or FEED study under internal opex in year 1 - placeholder for FY17 | 0 | 0 | 0 | 0 | 0 | 0 | MEJ | Pipeline | 0 | Pipeline | Exclude | MEJ | 0 | 0 | 100% | [10 empty] | 100% | $2015/16
Condamine River Strain Excavation | RBP | >0.3 % magnitude strain event at Condamine river; prioritised on FY15 dig program but requires river diversion and major works; | 0 | 200000 | 0 | 0 | 0 | 0 | SIB | Pipeline | 0 | Pipeline | Stay in Business | SIB | 200000 | 0 | 100% | [10 empty] | 100% | $2015/16
CP INTERFERENCE TESTING AND MITIGATION | RBP | Upgrades of CPUs and re-registration of CPUs requires interference testing and mitigation of third party assets. | 0 | 0 | 0 | 0 | 0 | 0 | MEJ | Pipeline | 0 | Pipeline | Exclude | MEJ | 0 | 0 | 50% | 50% | [9 empty] | 100% | $2015/16
DN200 & 300 METRO ANNUAL EXCAVATION PROGRAM | RBP | Forecast increase post FY18 ILI - include Lytton Road defect | 0 | 0 | 0 | 0 | 0 | 0 | MEJ | Pipeline | 0 | Pipeline | Exclude | MEJ | 0 | 0 | 100% | [10 empty] | 100% | $2015/16
DN250 INTEGRITY UPGRADE PROGRAM | RBP | Progressing integrity upgrade program based on ILI growth assessment and dent criticality; | 4900000 | 5293000 | 5970000 | 3980000 | 3680000 | 4231000 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 28054000 | AA | 100% | [10 empty] | 100% | $2015/16
DN250, DN300, DN200 Assessment of loss of cover and mitigation | RBP | Some areas on RBP flagged as shallow depth of cover. Identified need to survey, assess and mitigate as required. Was $50k FY16 - but not used. | 0 | 0 | 0 | 0 | 0 | 0 | MEJ | Pipeline | 0 | Pipeline | Exclude | MEJ | 0 | 0 | 100% | [10 empty] | 100% | $2015/16
Earthing and Lightning protection design review (Stations) | QLD | Some sites identified as an issue - needs assessment on whether SIB budget required | 0 | 0 | 0 | 0 | 0 | 0 | BAU | Station | 0 | Station | Stay in Business | BAU | 0 | 0 |  |  | 50% | 50% | [7 empty] | 100% | $2015/16
EMERGENCY STOPPLE FITTINGS FOR DN250 EMERGENCIES | RBP | DN250 emergency preparedness needs review - implement outcome of FEED works in FY15 | 0 | 0 | 0 | 0 | 0 | 0 | SIB | Pipeline | 0 | Pipeline | Stay in Business | SIB | 0 | 0 | 100% | [10 empty] | 100% | $2015/16
Environmental Offset Strategy | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEJ | Easement | 0 | Easement | Exclude | MEJ | 0 | 0 | [9 empty] | 100% |  | 100% | $2015/16
Files up to date on x-info | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEJ | Pipeline | 0 | Pipeline | Exclude | MEJ | 0 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Fire protection upgrades to RBP compressor stations (FM Global) | RBP | FEED completed in FY15 flagged these sites for potential water mist system | 0 | 0 | 0 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 0 | 0 |  |  | 100% | [8 empty] | 100% | $2015/16
Gas Measurement Upgrade - including shades | RBP | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 100000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
GIBSON ISLAND E/I REVIEW FEED | RBP | Incorporated in RTU upgrade works in FY16. this review is required to address Haz area, Flow computer and other component review. | 10000 | 0 | 0 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 10000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
Gibson Island Pressure Vessel platforms | RBP | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 80000 | 0 |  |  |  | 100% | [7 empty] | 100% | $2015/16
Lands Property Database | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEJ | Easement | 0 | Easement | Exclude | MEJ | 0 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Laser Scanner for Feature Assessment | RBP | Replacement of Laser Scanner for feature assessment; | 0 | 0 | 0 | 0 | 150000 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 150000 | AA | 50% | 50% | [9 empty] | 100% | $2015/16
LOSS OF SUPPLY DESIGN REVIEW | QLD | Critical sites for supply not fully understood | 15000 | 0 | 0 | 0 | 0 | 0 | BAU | Station | 0 | Station | Stay in Business | BAU | 15000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
METER PERFORMANCE PROGRAM FEED | QLD | Review status of existing meters and maintenance costs / process and assess for upgrading/replacing meters. - audits conducted on meter performance; | 0 | 10000 | 0 | 0 | 0 | 0 | BAU | Station | 0 | Station | Stay in Business | BAU | 10000 | 0 |  |  |  | 100% | [7 empty] | 100% | $2015/16
MP14 MLV Removal - study and implementation | RBP | Moved to Fy16 - P4 item. | 0 | 0 | 0 | 0 | 0 | 0 | BAU | Pipeline | 0 | Pipeline | Stay in Business | BAU | 0 | 0 |  | 100% | [9 empty] | 100% | $2015/16
PEAT lateral cleaning pigging | RBP | Liquids issue in Peat Lateral - also impacting CP isolation | 15000 | 0 | 0 | 0 | 0 | 0 | BAU | Pipeline | 0 | Pipeline | Stay in Business | BAU | 15000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
PEAT LATERAL ILI - DN250 | RBP | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 140000 | AA |  | 100% | [9 empty] | 100% | $2015/16
PEAT LATERAL LIQUIDS REMOVAL | RBP | Outcomes of FY14 works to be used - Implementation of liquids removal upgrade at Arubial, may need commercial input | 0 | 300000 | 0 | 0 | 0 | 0 | SIB | Station | AA-05 | Station | Stay in Business | SIB | 300000 | AA |  | 100% | [9 empty] | 100% | $2015/16
PIPELINE REPAIR & EXCAVATION PROGRAM (unplanned) | RBP | DN400 Excavations as required - include direct assessment of unpiggable lines, DCVG outcome, ILI repairs / corrosion rate re-assessment | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | SIB | Pipeline | 0 | Pipeline | Stay in Business | SIB | 500000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
Portable Slug Catcher - DN400 | QLD | Liquids issues in Peat Lateral and Wallumbilla from RBP reverse flow and BWP - more frequent cleaning pigging required. Need more efficient means of capturing liquids | 400000 | 0 | 0 | 0 | 0 | 0 | SIB | Station | AA-05 | Station | Stay in Business | SIB | 400000 | AA |  | 100% | [9 empty] | 100% | $2015/16
PURCHASE 3D SCANNER TOOL | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SIB | Tools | 0 | Tools | Stay in Business | SIB | 0 | 0 | 50% | 50% | [9 empty] | 100% | $2015/16
QLD OPERATIONS SIB FUNDING | QLD | regular tools funding | 210000 | 200000 | 200000 | 200000 | 200000 | 200000 | SIB | Facility | 0 | Facility | Stay in Business | SIB | 1210000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
QLD Tenure Audit | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEJ | Easement | 0 | Easement | Exclude | MEJ | 0 | 0 |  |  |  |  | 100% | [6 empty] | 100% | $2015/16
RBP - Security fencing upgrade for vent stacks | RBP | Isolation plan, hazardous area and security | 0 | 0 | 0 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 0 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP - Station painting program | RBP | Part of an overall QLD painting program - $80k per year across all assets - designated across 5 years | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | BAU | Station | 0 | Station | Stay in Business | BAU | 480000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP - TYPE B GAS COMPLIANCE UPGRADES | RBP | Ongoing program | 25000 | 110000 | 110000 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 245000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP & PEAT ISOLATION PLAN UPGRADES | RBP | FEED in progress - Metro Vent stack redesign; consider actuating MLVs and new offtake for blowdown (include Peat Lateral) | 100000 | 100000 | 100000 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 300000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP- AS4853 ELECTRICAL HAZARD UPGRADES | RBP | Review AS4853 Requirements for QLD assets; | 0 | 120000 | 0 | 0 | 0 | 0 | SIB | Pipeline | 0 | Pipeline | Stay in Business | SIB | 120000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP CE Lateral ILI - DN400 | RBP | DN400 Collinwood Park take off–Ellengrove - as per national pigging schedule | 0 | 0 | 10000 | 190000 | 0 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 200000 | AA |  | 100% | [9 empty] | 100% | $2015/16
RBP Cleaning Program (DN400) | RBP | Liquids being captured in Wallumbilla in reverse flow | 16000 | 0 | 0 | 0 | 0 | 0 | BAU | Pipeline | 0 | Pipeline | Stay in Business | BAU | 16000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP CP TELEMETRY UPGRADE | RBP | 10 units per year - supply and install, dependent on outcomes of FY15 works - refer to CP plan - purchases in blocks of 10. | 150000 | 150000 | 150000 | 150000 | 150000 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 750000 | AA | 50% | 50% | [9 empty] | 100% | $2015/16
RBP CP UPGRADE PROGRAM | RBP | Ref CP upgrade 5 year plan | 629000 | 642000 | 648000 | 648000 | 648000 | 648000 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 3863000 | AA | 50% | 50% | [9 empty] | 100% | $2015/16
RBP DN400 Supply Offtakes | RBP | New offtakes at existing stations off DN400 for supply reliability | 0 | 0 | 250000 | 0 | 100000 | 0 | SIB | Pipeline | 0 | Pipeline | Stay in Business | SIB | 350000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP HA RECTIFICATION | RBP | Implementation of HA inspections to address compliance - ongoing program - Kogan and Oakey completion first up - $100k insufficient for full completion of station package, hence increase based on typical actuals | 150000 | 50000 | 0 | 0 | 0 | 100000 | SIB | Station | 0 | Station | Stay in Business | SIB | 300000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP LOOPING ILI - DN400 | RBP | DN400 Wallumbilla to Swanbank (Roma to Brisbane – “Looping”) - as per national pigging schedule | 0 | 0 | 0 | 0 | 1800000 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 1800000 | AA |  | 100% | [9 empty] | 100% | $2015/16
RBP LYTTON LATERAL ILI - DN200 | RBP | DN200 Lytton Lateral from SEA block valve to Caltex Refinery - as per national pigging schedule - COMMISSIONED 2010 | 5000 | 140000 | 0 | 0 | 0 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 145000 | AA |  | 100% | [9 empty] | 100% | $2015/16
RBP MAINLINE ILI PROGRAM - DN250 | RBP | FY19 for DN250 ILI & Verification digs; [Verification digs carryover from remaining 2015 ILI] | 0 | 0 | 1500000 | 0 | 0 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 1500000 | AA | 100% | [10 empty] | 100% | $2015/16
RBP METRO (ORIGINAL) ILI - DN200 | RBP | DN200 “metro” from SEA block valve to Gibson Island - built 1970 - as per national pigging schedule | 0 | 60000 | 0 | 0 | 0 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 60000 | AA | 100% | [10 empty] | 100% | $2015/16
RBP METRO ILI - DN300 | RBP | DN300 “metro” from Bellbird Park to SEA block valve via Ellengrove and Mount Gravatt - built 1970 - as per national pigging schedule | 220000 | 0 | 0 | 0 | 0 | 220000 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 440000 | AA | 100% | [10 empty] | 100% | $2015/16
RBP METRO LOOP ILI - DN400 | RBP | As per national pigging strategy - commissioned 2013 - FY20 (strategic) or FY23 (non-strategic) TBC - $250k | 0 | 0 | 120000 | 0 | 0 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 120000 | AA |  | 100% | [9 empty] | 100% | $2015/16
RBP REPLACEMENT SPOOLS FOR DN250 CHECK VALVES | RBP | Removal of the DN250 check valves and their latching modifications from the RBP MLV sites. Replace with pipe spools. | 10000 | 0 | 0 | 0 | 0 | 0 | BAU | Pipeline | 0 | Pipeline | Stay in Business | BAU | 10000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP RISK MITIGATION - FEED and IMPLEMENTATION | RBP | ALARP study outcomes to be scoped and implemented | 8000000 | 1650000 | 300000 | 300000 | 300000 | 300000 | SIB | Pipeline | AA-02 | Pipeline | Stay in Business | SIB | 10850000 | AA | 100% | [10 empty] | 100% | $2015/16
RBP S20 Decommissioned Compressor Removal | RBP | Remove compressor, turbines, condensate tanks, lube oil, etc | 0 | 100000 | 100000 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 200000 | 0 |  |  | 100% | [8 empty] | 100% | $2015/16
RBP SCC EMAT ILI - DN300 | RBP | Consider EMAT tool for inspection of Metro | 0 | 0 | 0 | 0 | 0 | 900000 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 900000 | AA | 100% | [10 empty] | 100% | $2015/16
RBP SCCMP EMAT ILI - DN250 | RBP | SCC Managemennt Plan recommendations - timing within 4 years of identification - either hydrotesting or crack detection; Target FY17 start - FY18 complete | 0 | 1800000 | 1200000 | 0 | 0 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 3000000 | AA | 100% | [10 empty] | 100% | $2015/16
RBP SCRAPER TRAP MODIFICATIONS | RBP | Savings anticipated from minimising the number of ILI runs in the RBP - based on latest commercial proposal. Reduce to 4 sections per pipeline gives approx saving of $400-500k per pigging run. | 0 | 200000 | 200000 | 0 | 0 | 0 | SIB | Pipeline | AA-03 | Pipeline | Stay in Business | SIB | 400000 | AA | 50% | 50% | [9 empty] | 100% | $2015/16
RBP STATION FIRE SUPRESSION UPGRADES - BELLBIRD PARK | RBP | Follow up from FEED works in FY15; Upgrade station control rooms that are identified as requiring fire suppression; Followup from FM Global FY15 recommendations to review adequacy. | 0 | 0 | 0 | 75000 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 75000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
RBP STATION UPGRADES - HAZOP & Other | RBP | Address all required HAZOP Actions - incorporating FEED in FY16 and implementation across FY17, 18, 19; Include some upgrade items associated with S20 decommissioning (pipe supports upgrade etc); - Redesign vent stacks at MLVs and Compressor Stations for safe pipeline blowdown (FY18); - Actuate key MLV's for remote operation from IOC (FY19) - Scraper Station Upgrades (FY19) | 160000 | 305000 | 305000 | 100000 | 100000 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 970000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
ROW Erosion Repairs - | RBP | Erosion on ROW | 0 | 0 | 0 | 0 | 0 | 0 | MEJ | Easement | 0 | Easement | Exclude | MEJ | 0 | 0 |  |  |  |  | 100% | [6 empty] | 100% | $2015/16
SCOTIA / WOODROYD VENT EXTENSION | RBP | Extend vent lines above roof | 0 | 30000 | 0 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 30000 | 0 | 100% | [10 empty] | 100% | $2015/16
SIS demand/test tracking system | QLD | System and process for capturing trip tests and real system demands on the safety instrumented systems (SIS) across the sites. RBP will only pay a proportion of software costs. | 0 | 50000 | 0 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 50000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
SIS improvement program FEED and Implementation | QLD | APA's process safety risks across QLD assets, as well as the safety instrumented system (SIS) installed to mitigate those risks can be refined. This means we have difficulty managing those safety functions, to ensure they are effective. | 50000 | 0 | 0 | 0 | 0 | 0 | BAU | Station | 0 | Station | Stay in Business | BAU | 50000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
SMS Reviews - QLD | QLD | 5 yearly review required | 10000 | 0 | 0 | 0 | 0 | 0 | BAU | Pipeline | 0 | Pipeline | Stay in Business | BAU | 10000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
SMS, RLR, MEJ project review | QLD | Review compliance register and include in the MEJ plan | 0 | 0 | 0 | 0 | 0 | 0 | BAU | Pipeline | 0 | Pipeline | Stay in Business | BAU | 0 | 0 | [9 empty] | 100% |  | 100% | $2015/16
SOLAR S20 Unit Control Panel Upgrade FEED | RBP | SATURN 20 Panels Upgrade - may be driven out of nationals ESD requirements and operating philosophy. | 0 | 0 | 0 | 0 | 0 | 0 | BAU | Station | 0 | Station | Stay in Business | BAU | 0 | 0 |  |  | 100% | [8 empty] | 100% | $2015/16
Station Remaining Life Review | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Station | 0 | Station | Exclude | 0 | 0 | 0 | [9 empty] | 100% |  | 100% | $2015/16
SWANBANK ISOLATION VALVE | RBP | plan with shutdown works - bring procurement forward. Moved to Fy16 P4 item. FEED and procurement FY16. | 50000 | 0 | 0 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 50000 | 0 | [9 empty] | 100% |  | 100% | $2015/16
TOOWOOMBA DN250 RAIL CROSSING | RBP | Design Life finish in 2017; Requires pigging to be re-run by 2019. | 0 | 11000000 | 3500000 | 0 | 0 | 0 | SIB | Pipeline | AA-06 | Pipeline | Stay in Business | SIB | 14500000 | AA | 50% | 50% | [9 empty] | 100% | $2015/16
TOOWOOMBA RANGE SLOPE MONITORING WORKS | RBP | Linked to road project and ongoing survey data; being investigated in 2015 (NL). Further monitoring measures to be implemented. . | 300000 | 650000 | 0 | 0 | 0 | 0 | SIB | Pipeline | AA-06 | Pipeline | Stay in Business | SIB | 950000 | AA | 50% | 50% | [9 empty] | 100% | $2015/16
Toowoomba Slope Management | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BAU | Easement | 0 | Easement | Stay in Business | BAU | 0 | 0 | 50% | 50% | [9 empty] | 100% | $2015/16
TOOWOOMBA STATION HEATER INSTALLATION | RBP | Heater installation at Toowoomba MS. Recent upgrade project on Toowoomba Station | 0 | 250000 | 0 | 0 | 0 | 0 | SIB | Station | 0 | Station | Stay in Business | SIB | 250000 | 0 |  |  |  | 100% | [7 empty] | 100% | $2015/16
Turbine overhauls - Dalby | RBP | 50,000hrs major overhaul as per EAM regime - intermittent usage up to 4000 hrs per year - currently at approx 20000hrs | 0 | 0 | 0 | 0 | 0 | 1300000 | SIB | Station | AA-08 | Station | Stay in Business | SIB | 1300000 | AA |  |  | 100% | [8 empty] | 100% | $2015/16
VEHICLE PURCHASES | RBP | Status of existing vehicles and purchase dates | 0 | 0 | 0 | 0 | 0 | 0 | SIB | Operations | 0 | Operations | Stay in Business | SIB | 0 | 0 | [9 empty] | 100% |  | 100% | $2015/16
Wallumbilla MS Upgrade | RBP | General site deterioration as per site visit and email pre-Christmas - poor wiring, PSVs without tail etc | 0 | 0 | 0 | 0 | 0 | 0 | BAU | Station | 0 | Station | Stay in Business | BAU | 0 | 0 |  |  |  | 100% | [7 empty] | 100% | $2015/16
Applications and Renewals | APA | Software renewals |  | 6900000 | 8620000 | 6900000 | 8620000 | 6900000 | SIB | IT | RBP01 | IT | Stay in Business | SIB | 37940000 | RB | [8 empty] | 100% |  |  | 100% | $2014/15
Infrastructure Renewals | APA | Telecoms and IT infrastructure upgrades |  | 2250000 | 750000 | 750000 | 750000 |  | SIB | IT | RBP02 | IT | Stay in Business | SIB | 4500000 | RB | [8 empty] | 100% |  |  | 100% | $2014/15
AA Costs | Regulated | Access Arrangement Reset costs | 891355.52 | 70875.35 | 0 | 0 | 58008.08 | 891355.52 | SIB | AA | 0 | Capitalised AA costs | Stay in Business | SIB | 1911594.47 | 0 | [7 empty] | 100% |  |  |  | 100% | $2015/16
Remote Vehicle Comms - Journey Management | Transmission |  | 26315 | 0 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 26315 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Satellite Strategy | APA |  | 1592834 | 0 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 1592834 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Enterprise Content Management | APA |  | 4766127.9322 | 0 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 4766127.9322 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
APA Website Project | APA |  | 0 | 0 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 0 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
BI - Asset Datamart | APA |  | 0 | 0 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 0 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
APA Grid - Energy Components Upgrade | APA |  | 2548065 | 0 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 2548065 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Hyperion Upgrade to v 11-1-2-4 | APA |  | 700397 | 0 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 700397 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
APA Grid Services Initiatives Program | Transmission |  | 738522.7165 | 0 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 738522.7165 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
APA Grid Extend | Transmission |  | 7080567 | 1571587 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 8652154 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
BI - Transmission Dashboard | APA |  | 977526.446 | 0 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 977526.446 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
HR Systems Refresh | APA |  | 880580.0001 | 4659928.8 | 58565.6 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 5599074.4 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
SharePoint Upgrade | APA |  | 1046427.4362 | 697320.5638 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 1743748 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
SQL Server Upgrade | APA |  | 930084.5333 | 60930.4667 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 991015 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Upgrade Enterprise OSI PI Historian | Pipelines |  | 242399.2 | 3290.8 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 245690 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Hazardous Area Platform | Pipelines |  | 269310.8 | 1557287.2 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 1826598 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Form Digitisation Project | APA |  | 168732 | 1276736 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 1445468 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Enterprise Asset Management Upgrade FY18 | Pipelines |  | 133163.8889 | 2728842.6986 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 2862006.5875 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
PPM Refresh | APA |  | 23940 | 839189.5 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 863129.5 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
BizTalk System Upgrade FY18 | APA |  | 0 | 791311.2 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 791311.2 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Automated Testing Tool | APA |  | 0 | 421470 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 421470 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Oracle eBS Upgrade to v12 2 | APA |  | 0 | 916998.7764 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 916998.7764 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
CRM Upgrade | Transmission |  | 0 | 594865.9 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 594865.9 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
X-Info Aware Version 2 | Transmission |  | 0 | 270771 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 270771 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
ID Procurement Data | Pipelines |  | 0 | 289762 | 15720.6 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 305482.6 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Upgrade Enterprise OSI PI Historian 2017 | Pipelines |  | 17723.2 | 128386.8 | 0 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 146110 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Supplier Qualification and Compliance | APA |  | 0 | 112070.8 | 123703.36 | 0 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 235774.16 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
BizTalk System Upgrade FY20 | APA |  | 0 | 0 | 0 | 201049.3361 | 0 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 201049.3361 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16
Enterprise Asset Management Upgrade FY21 | Pipelines |  | 0 | 0 | 0 | 117290.3333 | 939791.6917 | 0 | SIB | IT | 0 | IT | Stay in Business | SIB | 1057082.025 | 0 | [8 empty] | 100% |  |  | 100% | $2015/16

## calculation¦RBP capex
#VALUE!
expenditure ('000)
project name | Real year | unit type | 17 | 18 | 19 | 20 | 21 | 22 |  |  | Original Pipeline | Pipelines | Compressors | Regulators and meters | Easements | Communications | Other | Capitalised AA costs | Group IT | SIB Capex | PMA | Total | Check
ALARM RATIONALISATION | $2015/16 | QLD | 27.904 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 13764.5 | 872.7316 | 0 | 0 | 0 | 0 | 0 | 891.3555 | 1378.68 | 902.9565 | 0 | 17810.2237 | 1
ANODE BED EASEMENTS PROGRAM | $2015/16 | RBP | 210 | 215 | 220 | 225 | 230 | 235 | AA-03 | 18 | 15461.5 | 6868.5 | 100 | 255.5808 | 0 | 0 | 0 | 70.8753 | 1570.8372 | 1004.5198 | 0 | 25331.8131 | 1
BELLBIRD PARK STATION UPGRADE | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 11329 | 2489 | 100 | 0 | 0 | 0 | 0 | 0 | 569.604 | 1056.6158 | 0 | 15544.2198 | 1
COMMISSION LEGAL ADVICE FOR ENCROACHMENT MANAGEMENT | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 4791.5 | 841.5 | 0 | 80 | 0 | 0 | 0 | 0 | 474.3732 | 516.6158 | 0 | 6703.9891 | 1
Condamine River Strain Excavation | $2015/16 | RBP | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 21 | 4569 | 2389 | 0 | 0 | 0 | 0 | 0 | 58.0081 | 613.7652 | 541.6158 | 0 | 8171.3891 | 1
CP INTERFERENCE TESTING AND MITIGATION | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 6092.5 | 441.5 | 1300 | 0 | 0 | 0 | 0 | 891.3555 | 410.7726 | 291.6158 | 0 | 9427.7439 | 1
DN200 & 300 METRO ANNUAL EXCAVATION PROGRAM | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
DN250 INTEGRITY UPGRADE PROGRAM | $2015/16 | RBP | 4900 | 5293 | 5970 | 3980 | 3680 | 4231 | AA-03 |  | 42243.5 | 13029.5 | 1500 | 335.5808 | 0 | 0 | 0 | 1020.239 | 3639.3521 | 3410.983
DN250, DN300, DN200 Assessment of loss of cover and mitigation | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earthing and Lightning protection design review (Stations) | $2015/16 | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total Nominal expenditure
EMERGENCY STOPPLE FITTINGS FOR DN250 EMERGENCIES | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17 | 18 | 19 | 20 | 21 | 22 | Total |  |  | Check nominal expenditure
Environmental Offset Strategy | $2015/16 | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17810.2237 | 25331.8131 | 15544.2198 | 6703.9891 | 8171.3891 | 9427.7439 | 82989.3786 |  |  | TRUE
Files up to date on x-info | $2015/16 | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fire protection upgrades to RBP compressor stations (FM Global) | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gas Measurement Upgrade - including shades | $2015/16 | RBP | 0 | 0 | 0 | 50 | 50 | 0 | 0
GIBSON ISLAND E/I REVIEW FEED | $2015/16 | RBP | 10 | 0 | 0 | 0 | 0 | 0 | 0
Gibson Island Pressure Vessel platforms | $2015/16 | RBP | 0 | 0 | 0 | 80 | 0 | 0 | 0
Lands Property Database | $2015/16 | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0
Laser Scanner for Feature Assessment | $2015/16 | RBP | 0 | 0 | 0 | 0 | 150 | 0 | AA-03
LOSS OF SUPPLY DESIGN REVIEW | $2015/16 | QLD | 8.3712 | 0 | 0 | 0 | 0 | 0 | 0
METER PERFORMANCE PROGRAM FEED | $2015/16 | QLD | 0 | 5.5808 | 0 | 0 | 0 | 0 | 0
MP14 MLV Removal - study and implementation | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
PEAT lateral cleaning pigging | $2015/16 | RBP | 15 | 0 | 0 | 0 | 0 | 0 | 0
PEAT LATERAL ILI - DN250 | $2015/16 | RBP | 0 | 0 | 0 | 140 | 0 | 0 | AA-03
PEAT LATERAL LIQUIDS REMOVAL | $2015/16 | RBP | 0 | 300 | 0 | 0 | 0 | 0 | AA-05
PIPELINE REPAIR & EXCAVATION PROGRAM (unplanned) | $2015/16 | RBP | 100 | 100 | 100 | 100 | 100 | 0 | 0
Portable Slug Catcher - DN400 | $2015/16 | QLD | 223.2316 | 0 | 0 | 0 | 0 | 0 | AA-05
PURCHASE 3D SCANNER TOOL | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
QLD OPERATIONS SIB FUNDING | $2015/16 | QLD | 117.1966 | 111.6158 | 111.6158 | 111.6158 | 111.6158 | 111.6158 | 0
QLD Tenure Audit | $2015/16 | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0
RBP - Security fencing upgrade for vent stacks | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
RBP - Station painting program | $2015/16 | RBP | 80 | 80 | 80 | 80 | 80 | 80 | 0
RBP - TYPE B GAS COMPLIANCE UPGRADES | $2015/16 | RBP | 25 | 110 | 110 | 0 | 0 | 0 | 0
RBP & PEAT ISOLATION PLAN UPGRADES | $2015/16 | RBP | 100 | 100 | 100 | 0 | 0 | 0 | 0
RBP- AS4853 ELECTRICAL HAZARD UPGRADES | $2015/16 | RBP | 0 | 120 | 0 | 0 | 0 | 0 | 0
RBP CE Lateral ILI - DN400 | $2015/16 | RBP | 0 | 0 | 10 | 190 | 0 | 0 | AA-03
RBP Cleaning Program (DN400) | $2015/16 | RBP | 16 | 0 | 0 | 0 | 0 | 0 | 0
RBP CP TELEMETRY UPGRADE | $2015/16 | RBP | 150 | 150 | 150 | 150 | 150 | 0 | AA-03
RBP CP UPGRADE PROGRAM | $2015/16 | RBP | 629 | 642 | 648 | 648 | 648 | 648 | AA-03
RBP DN400 Supply Offtakes | $2015/16 | RBP | 0 | 0 | 250 | 0 | 100 | 0 | 0
RBP HA RECTIFICATION | $2015/16 | RBP | 150 | 50 | 0 | 0 | 0 | 100 | 0
RBP LOOPING ILI - DN400 | $2015/16 | RBP | 0 | 0 | 0 | 0 | 1800 | 0 | AA-03
RBP LYTTON LATERAL ILI - DN200 | $2015/16 | RBP | 5 | 140 | 0 | 0 | 0 | 0 | AA-03
RBP MAINLINE ILI PROGRAM - DN250 | $2015/16 | RBP | 0 | 0 | 1500 | 0 | 0 | 0 | AA-03
RBP METRO (ORIGINAL) ILI - DN200 | $2015/16 | RBP | 0 | 60 | 0 | 0 | 0 | 0 | AA-03
RBP METRO ILI - DN300 | $2015/16 | RBP | 220 | 0 | 0 | 0 | 0 | 220 | AA-03
RBP METRO LOOP ILI - DN400 | $2015/16 | RBP | 0 | 0 | 120 | 0 | 0 | 0 | AA-03
RBP REPLACEMENT SPOOLS FOR DN250 CHECK VALVES | $2015/16 | RBP | 10 | 0 | 0 | 0 | 0 | 0 | 0
RBP RISK MITIGATION - FEED and IMPLEMENTATION | $2015/16 | RBP | 8000 | 1650 | 300 | 300 | 300 | 300 | AA-02
RBP S20 Decommissioned Compressor Removal | $2015/16 | RBP | 0 | 100 | 100 | 0 | 0 | 0 | 0
RBP SCC EMAT ILI - DN300 | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 900 | AA-03
RBP SCCMP EMAT ILI - DN250 | $2015/16 | RBP | 0 | 1800 | 1200 | 0 | 0 | 0 | AA-03
RBP SCRAPER TRAP MODIFICATIONS | $2015/16 | RBP | 0 | 200 | 200 | 0 | 0 | 0 | AA-03
RBP STATION FIRE SUPRESSION UPGRADES - BELLBIRD PARK | $2015/16 | RBP | 0 | 0 | 0 | 75 | 0 | 0 | 0
RBP STATION UPGRADES - HAZOP & Other | $2015/16 | RBP | 160 | 305 | 305 | 100 | 100 | 0 | 0
ROW Erosion Repairs - | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCOTIA / WOODROYD VENT EXTENSION | $2015/16 | RBP | 0 | 30 | 0 | 0 | 0 | 0 | 0
SIS demand/test tracking system | $2015/16 | QLD | 0 | 27.904 | 0 | 0 | 0 | 0 | 0
SIS improvement program FEED and Implementation | $2015/16 | QLD | 27.904 | 0 | 0 | 0 | 0 | 0 | 0
SMS Reviews - QLD | $2015/16 | QLD | 5.5808 | 0 | 0 | 0 | 0 | 0 | 0
SMS, RLR, MEJ project review | $2015/16 | QLD | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOLAR S20 Unit Control Panel Upgrade FEED | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
Station Remaining Life Review | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWANBANK ISOLATION VALVE | $2015/16 | RBP | 50 | 0 | 0 | 0 | 0 | 0 | 0
TOOWOOMBA DN250 RAIL CROSSING | $2015/16 | RBP | 0 | 11000 | 3500 | 0 | 0 | 0 | AA-06
TOOWOOMBA RANGE SLOPE MONITORING WORKS | $2015/16 | RBP | 300 | 650 | 0 | 0 | 0 | 0 | AA-06
Toowoomba Slope Management | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOOWOOMBA STATION HEATER INSTALLATION | $2015/16 | RBP | 0 | 250 | 0 | 0 | 0 | 0 | 0
Turbine overhauls - Dalby | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 1300 | AA-08
VEHICLE PURCHASES | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wallumbilla MS Upgrade | $2015/16 | RBP | 0 | 0 | 0 | 0 | 0 | 0 | 0
Applications and Renewals | $2014/15 | APA | 0 | 410.7726 | 513.168 | 410.7726 | 513.168 | 410.7726 | RBP01
Infrastructure Renewals | $2014/15 | APA | 0 | 133.9476 | 44.6492 | 44.6492 | 44.6492 | 0 | RBP02
AA Costs | $2015/16 | Regulated | 891.3555 | 70.8753 | 0 | 0 | 58.0081 | 891.3555 | 0
Remote Vehicle Comms - Journey Management | $2015/16 | Transmission | 1.7694 | 0 | 0 | 0 | 0 | 0 | 0
Satellite Strategy | $2015/16 | APA | 94.825 | 0 | 0 | 0 | 0 | 0 | 0
Enterprise Content Management | $2015/16 | APA | 283.7383 | 0 | 0 | 0 | 0 | 0 | 0
APA Website Project | $2015/16 | APA | 0 | 0 | 0 | 0 | 0 | 0 | 0
BI - Asset Datamart | $2015/16 | APA | 0 | 0 | 0 | 0 | 0 | 0 | 0
APA Grid - Energy Components Upgrade | $2015/16 | APA | 151.6921 | 0 | 0 | 0 | 0 | 0 | 0
Hyperion Upgrade to v 11-1-2-4 | $2015/16 | APA | 41.6962 | 0 | 0 | 0 | 0 | 0 | 0
APA Grid Services Initiatives Program | $2015/16 | Transmission | 49.6586 | 0 | 0 | 0 | 0 | 0 | 0
APA Grid Extend | $2015/16 | Transmission | 476.1008 | 105.6743 | 0 | 0 | 0 | 0 | 0
BI - Transmission Dashboard | $2015/16 | APA | 58.1944 | 0 | 0 | 0 | 0 | 0 | 0
HR Systems Refresh | $2015/16 | APA | 52.4229 | 277.4161 | 3.4865 | 0 | 0 | 0 | 0
SharePoint Upgrade | $2015/16 | APA | 62.2962 | 41.5131 | 0 | 0 | 0 | 0 | 0
SQL Server Upgrade | $2015/16 | APA | 55.37 | 3.6273 | 0 | 0 | 0 | 0 | 0
Upgrade Enterprise OSI PI Historian | $2015/16 | Pipelines | 14.4306 | 0.19591 | 0 | 0 | 0 | 0 | 0
Hazardous Area Platform | $2015/16 | Pipelines | 16.0327 | 92.7088 | 0 | 0 | 0 | 0 | 0
Form Digitisation Project | $2015/16 | APA | 10.045 | 76.007 | 0 | 0 | 0 | 0 | 0
Enterprise Asset Management Upgrade FY18 | $2015/16 | Pipelines | 7.9275 | 162.4542 | 0 | 0 | 0 | 0 | 0
PPM Refresh | $2015/16 | APA | 1.4252 | 49.9588 | 0 | 0 | 0 | 0 | 0
BizTalk System Upgrade FY18 | $2015/16 | APA | 0 | 47.1085 | 0 | 0 | 0 | 0 | 0
Automated Testing Tool | $2015/16 | APA | 0 | 25.0911 | 0 | 0 | 0 | 0 | 0
Oracle eBS Upgrade to v12 2 | $2015/16 | APA | 0 | 54.591 | 0 | 0 | 0 | 0 | 0
CRM Upgrade | $2015/16 | Transmission | 0 | 39.9991 | 0 | 0 | 0 | 0 | 0
X-Info Aware Version 2 | $2015/16 | Transmission | 0 | 18.2068 | 0 | 0 | 0 | 0 | 0
ID Procurement Data | $2015/16 | Pipelines | 0 | 17.2502 | 0.93588 | 0 | 0 | 0 | 0
Upgrade Enterprise OSI PI Historian 2017 | $2015/16 | Pipelines | 1.0551 | 7.6432 | 0 | 0 | 0 | 0 | 0
Supplier Qualification and Compliance | $2015/16 | APA | 0 | 6.6718 | 7.3643 | 0 | 0 | 0 | 0
BizTalk System Upgrade FY20 | $2015/16 | APA | 0 | 0 | 0 | 11.9689 | 0 | 0 | 0
Enterprise Asset Management Upgrade FY21 | $2015/16 | Pipelines | 0 | 0 | 0 | 6.9826 | 55.9479 | 0 | 0

## calculation¦real dollars
#VALUE!
real escalated expenditure ('000)
Project |  | currency | 17 | 18 | 19 | 20 | 21 | 22 | Total | Business case |  | Original Pipeline | Pipelines | Compressors | Regulators and meters | Easements | Communications | Other | Capitalised AA costs | Group IT | SIB Capex | PMA | Total | Check
ALARM RATIONALISATION | 0 | $2016/17 | 28.5457 | 0 | 0 | 0 | 0 | 0 | 28.5457 | 0 | 17 | 14081.0835 | 892.8045 | 0 | 0 | 0 | 0 | 0 | 911.8567 | 1410.3897 | 923.7245 | 0 | 18219.8588 | 1
ANODE BED EASEMENTS PROGRAM | AA-03 | $2016/17 | 214.83 | 219.945 | 225.06 | 230.175 | 235.29 | 240.405 | 1365.705 | AA | 18 | 15817.1145 | 7026.4755 | 102.3 | 261.4591 | 0 | 0 | 0 | 72.5055 | 1614.2712 | 1027.6237 | 0 | 25921.7496 | 1
BELLBIRD PARK STATION UPGRADE | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 11589.567 | 2546.247 | 102.3 | 0 | 0 | 0 | 0 | 0 | 590.1853 | 1080.918 | 0 | 15909.2173 | 1
COMMISSION LEGAL ADVICE FOR ENCROACHMENT MANAGEMENT | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 4901.7045 | 860.8545 | 0 | 81.84 | 0 | 0 | 0 | 0 | 472.0037 | 528.498 | 0 | 6844.9007 | 1
Condamine River Strain Excavation | 0 | $2016/17 | 0 | 204.6 | 0 | 0 | 0 | 0 | 204.6 | 0 | 21 | 4674.087 | 2443.947 | 0 | 0 | 0 | 0 | 0 | 59.3423 | 578.1274 | 554.073 | 0 | 8309.5767 | 1
CP INTERFERENCE TESTING AND MITIGATION | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 6232.6275 | 451.6545 | 1329.9 | 0 | 0 | 0 | 0 | 911.8567 | 425.7288 | 298.323 | 0 | 9650.0905 | 1
DN200 & 300 METRO ANNUAL EXCAVATION PROGRAM | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DN250 INTEGRITY UPGRADE PROGRAM | AA-03 | $2016/17 | 5012.7 | 5414.739 | 6107.31 | 4071.54 | 3764.64 | 4328.313 | 28699.242 | AA |  | 43215.1005 | 13329.1785 | 1534.5 | 343.2991 | 0 | 0 | 0 | 1043.7044 | 3680.3165 | 3489.4357 | 0 | 66635.5347 | 1
DN250, DN300, DN200 Assessment of loss of cover and mitigation | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earthing and Lightning protection design review (Stations) | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EMERGENCY STOPPLE FITTINGS FOR DN250 EMERGENCIES | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Environmental Offset Strategy | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Files up to date on x-info | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fire protection upgrades to RBP compressor stations (FM Global) | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gas Measurement Upgrade - including shades | 0 | $2016/17 | 0 | 0 | 0 | 51.15 | 51.15 | 0 | 102.3 | 0
GIBSON ISLAND E/I REVIEW FEED | 0 | $2016/17 | 10.23 | 0 | 0 | 0 | 0 | 0 | 10.23 | 0
Gibson Island Pressure Vessel platforms | 0 | $2016/17 | 0 | 0 | 0 | 81.84 | 0 | 0 | 81.84 | 0
Lands Property Database | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Laser Scanner for Feature Assessment | AA-03 | $2016/17 | 0 | 0 | 0 | 0 | 153.45 | 0 | 153.45 | AA
LOSS OF SUPPLY DESIGN REVIEW | 0 | $2016/17 | 8.5637 | 0 | 0 | 0 | 0 | 0 | 8.5637 | 0
METER PERFORMANCE PROGRAM FEED | 0 | $2016/17 | 0 | 5.7091 | 0 | 0 | 0 | 0 | 5.7091 | 0
MP14 MLV Removal - study and implementation | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PEAT lateral cleaning pigging | 0 | $2016/17 | 15.345 | 0 | 0 | 0 | 0 | 0 | 15.345 | 0
PEAT LATERAL ILI - DN250 | AA-03 | $2016/17 | 0 | 0 | 0 | 143.22 | 0 | 0 | 143.22 | AA
PEAT LATERAL LIQUIDS REMOVAL | AA-05 | $2016/17 | 0 | 306.9 | 0 | 0 | 0 | 0 | 306.9 | AA
PIPELINE REPAIR & EXCAVATION PROGRAM (unplanned) | 0 | $2016/17 | 102.3 | 102.3 | 102.3 | 102.3 | 102.3 | 0 | 511.5 | 0
Portable Slug Catcher - DN400 | AA-05 | $2016/17 | 228.366 | 0 | 0 | 0 | 0 | 0 | 228.366 | AA
PURCHASE 3D SCANNER TOOL | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QLD OPERATIONS SIB FUNDING | 0 | $2016/17 | 119.8921 | 114.183 | 114.183 | 114.183 | 114.183 | 114.183 | 690.807 | 0
QLD Tenure Audit | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RBP - Security fencing upgrade for vent stacks | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RBP - Station painting program | 0 | $2016/17 | 81.84 | 81.84 | 81.84 | 81.84 | 81.84 | 81.84 | 491.04 | 0
RBP - TYPE B GAS COMPLIANCE UPGRADES | 0 | $2016/17 | 25.575 | 112.53 | 112.53 | 0 | 0 | 0 | 250.635 | 0
RBP & PEAT ISOLATION PLAN UPGRADES | 0 | $2016/17 | 102.3 | 102.3 | 102.3 | 0 | 0 | 0 | 306.9 | 0
RBP- AS4853 ELECTRICAL HAZARD UPGRADES | 0 | $2016/17 | 0 | 122.76 | 0 | 0 | 0 | 0 | 122.76 | 0
RBP CE Lateral ILI - DN400 | AA-03 | $2016/17 | 0 | 0 | 10.23 | 194.37 | 0 | 0 | 204.6 | AA
RBP Cleaning Program (DN400) | 0 | $2016/17 | 16.368 | 0 | 0 | 0 | 0 | 0 | 16.368 | 0
RBP CP TELEMETRY UPGRADE | AA-03 | $2016/17 | 153.45 | 153.45 | 153.45 | 153.45 | 153.45 | 0 | 767.25 | AA
RBP CP UPGRADE PROGRAM | AA-03 | $2016/17 | 643.467 | 656.766 | 662.904 | 662.904 | 662.904 | 662.904 | 3951.849 | AA
RBP DN400 Supply Offtakes | 0 | $2016/17 | 0 | 0 | 255.75 | 0 | 102.3 | 0 | 358.05 | 0
RBP HA RECTIFICATION | 0 | $2016/17 | 153.45 | 51.15 | 0 | 0 | 0 | 102.3 | 306.9 | 0
RBP LOOPING ILI - DN400 | AA-03 | $2016/17 | 0 | 0 | 0 | 0 | 1841.4 | 0 | 1841.4 | AA
RBP LYTTON LATERAL ILI - DN200 | AA-03 | $2016/17 | 5.115 | 143.22 | 0 | 0 | 0 | 0 | 148.335 | AA
RBP MAINLINE ILI PROGRAM - DN250 | AA-03 | $2016/17 | 0 | 0 | 1534.5 | 0 | 0 | 0 | 1534.5 | AA
RBP METRO (ORIGINAL) ILI - DN200 | AA-03 | $2016/17 | 0 | 61.38 | 0 | 0 | 0 | 0 | 61.38 | AA
RBP METRO ILI - DN300 | AA-03 | $2016/17 | 225.06 | 0 | 0 | 0 | 0 | 225.06 | 450.12 | AA
RBP METRO LOOP ILI - DN400 | AA-03 | $2016/17 | 0 | 0 | 122.76 | 0 | 0 | 0 | 122.76 | AA
RBP REPLACEMENT SPOOLS FOR DN250 CHECK VALVES | 0 | $2016/17 | 10.23 | 0 | 0 | 0 | 0 | 0 | 10.23 | 0
RBP RISK MITIGATION - FEED and IMPLEMENTATION | AA-02 | $2016/17 | 8184 | 1687.95 | 306.9 | 306.9 | 306.9 | 306.9 | 11099.55 | AA
RBP S20 Decommissioned Compressor Removal | 0 | $2016/17 | 0 | 102.3 | 102.3 | 0 | 0 | 0 | 204.6 | 0
RBP SCC EMAT ILI - DN300 | AA-03 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 920.7 | 920.7 | AA
RBP SCCMP EMAT ILI - DN250 | AA-03 | $2016/17 | 0 | 1841.4 | 1227.6 | 0 | 0 | 0 | 3069 | AA
RBP SCRAPER TRAP MODIFICATIONS | AA-03 | $2016/17 | 0 | 204.6 | 204.6 | 0 | 0 | 0 | 409.2 | AA
RBP STATION FIRE SUPRESSION UPGRADES - BELLBIRD PARK | 0 | $2016/17 | 0 | 0 | 0 | 76.725 | 0 | 0 | 76.725 | 0
RBP STATION UPGRADES - HAZOP & Other | 0 | $2016/17 | 163.68 | 312.015 | 312.015 | 102.3 | 102.3 | 0 | 992.31 | 0
ROW Erosion Repairs - | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCOTIA / WOODROYD VENT EXTENSION | 0 | $2016/17 | 0 | 30.69 | 0 | 0 | 0 | 0 | 30.69 | 0
SIS demand/test tracking system | 0 | $2016/17 | 0 | 28.5457 | 0 | 0 | 0 | 0 | 28.5457 | 0
SIS improvement program FEED and Implementation | 0 | $2016/17 | 28.5457 | 0 | 0 | 0 | 0 | 0 | 28.5457 | 0
SMS Reviews - QLD | 0 | $2016/17 | 5.7091 | 0 | 0 | 0 | 0 | 0 | 5.7091 | 0
SMS, RLR, MEJ project review | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOLAR S20 Unit Control Panel Upgrade FEED | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Station Remaining Life Review | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SWANBANK ISOLATION VALVE | 0 | $2016/17 | 51.15 | 0 | 0 | 0 | 0 | 0 | 51.15 | 0
TOOWOOMBA DN250 RAIL CROSSING | AA-06 | $2016/17 | 0 | 11253 | 3580.5 | 0 | 0 | 0 | 14833.5 | AA
TOOWOOMBA RANGE SLOPE MONITORING WORKS | AA-06 | $2016/17 | 306.9 | 664.95 | 0 | 0 | 0 | 0 | 971.85 | AA
Toowoomba Slope Management | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOOWOOMBA STATION HEATER INSTALLATION | 0 | $2016/17 | 0 | 255.75 | 0 | 0 | 0 | 0 | 255.75 | 0
Turbine overhauls - Dalby | AA-08 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 1329.9 | 1329.9 | AA
VEHICLE PURCHASES | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wallumbilla MS Upgrade | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Applications and Renewals | RBP01 | $2016/17 | 0 | 425.7288 | 531.8525 | 425.7288 | 531.8525 | 425.7288 | 2340.8916 | RB
Infrastructure Renewals | RBP02 | $2016/17 | 0 | 138.8246 | 46.2749 | 46.2749 | 46.2749 | 0 | 277.6492 | RB
AA Costs | 0 | $2016/17 | 911.8567 | 72.5055 | 0 | 0 | 59.3423 | 911.8567 | 1955.5611 | 0
Remote Vehicle Comms - Journey Management | 0 | $2016/17 | 1.8101 | 0 | 0 | 0 | 0 | 0 | 1.8101 | 0
Satellite Strategy | 0 | $2016/17 | 97.006 | 0 | 0 | 0 | 0 | 0 | 97.006 | 0
Enterprise Content Management | 0 | $2016/17 | 290.2643 | 0 | 0 | 0 | 0 | 0 | 290.2643 | 0
APA Website Project | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BI - Asset Datamart | 0 | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
APA Grid - Energy Components Upgrade | 0 | $2016/17 | 155.181 | 0 | 0 | 0 | 0 | 0 | 155.181 | 0
Hyperion Upgrade to v 11-1-2-4 | 0 | $2016/17 | 42.6552 | 0 | 0 | 0 | 0 | 0 | 42.6552 | 0
APA Grid Services Initiatives Program | 0 | $2016/17 | 50.8008 | 0 | 0 | 0 | 0 | 0 | 50.8008 | 0
APA Grid Extend | 0 | $2016/17 | 487.0511 | 108.1048 | 0 | 0 | 0 | 0 | 595.1559 | 0
BI - Transmission Dashboard | 0 | $2016/17 | 59.5328 | 0 | 0 | 0 | 0 | 0 | 59.5328 | 0
HR Systems Refresh | 0 | $2016/17 | 53.6286 | 283.7966 | 3.5667 | 0 | 0 | 0 | 340.992 | 0
SharePoint Upgrade | 0 | $2016/17 | 63.729 | 42.4679 | 0 | 0 | 0 | 0 | 106.1969 | 0
SQL Server Upgrade | 0 | $2016/17 | 56.6435 | 3.7108 | 0 | 0 | 0 | 0 | 60.3543 | 0
Upgrade Enterprise OSI PI Historian | 0 | $2016/17 | 14.7625 | 0.20041 | 0 | 0 | 0 | 0 | 14.9629 | 0
Hazardous Area Platform | 0 | $2016/17 | 16.4014 | 94.8411 | 0 | 0 | 0 | 0 | 111.2426 | 0
Form Digitisation Project | 0 | $2016/17 | 10.276 | 77.7551 | 0 | 0 | 0 | 0 | 88.0312 | 0
Enterprise Asset Management Upgrade FY18 | 0 | $2016/17 | 8.1099 | 166.1906 | 0 | 0 | 0 | 0 | 174.3005 | 0
PPM Refresh | 0 | $2016/17 | 1.458 | 51.1079 | 0 | 0 | 0 | 0 | 52.5659 | 0
BizTalk System Upgrade FY18 | 0 | $2016/17 | 0 | 48.192 | 0 | 0 | 0 | 0 | 48.192 | 0
Automated Testing Tool | 0 | $2016/17 | 0 | 25.6682 | 0 | 0 | 0 | 0 | 25.6682 | 0
Oracle eBS Upgrade to v12 2 | 0 | $2016/17 | 0 | 55.8466 | 0 | 0 | 0 | 0 | 55.8466 | 0
CRM Upgrade | 0 | $2016/17 | 0 | 40.9191 | 0 | 0 | 0 | 0 | 40.9191 | 0
X-Info Aware Version 2 | 0 | $2016/17 | 0 | 18.6255 | 0 | 0 | 0 | 0 | 18.6255 | 0
ID Procurement Data | 0 | $2016/17 | 0 | 17.6469 | 0.95741 | 0 | 0 | 0 | 18.6043 | 0
Upgrade Enterprise OSI PI Historian 2017 | 0 | $2016/17 | 1.0794 | 7.8189 | 0 | 0 | 0 | 0 | 8.8983 | 0
Supplier Qualification and Compliance | 0 | $2016/17 | 0 | 6.8253 | 7.5337 | 0 | 0 | 0 | 14.359 | 0
0

## Calculation│RIN
#VALUE!
Inputs
| Labour | Material | Plant | Subcontract | Other | Overheads | Cost Total
Urban Risk Reduction | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Pipeline Integrity Management | #N/A | #N/A |  | #N/A | #N/A |  | #N/A
Toowoomba Crossing | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Dalby Turbine Overhaul |  |  |  | #N/A |  |  | #N/A
Applications and Renewals | 0.73312 | 0.15561 |  | 1.4522 |  |  | 2.3409
Infrastructure Renewals | #N/A | #N/A |  | #N/A |  |  | #N/A
| #N/A | #N/A | #N/A | #N/A | #N/A | Total
Urban Risk Reduction | 1.5253 | 2.5227 | 3.4908 | 0.2628 | 1.7855 | 9.587 |  | #N/A
Pipeline Integrity Management | #N/A | #N/A | #N/A | #N/A | 0 | #N/A |  | #N/A
Toowoomba Crossing | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
Dalby Turbine Overhaul | 0 | 0 | #N/A | 0 | 0 | #N/A |  | #N/A
Applications and Renewals | 0.73312 | 0.15561 | 1.4522 | 0 | 0 | 2.3409 |  | TRUE
Infrastructure Renewals | #N/A | #N/A | #N/A | 0 | 0 | #N/A |  | #N/A
Capex per year | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Urban Risk Reduction | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Pipeline Integrity Management | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Toowoomba Crossing | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Dalby Turbine Overhaul | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Applications and Renewals | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Infrastructure Renewals | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Percent of forecast capex
| Direct labour expenditure | Direct materials expenditure | Direct contractor expenditure | Other direct expenditure | Overheads | Total
Urban Risk Reduction | 15.91% | 26.31% | 36.41% | 2.741% | 18.62% | 100%
Pipeline Integrity Management | 0% | 0% | 0% | 0% | 0% | 0%
Toowoomba Crossing | 0% | 0% | 0% | 0% | 0% | 0%
Dalby Turbine Overhaul | 0% | 0% | 0% | 0% | 0% | 0%
Applications and Renewals | 31.32% | 6.647% | 62.03% | 0% | 0% | 100%
Infrastructure Renewals | #N/A | #N/A | #N/A | 0% | 0% | #N/A
Forecast Capex | #N/A | #N/A | #N/A | 2.4823 | 2.925 | #N/A |  | check | #N/A
Percentage | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | check | #N/A
Application to forecast
total forecast capex | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
total forecast capex | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 84.8554
Residual Capex | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10.1593 | check | 11.97%
Residual capex forecast
Direct labour expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct materials expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct contractor expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Other direct expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Overheads | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Business Cases
Urban Risk Reduction | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Row | 2 | 2 | 2 | 2 | 2 | 2
Direct labour expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct materials expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct contractor expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Other direct expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Overheads | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Check | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Pipeline Integrity Management | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Row | 3 | 3 | 3 | 3 | 3 | 3
Direct labour expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct materials expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct contractor expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Other direct expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Overheads | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Check | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Toowoomba Crossing | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Row | 4 | 4 | 4 | 4 | 4 | 4
Direct labour expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct materials expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct contractor expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Other direct expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Overheads | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Check | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Dalby Turbine Overhaul | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Row | 5 | 5 | 5 | 5 | 5 | 5
Direct labour expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct materials expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct contractor expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Other direct expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Overheads | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Check | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Applications and Renewals | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Row | 6 | 6 | 6 | 6 | 6 | 6
Direct labour expenditure | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0.73312
Direct materials expenditure | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0.15561
Direct contractor expenditure | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4522
Other direct expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overheads | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 2.3409
Check | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Infrastructure Renewals | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Row | 7 | 7 | 7 | 7 | 7 | 7
Direct labour expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct materials expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct contractor expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Other direct expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Overheads | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Check | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Total Capex | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Direct labour expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct materials expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Direct contractor expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Other direct expenditure | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Overheads | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Total | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Check | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Outputs│PTRM
#VALUE!
capex by asset type
asset type | Financial Year | 18 | 19 | 20 | 21 | 22 | Total (18-22) | check
Original Pipeline | $2016/17 | 15.8171 | 11.5896 | 4.9017 | 4.6741 | 6.2326 | 43.2151 | TRUE
Pipelines | $2016/17 | 7.0265 | 2.5462 | 0.86085 | 2.4439 | 0.45165 | 13.3292 | TRUE
Compressors | $2016/17 | 0.1023 | 0.1023 | 0 | 0 | 1.3299 | 1.5345 | TRUE
Regulators and meters | $2016/17 | 0.26146 | 0 | 0.08184 | 0 | 0 | 0.3433 | TRUE
Easements | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Communications | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Other | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Capitalised AA costs | $2016/17 | 0.072505 | 0 | 0 | 0.059342 | 0.91186 | 1.0437 | TRUE
Group IT | $2016/17 | 1.6143 | 0.59019 | 0.472 | 0.57813 | 0.42573 | 3.6803 | TRUE
SIB Capex | $2016/17 | 1.0276 | 1.0809 | 0.5285 | 0.55407 | 0.29832 | 3.4894 | TRUE
PMA | $2016/17 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
Total | $2016/17 | 25.9217 | 15.9092 | 6.8449 | 8.3096 | 9.6501 | 66.6355 | TRUE

## Outputs│RFM
#VALUE!
FY17 forecast for roll forward model
asset type | currency | 17
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | #N/A
#N/A | $2016/17 | 18.2199
| Check | TRUE

## Outputs│RIN
#VALUE!
4.1.1 - EXPANSION (by Project)
|  | EXPENDITURE Actual ($0's) |  |  | EXPENDITURE Forecast ($0's real, June 2017)
|  | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
Nil
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2 - REPLACEMENT (by Project)
|  | EXPENDITURE Actual ($0's) |  |  | EXPENDITURE Forecast ($0's real, June 2017)
|  | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
| #N/A |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Other |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| #N/A |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| #N/A |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| #N/A |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4.1.3 - NON SYSTEM CAPEX
|  | EXPENDITURE Actual ($0's) |  |  | EXPENDITURE Forecast ($0's real, June 2017)
|  | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
| #N/A |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| #N/A |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4.3 - FORECAST CAPEX
EXPENDITURE Forecast ($0's real, June 2017)
[5 empty] | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
| Direct labour expenditure |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Direct materials expenditure |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Direct contractor expenditure |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Other direct expenditure |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Overheads |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total |  |  |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[6 empty] | 18219858.8137 | #N/A | #N/A | #N/A | #N/A | #N/A
[6 empty] | 0 | #N/A | #N/A | #N/A | #N/A | #N/A

## Outputs│Tables
#VALUE!
[10 empty] | Projects |  |  | 17 | 18 | 19 | 20 | 21 | 22 | Total (18 - 22) | Check
| Table 4.10: Capital expenditure by driver over the forecast access arrangement period ($2016/17) | [8 empty] | Urban Risk Reduction | $2016/17 | AA-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | Pipeline Integrity Management | $2016/17 | AA-03 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total |  |  | Toowoomba Crossing | $2016/17 | AA-06 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Expansion | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Dalby Turbine Overhaul | $2016/17 | AA-08 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Replacement | 8.6955 | #N/A | #N/A | #N/A | #N/A | 37.5881 |  |  | Applications and Renewals | $2016/17 | RBP01 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Stay in Business | 17.2262 | #N/A | #N/A | #N/A | #N/A | 29.0474 |  |  | Infrastructure Renewals | $2016/17 | RBP02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Total | #N/A | #N/A | #N/A | #N/A | #N/A | 66.6355
[10 empty] | Percent of capex in projects |  | 17 | 17: 17-22; 18: 18-22
| Table 4.12: Forecast number of integrity upgrade digups | [8 empty] | Forecast | $m 2016/17 | 18.2199 | 17: 84.8554; 18: 66.6355
[10 empty] | Projects | $m 2016/17 | 14.7455 | 17: 74.6961; 18: 59.9505
|  | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 |  |  | Percent of capex in projects | Percent | 80.93% | 88.03% | 89.97%
| Integrity Digs | 108 | 116 | 130 | 91 | 85 | 100
Projects by size
| Table 4.13: Forecast capital expenditure Pipeline integrity management upgrade ($m 2016/17) | [8 empty] | Project |  | Value | Business Case
[10 empty] | DN250 INTEGRITY UPGRADE PROGRAM | $m 2016/17 | 28.6992 | AA-03
|  | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total |  |  | TOOWOOMBA DN250 RAIL CROSSING | $m 2016/17 | 14.8335 | AA-06
| ILI | 2.046 | 2.8951 | 0.33759 | 1.8414 | 1.1458 | 8.2658 |  |  | RBP RISK MITIGATION - FEED and IMPLEMENTATION | $m 2016/17 | 11.0996 | AA-02
| Integrity upgrade digups | 5.4147 | 6.1073 | 4.0715 | 3.7646 | 4.3283 | 23.6865 |  |  | RBP CP UPGRADE PROGRAM | $m 2016/17 | 3.9518 | AA-03
| CP upgrade | 1.0302 | 1.0414 | 1.0465 | 1.0516 | 0.90331 | 5.0731 |  |  | RBP SCCMP EMAT ILI - DN250 | $m 2016/17 | 3.069 | AA-03
| Other | 0.2046 | 0.2046 | 0 | 0.15345 | 0 | 0.56265 |  |  | Applications and Renewals | $m 2016/17 | 2.3409 | RBP01
| Integrity Management Upgrade | 8.6955 | 10.2484 | 5.4557 | 6.8111 | 6.3774 | 37.5881 |  |  | AA Costs | $m 2016/17 | 1.9556 | 0
[10 empty] | RBP LOOPING ILI - DN400 | $m 2016/17 | 1.8414 | AA-03
| Table 4.14: Forecast Capital expenditure on Toowoomba Range ($m 2016/17) | [8 empty] | RBP MAINLINE ILI PROGRAM - DN250 | $m 2016/17 | 1.5345 | AA-03
[10 empty] | ANODE BED EASEMENTS PROGRAM | $m 2016/17 | 1.3657 | AA-03
|  | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
| Towoomba Range | 11.9179 | #N/A | #N/A | #N/A | #N/A | 15.4985
Projects for 2016/17 by size
| Table 4.15: Forecast capital expenditure urban risk reduction ($m 2016/17) | [8 empty] | Project |  | Value | Business Case
[10 empty] | RBP RISK MITIGATION - FEED and IMPLEMENTATION | $m 2016/17 | 8.184 | AA-02
|  | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total |  |  | DN250 INTEGRITY UPGRADE PROGRAM | $m 2016/17 | 5.0127 | AA-03
| Urban risk reduction | 1.688 | #N/A | #N/A | #N/A | #N/A | 2.9156 |  |  | AA Costs | $m 2016/17 | 0.91186 | 0
[10 empty] | RBP CP UPGRADE PROGRAM | $m 2016/17 | 0.64347 | AA-03
| Table 4.16: Forecast Capital Expenditure Dalby turbine overhaul | [8 empty] | APA Grid Extend | $m 2016/17 | 0.48705 | 0
[10 empty] | TOOWOOMBA RANGE SLOPE MONITORING WORKS | $m 2016/17 | 0.3069 | AA-06
|  | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total |  |  | Enterprise Content Management | $m 2016/17 | 0.29026 | 0
| Dalby Turbine Overhaul | 0 | #N/A | #N/A | #N/A | #N/A | 1.3299 |  |  | Portable Slug Catcher - DN400 | $m 2016/17 | 0.22837 | AA-05
[10 empty] | RBP METRO ILI - DN300 | $m 2016/17 | 0.22506 | AA-03
| Table 4.17: Integration update plan | [8 empty] | ANODE BED EASEMENTS PROGRAM | $m 2016/17 | 0.21483 | AA-03
| Upgrade Projects | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 |  |  |  | Breakdown of Integrity digs by project ($m 2016/17)
| Energy Components | [6 empty] | ILI | bar: 2016/17; 2018/19; 2020/21
| Historian |  | X |  | X |  |  |  | Row | Project | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
| SCADA |  | X |  | X |  |  | 0 | 6 | ANODE BED EASEMENTS PROGRAM | 0.21483 | 0.21995 | 0.22506 | 0.23017 | 0.23529 | 0.24041 | 1.3657
| Middleware |  | X |  | X |  |  | 0 | 12 | DN250 INTEGRITY UPGRADE PROGRAM | 5.0127 | 5.4147 | 6.1073 | 4.0715 | 3.7646 | 4.3283 | 28.6992
| DBYD |  | X |  | X |  |  | 0 | 23 | Laser Scanner for Feature Assessment | 0 | 0 | 0 | 0 | 0.15345 | 0 | 0.15345
| Field Data / Mobility | X | X | X | X | X |  | 14 | 28 | PEAT LATERAL ILI - DN250 | 0 | 0 | 0 | 0.14322 | 0 | 0 | 0.14322
| GIS |  | X |  | X |  |  | 16 | 40 | RBP CE Lateral ILI - DN400 | 0 | 0 | 0.01023 | 0.19437 | 0 | 0 | 0.2046
| EAM | X |  | X |  | X |  | 0 | 42 | RBP CP TELEMETRY UPGRADE | 0.15345 | 0.15345 | 0.15345 | 0.15345 | 0.15345 | 0 | 0.76725
[8 empty] | 0 | 43 | RBP CP UPGRADE PROGRAM | 0.64347 | 0.65677 | 0.6629 | 0.6629 | 0.6629 | 0.6629 | 3.9518
| Table 4.18: RBP capital expenditure on applications upgrade | [6 empty] | 13 | 46 | RBP LOOPING ILI - DN400 | 0 | 0 | 0 | 0 | 1.8414 | 0 | 1.8414
[8 empty] | 20 | 47 | RBP LYTTON LATERAL ILI - DN200 | 0.005115 | 0.14322 | 0 | 0 | 0 | 0 | 0.14833
|  | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total | 14 | 48 | RBP MAINLINE ILI PROGRAM - DN250 | 0 | 0 | 1.5345 | 0 | 0 | 0 | 1.5345
| Applications renewal | 0.42573 | #N/A | #N/A | #N/A | #N/A | 2.3409 | 22 | 49 | RBP METRO (ORIGINAL) ILI - DN200 | 0 | 0.06138 | 0 | 0 | 0 | 0 | 0.06138
[8 empty] | 11 | 50 | RBP METRO ILI - DN300 | 0.22506 | 0 | 0 | 0 | 0 | 0.22506 | 0.45012
| AAI Table 3.3: Forecast conforming capital expenditure by category over the Access Arrangement Period | [6 empty] | 16 | 51 | RBP METRO LOOP ILI - DN400 | 0 | 0 | 0.12276 | 0 | 0 | 0 | 0.12276
[8 empty] | 14 | 55 | RBP SCC EMAT ILI - DN300 | 0 | 0 | 0 | 0 | 0 | 0.9207 | 0.9207
|  | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 |  | 16 | 56 | RBP SCCMP EMAT ILI - DN250 | 0 | 1.8414 | 1.2276 | 0 | 0 | 0 | 3.069
| Expansion | #N/A | #N/A | #N/A | #N/A | #N/A |  | 0 | 57 | RBP SCRAPER TRAP MODIFICATIONS | 0 | 0.2046 | 0.2046 | 0 | 0 | 0 | 0.4092
| Stay in Business | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  | Total | 6.2546 | 8.6955 | 10.2484 | 5.4557 | 6.8111 | 6.3774 | 43.8427
| Non System | #N/A | #N/A | #N/A | #N/A | #N/A
| Total | 25.9217 | #N/A | #N/A | #N/A | #N/A |  |  |  | Breakdown of Integrity digs by element ($m 2016/17)
[11 empty] | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total | Average
[10 empty] | ILI | 0.23017 | 2.046 | 2.8951 | 0.33759 | 1.8414 | 1.1458 | 8.496 | 1.416
[10 empty] | CP upgrade | 1.0117 | 1.0302 | 1.0414 | 1.0465 | 1.0516 | 0.90331 | 6.0848 | 1.0141
[10 empty] | DN250 INTEGRITY UPGRADE PROGRAM | 5.0127 | 5.4147 | 6.1073 | 4.0715 | 3.7646 | 4.3283 | 28.6992 | 4.7832
[10 empty] | Other | 0 | 0.2046 | 0.2046 | 0 | 0.15345 | 0 | 0.56265 | 0.093775
[10 empty] | Total | 6.2546 | 8.6955 | 10.2484 | 5.4557 | 6.8111 | 6.3774 | 43.8427 | 7.3071
ILI breakdown
[10 empty] | Original | 0.22506 | 1.9028 | 2.7621 | 0.14322 | 0 | 1.1458 | 6.1789
[10 empty] | Looping | 0 | 0 | 0.13299 | 0.19437 | 1.8414 | 0 | 2.1688
[10 empty] | Laterals | 0.005115 | 0.14322 | 0 | 0 | 0 | 0 | 0.14833
[10 empty] | Other | 0 | 0.2046 | 0.2046 | 0 | 0 | 0 | 0.4092
[10 empty] | Total ILI | 0.23017 | 2.2506 | 3.0997 | 0.33759 | 1.8414 | 1.1458 | 8.9052
Breakdown of Integrity digs by project ($m nominal)
[10 empty] | Project | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
[10 empty] | ANODE BED EASEMENTS PROGRAM | 0.21 | 0.215 | 0.22 | 0.225 | 0.23 | 0.235 | 1.335
[10 empty] | DN250 INTEGRITY UPGRADE PROGRAM | 4.9 | 5.293 | 5.97 | 3.98 | 3.68 | 4.231 | 28.054
[10 empty] | Laser Scanner for Feature Assessment | 0 | 0 | 0 | 0 | 0.15 | 0 | 0.15
[10 empty] | PEAT LATERAL ILI - DN250 | 0 | 0 | 0 | 0.14 | 0 | 0 | 0.14
[10 empty] | RBP CE Lateral ILI - DN400 | 0 | 0 | 0.01 | 0.19 | 0 | 0 | 0.2
[10 empty] | RBP CP TELEMETRY UPGRADE | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0 | 0.75
[10 empty] | RBP CP UPGRADE PROGRAM | 0.629 | 0.642 | 0.648 | 0.648 | 0.648 | 0.648 | 3.863
[10 empty] | RBP LOOPING ILI - DN400 | 0 | 0 | 0 | 0 | 1.8 | 0 | 1.8
[10 empty] | RBP LYTTON LATERAL ILI - DN200 | 0.005 | 0.14 | 0 | 0 | 0 | 0 | 0.145
[10 empty] | RBP MAINLINE ILI PROGRAM - DN250 | 0 | 0 | 1.5 | 0 | 0 | 0 | 1.5
[10 empty] | RBP METRO (ORIGINAL) ILI - DN200 | 0 | 0.06 | 0 | 0 | 0 | 0 | 0.06
[10 empty] | RBP METRO ILI - DN300 | 0.22 | 0 | 0 | 0 | 0 | 0.22 | 0.44
[10 empty] | RBP METRO LOOP ILI - DN400 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0.12
[10 empty] | RBP SCC EMAT ILI - DN300 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.9
[10 empty] | RBP SCCMP EMAT ILI - DN250 | 0 | 1.8 | 1.2 | 0 | 0 | 0 | 3
[10 empty] | RBP SCRAPER TRAP MODIFICATIONS | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0.4
[10 empty] | Total | 6.114 | 8.5 | 10.018 | 5.333 | 6.658 | 6.234 | 42.857
Comparison with numbers in business case
[10 empty] | Business Case | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | Total
[10 empty] | Inline Inspection of Pipelines | 225000 | 2000000 | 2830000 | 330000 | 1800000 | 1120000 | 8305000
[10 empty] | Coating Refurbishment and Life Extension | 4913000 | 5293000 | 5971000 | 3983000 | 3677000 | 4231000 | 28068000
[10 empty] | Laser Scanner for Feature Assessment | $ - | $ - | $ - | $ - | 150000 | $ - | 150000
[10 empty] | Easement Acquisition for CP | 210000 | 215000 | 220000 | 225000 | 230000 | 235000 | 1335000
[10 empty] | CP Upgrade Programme | 629000 | 642000 | 648000 | 648000 | 648000 | 648000 | 3863000
[10 empty] | CP Telemetry Installation | 150000 | 150000 | 150000 | 150000 | 150000 | $ - | 750000
[10 empty] | Total Forecast Capex | 6127000 | 8300000 | 9819000 | 5336000 | 6655000 | 6234000 | 42471000
[10 empty] | Business Case | [6 empty] | Total
[10 empty] | Inline Inspection of Pipelines | 0.23 | 2 | 2.83 | 0.33 | 1.8 | 1.12 | 8.31
[10 empty] | Coating Refurbishment and Life Extension | 4.91 | 5.29 | 5.97 | 3.98 | 3.68 | 4.23 | 28.06
[10 empty] | Laser Scanner for Feature Assessment | 0 | 0 | 0 | 0 | 0.15 | 0 | 0.15
[10 empty] | Easement Acquisition for CP | 0.21 | 0.22 | 0.22 | 0.23 | 0.23 | 0.24 | 1.35
[10 empty] | CP Upgrade Programme | 0.63 | 0.64 | 0.65 | 0.65 | 0.65 | 0.65 | 3.87
[10 empty] | CP Telemetry Installation | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0 | 0.75
[10 empty] | Total Forecast Capex | 6.13 | 8.3 | 9.82 | 5.34 | 6.66 | 6.24 | 42.49
Forecast capex organised in same way as BC
[10 empty] | Inline Inspection of Pipelines | 0.23 | 2 | 2.83 | 0.33 | 1.8 | 1.12
[10 empty] | Coating Refurbishment and Life Extension | 4.9 | 5.29 | 5.97 | 3.98 | 3.68 | 4.23
[10 empty] | Laser Scanner for Feature Assessment | 0 | 0 | 0 | 0 | 0.15 | 0
[10 empty] | Easement Acquisition for CP | 0.21 | 0.22 | 0.22 | 0.23 | 0.23 | 0.24
[10 empty] | CP Upgrade Programme | 0.64 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66
[10 empty] | CP Telemetry Installation | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0
[10 empty] | Total Forecast Capex | 6.13 | 8.32 | 9.83 | 5.35 | 6.67 | 6.25
Difference
[10 empty] | Inline Inspection of Pipelines | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Coating Refurbishment and Life Extension | -0.01 | 0 | 0 | 0 | 0 | 0
[10 empty] | Laser Scanner for Feature Assessment | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Easement Acquisition for CP | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | CP Upgrade Programme | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01
[10 empty] | CP Telemetry Installation | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total Forecast Capex | 0 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01
Nominal cost estimates for checking business cases
[11 empty] | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
[9 empty] | AA-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10850
[11 empty] | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
[9 empty] | AA-02 | Urban Risk Reduction | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11099.55
[11 empty] | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
[9 empty] | AA-06 | Toowoomba Crossing | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15450
[11 empty] | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
[9 empty] | AA-08 | Dalby Turrbine overhaul | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1300
IMU real
[11 empty] | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
[9 empty] | AA-03 | Integrity Management Upgrade | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 43842.711
[11 empty] | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | Total
[9 empty] | AA-03 | Integrity Management Upgrade | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 42857

## Outputs│Graphs
#VALUE!
Figure 4.3: Capital expenditure by asset class over the forecast AA period ($2015/16)