## Tables
Powercor REFCLs Tranche 2 Contingent Project Application
Tables
Summary of total expenditure requirements ($m real 2015)
| Forecast expenditure | 2016 | 2017 | 2018 | 2019 | 2020 | Total
| Project costs (capitalised) |  | 0 | 64.4862 | 45.9856 | 0 | 110.4718
| Project costs (expensed) |  | 0 | 2.532 | 1.8548 | 0 | 4.3868
| Incremental re-balancing works |  | 0 | 0 | 0 | 0.16356 | 0.16356
| Incremental compliance testing |  | 0 | 0 | 0 | 0.24293 | 0.24293
| Incremental technical support |  | 0 | 0 | 0 | 0.044011 | 0.044011
| Total |  | 0 | 67.0182 | 47.8404 | 0.4505 | 115.3091
Summary of incremental revenue requirements ($m real 2015)
| Building block components | 2016 | 2017 | 2018 | 2019 | 2020 | Total
| Return on capital |  | 0.06723 | 0.066374 | 4.2786 | 7.0364 | 11.4486
| Return of capital (regulatory depreciation) |  | 0.0048438 | 0.0056851 | 5.3613 | 7.0487 | 12.4205
| Operating expenditure |  | 0.00057187 | 2.7153 | 2.0721 | 0.56633 | 5.3542
| Net tax allowance |  | -0.040041 | -0.039886 | 0.73901 | 0.6989 | 1.358
| Annual revenue requirement (unsmoothed) |  | 0.032605 | 2.7475 | 12.4509 | 15.3503 | 30.5813
| Annual revenue requirement (smoothed) |  | 0 | 0 | 14.977 | 15.7987 | 30.7756
Check:
0.000126
1

## PTRM_inputs
Powercor REFCLs Tranche 2 Contingent Project Application
PTRM Inputs
CAPEX FOR PTRM
| 2018 debt update PTRM with incremental contingent project capex ($m 2015) |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
|  | Subtransmission |  | 47.0818 | 50.2589 | 46.4511 | 47.6864 | 48.1175
|  | Distribution |  | 293.5061 | 327.7156 | 331.8402 | 302.9272 | 282.4914
|  | Standard metering |  | 0 | 0 | 0 | 0 | 0
|  | Public lighting |  | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control |  | 5.9462 | 18.2034 | 45.7461 | 31.6068 | 8.1689
|  | Non-network general assets - IT |  | 39.8364 | 39.6901 | 33.4936 | 24.9294 | 19.0885
|  | Non-network general assets - Other |  | 17.1138 | 17.103 | 17.1254 | 17.182 | 17.2527
|  | VBRC |  | 11.7694 | 13.0727 | 10.1556 | 13.2291 | 13.1811
|  | Supervisory cables |  | 0 | 0 | 0 | 0 | 0
|  | Old SWER ACRs |  | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0.068474 | 0.18442 | 0.23591 | 0.21643 | 0.29612
|  | Surge arrestors |  | 0 | 0 | 0 | 0 | 0
|  | ACRs |  | 0 | 0 | 0 | 0 | 0 | 1
OPEX FOR PTRM
| 2018 debt update PTRM with incremental contingent project opex ($m 2015) |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Total opex ex. debt raising costs |  |  | 225.5466 | 231.4132 | 241.2425 | 243.7584 | 249.1378 | 1

## Calcs_for_PTRM
Powercor REFCLs Tranche 2 Contingent Project Application
Calculations for PTRM
CAPEX
| From Substitution PTRM with adjusted inflation provided by AER, 25 May 2018 ($m 2015) |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
|  | Subtransmission |  | 47.0818 | 50.2589 | 46.4511 | 47.6864 | 48.1175
|  | Distribution |  | 293.5061 | 327.7156 | 294.5473 | 280.9396 | 282.4914
|  | Standard metering |  | 0 | 0 | 0 | 0 | 0
|  | Public lighting |  | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control |  | 5.9462 | 18.2034 | 18.6508 | 7.6088 | 8.1689
|  | Non-network general assets - IT |  | 39.8364 | 39.6901 | 33.4936 | 24.9294 | 19.0885
|  | Non-network general assets - Other |  | 17.1138 | 17.103 | 17.1254 | 17.182 | 17.2527
|  | VBRC |  | 11.7694 | 13.0727 | 10.1556 | 13.2291 | 13.1811
|  | Supervisory cables |  | 0 | 0 | 0 | 0 | 0
|  | Old SWER ACRs |  | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0.068474 | 0.18442 | 0.23591 | 0.21643 | 0.29612
| Incremental contingent project capex ($m 2015) |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
|  | Subtransmission |  | 0 | 0 | 0 | 0 | 0
|  | Distribution |  | 0 | 0 | 37.391 | 21.9876 | 0
|  | Standard metering |  | 0 | 0 | 0 | 0 | 0
|  | Public lighting |  | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control |  | 0 | 0 | 27.0952 | 23.998 | 0
|  | Non-network general assets - IT |  | 0 | 0 | 0 | 0 | 0
|  | Non-network general assets - Other |  | 0 | 0 | 0 | 0 | 0
|  | VBRC |  | 0 | 0 | 0 | 0 | 0
|  | Supervisory cables |  | 0 | 0 | 0 | 0 | 0
|  | Old SWER ACRs |  | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0
| Remove repex already provided in 2016-20 EDPR |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
|  | Subtransmission |  | 0 | 0 | 0 | 0 | 0
|  | Distribution |  | 0 | 0 | -0.09801 | 0 | 0
|  | Standard metering |  | 0 | 0 | 0 | 0 | 0
|  | Public lighting |  | 0 | 0 | 0 | 0 | 0
|  | SCADA/Network control |  | 0 | 0 | 0 | 0 | 0
|  | Non-network general assets - IT |  | 0 | 0 | 0 | 0 | 0
|  | Non-network general assets - Other |  | 0 | 0 | 0 | 0 | 0
|  | VBRC |  | 0 | 0 | 0 | 0 | 0
|  | Supervisory cables |  | 0 | 0 | 0 | 0 | 0
|  | Old SWER ACRs |  | 0 | 0 | 0 | 0 | 0
|  | Land |  | 0 | 0 | 0 | 0 | 0
OPEX
| From 2018 debt update PTRM ($m 2015) |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Total opex ex. debt raising costs |  |  | 225.5466 | 231.4132 | 238.7105 | 241.9036 | 248.6873
| Incremental opex ($m 2015) |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Incremental contingent project opex |  |  | 0 | 0 | 2.532 | 1.8548 | 0.4505

## Year_Summary
Powercor REFCLs Tranche 2 Contingent Project Application
Summary by Year
(real 2015 dollars)
OPEX
| Cumulative real labour escalation from 2018 |  |  |  | 100% | 100% | 100.6% | 101.2%
| Incremental operating costs before wage escalation |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Incremental technical support | $m real 2015 |  |  | 0 | 0 | 0 | 0.043477
| Incremental re-balancing works | $m real 2015 |  |  | 0 | 0 | 0 | 0.16158
| Incremental compliance testing | $m real 2015 |  |  | 0 | 0 | 0 | 0.23998
| Total | $m real 2015 |  |  | 0 | 0 | 0 | 0.44503
| Incremental operating costs with real escalation ($m real 2015) |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Incremental technical support | $m real 2015 |  |  | 0 | 0 | 0 | 0.044011
| Incremental re-balancing works | $m real 2015 |  |  | 0 | 0 | 0 | 0.16356
| Incremental compliance testing | $m real 2015 |  |  | 0 | 0 | 0 | 0.24293
| Total | $m real 2015 |  |  | 0 | 0 | 0 | 0.4505
| Incremental contingent project opex |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Distribution Code voltage variation payment | $m real 2015 |  |  | 0 | 0 | 0 | 0
| PMO costs | $m real 2015 |  |  | 0 | 2.532 | 1.8548 | 0
| Incremental operating costs | $m real 2015 |  |  | 0 | 0 | 0 | 0.4505
| Total Opex | $m real 2015 |  |  | 0 | 2.532 | 1.8548 | 0.4505
CAPEX
| Capex by category |  | Allocation | 2016 | 2017 | 2018 | 2019 | 2020
| Capex categorised directly | $m real 2015 | Direct |  | 0 | 55.0964 | 37.8492 | 0
| Other capex | $m real 2015 | Pro-rata |  | 0 | 9.3898 | 8.1364 | 0
| Total capex | $m real 2015 |  |  | 0 | 64.4862 | 45.9856 | 0
| Check |  |  |  | 0 | 0 | 0 | 0
| Percentage capex by category (directly categorised) |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Distribution | % |  |  | 0% | 57.98% | 47.81% | 0%
| SCADA/Network control | % |  |  | 0% | 42.02% | 52.19% | 0%
| Total % | % |  |  | 0% | 100% | 100% | 0%
| Incremental contingent project capex by category |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Distribution | $m real 2015 |  |  | 0 | 37.391 | 21.9876 | 0
| SCADA/Network control | $m real 2015 |  |  | 0 | 27.0952 | 23.998 | 0
| Total project capex | $m real 2015 |  |  | 0 | 64.4862 | 45.9856 | 0
| Total capex ($m 2015) |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Distribution | $m real 2015 |  |  | 0 | 37.391 | 21.9876 | 0
| SCADA/Network control | $m real 2015 |  |  | 0 | 27.0952 | 23.998 | 0
| Total capex | $m real 2015 |  |  | 0 | 64.4862 | 45.9856 | 0

## Cost_Summary
Powercor REFCLs Tranche 2 Contingent Project Application
Cost summary by site
Costs ($000s 2015)
|  |  |  | BAN | BAS | BETS | BGO | CTN | GL | Total
Design
|  |  | Design | 1383.2612 | 1064.3035 | 792.5914 | 1069.0084 | 877.869 | 985.2992 | 6172.3328
Feeder works
|  |  | Surge arrestor sites (single phase) | 1317.7229 | 1286.374 | 597.7661 | 501.3047 | 280.3461 | 526.5549 | 4510.0686
|  |  | Surge arrestor sites (three phase) | 1740.9111 | 1358.7114 | 1048.4006 | 465.3198 | 637.6911 | 1085.1807 | 6336.2147
|  |  | ACRs | 666.2634 | 565.518 | 50.1531 | 150.4594 | 400.0069 | 200.0034 | 2032.4042
|  |  | ACR/gas switch control box replacement | 312.0644 | 149.1294 | 137.5613 | 30.5692 | 106.6077 | 60.9187 | 796.8507
|  |  | Admittance balancing units (single phase) | 1031.5998 | 1002.6543 | 315.1114 | 346.6226 | 408.3282 | 628.1972 | 3732.5135
|  |  | Admittance balancing units (three phase) | 2711.8941 | 2153.2298 | 1219.399 | 940.6793 | 1529.5823 | 1494.8191 | 10049.6036
|  |  | Re-phasing | 65.585 | 68.8945 | 20.8724 | 22.2639 | 29.0744 | 22.1519 | 228.842
|  |  | Fusesavers | 774.7149 | 749.0005 | 258.8492 | 284.7341 | 284.5163 | 478.5047 | 2830.3197
|  |  | HV Regulators upgrade (control box) | 90.0288 | 112.7997 | 0 | 0 | 0 | 22.8767 | 225.7052
|  |  | HV Regulators upgrade (close delta) | 364.3338 | 364.7667 | 361.4887 | 361.4887 | 1444.3001 | 541.6125 | 3437.9904
|  |  | Distribution switchgear (installed) | 869.526 | 579.684 | 483.07 | 579.684 | 0 | 193.228 | 2705.192
|  |  | UG cable testing | 625.174 | 401.529 | 223.069 | 239.925 | 61.411 | 187.943 | 1739.051
|  |  | UG cable replacement | 3310.008 | 2026.752 | 1002.768 | 1099.488 | 75.192 | 801.216 | 8315.424
|  |  | Capacitance reducing isolation substation (6 MVA) | 800.379 | 0 | 0 | 0 | 0 | 0 | 800.379
|  |  | HV customer works | 805.254 | 436.389 | 270.097 | 135.049 | 270.097 | 67.524 | 1984.41
|  |  | ZSS Feeder Exit Relocation | 439.3291 | 198.062 | 0 | 0 | 0 | 697.9282 | 1335.3193
|  |  | GFN on feeder and associated equipment | 1698.7168 | 0 | 0 | 0 | 0 | 0 | 1698.7168
Substation
Primary Plant
|  |  | GFN | 4483.2509 | 4206.3099 | 2635.3364 | 2566.1523 | 1447.1152 | 3225.4646 | 18563.6292
|  |  | GFN enclosure | 144.921 | 144.921 | 144.921 | 144.921 | 144.921 | 0 | 724.605
|  |  | Indoor switchboard and switch room (incl GFN enclosure) | 0 | 0 | 0 | 0 | 0 | 870.491 | 870.491
|  |  | RMU | 200.427 | 200.427 | 133.618 | 133.618 | 133.618 | 133.618 | 935.326
|  |  | Station service transformer (500kVA) | 0 | 0 | 94.682 | 94.682 | 47.341 | 94.682 | 331.387
|  |  | Station service transformer (750kVA) | 104.344 | 104.344 | 0 | 0 | 0 | 0 | 208.688
|  |  | Cap bank | 309.177 | 0 | 0 | 0 | 0 | 0 | 309.177
|  |  | AC board (Including change over) | 48.307 | 48.307 | 48.307 | 48.307 | 48.307 | 48.307 | 289.842
|  |  | Indoor switchboard | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Voltage transformer | 49.563 | 49.563 | 0 | 0 | 16.521 | 33.042 | 148.689
|  |  | Earth grid modification | 216.852 | 216.852 | 216.852 | 216.852 | 0 | 216.852 | 1084.26
|  | 0 | Other | 352.189 | 276.057 | 205.017 | 245.595 | 175.153 | 254.39 | 1508.401
0
|  | SCADA / Protection & Control/ Comms |  | 2128.8862 | 1280.3602 | 1025.9738 | 767.5258 | 595.5113 | 1927.5163 | 7725.7736
|  | Commissioning |  | 1255.073 | 717.31 | 578.377 | 458.767 | 514.421 | 370.789 | 3894.737
|  | Construction delivery & site control |  | 1357.114 | 1052.038 | 580.392 | 417.234 | 541.07 | 662.758 | 4610.606
Contracts
|  | 0 | Traffic control | 649.397 | 575.387 | 293.2 | 223.096 | 180.392 | 268.054 | 2189.526
|  | 0 | Line survey | 275.221 | 275.221 | 144.18 | 91.642 | 107.944 | 220.294 | 1114.502
|  | 0 | Civil works | 930.4492 | 897.402 | 657.1662 | 595.7929 | 390.9006 | 900.7709 | 4372.4819
|  |  | Mob/Demob | 33.815 | 33.815 | 33.815 | 33.815 | 33.815 | 33.815 | 202.89
|  |  | Other | 181.151 | 160.862 | 115.937 | 200.957 | 323.174 | 159.413 | 1141.494
Other Project Costs
|  |  | Test trailer | 0 | 0 | 0 | 0 | 0 | 0 | 154.582
|  |  | Spare GFN | 0 | 0 | 0 | 0 | 0 | 0 | 1159.367
| Total capital cost |  |  | 31726.9035 | 22756.974 | 13688.9716 | 12465.5529 | 11105.2262 | 17414.2151 | 110471.7923
| PMO cost |  |  | 1275.0353 | 914.5533 | 550.13 | 500.9635 | 446.2949 | 699.8394 | 4386.8164
| Distribution Code voltage variation payment |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Project Cost |  |  | 33001.9388 | 23671.5273 | 14239.1017 | 12966.5164 | 11551.5211 | 18114.0545 | 114858.6087
TRUE

## Project_inputs
Powercor REFCLs Tranche 2 Contingent Project Application
Project inputs
MAJOR ITEM UNIT COSTS
(real 2015 dollars)
Feeder works
|  |  | Surge arrestor sites (single phase) | 357 | $/ea
|  |  | Surge arrestor sites (three phase) | 531 | $/ea
|  |  | ACRs | 24347 | $/ea
|  |  | ACR/gas switch control box replacement | 5976 | $/ea
|  |  | Admittance balancing units (single phase) | 14347 | $/ea
|  |  | Admittance balancing units (three phase) | 21835 | $/ea
|  |  | Re-phasing | 205 | $/ea
|  |  | Fusesavers | 11265 | $/ea
|  |  | HV Regulators upgrade (control box) | 13623 | $/ea
|  |  | HV Regulators upgrade (close delta) | 145694 | $/ea
|  |  | Distribution switchgear (installed) | 96614 | $/ea
UG cable testing
|  |  | UG cable replacement | 312 | $/m
|  |  | Capacitance reducing isolation substation (6 MVA) | 800379 | $/ea
|  |  | HV customer works |  | $/ea
ZSS Feeder Exit Relocation
GFN on feeder and associated equipment
Substation
Primary Plant
|  |  | GFN | 1159367 | $/ea
|  |  | GFN enclosure | 144921 | $/ea
|  |  | Indoor switchboard and switch room (incl GFN enclosure) | 870491 | $/ea
|  |  | RMU | 66809 | $/ea
|  |  | Station service transformer (500kVA) | 47341 | $/ea
|  |  | Station service transformer (750kVA) | 52172 | $/ea
|  |  | Cap bank | 309177 | $/ea
|  |  | AC board (Including change over) | 48307 | $/ea
|  |  | Indoor switchboard | 401914 | $/ea
|  |  | 22kV circuit breaker (outdoor) | 68615 | $/ea
|  |  | Voltage transformer | 16521 | $/ea
|  |  | Earth grid modification | 216852 | $/ea
Other
OPEX
(real 2015 dollars)
|  | Incremental technical support |  | 86953 | $ pa
|  | Incremental re-balancing works |  | 166659 | $ pa
|  | Incremental re-balancing works - per feeder cost |  | 2898 | $ pa/feeder
|  | Incremental compliance testing |  | 8888 | $ pa/feeder
| Feeders |  |  | Feeders by ZSS
|  | BAN |  | 12
|  | BAS |  | 9
|  | BETS |  | 8
|  | BGO |  | 7
|  | CTN |  | 6
|  | GL |  | 9
|  | Total |  | 51
CAPEX
| Capex asset categories |  |  | Standard Life (yrs)
|  | Distribution |  | 50
|  | SCADA/Network control |  | 13
OTHER COSTS
| Distribution Code voltage variation payment |  |  |  | 2016 | 2017 | 2018 | 2019 | 2020
|  | BAN |  |  |  |  | 0 | 0 | 0
|  | BAS |  |  |  |  | 0 | 0 | 0
|  | BETS |  |  |  |  | 0 | 0 | 0
|  | BGO |  |  |  |  | 0 | 0 | 0
|  | CTN |  |  |  |  | 0 | 0 | 0
|  | GL |  |  |  |  | 0 | 0 | 0
| Total | [5 empty] | 0 | 0 | 0
| Test trailer | [5 empty] | 154582 | 0 | 0
| Spare GFN | [5 empty] | 1159367 | 0 | 0
PMO COST
| Total PMO Costs |  |  | 4349352
TIMING
|  | First year of project |  | 2018
| Real labour escalation |  |  |  | 2016 | 2017 | 2018 | 2019 | 2020
|  | Wage escalation (real) |  |  |  |  | 0% | 0.5936% | 0.632%
|  | Cumulative real labour escalation from 2018 |  |  |  | 1 | 100% | 100.6% | 101.2%
| Project timing |  |  |  | Design | Construction | Commissioning | Operation
|  | BAN |  |  | 2018 | 2018 | 2019 | 2019
|  | BAS |  |  | 2018 | 2019 | 2019 | 2020
|  | BETS |  |  | 2018 | 2019 | 2019 | 2020
|  | BGO |  |  | 2018 | 2019 | 2019 | 2020
|  | CTN |  |  | 2018 | 2018 | 2019 | 2019
|  | GL |  |  | 2018 | 2018 | 2019 | 2019

## Asset_groups
Powercor REFCLs Tranche 2 Contingent Project Application
Asset groups
(real 2015 dollars)
|  |  |  | Type | Allocation Basis | Depreciation category
Design & Project Management Labour
|  |  | Design | Capex | Direct | Distribution
Feeder works
|  |  | Surge arrestor sites (single phase) | Capex | Direct | Distribution
|  |  | Surge arrestor sites (three phase) | Capex | Direct | Distribution
|  |  | ACRs | Capex | Direct | Distribution
|  |  | ACR/gas switch control box replacement | Capex | Direct | Distribution
|  |  | Admittance balancing units (single phase) | Capex | Direct | SCADA/Network control
|  |  | Admittance balancing units (three phase) | Capex | Direct | SCADA/Network control
|  |  | Re-phasing | Capex | Direct | Distribution
|  |  | Fusesavers | Capex | Direct | SCADA/Network control
|  |  | HV Regulators upgrade (control box) | Capex | Direct | Distribution
|  |  | HV Regulators upgrade (close delta) | Capex | Direct | Distribution
|  |  | Distribution switchgear (installed) | Capex | Direct | Distribution
|  |  | UG cable testing | Capex | Direct | Distribution
|  |  | UG cable replacement | Capex | Direct | Distribution
|  |  | Capacitance reducing isolation substation (6 MVA) | Capex | Direct | Distribution
|  |  | HV customer works | Capex | Direct | Distribution
|  |  | ZSS Feeder Exit Relocation | Capex | Direct | Distribution
|  |  | GFN on feeder and associated equipment | Capex | Direct | Distribution
Substation
Primary Plant
|  |  | GFN | Capex | Direct | SCADA/Network control
|  |  | GFN enclosure | Capex | Direct | Distribution
|  |  | Indoor switchboard and switch room (incl GFN enclosure) | Capex | Direct | Distribution
|  |  | RMU | Capex | Direct | Distribution
|  |  | Station service transformer (500kVA) | Capex | Direct | Distribution
|  |  | Station service transformer (750kVA) | Capex | Direct | Distribution
|  |  | Cap bank | Capex | Direct | Distribution
|  |  | AC board (Including change over) | Capex | Direct | Distribution
|  |  | Indoor switchboard | Capex | Direct | Distribution
|  |  | 22kV circuit breaker (outdoor) | Capex | Direct | Distribution
|  |  | Voltage transformer | Capex | Direct | Distribution
|  |  | Earth grid modification | Capex | Direct | Distribution
|  |  | Other | Capex | Direct | Distribution
|  |  | SCADA / Protection & Control/ Comms | Capex | Direct | SCADA/Network control
|  |  | Commissioning | Capex | Pro-rata
|  |  | Construction delivery & site control | Capex | Pro-rata
Contracts
|  |  | Traffic control | Capex | Pro-rata
|  |  | Line survey | Capex | Pro-rata
|  |  | Civil works | Capex | Pro-rata
|  |  | Mob/Demob | Capex | Pro-rata
|  |  | Other | Capex | Pro-rata
Other
|  |  | Distribution Code voltage variation payment | Opex | Pro-rata
|  |  | PMO costs | Opex | Pro-rata
|  |  | Test trailer | Capex | Direct | Distribution
|  |  | Spare GFN | Capex | Direct | Distribution

## BAN_volumes
Powercor REFCLs Tranche 2 Contingent Project Application
Volumes: |  |  | BAN
(real 2015 dollars)
Resource partner rates used |  |  |  | Ballarat
Design |  |  |  | 2018
Construction |  |  |  | 2018
[5 empty] | Materials |  | Contracts ($) | Labour ($) | Labour (hours)
| Year incurred |  |  |  | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018
[5 empty] | Unit cost (ea) | Qty | Contracts | Other Labour ($) | Design hrs | Live Linework | General Linework | Sub Tester | Fitter
| Labour Rates ($/hr) | [7 empty] | 196.0404 | 181.9551 | 166.8922 | 235.9085 | 164.5629
| Design (hours) | [7 empty] | 7056
Feeder works
|  |  | Surge arrestor sites (single phase) |  | 357 | 1079 |  |  |  | 5125 | 0 | 0 | 0
|  |  | Surge arrestor sites (three phase) |  | 531 | 1104 |  |  |  | 6346 | 0 | 0 | 0
|  |  | ACRs |  | 24347 | 13 |  |  |  | 1248 | 0 | 520 | 0
|  |  | ACR/gas switch control box replacement |  | 5976 | 21 |  |  |  | 0 | 168 | 672 | 0
|  |  | Admittance balancing units (single phase) |  | 14347 | 32 |  |  |  | 0 | 1760 | 512 | 960
|  |  | Admittance balancing units (three phase) |  | 21835 | 77 |  |  |  | 0 | 2156 | 1232 | 2310
|  |  | Re-phasing |  | 205 | 43 |  |  |  | 312 | 0 | 0 | 0
|  |  | Fusesavers |  | 11265 | 59 |  |  |  | 604.9841 | 0 | 0 | 0
|  |  | HV Regulators upgrade (control box) |  | 13623 | 4 |  |  |  | 0 | 32 | 128 | 0
|  |  | HV Regulators upgrade (close delta) |  | 145694 | 2 |  |  |  | 0 | 324 | 80 | 0
|  |  | Distribution switchgear (installed) |  | 96614 | 9
|  |  | UG cable testing |  | 625174 | 1
|  |  | UG cable replacement |  | 312 | 10609
|  |  | Capacitance reducing isolation substation (6 MVA) |  | 800379 | 1
|  |  | HV customer works |  | 346585 | 1 | 90000 | 368669
|  |  | ZSS Feeder Exit Relocation |  | 104343 | 1 | 289842 |  |  | 72 | 192
|  |  | GFN on feeder and associated equipment |  | 1515052 | 1 | [5 empty] | 360 | 600
Substation
Primary Plant
|  |  | GFN |  | 1159367 | 3 | [6 empty] | 6108
|  |  | GFN enclosure |  | 144921 | 1
|  |  | Indoor switchboard and switch room (incl GFN enclosure) |  | 870491
|  |  | RMU |  | 66809 | 3
|  |  | Station service transformer (500kVA) |  | 47341 | 0
|  |  | Station service transformer (750kVA) |  | 52172 | 2
|  |  | Cap bank |  | 309177 | 1
|  |  | AC board (Including change over) |  | 48307 | 1
|  |  | Indoor switchboard |  | 401914
|  |  | 22kV circuit breaker (outdoor) |  | 68615
|  |  | Voltage transformer |  | 16521 | 3
|  |  | Earth grid modification |  | 216852 | 1
|  |  | Other |  | 352189 | 1
|  | SCADA / Protection & Control/ Comms |  |  | 483593 | 1 |  | 17802 |  |  |  | 5556 | 1925
|  | Commissioning | [5 empty] | 1255073
|  | Construction delivery & site control | [5 empty] | 1357114
Contracts
|  |  | Traffic control |  |  |  | 649397
|  |  | Line survey |  |  |  | 275221
|  |  | Civil works |  |  |  | 930449.1689
|  |  | Mob/Demob |  |  |  | 33815
|  |  | Other |  |  |  | 181151

## BAS_volumes
Powercor REFCLs Tranche 2 Contingent Project Application
Volumes: |  |  | BAS
(real 2015 dollars)
Resource partner rates used |  |  |  | Ballarat
Design |  |  |  | 2018
Construction |  |  |  | 2019
[5 empty] | Materials |  | Contracts ($) | Labour ($) | Labour (hours)
| Year incurred |  |  |  | 2019 | 2019 | 2019 | 2019 | 2018 | 2019 | 2019 | 2019 | 2019
[5 empty] | Unit cost (ea) | Qty | Contracts | Other Labour ($) | Design | Live Linework | General Linework | Sub Tester | Fitter
| Labour Rates ($/hr) | [7 empty] | 196.0404 | 183.0351 | 167.8828 | 237.3088 | 165.5396
| Design (hours) | [7 empty] | 5429
Feeder works
|  |  | Surge arrestor sites (single phase) |  | 357 | 1049 |  |  |  | 4982 | 0 | 0 | 0
|  |  | Surge arrestor sites (three phase) |  | 531 | 857 |  |  |  | 4937 | 0 | 0 | 0
|  |  | ACRs |  | 24347 | 11 |  |  |  | 1056 | 0 | 440 | 0
|  |  | ACR/gas switch control box replacement |  | 5976 | 10 |  |  |  | 0 | 80 | 320 | 0
|  |  | Admittance balancing units (single phase) |  | 14347 | 31 |  |  |  | 0 | 1705 | 496 | 930
|  |  | Admittance balancing units (three phase) |  | 21835 | 61 |  |  |  | 0 | 1708 | 976 | 1830
|  |  | Re-phasing |  | 205 | 45 |  |  |  | 326 | 0 | 0 | 0
|  |  | Fusesavers |  | 11265 | 57 |  |  |  | 584.0164 | 0 | 0 | 0
|  |  | HV Regulators upgrade (control box) |  | 13623 | 5 |  |  |  | 0 | 40 | 160 | 0
|  |  | HV Regulators upgrade (close delta) |  | 145694 | 2 |  |  |  | 0 | 324 | 80 | 0
|  |  | Distribution switchgear (installed) |  | 96614 | 6
|  |  | UG cable testing |  | 401529 | 1
|  |  | UG cable replacement |  | 312 | 6496
|  |  | Capacitance reducing isolation substation (6 MVA) |  | 800379 | 0
|  |  | HV customer works |  | 185466 | 1 | 50000 | 200923
|  |  | ZSS Feeder Exit Relocation |  | 56036 | 1 | 96614 |  |  | 72 | 192
|  |  | GFN on feeder and associated equipment |  | 0 | 0
Substation
Primary Plant
|  |  | GFN |  | 1159367 | 3 | [6 empty] | 4399
|  |  | GFN enclosure |  | 144921 | 1
|  |  | Indoor switchboard and switch room (incl GFN enclosure) |  | 870491
|  |  | RMU |  | 66809 | 3
|  |  | Station service transformer (500kVA) |  | 47341
|  |  | Station service transformer (750kVA) |  | 52172 | 2
|  |  | Cap bank |  | 309177
|  |  | AC board (Including change over) |  | 48307 | 1
|  |  | Indoor switchboard |  | 401914
|  |  | 22kV circuit breaker (outdoor) |  | 68615
|  |  | Voltage transformer |  | 16521 | 3
|  |  | Earth grid modification |  | 216852 | 1
|  |  | Other |  | 276057 | 1
|  | SCADA / Protection & Control/ Comms |  |  | 215757 | 1 |  | 17802 |  |  |  | 3445 | 1385
|  | Commissioning | [5 empty] | 717310
|  | Construction delivery & site control | [5 empty] | 1052038
Contracts
|  |  | Traffic control |  |  |  | 575387
|  |  | Line survey |  |  |  | 275221
|  |  | Civil works |  |  |  | 897402.0171
|  |  | Mob/Demob |  |  |  | 33815
|  |  | Other |  |  |  | 160862

## BETS_volumes
Powercor REFCLs Tranche 2 Contingent Project Application
Volumes: |  |  | BETS
(real 2015 dollars)
Resource partner rates used |  |  |  | Bendigo
Design |  |  |  | 2018
Construction |  |  |  | 2019
[5 empty] | Materials |  | Contracts ($) | Labour ($) | Labour (hours)
| Year incurred |  |  |  | 2019 | 2019 | 2019 | 2019 | 2018 | 2019 | 2019 | 2019 | 2019
[5 empty] | Unit cost (ea) | Qty | Contracts | Other Labour ($) | Design | Live Linework | General Linework | Sub Tester | Fitter
| Labour Rates ($/hr) | [7 empty] | 196.0404 | 163.6544 | 154.0433 | 252.3827 | 155.1212
| Design (hours) | [7 empty] | 4043
Feeder works
|  |  | Surge arrestor sites (single phase) |  | 357 | 527 |  |  |  | 2503 | 0 | 0 | 0
|  |  | Surge arrestor sites (three phase) |  | 531 | 712 |  |  |  | 4096 | 0 | 0 | 0
|  |  | ACRs |  | 24347 | 1 |  |  |  | 96 | 0 | 40 | 0
|  |  | ACR/gas switch control box replacement |  | 5976 | 9 |  |  |  | 0 | 72 | 288 | 0
|  |  | Admittance balancing units (single phase) |  | 14347 | 10 |  |  |  | 0 | 550 | 160 | 300
|  |  | Admittance balancing units (three phase) |  | 21835 | 35 |  |  |  | 0 | 980 | 560 | 1050
|  |  | Re-phasing |  | 205 | 15 |  |  |  | 108.75 | 0 | 0 | 0
|  |  | Fusesavers |  | 11265 | 20 |  |  |  | 205 | 0 | 0 | 0
|  |  | HV Regulators upgrade (control box) |  | 13623 |  |  |  |  | 0 | 0 | 0 | 0
|  |  | HV Regulators upgrade (close delta) |  | 145694 | 2 |  |  |  | 0 | 324 | 80 | 0
|  |  | Distribution switchgear (installed) |  | 96614 | 5
|  |  | UG cable testing |  | 223069 | 1
|  |  | UG cable replacement |  | 312 | 3214
|  |  | Capacitance reducing isolation substation (6 MVA) |  | 800379
|  |  | HV customer works |  | 97388 | 1 | 40000 | 132709
|  |  | ZSS Feeder Exit Relocation |  | 0 | 0
|  |  | GFN on feeder and associated equipment |  | 0 | 0
Substation
Primary Plant
|  |  | GFN |  | 1159367 | 2 | [6 empty] | 2041
|  |  | GFN enclosure |  | 144921 | 1
|  |  | Indoor switchboard and switch room (incl GFN enclosure) |  | 870491
|  |  | RMU |  | 66809 | 2
|  |  | Station service transformer (500kVA) |  | 47341 | 2
|  |  | Station service transformer (750kVA) |  | 52172
|  |  | Cap bank |  | 309177
|  |  | AC board (Including change over) |  | 48307 | 1
|  |  | Indoor switchboard |  | 401914
|  |  | 22kV circuit breaker (outdoor) |  | 68615
|  |  | Voltage transformer |  | 16521
|  |  | Earth grid modification |  | 216852 | 1
|  |  | Other |  | 205017 | 1
|  | SCADA / Protection & Control/ Comms |  |  | 274309 | 1 |  | 17802 |  |  |  | 2196 | 1158
|  | Commissioning | [5 empty] | 578377
|  | Construction delivery & site control | [5 empty] | 580392
Contracts
|  |  | Traffic control |  |  |  | 293200
|  |  | Line survey |  |  |  | 144180
|  |  | Civil works |  |  |  | 657166.2191
|  |  | Mob/Demob |  |  |  | 33815
|  |  | Other |  |  |  | 115937

## BGO_volumes
Powercor REFCLs Tranche 2 Contingent Project Application
Volumes: |  |  | BGO
(real 2015 dollars)
Resource partner rates used |  |  |  | Bendigo
Design |  |  |  | 2018
Construction |  |  |  | 2019
[5 empty] | Materials |  | Contracts ($) | Labour ($) | Labour (hours)
| Year incurred |  |  |  | 2019 | 2019 | 2019 | 2019 | 2018 | 2019 | 2019 | 2019 | 2019
[5 empty] | Unit cost (ea) | Qty | Contracts | Other Labour ($) | Design | Live Linework | General Linework | Sub Tester | Fitter
| Labour Rates ($/hr) | [7 empty] | 196.0404 | 163.6544 | 154.0433 | 252.3827 | 155.1212
| Design (hours) | [7 empty] | 5453
Feeder works
|  |  | Surge arrestor sites (single phase) |  | 357 | 442 |  |  |  | 2099 | 0 | 0 | 0
|  |  | Surge arrestor sites (three phase) |  | 531 | 316 |  |  |  | 1818 | 0 | 0 | 0
|  |  | ACRs |  | 24347 | 3 |  |  |  | 288 | 0 | 120 | 0
|  |  | ACR/gas switch control box replacement |  | 5976 | 2 |  |  |  | 0 | 16 | 64 | 0
|  |  | Admittance balancing units (single phase) |  | 14347 | 11 |  |  |  | 0 | 605 | 176 | 330
|  |  | Admittance balancing units (three phase) |  | 21835 | 27 |  |  |  | 0 | 756 | 432 | 810
|  |  | Re-phasing |  | 205 | 16 |  |  |  | 116 | 0 | 0 | 0
|  |  | Fusesavers |  | 11265 | 22 |  |  |  | 225.5 | 0 | 0 | 0
|  |  | HV Regulators upgrade (control box) |  | 13623 |  |  |  |  | 0 | 0 | 0 | 0
|  |  | HV Regulators upgrade (close delta) |  | 145694 | 2 |  |  |  | 0 | 324 | 80 | 0
|  |  | Distribution switchgear (installed) |  | 96614 | 6
|  |  | UG cable testing |  | 239925 | 1
|  |  | UG cable replacement |  | 312 | 3524
|  |  | Capacitance reducing isolation substation (6 MVA) |  | 800379
|  |  | HV customer works |  | 48694 | 1 | 20000 | 66355
|  |  | ZSS Feeder Exit Relocation |  | 0 | 0
|  |  | GFN on feeder and associated equipment |  | 0 | 0
Substation
Primary Plant
|  |  | GFN |  | 1159367 | 2 | [6 empty] | 1595
|  |  | GFN enclosure |  | 144921 | 1
|  |  | Indoor switchboard and switch room (incl GFN enclosure) |  | 870491
|  |  | RMU |  | 66809 | 2
|  |  | Station service transformer (500kVA) |  | 47341 | 2
|  |  | Station service transformer (750kVA) |  | 52172
|  |  | Cap bank |  | 309177
|  |  | AC board (Including change over) |  | 48307 | 1
|  |  | Indoor switchboard |  | 401914
|  |  | 22kV circuit breaker (outdoor) |  | 68615
|  |  | Voltage transformer |  | 16521
|  |  | Earth grid modification |  | 216852 | 1
|  |  | Other |  | 245595 | 1
|  | SCADA / Protection & Control/ Comms |  |  | 274309 | 1 |  | 17802 |  |  |  | 1333 | 896
|  | Commissioning | [5 empty] | 458767
|  | Construction delivery & site control | [5 empty] | 417234
Contracts
|  |  | Traffic control |  |  |  | 223096
|  |  | Line survey |  |  |  | 91642
|  |  | Civil works |  |  |  | 595792.9371
|  |  | Mob/Demob |  |  |  | 33815
|  |  | Other |  |  |  | 200957

## CTN_volumes
Powercor REFCLs Tranche 2 Contingent Project Application
Volumes: |  |  | CTN
(real 2015 dollars)
Resource partner rates used |  |  |  | Bendigo
Design |  |  |  | 2018
Construction |  |  |  | 2018
[5 empty] | Materials |  | Contracts ($) | Labour ($) | Labour (hours)
| Year incurred |  |  |  | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018
[5 empty] | Unit cost (ea) | Qty | Contracts | Other Labour ($) | Design | Live Linework | General Linework | Sub Tester | Fitter
| Labour Rates ($/hr) | [7 empty] | 196.0404 | 162.6888 | 153.1344 | 250.8935 | 154.2059
| Design (hours) | [7 empty] | 4478
Feeder works
|  |  | Surge arrestor sites (single phase) |  | 357 | 248 |  |  |  | 1179 | 0 | 0 | 0
|  |  | Surge arrestor sites (three phase) |  | 531 | 446 |  |  |  | 2464 | 0 | 0 | 0
|  |  | ACRs |  | 24347 | 8 |  |  |  | 768 | 0 | 320 | 0
|  |  | ACR/gas switch control box replacement |  | 5976 | 7 |  |  |  | 0 | 56 | 224 | 0
|  |  | Admittance balancing units (single phase) |  | 14347 | 13 |  |  |  | 0 | 715 | 208 | 390
|  |  | Admittance balancing units (three phase) |  | 21835 | 44 |  |  |  | 0 | 1232 | 704 | 1320
|  |  | Re-phasing |  | 205 | 21 |  |  |  | 152.25 | 0 | 0 | 0
|  |  | Fusesavers |  | 11265 | 22 |  |  |  | 225.5 | 0 | 0 | 0
|  |  | HV Regulators upgrade (control box) |  | 13623 |  |  |  |  | 0 | 0 | 0 | 0
|  |  | HV Regulators upgrade (close delta) |  | 145694 | 8 |  |  |  | 0 | 1296 | 320 | 0
|  |  | Distribution switchgear (installed) |  | 96614
|  |  | UG cable testing |  | 61411 | 1
|  |  | UG cable replacement |  | 312 | 241
|  |  | Capacitance reducing isolation substation (6 MVA) |  | 800379
|  |  | HV customer works |  | 97388 | 1 | 40000 | 132709
|  |  | ZSS Feeder Exit Relocation |  | 0 | 0
|  |  | GFN on feeder and associated equipment |  | 0 | 0
Substation
Primary Plant
|  |  | GFN |  | 1159367 | 1 | [6 empty] | 1866
|  |  | GFN enclosure |  | 144921 | 1
|  |  | Indoor switchboard and switch room (incl GFN enclosure) |  | 870491
|  |  | RMU |  | 66809 | 2
|  |  | Station service transformer (500kVA) |  | 47341 | 1
|  |  | Station service transformer (750kVA) |  | 52172
|  |  | Cap bank |  | 309177
|  |  | AC board (Including change over) |  | 48307 | 1
|  |  | Indoor switchboard |  | 401914
|  |  | 22kV circuit breaker (outdoor) |  | 68615
|  |  | Voltage transformer |  | 16521 | 1
|  |  | Earth grid modification |  | 216852 | 0
|  |  | Other |  | 175153 | 1
|  | SCADA / Protection & Control/ Comms |  |  | 100498 | 1 |  | 17802 |  |  |  | 1379 | 851
|  | Commissioning | [5 empty] | 514421
|  | Construction delivery & site control | [5 empty] | 541070
Contracts
|  |  | Traffic control |  |  |  | 180392
|  |  | Line survey |  |  |  | 107944
|  |  | Civil works |  |  |  | 390900.5958
|  |  | Mob/Demob |  |  |  | 33815
|  |  | Other |  |  |  | 323174

## GL_volumes
Powercor REFCLs Tranche 2 Contingent Project Application
Volumes: |  |  | GL
(real 2015 dollars)
Resource partner rates used |  |  |  | Bendigo
Design |  |  |  | 2018
Construction |  |  |  | 2018
[5 empty] | Materials |  | Contracts ($) | Labour ($) | Labour (hours)
| Year incurred |  |  |  | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018
[5 empty] | Unit cost (ea) | Qty | Contracts | Other Labour ($) | Design | Live Linework | General Linework | Sub Tester | Fitter
| Labour Rates ($/hr) | [7 empty] | 196.0404 | 162.6888 | 153.1344 | 250.8935 | 154.2059
| Design (hours) | [7 empty] | 5026
Feeder works
|  |  | Surge arrestor sites (single phase) |  | 357 | 466 |  |  |  | 2214 | 0 | 0 | 0
|  |  | Surge arrestor sites (three phase) |  | 531 | 740 |  |  |  | 4255 | 0 | 0 | 0
|  |  | ACRs |  | 24347 | 4 |  |  |  | 384 | 0 | 160 | 0
|  |  | ACR/gas switch control box replacement |  | 5976 | 4 |  |  |  | 0 | 32 | 128 | 0
|  |  | Admittance balancing units (single phase) |  | 14347 | 20 |  |  |  | 0 | 1100 | 320 | 600
|  |  | Admittance balancing units (three phase) |  | 21835 | 43 |  |  |  | 0 | 1204 | 688 | 1290
|  |  | Re-phasing |  | 205 | 16 |  |  |  | 116 | 0 | 0 | 0
|  |  | Fusesavers |  | 11265 | 37 |  |  |  | 379.25 | 0 | 0 | 0
|  |  | HV Regulators upgrade (control box) |  | 13623 | 1 |  |  |  | 0 | 8 | 32 | 0
|  |  | HV Regulators upgrade (close delta) |  | 145694 | 3 |  |  |  | 0 | 486 | 120 | 0
|  |  | Distribution switchgear (installed) |  | 96614 | 2
|  |  | UG cable testing |  | 187943 | 1
|  |  | UG cable replacement |  | 312 | 2568
|  |  | Capacitance reducing isolation substation (6 MVA) |  | 800379
|  |  | HV customer works |  | 24347 | 1 | 10000 | 33177
|  |  | ZSS Feeder Exit Relocation |  | 80324 | 1 | 567607 |  |  | 72 | 250
|  |  | GFN on feeder and associated equipment |  | 0 | 0
Substation
Primary Plant
|  |  | GFN |  | 1159367 | 2 | [6 empty] | 5880
|  |  | GFN enclosure |  | 144921 | 0
|  |  | Indoor switchboard and switch room (incl GFN enclosure) |  | 870491 | 1
|  |  | RMU |  | 66809 | 2
|  |  | Station service transformer (500kVA) |  | 47341 | 2
|  |  | Station service transformer (750kVA) |  | 52172
|  |  | Cap bank |  | 309177
|  |  | AC board (Including change over) |  | 48307 | 1
|  |  | Indoor switchboard |  | 401914 | 0
|  |  | 22kV circuit breaker (outdoor) |  | 68615
|  |  | Voltage transformer |  | 16521 | 2
|  |  | Earth grid modification |  | 216852 | 1
|  |  | Other |  | 254390 | 1
|  | SCADA / Protection & Control/ Comms |  |  | 157725 | 1 |  | 17802 |  |  |  | 4924 | 3350
|  | Commissioning | [5 empty] | 370789
|  | Construction delivery & site control | [5 empty] | 662758
Contracts
|  |  | Traffic control |  |  |  | 268054
|  |  | Line survey |  |  |  | 220294
|  |  | Civil works |  |  |  | 900770.9382
|  |  | Mob/Demob |  |  |  | 33815
|  |  | Other |  |  |  | 159413

## BAN_cost
Powercor REFCLs Tranche 2 Contingent Project Application
Costs: |  |  | BAN
(real 2015 dollars)
Design |  |  | 2018
Construction |  |  | 2018
|  |  |  | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2017 | 2018 | 2019 | 2020 | Total
|  |  |  | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total | Total | Total | Total | Total Cost
Design
|  |  | Design | 0 | 0 | 0 | 0 | 1383261.2432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1383261.2432 | 0 | 0 | 1383261.2432
Feeder works
|  |  | Surge arrestor sites (single phase) | 0 | 0 | 0 | 385203 | 932519.8877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317722.8877 | 0 | 0 | 1317722.8877
|  |  | Surge arrestor sites (three phase) | 0 | 0 | 0 | 586224 | 1154687.0649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1740911.0649 | 0 | 0 | 1740911.0649
|  |  | ACRs | 0 | 0 | 0 | 316511 | 349752.3898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666263.3898 | 0 | 0 | 666263.3898
|  |  | ACR/gas switch control box replacement | 0 | 0 | 0 | 125496 | 186568.4094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312064.4094 | 0 | 0 | 312064.4094
|  |  | Admittance balancing units (single phase) | 0 | 0 | 0 | 459104 | 572495.7853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1031599.7853 | 0 | 0 | 1031599.7853
|  |  | Admittance balancing units (three phase) | 0 | 0 | 0 | 1681295 | 1030599.0825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2711894.0825 | 0 | 0 | 2711894.0825
|  |  | Re-phasing | 0 | 0 | 0 | 8815 | 56769.9912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65584.9912 | 0 | 0 | 65584.9912
|  |  | Fusesavers | 0 | 0 | 0 | 664635 | 110079.9474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774714.9474 | 0 | 0 | 774714.9474
|  |  | HV Regulators upgrade (control box) | 0 | 0 | 0 | 54492 | 35536.8399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90028.8399 | 0 | 0 | 90028.8399
|  |  | HV Regulators upgrade (close delta) | 0 | 0 | 0 | 291388 | 72945.7562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364333.7562 | 0 | 0 | 364333.7562
|  |  | Distribution switchgear (installed) | 0 | 0 | 0 | 869526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869526 | 0 | 0 | 869526
|  |  | UG cable testing | 0 | 0 | 0 | 625174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625174 | 0 | 0 | 625174
|  |  | UG cable replacement | 0 | 0 | 0 | 3310008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310008 | 0 | 0 | 3310008
|  |  | Capacitance reducing isolation substation (6 MVA) | 0 | 0 | 0 | 800379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800379 | 0 | 0 | 800379
|  |  | HV customer works | 0 | 0 | 0 | 346585 | 368669 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805254 | 0 | 0 | 805254
|  |  | ZSS Feeder Exit Relocation | 0 | 0 | 0 | 104343 | 45144.0712 | 289842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439329.0712 | 0 | 0 | 439329.0712
|  |  | GFN on feeder and associated equipment | 0 | 0 | 0 | 1515052 | 183664.7771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1698716.7771 | 0 | 0 | 1698716.7771
Substation
Primary Plant
|  |  | GFN | 0 | 0 | 0 | 3478101 | 1005149.9253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4483250.9253 | 0 | 0 | 4483250.9253
|  |  | GFN enclosure | 0 | 0 | 0 | 144921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144921 | 0 | 0 | 144921
|  |  | Indoor switchboard and switch room (incl GFN enclosure) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | RMU | 0 | 0 | 0 | 200427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200427 | 0 | 0 | 200427
|  |  | Station service transformer (500kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Station service transformer (750kVA) | 0 | 0 | 0 | 104344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104344 | 0 | 0 | 104344
|  |  | Cap bank | 0 | 0 | 0 | 309177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309177 | 0 | 0 | 309177
|  |  | AC board (Including change over) | 0 | 0 | 0 | 48307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48307 | 0 | 0 | 48307
|  |  | Indoor switchboard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Voltage transformer | 0 | 0 | 0 | 49563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49563 | 0 | 0 | 49563
|  |  | Earth grid modification | 0 | 0 | 0 | 216852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216852 | 0 | 0 | 216852
|  |  | Other | 0 | 0 | 0 | 352189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352189 | 0 | 0 | 352189
|  |  | SCADA / Protection & Control/ Comms | 0 | 0 | 0 | 483593 | 1645293.1773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2128886.1773 | 0 | 0 | 2128886.1773
|  |  | Commissioning | 0 | 0 | 0 | 0 | 1255073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255073 | 0 | 0 | 1255073
|  |  | Construction delivery & site control | 0 | 0 | 0 | 0 | 1357114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1357114 | 0 | 0 | 1357114
Contracts
|  |  | Traffic control | 0 | 0 | 0 | 0 | 0 | 649397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649397 | 0 | 0 | 649397
|  |  | Line survey | 0 | 0 | 0 | 0 | 0 | 275221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275221 | 0 | 0 | 275221
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 930449.1689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930449.1689 | 0 | 0 | 930449.1689
|  |  | Mob/Demob | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 0 | 33815
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 181151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181151 | 0 | 0 | 181151
|  | Total construction |  | 0 | 0 | 0 | 17531704 | 11745324.3485 | 2449875.1689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31726903.5174 | 0 | 0 | 31726903.5174
|  |  | Distribution Code voltage variation payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total site cost |  | 0 | 0 | 0 | 17531704 | 11745324.3485 | 2449875.1689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31726903.5174 | 0 | 0 | 31726903.5174

## BAS_cost
Powercor REFCLs Tranche 2 Contingent Project Application
Costs: |  |  | BAS
(real 2015 dollars)
Design |  |  | 2018
Construction |  |  | 2019
|  |  |  | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2017 | 2018 | 2019 | 2020 | Total
|  |  |  | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total | Total | Total | Total | Total Cost
Design
|  |  | Design | 0 | 0 | 0 | 0 | 1064303.4707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064303.4707 | 0 | 0 | 1064303.4707
Feeder works
|  |  | Surge arrestor sites (single phase) | 0 | 0 | 0 | 0 | 0 | 0 | 374493 | 911881.0087 | 0 | 0 | 0 | 0 | 0 | 0 | 1286374.0087 | 0 | 1286374.0087
|  |  | Surge arrestor sites (three phase) | 0 | 0 | 0 | 0 | 0 | 0 | 455067 | 903644.4279 | 0 | 0 | 0 | 0 | 0 | 0 | 1358711.4279 | 0 | 1358711.4279
|  |  | ACRs | 0 | 0 | 0 | 0 | 0 | 0 | 267817 | 297700.9622 | 0 | 0 | 0 | 0 | 0 | 0 | 565517.9622 | 0 | 565517.9622
|  |  | ACR/gas switch control box replacement | 0 | 0 | 0 | 0 | 0 | 0 | 59760 | 89369.4384 | 0 | 0 | 0 | 0 | 0 | 0 | 149129.4384 | 0 | 149129.4384
|  |  | Admittance balancing units (single phase) | 0 | 0 | 0 | 0 | 0 | 0 | 444757 | 557897.2543 | 0 | 0 | 0 | 0 | 0 | 0 | 1002654.2543 | 0 | 1002654.2543
|  |  | Admittance balancing units (three phase) | 0 | 0 | 0 | 0 | 0 | 0 | 1331935 | 821294.8056 | 0 | 0 | 0 | 0 | 0 | 0 | 2153229.8056 | 0 | 2153229.8056
|  |  | Re-phasing | 0 | 0 | 0 | 0 | 0 | 0 | 9225 | 59669.4518 | 0 | 0 | 0 | 0 | 0 | 0 | 68894.4518 | 0 | 68894.4518
|  |  | Fusesavers | 0 | 0 | 0 | 0 | 0 | 0 | 642105 | 106895.5154 | 0 | 0 | 0 | 0 | 0 | 0 | 749000.5154 | 0 | 749000.5154
|  |  | HV Regulators upgrade (control box) | 0 | 0 | 0 | 0 | 0 | 0 | 68115 | 44684.7192 | 0 | 0 | 0 | 0 | 0 | 0 | 112799.7192 | 0 | 112799.7192
|  |  | HV Regulators upgrade (close delta) | 0 | 0 | 0 | 0 | 0 | 0 | 291388 | 73378.7393 | 0 | 0 | 0 | 0 | 0 | 0 | 364766.7393 | 0 | 364766.7393
|  |  | Distribution switchgear (installed) | 0 | 0 | 0 | 0 | 0 | 0 | 579684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579684 | 0 | 579684
|  |  | UG cable testing | 0 | 0 | 0 | 0 | 0 | 0 | 401529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401529 | 0 | 401529
|  |  | UG cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 2026752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026752 | 0 | 2026752
|  |  | Capacitance reducing isolation substation (6 MVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV customer works | 0 | 0 | 0 | 0 | 0 | 0 | 185466 | 200923 | 50000 | 0 | 0 | 0 | 0 | 0 | 436389 | 0 | 436389
|  |  | ZSS Feeder Exit Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 56036 | 45412.0322 | 96614 | 0 | 0 | 0 | 0 | 0 | 198062.0322 | 0 | 198062.0322
|  |  | GFN on feeder and associated equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Substation
Primary Plant
|  |  | GFN | 0 | 0 | 0 | 0 | 0 | 0 | 3478101 | 728208.9178 | 0 | 0 | 0 | 0 | 0 | 0 | 4206309.9178 | 0 | 4206309.9178
|  |  | GFN enclosure | 0 | 0 | 0 | 0 | 0 | 0 | 144921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144921 | 0 | 144921
|  |  | Indoor switchboard and switch room (incl GFN enclosure) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | RMU | 0 | 0 | 0 | 0 | 0 | 0 | 200427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200427 | 0 | 200427
|  |  | Station service transformer (500kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Station service transformer (750kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 104344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104344 | 0 | 104344
|  |  | Cap bank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AC board (Including change over) | 0 | 0 | 0 | 0 | 0 | 0 | 48307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48307 | 0 | 48307
|  |  | Indoor switchboard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Voltage transformer | 0 | 0 | 0 | 0 | 0 | 0 | 49563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49563 | 0 | 49563
|  |  | Earth grid modification | 0 | 0 | 0 | 0 | 0 | 0 | 216852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216852 | 0 | 216852
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 0 | 276057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276057 | 0 | 276057
[16 empty] | 0 | 0 | 0 | 0 | 0
|  |  | SCADA / Protection & Control/ Comms | 0 | 0 | 0 | 0 | 0 | 0 | 215757 | 1064603.1897 | 0 | 0 | 0 | 0 | 0 | 0 | 1280360.1897 | 0 | 1280360.1897
|  |  | Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 717310 | 0 | 0 | 0 | 0 | 0 | 0 | 717310 | 0 | 717310
|  |  | Construction delivery & site control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052038 | 0 | 0 | 0 | 0 | 0 | 0 | 1052038 | 0 | 1052038
Contracts
|  |  | Traffic control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575387 | 0 | 0 | 0 | 0 | 0 | 575387 | 0 | 575387
|  |  | Line survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275221 | 0 | 0 | 0 | 0 | 0 | 275221 | 0 | 275221
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897402.0171 | 0 | 0 | 0 | 0 | 0 | 897402.0171 | 0 | 897402.0171
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 33815
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160862 | 0 | 0 | 0 | 0 | 0 | 160862 | 0 | 160862
|  | Total construction |  | 0 | 0 | 0 | 0 | 1064303.4707 | 0 | 11928458 | 7674911.4625 | 2089301.0171 | 0 | 0 | 0 | 0 | 1064303.4707 | 21692670.4796 | 0 | 22756973.9503
|  |  | Distribution Code voltage variation payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total site cost |  | 0 | 0 | 0 | 0 | 1064303.4707 | 0 | 11928458 | 7674911.4625 | 2089301.0171 | 0 | 0 | 0 | 0 | 1064303.4707 | 21692670.4796 | 0 | 22756973.9503

## BETS_cost
Powercor REFCLs Tranche 2 Contingent Project Application
Costs: |  |  | BETS
(real 2015 dollars)
Design |  |  | 2018
Construction |  |  | 2019
|  |  |  | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2017 | 2018 | 2019 | 2020 | Total
|  |  |  | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total | Total | Total | Total | Total Cost
Design
|  |  | Design | 0 | 0 | 0 | 0 | 792591.4408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792591.4408 | 0 | 0 | 792591.4408
Feeder works
|  |  | Surge arrestor sites (single phase) | 0 | 0 | 0 | 0 | 0 | 0 | 188139 | 409627.0563 | 0 | 0 | 0 | 0 | 0 | 0 | 597766.0563 | 0 | 597766.0563
|  |  | Surge arrestor sites (three phase) | 0 | 0 | 0 | 0 | 0 | 0 | 378072 | 670328.5747 | 0 | 0 | 0 | 0 | 0 | 0 | 1048400.5747 | 0 | 1048400.5747
|  |  | ACRs | 0 | 0 | 0 | 0 | 0 | 0 | 24347 | 25806.1351 | 0 | 0 | 0 | 0 | 0 | 0 | 50153.1351 | 0 | 50153.1351
|  |  | ACR/gas switch control box replacement | 0 | 0 | 0 | 0 | 0 | 0 | 53784 | 83777.3452 | 0 | 0 | 0 | 0 | 0 | 0 | 137561.3452 | 0 | 137561.3452
|  |  | Admittance balancing units (single phase) | 0 | 0 | 0 | 0 | 0 | 0 | 143470 | 171641.4224 | 0 | 0 | 0 | 0 | 0 | 0 | 315111.4224 | 0 | 315111.4224
|  |  | Admittance balancing units (three phase) | 0 | 0 | 0 | 0 | 0 | 0 | 764225 | 455174.0396 | 0 | 0 | 0 | 0 | 0 | 0 | 1219399.0396 | 0 | 1219399.0396
|  |  | Re-phasing | 0 | 0 | 0 | 0 | 0 | 0 | 3075 | 17797.42 | 0 | 0 | 0 | 0 | 0 | 0 | 20872.42 | 0 | 20872.42
|  |  | Fusesavers | 0 | 0 | 0 | 0 | 0 | 0 | 225300 | 33549.1596 | 0 | 0 | 0 | 0 | 0 | 0 | 258849.1596 | 0 | 258849.1596
|  |  | HV Regulators upgrade (control box) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV Regulators upgrade (close delta) | 0 | 0 | 0 | 0 | 0 | 0 | 291388 | 70100.6545 | 0 | 0 | 0 | 0 | 0 | 0 | 361488.6545 | 0 | 361488.6545
|  |  | Distribution switchgear (installed) | 0 | 0 | 0 | 0 | 0 | 0 | 483070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483070 | 0 | 483070
|  |  | UG cable testing | 0 | 0 | 0 | 0 | 0 | 0 | 223069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223069 | 0 | 223069
|  |  | UG cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 1002768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1002768 | 0 | 1002768
|  |  | Capacitance reducing isolation substation (6 MVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV customer works | 0 | 0 | 0 | 0 | 0 | 0 | 97388 | 132709 | 40000 | 0 | 0 | 0 | 0 | 0 | 270097 | 0 | 270097
|  |  | ZSS Feeder Exit Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | GFN on feeder and associated equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Substation
Primary Plant
|  |  | GFN | 0 | 0 | 0 | 0 | 0 | 0 | 2318734 | 316602.3616 | 0 | 0 | 0 | 0 | 0 | 0 | 2635336.3616 | 0 | 2635336.3616
|  |  | GFN enclosure | 0 | 0 | 0 | 0 | 0 | 0 | 144921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144921 | 0 | 144921
|  |  | Indoor switchboard and switch room (incl GFN enclosure) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | RMU | 0 | 0 | 0 | 0 | 0 | 0 | 133618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133618 | 0 | 133618
|  |  | Station service transformer (500kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 94682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94682 | 0 | 94682
|  |  | Station service transformer (750kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cap bank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AC board (Including change over) | 0 | 0 | 0 | 0 | 0 | 0 | 48307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48307 | 0 | 48307
|  |  | Indoor switchboard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Voltage transformer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Earth grid modification | 0 | 0 | 0 | 0 | 0 | 0 | 216852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216852 | 0 | 216852
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 0 | 205017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205017 | 0 | 205017
[16 empty] | 0 | 0 | 0 | 0 | 0
|  |  | SCADA / Protection & Control/ Comms | 0 | 0 | 0 | 0 | 0 | 0 | 274309 | 751664.8189 | 0 | 0 | 0 | 0 | 0 | 0 | 1025973.8189 | 0 | 1025973.8189
|  |  | Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578377 | 0 | 0 | 0 | 0 | 0 | 0 | 578377 | 0 | 578377
|  |  | Construction delivery & site control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580392 | 0 | 0 | 0 | 0 | 0 | 0 | 580392 | 0 | 580392
Contracts
|  |  | Traffic control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 293200 | 0 | 0 | 0 | 0 | 0 | 293200 | 0 | 293200
|  |  | Line survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144180 | 0 | 0 | 0 | 0 | 0 | 144180 | 0 | 144180
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657166.2191 | 0 | 0 | 0 | 0 | 0 | 657166.2191 | 0 | 657166.2191
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 33815
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115937 | 0 | 0 | 0 | 0 | 0 | 115937 | 0 | 115937
|  | Total construction |  | 0 | 0 | 0 | 0 | 792591.4408 | 0 | 7314535 | 4297546.988 | 1284298.2191 | 0 | 0 | 0 | 0 | 792591.4408 | 12896380.2071 | 0 | 13688971.6479
|  |  | Distribution Code voltage variation payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total site cost |  | 0 | 0 | 0 | 0 | 792591.4408 | 0 | 7314535 | 4297546.988 | 1284298.2191 | 0 | 0 | 0 | 0 | 792591.4408 | 12896380.2071 | 0 | 13688971.6479

## BGO_cost
Powercor REFCLs Tranche 2 Contingent Project Application
Costs: |  |  | BGO
(real 2015 dollars)
Design |  |  | 2018
Construction |  |  | 2019
|  |  |  | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2017 | 2018 | 2019 | 2020 | Total
|  |  |  | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total | Total | Total | Total | Total Cost
Design
|  |  | Design | 0 | 0 | 0 | 0 | 1069008.4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1069008.4409 | 0 | 0 | 1069008.4409
Feeder works
|  |  | Surge arrestor sites (single phase) | 0 | 0 | 0 | 0 | 0 | 0 | 157794 | 343510.6636 | 0 | 0 | 0 | 0 | 0 | 0 | 501304.6636 | 0 | 501304.6636
|  |  | Surge arrestor sites (three phase) | 0 | 0 | 0 | 0 | 0 | 0 | 167796 | 297523.7668 | 0 | 0 | 0 | 0 | 0 | 0 | 465319.7668 | 0 | 465319.7668
|  |  | ACRs | 0 | 0 | 0 | 0 | 0 | 0 | 73041 | 77418.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 150459.4054 | 0 | 150459.4054
|  |  | ACR/gas switch control box replacement | 0 | 0 | 0 | 0 | 0 | 0 | 11952 | 18617.1878 | 0 | 0 | 0 | 0 | 0 | 0 | 30569.1878 | 0 | 30569.1878
|  |  | Admittance balancing units (single phase) | 0 | 0 | 0 | 0 | 0 | 0 | 157817 | 188805.5647 | 0 | 0 | 0 | 0 | 0 | 0 | 346622.5647 | 0 | 346622.5647
|  |  | Admittance balancing units (three phase) | 0 | 0 | 0 | 0 | 0 | 0 | 589545 | 351134.2591 | 0 | 0 | 0 | 0 | 0 | 0 | 940679.2591 | 0 | 940679.2591
|  |  | Re-phasing | 0 | 0 | 0 | 0 | 0 | 0 | 3280 | 18983.9147 | 0 | 0 | 0 | 0 | 0 | 0 | 22263.9147 | 0 | 22263.9147
|  |  | Fusesavers | 0 | 0 | 0 | 0 | 0 | 0 | 247830 | 36904.0756 | 0 | 0 | 0 | 0 | 0 | 0 | 284734.0756 | 0 | 284734.0756
|  |  | HV Regulators upgrade (control box) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV Regulators upgrade (close delta) | 0 | 0 | 0 | 0 | 0 | 0 | 291388 | 70100.6545 | 0 | 0 | 0 | 0 | 0 | 0 | 361488.6545 | 0 | 361488.6545
|  |  | Distribution switchgear (installed) | 0 | 0 | 0 | 0 | 0 | 0 | 579684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579684 | 0 | 579684
|  |  | UG cable testing | 0 | 0 | 0 | 0 | 0 | 0 | 239925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239925 | 0 | 239925
|  |  | UG cable replacement | 0 | 0 | 0 | 0 | 0 | 0 | 1099488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1099488 | 0 | 1099488
|  |  | Capacitance reducing isolation substation (6 MVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV customer works | 0 | 0 | 0 | 0 | 0 | 0 | 48694 | 66355 | 20000 | 0 | 0 | 0 | 0 | 0 | 135049 | 0 | 135049
|  |  | ZSS Feeder Exit Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | GFN on feeder and associated equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Substation
Primary Plant
|  |  | GFN | 0 | 0 | 0 | 0 | 0 | 0 | 2318734 | 247418.3081 | 0 | 0 | 0 | 0 | 0 | 0 | 2566152.3081 | 0 | 2566152.3081
|  |  | GFN enclosure | 0 | 0 | 0 | 0 | 0 | 0 | 144921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144921 | 0 | 144921
|  |  | Indoor switchboard and switch room (incl GFN enclosure) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | RMU | 0 | 0 | 0 | 0 | 0 | 0 | 133618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133618 | 0 | 133618
|  |  | Station service transformer (500kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 94682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94682 | 0 | 94682
|  |  | Station service transformer (750kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cap bank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AC board (Including change over) | 0 | 0 | 0 | 0 | 0 | 0 | 48307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48307 | 0 | 48307
|  |  | Indoor switchboard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Voltage transformer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Earth grid modification | 0 | 0 | 0 | 0 | 0 | 0 | 216852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216852 | 0 | 216852
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 0 | 245595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245595 | 0 | 245595
[16 empty] | 0 | 0 | 0 | 0 | 0
|  |  | SCADA / Protection & Control/ Comms | 0 | 0 | 0 | 0 | 0 | 0 | 274309 | 493216.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 767525.7701 | 0 | 767525.7701
|  |  | Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458767 | 0 | 0 | 0 | 0 | 0 | 0 | 458767 | 0 | 458767
|  |  | Construction delivery & site control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417234 | 0 | 0 | 0 | 0 | 0 | 0 | 417234 | 0 | 417234
Contracts
|  |  | Traffic control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223096 | 0 | 0 | 0 | 0 | 0 | 223096 | 0 | 223096
|  |  | Line survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91642 | 0 | 0 | 0 | 0 | 0 | 91642 | 0 | 91642
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595792.9371 | 0 | 0 | 0 | 0 | 0 | 595792.9371 | 0 | 595792.9371
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 33815
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200957 | 0 | 0 | 0 | 0 | 0 | 200957 | 0 | 200957
|  | Total construction |  | 0 | 0 | 0 | 0 | 1069008.4409 | 0 | 7145252 | 3085989.5704 | 1165302.9371 | 0 | 0 | 0 | 0 | 1069008.4409 | 11396544.5075 | 0 | 12465552.9485
|  |  | Distribution Code voltage variation payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total site cost |  | 0 | 0 | 0 | 0 | 1069008.4409 | 0 | 7145252 | 3085989.5704 | 1165302.9371 | 0 | 0 | 0 | 0 | 1069008.4409 | 11396544.5075 | 0 | 12465552.9485

## CTN_cost
Powercor REFCLs Tranche 2 Contingent Project Application
Costs: |  |  | CTN
(real 2015 dollars)
Design |  |  | 2018
Construction |  |  | 2018
|  |  |  | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2017 | 2018 | 2019 | 2020 | Total
|  |  |  | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total | Total | Total | Total | Total Cost
Design
|  |  | Design | 0 | 0 | 0 | 0 | 877869.0259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877869.0259 | 0 | 0 | 877869.0259
Feeder works
|  |  | Surge arrestor sites (single phase) | 0 | 0 | 0 | 88536 | 191810.0574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280346.0574 | 0 | 0 | 280346.0574
|  |  | Surge arrestor sites (three phase) | 0 | 0 | 0 | 236826 | 400865.1241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637691.1241 | 0 | 0 | 637691.1241
|  |  | ACRs | 0 | 0 | 0 | 194776 | 205230.8952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400006.8952 | 0 | 0 | 400006.8952
|  |  | ACR/gas switch control box replacement | 0 | 0 | 0 | 41832 | 64775.6694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106607.6694 | 0 | 0 | 106607.6694
|  |  | Admittance balancing units (single phase) | 0 | 0 | 0 | 186511 | 221817.2121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408328.2121 | 0 | 0 | 408328.2121
|  |  | Admittance balancing units (three phase) | 0 | 0 | 0 | 960740 | 568842.3239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1529582.3239 | 0 | 0 | 1529582.3239
|  |  | Re-phasing | 0 | 0 | 0 | 4305 | 24769.3649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29074.3649 | 0 | 0 | 29074.3649
|  |  | Fusesavers | 0 | 0 | 0 | 247830 | 36686.3172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284516.3172 | 0 | 0 | 284516.3172
|  |  | HV Regulators upgrade (control box) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV Regulators upgrade (close delta) | 0 | 0 | 0 | 1165552 | 278748.0575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1444300.0575 | 0 | 0 | 1444300.0575
|  |  | Distribution switchgear (installed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | UG cable testing | 0 | 0 | 0 | 61411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61411 | 0 | 0 | 61411
|  |  | UG cable replacement | 0 | 0 | 0 | 75192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75192 | 0 | 0 | 75192
|  |  | Capacitance reducing isolation substation (6 MVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV customer works | 0 | 0 | 0 | 97388 | 132709 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270097 | 0 | 0 | 270097
|  |  | ZSS Feeder Exit Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | GFN on feeder and associated equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Substation
Primary Plant
|  |  | GFN | 0 | 0 | 0 | 1159367 | 287748.1698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1447115.1698 | 0 | 0 | 1447115.1698
|  |  | GFN enclosure | 0 | 0 | 0 | 144921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144921 | 0 | 0 | 144921
|  |  | Indoor switchboard and switch room (incl GFN enclosure) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | RMU | 0 | 0 | 0 | 133618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133618 | 0 | 0 | 133618
|  |  | Station service transformer (500kVA) | 0 | 0 | 0 | 47341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47341 | 0 | 0 | 47341
|  |  | Station service transformer (750kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cap bank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AC board (Including change over) | 0 | 0 | 0 | 48307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48307 | 0 | 0 | 48307
|  |  | Indoor switchboard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Voltage transformer | 0 | 0 | 0 | 16521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16521 | 0 | 0 | 16521
|  |  | Earth grid modification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 175153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175153 | 0 | 0 | 175153
[16 empty] | 0 | 0 | 0 | 0 | 0
|  |  | SCADA / Protection & Control/ Comms | 0 | 0 | 0 | 100498 | 495013.3456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595511.3456 | 0 | 0 | 595511.3456
|  |  | Commissioning | 0 | 0 | 0 | 0 | 514421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514421 | 0 | 0 | 514421
|  |  | Construction delivery & site control | 0 | 0 | 0 | 0 | 541070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541070 | 0 | 0 | 541070
Contracts
|  |  | Traffic control | 0 | 0 | 0 | 0 | 0 | 180392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180392 | 0 | 0 | 180392
|  |  | Line survey | 0 | 0 | 0 | 0 | 0 | 107944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107944 | 0 | 0 | 107944
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 390900.5958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390900.5958 | 0 | 0 | 390900.5958
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 0 | 33815
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 323174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323174 | 0 | 0 | 323174
|  | Total construction |  | 0 | 0 | 0 | 5186625 | 4842375.5628 | 1076225.5958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11105226.1586 | 0 | 0 | 11105226.1586
|  |  | Distribution Code voltage variation payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total site cost |  | 0 | 0 | 0 | 5186625 | 4842375.5628 | 1076225.5958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11105226.1586 | 0 | 0 | 11105226.1586

## GL_cost
Powercor REFCLs Tranche 2 Contingent Project Application
Costs: |  |  | GL
(real 2015 dollars)
Design |  |  | 2018
Construction |  |  | 2018
|  |  |  | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2017 | 2018 | 2019 | 2020 | Total
|  |  |  | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total | Total | Total | Total | Total Cost
Design
|  |  | Design | 0 | 0 | 0 | 0 | 985299.1792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985299.1792 | 0 | 0 | 985299.1792
Feeder works
|  |  | Surge arrestor sites (single phase) | 0 | 0 | 0 | 166362 | 360192.9321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526554.9321 | 0 | 0 | 526554.9321
|  |  | Surge arrestor sites (three phase) | 0 | 0 | 0 | 392940 | 692240.7074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085180.7074 | 0 | 0 | 1085180.7074
|  |  | ACRs | 0 | 0 | 0 | 97388 | 102615.4476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200003.4476 | 0 | 0 | 200003.4476
|  |  | ACR/gas switch control box replacement | 0 | 0 | 0 | 23904 | 37014.6682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60918.6682 | 0 | 0 | 60918.6682
|  |  | Admittance balancing units (single phase) | 0 | 0 | 0 | 286940 | 341257.2493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628197.2493 | 0 | 0 | 628197.2493
|  |  | Admittance balancing units (three phase) | 0 | 0 | 0 | 938905 | 555914.0892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1494819.0892 | 0 | 0 | 1494819.0892
|  |  | Re-phasing | 0 | 0 | 0 | 3280 | 18871.8971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22151.8971 | 0 | 0 | 22151.8971
|  |  | Fusesavers | 0 | 0 | 0 | 416805 | 61699.7152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478504.7152 | 0 | 0 | 478504.7152
|  |  | HV Regulators upgrade (control box) | 0 | 0 | 0 | 13623 | 9253.6671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22876.6671 | 0 | 0 | 22876.6671
|  |  | HV Regulators upgrade (close delta) | 0 | 0 | 0 | 437082 | 104530.5215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541612.5215 | 0 | 0 | 541612.5215
|  |  | Distribution switchgear (installed) | 0 | 0 | 0 | 193228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193228 | 0 | 0 | 193228
|  |  | UG cable testing | 0 | 0 | 0 | 187943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187943 | 0 | 0 | 187943
|  |  | UG cable replacement | 0 | 0 | 0 | 801216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801216 | 0 | 0 | 801216
|  |  | Capacitance reducing isolation substation (6 MVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | HV customer works | 0 | 0 | 0 | 24347 | 33177 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67524 | 0 | 0 | 67524
|  |  | ZSS Feeder Exit Relocation | 0 | 0 | 0 | 80324 | 49997.1823 | 567607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697928.1823 | 0 | 0 | 697928.1823
|  |  | GFN on feeder and associated equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Substation
Primary Plant
|  |  | GFN | 0 | 0 | 0 | 2318734 | 906730.5671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225464.5671 | 0 | 0 | 3225464.5671
|  |  | GFN enclosure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Indoor switchboard and switch room (incl GFN enclosure) | 0 | 0 | 0 | 870491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 870491 | 0 | 0 | 870491
|  |  | RMU | 0 | 0 | 0 | 133618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133618 | 0 | 0 | 133618
|  |  | Station service transformer (500kVA) | 0 | 0 | 0 | 94682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94682 | 0 | 0 | 94682
|  |  | Station service transformer (750kVA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cap bank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AC board (Including change over) | 0 | 0 | 0 | 48307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48307 | 0 | 0 | 48307
|  |  | Indoor switchboard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 22kV circuit breaker (outdoor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Voltage transformer | 0 | 0 | 0 | 33042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33042 | 0 | 0 | 33042
|  |  | Earth grid modification | 0 | 0 | 0 | 216852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216852 | 0 | 0 | 216852
|  |  | Other | 0 | 0 | 0 | 254390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254390 | 0 | 0 | 254390
[16 empty] | 0 | 0 | 0 | 0 | 0
|  |  | SCADA / Protection & Control/ Comms | 0 | 0 | 0 | 157725 | 1769791.3101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1927516.3101 | 0 | 0 | 1927516.3101
|  |  | Commissioning | 0 | 0 | 0 | 0 | 370789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370789 | 0 | 0 | 370789
|  |  | Construction delivery & site control | 0 | 0 | 0 | 0 | 662758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662758 | 0 | 0 | 662758
Contracts
|  |  | Traffic control | 0 | 0 | 0 | 0 | 0 | 268054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268054 | 0 | 0 | 268054
|  |  | Line survey | 0 | 0 | 0 | 0 | 0 | 220294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220294 | 0 | 0 | 220294
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 900770.9382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900770.9382 | 0 | 0 | 900770.9382
|  |  | Civil works | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33815 | 0 | 0 | 33815
|  |  | Other | 0 | 0 | 0 | 0 | 0 | 159413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159413 | 0 | 0 | 159413
|  | Total construction |  | 0 | 0 | 0 | 8192128 | 7062133.1336 | 2159953.9382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17414215.0718 | 0 | 0 | 17414215.0718
|  |  | Distribution Code voltage variation payment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total site cost |  | 0 | 0 | 0 | 8192128 | 7062133.1336 | 2159953.9382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17414215.0718 | 0 | 0 | 17414215.0718

## Tot_cost
Powercor REFCLs Tranche 2 Contingent Project Application
Costs: |  |  | TOTAL
(real 2015 dollars)
|  |  |  | Capex Flag | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2017 | 2018 | 2019 | 2020 | Total | 2017 | 2018 | 2019 | 2020 | Total
[5 empty] | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Materials | Labour | Contracts | Total Cost | Total Cost | Total Cost | Total Cost | Total Cost | Capex | Capex | Capex | Capex | Capex
Design
| Design |  | Design | TRUE | 0 | 0 | 0 | 0 | 6172332.8007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6172332.8007 | 0 | 0 | 6172332.8007 | 0 | 6172332.8007 | 0 | 0 | 6172332.8007
Feeder works
| Feeder works |  | Surge arrestor sites (single phase) | TRUE | 0 | 0 | 0 | 640101 | 1484522.8772 | 0 | 720426 | 1665018.7286 | 0 | 0 | 0 | 0 | 0 | 2124623.8772 | 2385444.7286 | 0 | 4510068.6058 | 0 | 2124623.8772 | 2385444.7286 | 0 | 4510068.6058
| Feeder works |  | Surge arrestor sites (three phase) | TRUE | 0 | 0 | 0 | 1215990 | 2247792.8964 | 0 | 1000935 | 1871496.7694 | 0 | 0 | 0 | 0 | 0 | 3463782.8964 | 2872431.7694 | 0 | 6336214.6658 | 0 | 3463782.8964 | 2872431.7694 | 0 | 6336214.6658
| Feeder works |  | ACRs | TRUE | 0 | 0 | 0 | 608675 | 657598.7326 | 0 | 365205 | 400925.5027 | 0 | 0 | 0 | 0 | 0 | 1266273.7326 | 766130.5027 | 0 | 2032404.2354 | 0 | 1266273.7326 | 766130.5027 | 0 | 2032404.2354
| Feeder works |  | ACR/gas switch control box replacement | TRUE | 0 | 0 | 0 | 191232 | 288358.7471 | 0 | 125496 | 191763.9715 | 0 | 0 | 0 | 0 | 0 | 479590.7471 | 317259.9715 | 0 | 796850.7185 | 0 | 479590.7471 | 317259.9715 | 0 | 796850.7185
| Feeder works |  | Admittance balancing units (single phase) | TRUE | 0 | 0 | 0 | 932555 | 1135570.2467 | 0 | 746044 | 918344.2414 | 0 | 0 | 0 | 0 | 0 | 2068125.2467 | 1664388.2414 | 0 | 3732513.4881 | 0 | 2068125.2467 | 1664388.2414 | 0 | 3732513.4881
| Feeder works |  | Admittance balancing units (three phase) | TRUE | 0 | 0 | 0 | 3580940 | 2155355.4955 | 0 | 2685705 | 1627603.1044 | 0 | 0 | 0 | 0 | 0 | 5736295.4955 | 4313308.1044 | 0 | 10049603.5999 | 0 | 5736295.4955 | 4313308.1044 | 0 | 10049603.5999
| Feeder works |  | Re-phasing | TRUE | 0 | 0 | 0 | 16400 | 100411.2532 | 0 | 15580 | 96450.7865 | 0 | 0 | 0 | 0 | 0 | 116811.2532 | 112030.7865 | 0 | 228842.0398 | 0 | 116811.2532 | 112030.7865 | 0 | 228842.0398
| Feeder works |  | Fusesavers | TRUE | 0 | 0 | 0 | 1329270 | 208465.9797 | 0 | 1115235 | 177348.7506 | 0 | 0 | 0 | 0 | 0 | 1537735.9797 | 1292583.7506 | 0 | 2830319.7304 | 0 | 1537735.9797 | 1292583.7506 | 0 | 2830319.7304
| Feeder works |  | HV Regulators upgrade (control box) | TRUE | 0 | 0 | 0 | 68115 | 44790.5069 | 0 | 68115 | 44684.7192 | 0 | 0 | 0 | 0 | 0 | 112905.5069 | 112799.7192 | 0 | 225705.2262 | 0 | 112905.5069 | 112799.7192 | 0 | 225705.2262
| Feeder works |  | HV Regulators upgrade (close delta) | TRUE | 0 | 0 | 0 | 1894022 | 456224.3352 | 0 | 874164 | 213580.0483 | 0 | 0 | 0 | 0 | 0 | 2350246.3352 | 1087744.0483 | 0 | 3437990.3836 | 0 | 2350246.3352 | 1087744.0483 | 0 | 3437990.3836
| Feeder works |  | Distribution switchgear (installed) | TRUE | 0 | 0 | 0 | 1062754 | 0 | 0 | 1642438 | 0 | 0 | 0 | 0 | 0 | 0 | 1062754 | 1642438 | 0 | 2705192 | 0 | 1062754 | 1642438 | 0 | 2705192
| Feeder works |  | UG cable testing | TRUE | 0 | 0 | 0 | 874528 | 0 | 0 | 864523 | 0 | 0 | 0 | 0 | 0 | 0 | 874528 | 864523 | 0 | 1739051 | 0 | 874528 | 864523 | 0 | 1739051
| Feeder works |  | UG cable replacement | TRUE | 0 | 0 | 0 | 4186416 | 0 | 0 | 4129008 | 0 | 0 | 0 | 0 | 0 | 0 | 4186416 | 4129008 | 0 | 8315424 | 0 | 4186416 | 4129008 | 0 | 8315424
| Feeder works |  | Capacitance reducing isolation substation (6 MVA) | TRUE | 0 | 0 | 0 | 800379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800379 | 0 | 0 | 800379 | 0 | 800379 | 0 | 0 | 800379
| Feeder works |  | HV customer works | TRUE | 0 | 0 | 0 | 468320 | 534555 | 140000 | 331548 | 399987 | 110000 | 0 | 0 | 0 | 0 | 1142875 | 841535 | 0 | 1984410 | 0 | 1142875 | 841535 | 0 | 1984410
| #REF! |  | ZSS Feeder Exit Relocation | TRUE | 0 | 0 | 0 | 184667 | 95141.2535 | 857449 | 56036 | 45412.0322 | 96614 | 0 | 0 | 0 | 0 | 1137257.2535 | 198062.0322 | 0 | 1335319.2857 | 0 | 1137257.2535 | 198062.0322 | 0 | 1335319.2857
| #REF! |  | GFN on feeder and associated equipment | TRUE | 0 | 0 | 0 | 1515052 | 183664.7771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1698716.7771 | 0 | 0 | 1698716.7771 | 0 | 1698716.7771 | 0 | 0 | 1698716.7771
Substation
| Substation | Primary Plant
| Substation |  | GFN | TRUE | 0 | 0 | 0 | 6956202 | 2199628.6622 | 0 | 8115569 | 1292229.5875 | 0 | 0 | 0 | 0 | 0 | 9155830.6622 | 9407798.5875 | 0 | 18563629.2497 | 0 | 9155830.6622 | 9407798.5875 | 0 | 18563629.2497
| Substation |  | GFN enclosure | TRUE | 0 | 0 | 0 | 289842 | 0 | 0 | 434763 | 0 | 0 | 0 | 0 | 0 | 0 | 289842 | 434763 | 0 | 724605 | 0 | 289842 | 434763 | 0 | 724605
| Substation |  | Indoor switchboard and switch room (incl GFN enclosure) | TRUE | 0 | 0 | 0 | 870491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 870491 | 0 | 0 | 870491 | 0 | 870491 | 0 | 0 | 870491
| Substation |  | RMU | TRUE | 0 | 0 | 0 | 467663 | 0 | 0 | 467663 | 0 | 0 | 0 | 0 | 0 | 0 | 467663 | 467663 | 0 | 935326 | 0 | 467663 | 467663 | 0 | 935326
| Substation |  | Station service transformer (500kVA) | TRUE | 0 | 0 | 0 | 142023 | 0 | 0 | 189364 | 0 | 0 | 0 | 0 | 0 | 0 | 142023 | 189364 | 0 | 331387 | 0 | 142023 | 189364 | 0 | 331387
| Substation |  | Station service transformer (750kVA) | TRUE | 0 | 0 | 0 | 104344 | 0 | 0 | 104344 | 0 | 0 | 0 | 0 | 0 | 0 | 104344 | 104344 | 0 | 208688 | 0 | 104344 | 104344 | 0 | 208688
| Substation |  | Cap bank | TRUE | 0 | 0 | 0 | 309177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309177 | 0 | 0 | 309177 | 0 | 309177 | 0 | 0 | 309177
| Substation |  | AC board (Including change over) | TRUE | 0 | 0 | 0 | 144921 | 0 | 0 | 144921 | 0 | 0 | 0 | 0 | 0 | 0 | 144921 | 144921 | 0 | 289842 | 0 | 144921 | 144921 | 0 | 289842
| Substation |  | Indoor switchboard | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Substation |  | 22kV circuit breaker (outdoor) | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Substation |  | Voltage transformer | TRUE | 0 | 0 | 0 | 99126 | 0 | 0 | 49563 | 0 | 0 | 0 | 0 | 0 | 0 | 99126 | 49563 | 0 | 148689 | 0 | 99126 | 49563 | 0 | 148689
| Substation |  | Earth grid modification | TRUE | 0 | 0 | 0 | 433704 | 0 | 0 | 650556 | 0 | 0 | 0 | 0 | 0 | 0 | 433704 | 650556 | 0 | 1084260 | 0 | 433704 | 650556 | 0 | 1084260
| Substation |  | Other | TRUE | 0 | 0 | 0 | 781732 | 0 | 0 | 726669 | 0 | 0 | 0 | 0 | 0 | 0 | 781732 | 726669 | 0 | 1508401 | 0 | 781732 | 726669 | 0 | 1508401
Substation
| Substation |  | SCADA / Protection & Control/ Comms | TRUE | 0 | 0 | 0 | 741816 | 3910097.833 | 0 | 764375 | 2309484.7786 | 0 | 0 | 0 | 0 | 0 | 4651913.833 | 3073859.7786 | 0 | 7725773.6116 | 0 | 4651913.833 | 3073859.7786 | 0 | 7725773.6116
| Substation |  | Commissioning | TRUE | 0 | 0 | 0 | 0 | 2140283 | 0 | 0 | 1754454 | 0 | 0 | 0 | 0 | 0 | 2140283 | 1754454 | 0 | 3894737 | 0 | 2140283 | 1754454 | 0 | 3894737
| Substation |  | Construction delivery & site control | TRUE | 0 | 0 | 0 | 0 | 2560942 | 0 | 0 | 2049664 | 0 | 0 | 0 | 0 | 0 | 2560942 | 2049664 | 0 | 4610606 | 0 | 2560942 | 2049664 | 0 | 4610606
Contracts
| Contracts |  | Traffic control | TRUE | 0 | 0 | 0 | 0 | 0 | 1097843 | 0 | 0 | 1091683 | 0 | 0 | 0 | 0 | 1097843 | 1091683 | 0 | 2189526 | 0 | 1097843 | 1091683 | 0 | 2189526
| Contracts |  | Line survey | TRUE | 0 | 0 | 0 | 0 | 0 | 603459 | 0 | 0 | 511043 | 0 | 0 | 0 | 0 | 603459 | 511043 | 0 | 1114502 | 0 | 603459 | 511043 | 0 | 1114502
| Contracts |  | Civil works | TRUE | 0 | 0 | 0 | 0 | 0 | 2222120.7029 | 0 | 0 | 2150361.1733 | 0 | 0 | 0 | 0 | 2222120.7029 | 2150361.1733 | 0 | 4372481.8762 | 0 | 2222120.7029 | 2150361.1733 | 0 | 4372481.8762
| Contracts |  | Mob/Demob | TRUE | 0 | 0 | 0 | 0 | 0 | 101445 | 0 | 0 | 101445 | 0 | 0 | 0 | 0 | 101445 | 101445 | 0 | 202890 | 0 | 101445 | 101445 | 0 | 202890
| Contracts |  | Other | TRUE | 0 | 0 | 0 | 0 | 0 | 663738 | 0 | 0 | 477756 | 0 | 0 | 0 | 0 | 663738 | 477756 | 0 | 1141494 | 0 | 663738 | 477756 | 0 | 1141494
Other
| Distribution Code voltage variation payment |  | Distribution Code voltage variation payment | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PMO costs |  | PMO costs | FALSE | [12 empty] | 0 | 2532014.3221 | 1854802.0687 | 0 | 4386816.3908 | 0 | 0 | 0 | 0 | 0
|  |  | Test trailer | TRUE | [12 empty] | 0 | 154582 | 0 | 0 | 154582 | 0 | 154582 | 0 | 0 | 154582
|  |  | Spare GFN | TRUE | [12 empty] | 0 | 1159367 | 0 | 0 | 1159367 | 0 | 1159367 | 0 | 0 | 1159367
|  | Total capital cost |  |  | 0 | 0 | 0 | 30910457 | 26575736.3972 | 5686054.7029 | 26388245 | 15058448.021 | 4538902.1733 | 0 | 0 | 0 | 0 | 64486197.1002 | 45985595.1942 | 0 | 110471792.2944 | 0 | 64486197.1002 | 45985595.1942 | 0 | 110471792.2944
|  | Total project cost |  |  | 0 | 0 | 0 | 30910457 | 26575736.3972 | 5686054.7029 | 26388245 | 15058448.021 | 4538902.1733 | 0 | 0 | 0 | 0 | 67018211.4222 | 47840397.2629 | 0 | 114858608.6852
|  |  | check | 1

## Labour_rates
Powercor REFCLs Tranche 2 Contingent Project Application
Labour Rates
(real 2015 dollars)
DESIGN RATES
| Design Rates |  | 2016 | 2017 | 2018 | 2019 | 2020
| Design | 2015 $/hr |  |  | 196.0404 | 197.2041 | 198.4503
BALLARAT RESOURCE PARTNER RATES
| Rate per person per hour (with vehicles allocated) |  | 2016 | 2017 | 2018 | 2019 | 2020
| Live Linework | 2015 $/hr |  |  | 181.9551 | 183.0351 | 184.1918
| General Linework | 2015 $/hr |  |  | 166.8922 | 167.8828 | 168.9438
| Sub Tester | 2015 $/hr |  |  | 235.9085 | 237.3088 | 238.8085
| Fitter | 2015 $/hr |  |  | 164.5629 | 165.5396 | 166.5858
BENDIGO RESOURCE PARTNER RATES
| Rate per person per hour (with vehicles allocated) |  | 2016 | 2017 | 2018 | 2019 | 2020
| Live Linework | 2015 $/hr |  |  | 162.6888 | 163.6544 | 164.6887
| General Linework | 2015 $/hr |  |  | 153.1344 | 154.0433 | 155.0168
| Sub Tester | 2015 $/hr |  |  | 250.8935 | 252.3827 | 253.9777
| Fitter | 2015 $/hr |  |  | 154.2059 | 155.1212 | 156.1015