## MV-31 COMPLIANCE AUDIT REPORT
|  | VEGETATION SERVICES | [17 empty] | MV31 Myponga 11kv 2 Page Feeder
COMPLIANCE AUDIT REPORT
| Auditor: | Paul Osborn |  | Issued Date: | 2018-05-10 |  |  | Start Date: |  | 2018-05-16 |  |  |  | Finish Date: |  | 2018-05-21 |  |  |  | ANNUAL AUDIT 2018
| Contractor / Crew No: | Active Tree Services |  | Audit Type: | 6 sites per page of feeder plan - 4 random & 2 identified plus minium 4 spans | [14 empty] | Feeder Cycle: Annual
SAP Noti No | Contractors Job no | Location | Audited | Risk Area | Identified Units/Span/PSL | Scoped As (S/N/P) | Span Length | Voltage | Not Scoped (Extra Span) | Not Scoped (Extra Prune) | Scopers Name | CZ Infringement | Bend or Grow into CZ | Not Trimmed To Parameters | V (Regulations) | H (Regulations) | V (Achieved / Actual) | H (Achieved / Actual) | Other | Comments
Random Cut Sites
| 3400195 | TF9-102/1-2 | 12 | HBRFA | 8 | [14 empty] | compliant, some fast growers at this location, may require trimming in 2018 presummer works.
| 3400036 | TF45-71/0-1 | 10 | HBRFA | 7 | [14 empty] | compliant
| 3399924 | TF87-5/0-1 | 16 | HBRFA | 8 | [14 empty] | compliant
| 3393498 | TF100-83/2-3 | 10 | HBRFA | 5 | [14 empty] | compliant
Randomly Selected Locations
|  | TF28 | 12 | HBRFA | 7 | [14 empty] | compliant, 1 site defered at this location.
|  | TF75 | 10 | HBRFA | 3 | [14 empty] | compliant
|  | TF56 | 8 | HBRFA | 4 | [14 empty] | compliant
|  | TF90 | 10 | HBRFA | 3 | [14 empty] | compliant, some fast growers at this location, may require trimming in 2018 presummer works.
|  | TF18 | 8 | HBRFA | 2 | [14 empty] | compliant
|  | TF93 | 8 | HBRFA | 0 | [14 empty] | compliant
|  | TF19 | 14 | HBRFA | 5 | [14 empty] | compliant
|  | TF8 | 10 | HBRFA | 3 | [14 empty] | compliant
Drive By's
|  | TOTALS | 128 |  | 55 |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | 0
Note on D9: Total number of HV and LV spans audited at each site.
Note on T9: Any Damage, customer complaints, clean up problems, stump mulching required etc etc. 1 = Yes

## MV-31 Non Conformances
Photo 1 | Photo 2
Photo 3 | Photo 4
Photo 5 | Photo 6
Photo 7 | Photo 8
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX

## MV-31 COMPLI Sum & Addit Work
|  | COMPLIANCE AUDIT SUMMARY | [7 empty] | MV31 Myponga 11kv 2 Page Feeder
ADDITIONAL WORK & FEEDER COMPLETION
| Spans Audited | No of CZ Infringements | No. PSL Infringements | No of Other NCRs | Remedial Work Required (Y/N) | Completion Target (Date) | Satisfactory Completed (Date) | Work Order Completed (Date) | Auditor | Comments
1st Audit | 128 | 0 | 0 | 0 | no |  |  |  | P Osborn
Re Audit
Re Audit
Overall Comments
<SFNI>AUSF Scope Audit Fail - needed trimming
| <SFRW> | Scope Audit Fail - no trimming required
| <CFNC>AUCF |  | Trimming Audit Fail - no trimming has occurred
| <CFIC>AUCF |  | Trimming Audit Fail - insufficient Trimming

## MV-31 ATS REMEDIAL REPORT
|  | ATS REMEDIAL ACTION REPORT | [17 empty] | MV31 Myponga 11kv 2 Page Feeder
| Auditor: |  |  | Issued by ETSA Date: | [5 empty] | Remedial Action Completed Date: | [9 empty] | ANNUAL AUDIT 2012
ANNUAL AUDIT 2013
| Contractor / Crew No: |  |  | Audit Type: | REMEDIAL ACTION | [14 empty] | Feeder Cycle: Annual
SAP Noti No | Contractors Job no | Location | Audited | Risk Area | Identified Unit/Span/PSL | Scoped As (S/N/P) | Span Length | Voltage | Not Scoped (Extra Span) | Not Scoped (Extra Unit) | CZ Infringement | Bend or Grow into CZ | Not Cyclic Compliant | V (Regulations) | H (Regulations) | V (Achieved / Actual) | H (Achieved / Actual) | Other | Photo Number | Remedial Action Performed Comments
Random Cut Sites
Randomly Selected Locations
Drive By's
|  | TOTALS | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Note on D8: Total number of HV and LV spans audited at each site.
Note on T8: Any Damage, customer complaints, clean up problems, stump mulching required etc etc. 1 = Yes

## MTB-41 SCOPE AUDIT REPORT
|  | VEGETATION SERVICES | [14 empty] | MTB41 Balhannah 11kv 2 Page Feeder
SCOPE AUDIT REPORT
| Auditor: | Paul Osborn |  | Issued Date: | 2018-01-08 |  |  | Start Date: |  | 2018-01-17 |  |  | Finish Date: |  | 2018-01-18 |  | ANNUAL AUDIT 2018
Contractor / Scoper Name: |  | ATS/ B Cracknell, C Stocker, T Boafo, L Hall |  | Audit Type: | 6 sites per page of feeder plan - 4 random & 2 identified plus minium 4 spans | [11 empty] | Feeder Cycle: Annual
SAP Noti No | Contractors Job no | Location | Audited | Risk Area | Identified Units/Span/PSL | Scoped As (S/N/P) | Span Length | Voltage | Extra No. of Units | Extra No. Spans | Extra No. of PSL | Remove Units from Works | Remove Spans from Works | Scopers Name | Change Notes |  | Comments
Random Cut Sites
| 3290735 | TF43-42/0-1 | 12 | HBRFA | 7 | [8 empty] | B Cracknell C Stocker |  | verified
| 3296278 | TF31-12/3-4 | 10 | HBRFA | 7 | [8 empty] | T Boafo |  | verified
| 3293613 | TF26-22/0-1 | 10 | HBRFA | 6 | [8 empty] | L hall |  | verified
| 3290810 | TF17-6/1-2 | 12 | HBRFA | 7 | [8 empty] | B Cracknell L Hall |  | 1 site not verified
15259105 | 3293687 | TF6-54/2-3 |  | HBRFA |  | N | 49 | 240 |  | 1 |  |  |  | L hall |  | B&G infringement, Compliance Clearance V=1.0m H=1.0m, actual V=2.3m, scoper made judgement call, fast grower, trim span to compliance, Photo 2.
Randomly Selected Locations
|  | TF2 | 10 | HBRFA | 7 | [8 empty] | B Cracknell |  | verified
|  | TF52 | 8 | HBRFA | 3 | [8 empty] | T Boafo |  | 1 site not verified
15259104 | 3293163 | TF27-28/0-1 |  | HBRFA |  | N | 170 | 11 |  | 1 |  |  |  | T Boafo |  | B&G infringement, Compliance Clearance @ 36m V=2.2m H=3.9m, actual V=2.2m H=4.0m, fast grower, trim span to compliance. Photo 1.
|  | TF44 | 8 | HBRFA | 3 | [8 empty] | T Boafo |  | verified
|  | TF16 | 8 | HBRFA | 3 | [8 empty] | T Boafo |  | verified
|  | TF47 | 14 | HBRFA | 7 | [8 empty] | T Boafo |  | verified
|  | DF9909 | 12 | HBRFA | 6 | [8 empty] | L Hall |  | verified
|  | TF30 | 20 | HBRFA | 9 | [8 empty] | L Hall |  | verified
|  | TF8 | 12 | HBRFA | 6 | [8 empty] | L Hall |  | verified
Drive By's
|  | TOTALS | 136 |  | 71 |  |  |  | 0 | 2 | 0 | 0 | 0 | 0 | 0
No. that can be removed from works
[5 empty] | Spans |  | Units |  | PSLs
[5 empty] | 0 |  | 0 |  | 0
Overall Comments
2 sites not identified.
Note on D9: Total number of HV and LV spans audited at each site.

## MTB-41 Non Conformances
Photo 1 | 3293163 | TF27-28/0-1 | Photo 2 | 3293687 | TF6-54/2-3
Photo 3 |  |  | Photo 4
Photo 5 |  |  | Photo 6
Photo 7 |  |  | Photo 8
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX
SIZE/CROP
PHOTO TO FIT WITHIN THIS BOX