## Summary
30 Year NPV Analysis
The following 8 options have been evaluated in this model. A number of assumptions have been made throughout the analysis and have been detailed and listed on the following worksheets.
Option A | Redevelopment Dalrymple Rd, Garbutt - Value Managed Scope
Option B | Redevelopment Dalrymple Rd, Garbutt - Original Scope pre 420 Flinders St
Option C | Redevelopment Dalrymple Rd, Garbutt - Value Managed Scope with 12 month delay
Option D | Redevelopment Ingham Rd, Mt St John - AER 2010-15 Strategy & Submission
Option E / Do Nothing | Business As Usual - Do Nothing. Historical maintenance and capex work continues
Option F | Business As Usual with BCA Compliance addressed in all buildings
Option G | Business As Usual with BCA Compliance and Refurbishment to current standard addressed in all buildings
Option H | Redevelopment Dalrymple Rd, Garbutt - Value Managed Scope with 36 month delay. Fully delivered AER 2015-20
Commercial Outcomes - Without Ergon Overheads ($ M) | Option A | Option B | Option C | Option D | Option F | Option G | Option H | Option E / Do Nothing
Present Cost of Implementation | -41.9727 | -51.1294 | -40.5344 | -77.0964 | -20.3075 | -36.2174 | -36.2611 | 0
Present Cost of Lifecycle | -14.9314 | -19.0465 | -16.8311 | -19.4033 | -53.5048 | -35.4464 | -21.2489 | -56.0192
Present Value of Benefits | 3.6152 | 3.6152 | 3.6152 | 21.9178 | 0 | 0 | 2.8994 | 0
NPV (9.72% WACC) | -53.289 | -66.5607 | -53.7503 | -74.582 | -73.8123 | -71.6638 | -54.6107 | -56.0192
Option Rankings | 1 | 4 | 2 | 7 | 6 | 5 | 3
Risk Score | 0 | 0 | 0 | -9 | -29 | -21 | -4 | -43
Cost per risk point relieved | 1.2393 | 1.5479 | 1.25 | 2.1936 | 5.2723 | 3.2574 | 1.4003
Summary of Key Financial Assumptions
| Option A | Option B | Option C | Option D | Option F | Option G | Option H | Option E / Do Nothing
Build Start | 13/14 | 13/14 | 14/15 | 13/14 | 13/14 | 13/14 | 16/17 | N/A
Build Finish | 16/17 | 16/17 | 17/18 | 16/17 | 15/16 | 18/19 | 19/20 | N/A
Time Frame | 3 years | 3 years | 3 years | 3 years | 2 years | 5 years | 3 years | N/A
Construction $ | 48987265.3 | 59935876.5095 | 48987265.3 | 95185706.365 | 0 | 0 | 48987265.3 | N/A
Overheads $ | 24493632.65 | 28850980.6047 | 24493632.65 | 50648814.0818 | 0 | 0 | 24493632.65 | N/A
Escalations/Delays $ | 0 | 0 | 299334.2561 | 6111921.7985 | 0 | 0 | 2570003.5222 | N/A
C. Interest $ | 3373448.0985 | 3908797.5371 | 3373448.0985 | 6875315.8427 | 0 | 0 | 3373448.0985 | N/A
Total Redevelopment $ | 76854346.0485 | 92695654.6514 | 77153680.3046 | 158821758.088 | 0 | 0 | 79424349.5707 | 0
Garbutt Compliance Works | 0 | 0 | 0 | 0 | 21400509 | 0 | 0 | 0
Garbutt Compliance & Refurb Works | 0 | 0 | 0 | 0 | 0 | 40256509 | 0 | 0
Price Escalations $ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overheads $ | 0 | 0 | 0 | 0 | 11187779.5 | 21027924.5256 | 0 | 0
C. Interest $ | 0 | 0 | 0 | 0 | 3320419.1146 | 4477005.7741 | 0 | 0
Total Compliance Works $ | 0 | 0 | 0 | 0 | 35908707.6146 | 65761439.2997 | 0 | 0
Total Implementation Cost $ | 76854346.0485 | 92695654.6514 | 77153680.3046 | 158821758.088 | 35908707.6146 | 65761439.2997 | 79424349.5707 | 0
Ingham Rd Sale | 5292963.3705 | 5292963.3705 | 5292963.3705 | 5292963.3705 | 0 | 0 | 5616935.0725 | 0
Garbutt Site Sale | 0 | 0 | 0 | 45590391.3078 | 0 | 0 | 0 | 0
Lifecycle Costs $ (20y Opex & Capex) | 47846622.2803 | 64818842.979 | 49989551.4983 | 56148315.7175 | 216250286.8149 | 142402957.3712 | 55943614.6991 | 223331508.8619
Avg $ / Year | 2392331.114 | 3240942.149 | 2499477.5749 | 2807415.7859 | 10812514.3407 | 7120147.8686 | 2797180.735 | 11166575.4431
Total Option Cost (20y Opex & Capex) $ | 119408004.9583 | 152221534.2599 | 121850268.4324 | 164086719.1272 | 252158994.4295 | 208164396.6708 | 129751029.1973 | 223331508.8619
Option Descriptions
Option A | Redevelopment Dalrymple Rd, Garbutt - Value Managed Scope
This option delivers a more efficient redeveloped main office building including site amenities solution, a redeveloped Stores building (bg 3) into the workshop and support offices, and the adaptation of ARK Homes as the new Logistics warehouse. Delivery over three years into next regulatory period. Removes all significant risk and is the most cost effective resolution.
Option B | Redevelopment Dalrymple Rd, Garbutt - Original Scope pre 420 Flinders St
This option delivers a redeveloped main office building including site amenities solution, ecolink and an office extension. It includes a redeveloped Stores building (bg 3) as the workshop and support offices, and the adaptation of ARK Homes as the new Logistics warehouse. Delivery over three years into next regulatory period, with execution of both stages partially overlapping each other. Removes all significant risk and is the 4th cost effective resolution, but provides greater capacity for changing staff requirements
Option C | Redevelopment Dalrymple Rd, Garbutt - Value Managed Scope with 12 month delay
This option is consistent with Option A, but with a 12 month deferral period applied to the timeframes in anticipation of delays in gaining approval. This option maps the cost of internal labour, extensions to the tender, additional interest and design review costs. In terms of the Present Cost of Capex it represents a $176,000 increase over the 20 year period, although in real terms it will cost the business $1.3 million in capex plus the increased maintenance cost for one year. It also holds a greater risk of non-approval through the AER 2015-20 regulatory submission as the majority to pushed into that period.
Option D | Redevelopment Ingham Rd, Mt St John - AER 2010-15 Strategy & Submission
This option represents the previous strategic direction for Townsville as presented in the AER 2010-15 Regulatory Submission. It involves the development of a greenfield site at Ingham Rd, Mt St John previously purchased by Ergon in 2007. The scope includes the full planning, design, construction and relocation of 'blue collar' services to the new site and selling the parts of Garbutt which are owned by the business. It is the least cost effective option, and strategically implausible now due to the executed CBD strategy.
Option E / Do Nothing | Business As Usual - Do Nothing. Historical maintenance and capex work continues
This option represents Business As Usual / Doing Nothing. It continues to map the trending maintenance and capital costs on the Garbutt site over the 20 year period without any significant capital investment or Planned Corrective to meet the aging asset base.
Option F | Business As Usual with BCA Compliance addressed in all buildings
This option represents Business As Usual as above, but with resolution of the current and outstanding areas of non-compliance across all buildings on the Garbutt site. It continues to map the trending maintenance and BAU capital costs over the 20 year period, with only minor reductions where the BCA compliance work improves asset efficiency on the site. Mitigates building related risk, but site risks remain. Can be delivered over two years.
Option G | Business As Usual with BCA Compliance and Refurbishment to current standard addressed in all buildings
This option represents Business As Usual as above, but with resolution of non-compliance and the refurbishment up to current standard for all buildings on the Garbutt site. The site layout will remain as it is currently and the majority of the 23 buildings will be refurbished, relieving the buildings risks but only minor site related risks. Will require a period of five years for delivery due to the extensiveness of the scope and staging requirements around the site.
Option H | Redevelopment Dalrymple Rd, Garbutt - Value Managed Scope with 36 month delay. Fully delivered AER 2015-20
This option is consistent with Option A, but with full deferral into the 2015-20 regulatory period (36 months delay). This option maps the cost of internal labour, tender extensions, DA extensions, additional interest and design reassessment costs during the deferral period. In terms of the Present Cost of Capex it represents a $100,000 increase over the 20 year period, although in real terms it will cost the business $4.6 million in capex plus the increased maintenance cost for those years.
Note on F28: Includes Detailed design time
Note on H28: Includes Detailed design time

## Assumptions
Assumptions
Confirmed
| Planned Business Case Stage: | Gate 3 | WACC: | 9.72% |  |  | To Be Confirmed
Need More Data
Option A
| Brief Outline | Value Managed - Dalrymple Rd, Garbutt Redevelopment
| To Be Confirmed | This is the preferred option and is based on the strategic development of Dalrymple Rd, Garbutt utilising a value-managed methodology. It represents a full site development, including a refurbished main office building, adaptation of ARK Homes as the Logistics Warehouse, and the conversion of the existing warehouse to accommodate workshop activities and support staff.
Operational Assumptions
| Confirmed | Garbutt will operate as the sole 'blue-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | 420 Flinders St will continue to operate as the sole 'white-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | Hartley St, Townsville will continue to operate as the T&D Centre for Townsville in the near future. |  |  | -
| Confirmed | The existing leased accommodation at Tesla House (15 Dalrymple Rd) will be maintained for decanting purposes until the end of stage 1 |  |  | -
| Confirmed | No other leased accommodation or storage will be required over the next 20 years except what is being phased out as a response to the Flinders St relocation |  |  | -
| Confirmed | No impact on the OCCN (Control Centre) portion of the office will be experienced |  |  | -
| Confirmed | No other BAU capex works will be undertaken in the lead-up and during the Garbutt redevelopment |  |  | -
| Confirmed | Due to the limited (if any) impact (financial or otherwise) on 420 Flinders St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on Hartley St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on the OCCN during the Garbutt redevelopment, it will be excluded from the NPV for this option
| Confirmed | Continue to maintain unaffected portions of the Garbutt site during the redevelopment |  |  | -
| Confirmed | Land contamination remediation (both known and unknown) is accounted for within the scope of works for the redevelopment |  |  | -
| Confirmed | Removal of asbestos containing material is accounted for within the scope of works for the redevelopment |  |  | -
| Confirmed | The current 'Stores' building (BG3) aka Logistics, will be transitioned to BG18 (ARK) during the Redevelopment and BG3 will become a shared Workshop and office accommodation catering for what is currently known as the 'Depot', inclusive of buildings 4 to 15 |  |  | -
| Confirmed | Staff locations have yet to be finalised, but it is expected staff currently in BGs4-15 will be relocated into the refurbished BG3 building, with some moving to the Office. Forecast staff numbers within the 'Garbutt Site Details' worksheet |  |  | - | See 'Garbutt Site Details' worksheet
Timing Assumptions
| Confirmed | Shareholding approval will be received by end of April 2014 |  |  | 13/14 | Link to Project Delivery Schedule:
| Confirmed | Construction of stage 1 Garbutt Redevelopment (ARK Homes & Office) will begin 4th Qtr 13/14 (May 2014) |  |  | 13/14 | http://esp/ess/ss/Property%20Major%20Projects%20Supporting%20Information/
| Confirmed | Construction of stage 1 Garbutt Redevelopment (ARK Homes & Office) will conclude 4th Qtr 14/15 (June 15) |  |  | 14/15
| Confirmed | Tender of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will begin 1st Qtr 15/16 |  |  | 15/16
| Confirmed | Construction of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will begin 3rd Qtr 15/16 (Jan 2016) |  |  | 15/16
| Confirmed | Construction of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will conclude 3rd Qtr 16/17 (Jan 2017) |  |  | 16/17
| Confirmed | Relocation of staff and operations to the new Logistics building (ARK) will occur 4th Qtr 14/15 (June 2015) |  |  | 14/15
| Confirmed | Relocation of staff and operations to the Office building will occur 4th Qtr 14/15 (June 2015) |  |  | 14/15
| Confirmed | Relocation of staff and operations to the new Workshop building will occur 2nd Qtr 16/17 (Oct 2016) |  |  | 16/17
| Confirmed | Final handover and practical completion will occur 3rd Qtr 16/17 (Jan 2017) |  |  | 16/17
| Confirmed | Sale of Ingham Rd will occur in 2017/18 |  |  | 17/18
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Stores will transition between current and new on beginning of 1st Qtr 15/16 |  |  | 15/16
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Office will transition between current and new on beginning of 1st Qtr 15/16 |  |  | 15/16
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Depot will transition between current and new on beginning of 3rd Qtr 16/17 (6 months each way) |  |  | 16/17
| Confirmed | Off-site Inventory Storage no longer required on completion of ARK Homes site as Logistics facility - 4th Qtr 14/15 (June 2015) |  |  | 14/15
| Confirmed | Tesla House - 15 Dalrymple Road will be relinquished 4th Qtr 14/15 (June 2015) |  |  | 14/15
Financial Assumptions
Capex
| To Be Confirmed | No other CAPEX requirements prior to construction, during the project or within 15 years after completion |  |  | - | Link to Constructed Design Estimate:
| Confirmed | Garbutt Site Redevelopment | Based on Davis Landgon Contract Documentation Cost Plan. |  | 37967000 | http://esp/ess/ss/Property%20Major%20Projects%20Supporting%20Information/
| Confirmed | EECL Costs based on estimates provided by subsequent providers or where an internal cost, the historical record of similar projects |  |  | 8786350
| Confirmed | There is no CAPEX impact of the Garbutt Redevelopment on Hartley St or Flinders St sites in Townsville |  |  | 0
| Confirmed | Already incurred Project (design) costs as at 30 Nov 2013 with forecast costs up to beginning of construction |  |  | 2233915.3
| Confirmed | Capitalised Interest applied at 7.11% p.a. based on supplied monthly cash-flow by S.Hardy |  |  | 3373448.0985 | See 'Itemised Costing' worksheet
| Confirmed | Overheads applied to project |  |  | 24493632.65 | See 'Project Cost' worksheet
| Confirmed | Overhead rate applied to Redevelopment |  |  | 50%
| Confirmed | Sale of Ingham Rd represents the valuation as at October 2011 with a forecast 2% p.a. indexation up until sale date |  |  | 5292963.3705
| Opex | Opex escalations applied at consistent rate of 3% p.a. pre and post redevelopment |  |  | 3%
| Confirmed | Pre-execution baseline uses stores maintenance BAU Option with one year escalation |  |  | 60637.3772
| Confirmed | Pre-execution baseline uses stores non-maintenance BAU Option with one year escalation |  |  | 123121.6989
| Confirmed | Pre-execution baseline uses office maintenance BAU Option with one year escalation |  |  | 260661.2245
| Confirmed | Pre-execution baseline uses office non-maintenance BAU Option with one year escalation |  |  | 580910.6985
| Confirmed | Pre-execution baseline uses depot maintenance BAU Option with one year escalation |  |  | 289559.3732
| Confirmed | Pre-execution baseline uses depot non-maintenance BAU Option with one year escalation |  |  | 598014.8467
| Confirmed | Pre-execution baseline Tesla House maintenance and non-maintenance 12/13 with one year escalation at 4% p.a. |  |  | 331626.88
| Confirmed | Post-execution baseline in Stores maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm |  |  | 44476.4758 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline stores non-maintenance reflective of changes in land tax and increase in rates due to move to ARK building, all other costs remain consistent |  |  | 98977.4706 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm. Correctived costs related to OCCN remain in total |  |  | 98989.7362 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office non-maintenance related to the move to a consolidated open and shared service office efficient floor plan. Four kitchenettes reduced to one kitchen (20% saving in amenities), document destruction bins reduced by half (40% saving in recycling/shredding), electricity usage reduced through usage of efficiency devices, time sensitive, segmented lights & air-con usage (electricity saving of 40%), lease of donga no longer required (100% saving). |  |  | 444485.9488 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Depot maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm. Grounds maintenance remains. |  |  | 42514.46 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline depot non-maintenance considerable savings quantified through the reduction from 11 buildings to 1 and the centralisation of many staff services and recurring costs. Amenities reduced against staff numbers with a 80% saving (aligned to costs recorded in BG1-Office), cleaning by cost/sqm with a similar saving of 70%, rates & land tax now reflective of 24 Dalrymple Rd (currently BG3), electricity reduced by cost/sqm and a 60% saving (smaller saving due to continuation of workshop tools and devices). |  |  | 237454.5622 | See 'Opex Baseline' worksheet
| Confirmed | Off-site Inventory Storage - Based on current cost for Fleet, Procurement & Logistics to annually lease temporary storage to relieve pressures of inventory at the Garbutt site. In the last twelve months, portions of the ARK Homes site have been utilised on a temporary basis to relieve some of these costs, which will continue in the short-term until the completion of the ARK Homes portion of the redevelopment, where it will be removed |  |  | 182000
| Confirmed | Maintenance & most non-maintenance costs reduced during redevelopment of the relevant stage. All building maintenance ceases, and all non land related non-maintenance is removed |  |  | 0
Option B
| Brief Outline | Original Scope – Dalrymple Rd, Garbutt Redevelopment
| To Be Confirmed | This is the original scope based on the strategic development of Dalrymple Rd, Garbutt utilising the previous methodology, prior to the 420 Flinders Street direction. It represents a full site development, including a refurbished main office building including extension and eco-link, adaptation of ARK Homes as the Logistics Warehouse, and the conversion of the existing warehouse to accommodate workshop activities and support staff.
Operational Assumptions
| Confirmed | Garbutt will operate as the sole 'blue-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | 420 Flinders St will continue to operate as the sole 'white-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | Hartley St, Townsville will continue to operate as the T&D Centre for Townsville in the near future. |  |  | -
| Confirmed | The existing leased accommodation at Tesla House (15 Dalrymple Rd) will be maintained for decanting purposes until the end of stage 1 |  |  | -
| Confirmed | No other leased accommodation or storage will be required over the next 20 years except what is being phased out as a response to the Flinders St relocation |  |  | -
| Confirmed | Only 15 Dalrymple Rd will be utilised during the stage 1 Garbutt redevelopment for decanting purposes |  |  | -
| Confirmed | No impact on the OCCN (Control Centre) portion of the office will be experienced |  |  | -
| Confirmed | No other BAU capex works will be undertaken in the lead-up and during the Garbutt redevelopment |  |  | -
| Confirmed | Due to the limited (if any) impact (financial or otherwise) on 420 Flinders St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on Hartley St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on the OCCN during the Garbutt redevelopment, it will be excluded from the NPV for this option
| Confirmed | Continue to maintain unaffected portions of the Garbutt site during the redevelopment |  |  | -
| Confirmed | Land contamination remediation (both known and unknown) is accounted for within the scope of works for the redevelopment |  |  | -
| Confirmed | Removal of asbestos containing material is accounted for within the scope of works for the redevelopment |  |  | -
| Confirmed | The current 'Stores' building (BG3) aka Logistics, will be transitioned to BG18 (ARK) during the Redevelopment and BG3 will become a shared Workshop and office accommodation catering for what is currently known as the 'Depot', inclusive of buildings 4 to 15 |  |  | -
| Confirmed | Staff locations have yet to be finalised, but it is expected staff currently in BGs4-15 will be relocated into the refurbished BG3 building, with some moving to the Office. Forecast staff numbers within the 'Garbutt Site Details' worksheet |  |  | - | See 'Garbutt Site Details' worksheet
Timing Assumptions
| Confirmed | Shareholding approval will be received by end of April 2014 |  |  | 13/14 | Link to Project Delivery Schedule:
| Confirmed | Detailed Design and tender decision for Original Scope will be completed by 4th Qtr 13/14 (June 2014) |  |  | 13/14 | http://esp/ess/ss/Property%20Major%20Projects%20Supporting%20Information/
| Confirmed | Construction of stage 1 Garbutt Redevelopment (ARK Homes & Office) will begin 1st Qtr 14/15 |  |  | 14/15
| Confirmed | Construction of stage 1 Garbutt Redevelopment (ARK Homes & Office) will conclude 3rd Qtr 15/16 |  |  | 15/16
| Confirmed | Tender of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will begin 1st Qtr 15/16 |  |  | 15/16
| Confirmed | Construction of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will begin 4th Qtr 15/16 |  |  | 15/16
| Confirmed | Construction of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will conclude 4th Qtr 16/17 |  |  | 16/17
| Confirmed | Relocation of staff and operations to the new Logistics building (ARK) will occur 4th Qtr 14/15 (June 2015) |  |  | 14/15
| Confirmed | Relocation of staff and operations to the Office building will occur 3rd Qtr 15/16 |  |  | 15/16
| Confirmed | Relocation of staff and operations to the new Workshop building will occur 3rd Qtr 16/17 |  |  | 16/17
| Confirmed | Final handover and practical completion will occur 4th Qtr 16/17 |  |  | 16/17
| Confirmed | Sale of Ingham Rd will occur in 2017/18 |  |  | 17/18
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Stores will transition between current and new on beginning of 1st Qtr 15/16 |  |  | 15/16
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Office will transition between current and new on beginning of 1st Qtr 16/17 |  |  | 15/16
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Depot will transition between current and new on beginning of 4th Qtr 16/17 |  |  | 16/17
| Confirmed | Off-site Inventory Storage no longer required on completion of ARK Homes site as Logistics facility - 1st Qtr 15/16 |  |  | 15/16
| Confirmed | Tesla House - 15 Dalrymple Road will be relinquished 4th Qtr 15/16, requiring a one year extension of lease |  |  | 15/16
Financial Assumptions
Capex
| Confirmed | No other CAPEX requirements prior to construction, during the project or within 15 years after completion |  |  | -
| Confirmed | Garbutt Site Redevelopment | Based on Lend Lease Constructed Design estimate. Additional costs include EE related expenses as detailed (attached) |  | 46266710.39
| Confirmed | EECL Costs based on estimates provided by subsequent providers or where an internal cost, the historical record of similar projects |  |  | 9201335.5195
| Confirmed | There is no CAPEX impact of the Garbutt Redevelopment on Hartley St or Flinders St sites in Townsville |  |  | 0
| Confirmed | Already incurred Project (design) costs as at 30 Nov 2013 with forecast costs up to beginning of construction, including the additional cost of a renewed detailed design and associated consultants |  |  | 4467830.6
| Confirmed | Capitalised Interest applied at 7.11% p.a. based on supplied monthly cash-flow by S.Hardy |  |  | 3908797.5371 | See 'Project Cost' worksheet
| Confirmed | Overheads applied to project |  |  | 28850980.6047 | See 'Cash-flow' worksheet
| Confirmed | Overhead rate applied to Redevelopment |  |  | 50%
| Confirmed | Sale of Ingham Rd represents the valuation as at October 2011 with a forecast 2% p.a. indexation up until sale date |  |  | 5292963.3705
| Opex | Opex escalations applied at consistent rate of 3% p.a. pre and post redevelopment |  |  | 3%
| Confirmed | Pre-execution baseline uses stores maintenance BAU Option with one year escalation |  |  | 60637.3772
| Confirmed | Pre-execution baseline uses stores non-maintenance BAU Option with one year escalation |  |  | 123121.6989
| Confirmed | Pre-execution baseline uses office maintenance BAU Option with one year escalation |  |  | 260661.2245
| Confirmed | Pre-execution baseline uses office non-maintenance BAU Option with one year escalation |  |  | 580910.6985
| Confirmed | Pre-execution baseline uses depot maintenance BAU Option with one year escalation |  |  | 289559.3732
| Confirmed | Pre-execution baseline uses depot non-maintenance BAU Option with one year escalation |  |  | 598014.8467
| Confirmed | Baseline Tesla House maintenance and non-maintenance 12/13 with one year escalation at 4% p.a. |  |  | 331626.88
| Confirmed | Post-execution baseline in Stores maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm |  |  | 44476.4758 | See 'Opex Baseline' worksheet
| Confirmed | 'Post-execution baseline in Stores non-maintenance reflective of changes in land tax and increase in rates due to move to ARK building, all other costs remain consistent |  |  | 98977.4706 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm. Correctived costs related to OCCN remain in total |  |  | 203333.0515 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office non-maintenance related to the move to a consolidated open and shared service office efficient floor plan. Four kitchenettes reduced to two kitchens (10% saving in amenities), document destruction bins reduced by half (40% Post-execution baseline saving in recycling/shredding), electricity usage reduced through removal of buildings and efficiency devices, time sensitive, segmented lights & air-con usage (electricity saving of 20%), lease of donga no longer required (100% saving). |  |  | 720561.5723 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Depot maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm. Grounds maintenance remains. |  |  | 42514.46 | See 'Opex Baseline' worksheet
| Confirmed | 'Post-execution baseline in Depot non-maintenance considerable savings quantified through the reduction from 11 buildings to 1 and the centralisation of many staff services and recurring costs. Amenities reduced against staff numbers with a 80% saving (aligned to costs recorded in BG1-Office), cleaning by cost/sqm with a similar saving of 70%, rates & land tax now reflective of 24 Dalrymple Rd (currently BG3), electricity reduced by cost/sqm and a 60% saving (smaller saving due to continuation of workshop tools and devices). |  |  | 237454.5622 | See 'Opex Baseline' worksheet
| Confirmed | Off-site Inventory Storage - Based on current cost for Fleet, Procurement & Logistics to annually lease temporary storage to relieve pressures of inventory at the Garbutt site. In the last twelve months, portions of the ARK Homes site have been utilised on a temporary basis to relieve some of these costs, which will continue in the short-term until the completion of the ARK Homes portion of the redevelopment, where it will be removed |  |  | 182000
| Confirmed | Maintenance & most non-maintenance costs reduced during redevelopment of the relevant stage. All building maintenance ceases, and all non land related non-maintenance is removed |  |  | 0
Option C
| Brief Outline | Value Managed - Dalrymple Rd, Garbutt Redevelopment with 12 month approval delay
| To Be Confirmed | This is as per Option 1, preferred scope of works, but applies a 12 month postponement due to potential approval delays as realised in the Glenmore Rd submission. This is not a valid option for selection, but highlights to costs and risks to the business as a result of a delay in progressing the project
Operational Assumptions
| Confirmed | Garbutt will operate as the sole 'blue-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | 420 Flinders St will continue to operate as the sole 'white-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | Hartley St, Townsville will continue to operate as the T&D Centre for Townsville in the near future. |  |  | -
| Confirmed | The existing leased accommodation at Tesla House (15 Dalrymple Rd) will be maintained for decanting purposes until the end of stage 1 |  |  | -
| Confirmed | No other leased accommodation or storage will be required over the next 20 years except what is being phased out as a response to the Flinders St relocation |  |  | -
| Confirmed | No impact on the OCCN (Control Centre) portion of the office will be experienced |  |  | -
| Confirmed | No other BAU capex works will be undertaken in the lead-up and during the Garbutt redevelopment |  |  | -
| Confirmed | Due to the limited (if any) impact (financial or otherwise) on 420 Flinders St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on Hartley St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on the OCCN during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Continue to maintain unaffected portions of the Garbutt site during the redevelopment |  |  | -
| Confirmed | Land contamination remediation (both known and unknown) is accounted for within the scope of works for the redevelopment |  |  | -
| Confirmed | Removal of asbestos containing material is accounted for within the scope of works for the redevelopment |  |  | -
| Confirmed | The current 'Stores' building (BG3) aka Logistics, will be transitioned to BG18 (ARK) during the Redevelopment and BG3 will become a shared Workshop and office accommodation catering for what is currently known as the 'Depot', inclusive of buildings 4 to 15 |  |  | -
| Confirmed | Staff locations have yet to be finalised, but it is expected staff currently in BGs4-15 will be relocated into the refurbished BG3 building, with some moving to the Office. Forecast staff numbers within the 'Garbutt Site Details' worksheet |  |  | - | See 'Garbutt Site Details' worksheet
Timing Assumptions
| Confirmed | Shareholding approval will be received by end of April 2015 |  |  | 14/15 | Link to Project Delivery Schedule:
| Confirmed | Construction of stage 1 Garbutt Redevelopment (ARK Homes & Office) will begin 4th Qtr 14/15 |  |  | 14/15 | http://esp/ess/ss/Property%20Major%20Projects%20Supporting%20Information/
| Confirmed | Construction of stage 1 Garbutt Redevelopment (ARK Homes & Office) will conclude 4th Qtr 15/16 |  |  | 15/16
| Confirmed | Tender of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will begin 1st Qtr 16/17 |  |  | 16/17
| Confirmed | Construction of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will begin 3rd Qtr 16/17 |  |  | 16/17
| Confirmed | Construction of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will conclude 3rd Qtr 17/18 |  |  | 17/18
| Confirmed | Relocation of staff and operations to the new Logistics building (ARK) will occur 4th Qtr 15/16 |  |  | 15/16
| Confirmed | Relocation of staff and operations to the Office building will occur 4th Qtr 15/16 |  |  | 15/16
| Confirmed | Relocation of staff and operations to the new Workshop building will occur 2nd Qtr 17/18 |  |  | 17/18
| Confirmed | Final handover and practical completion will occur 3rd Qtr 17/18 |  |  | 17/18
| Confirmed | Sale of Ingham Rd will occur in 2017/18 |  |  | 18/19
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Stores will transition between current and new on beginning of 1st Qtr 16/17 |  |  | 16/17
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Office will transition between current and new on beginning of 1st Qtr 16/17 |  |  | 16/17
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Depot will transition between current and new on beginning of 3rd Qtr 17/18 (6 months each way) |  |  | 17/18
| Confirmed | Off-site Inventory Storage no longer required on completion of ARK Homes site as Logistics facility - 4th Qtr 15/16 |  |  | 15/16
| Confirmed | Tesla House - 15 Dalrymple Road will be relinquished 4th Qtr 15/16, requiring a one year extension of lease |  |  | 15/16
Financial Assumptions
Capex
| Confirmed | No other CAPEX requirements prior to construction, during the project or within 15 years after completion |  |  | - | Link to Constructed Design Estimate:
| Confirmed | Garbutt Site Redevelopment | Based on Davis Landgon Contract Documentation Cost Plan. Additional costs include EE related expenses as detailed (attached) |  | 37967000 | http://esp/ess/ss/Property%20Major%20Projects%20Supporting%20Information/
| Confirmed | EECL Costs based on estimates provided by subsequent providers or where an internal cost, the historical record of similar projects |  |  | 8786350
| Confirmed | There is no CAPEX impact of the Garbutt Redevelopment on Hartley St or Flinders St sites in Townsville |  |  | 0
| Confirmed | Already incurred Project (design) costs as at 30 Nov 2013 with forecast costs up to beginning of construction |  |  | 2233915.3
| Confirmed | Costs associated with a twelve month delay, including tender extension fee, internal labour costs and capitalised Interest |  |  | 299334.2561
| Confirmed | Consultant/QS costs associated with twelth month delay, based on Glenmore Rd where multiple reviews, reconfirmation of costs and rework was performed to satisfy the Board and Shareholding Minister requirements. Split over two FY's |  |  | 572196
| Confirmed | Capitalised Interest applied at 7.11% p.a. based on supplied monthly cash-flow by S.Hardy |  |  | 3373448.0985 | See 'Itemised Costing' worksheet
| Confirmed | Overheads applied to project |  |  | 24493632.65 | See 'Project Cost' worksheet
| Confirmed | Overhead rate applied to Redevelopment |  |  | 50%
| Confirmed | Redevelopment costs flowed based on straight 75% of Option 1 costs pushed out into following year for each yearly cash-flow |  |  | -
| Confirmed | Minor BAU Capex costs based on Option 5 - BAU for one year of the deferral period (split 6 months each FY) |  |  | 432050.2844
| Confirmed | Garbutt Redevelopment Construction costs escalated by one year based on escalations documented in Cost Plan |  |  | 1.5%
| Confirmed | Sale of Ingham Rd represents the valuation as at October 2011 with a forecast 2% p.a. indexation up until sale date |  |  | 5292963.3705
| Opex | Opex escalations applied at consistent rate of 3% p.a. pre and post redevelopment |  |  | 3%
| Confirmed | Pre-execution baseline uses stores maintenance BAU Option with one year escalation |  |  | 60637.3772
| Confirmed | Pre-execution baseline uses stores non-maintenance BAU Option with one year escalation |  |  | 123121.6989
| Confirmed | Pre-execution baseline uses office maintenance BAU Option with one year escalation |  |  | 260661.2245
| Confirmed | Pre-execution baseline uses office non-maintenance BAU Option with one year escalation |  |  | 580910.6985
| Confirmed | Pre-execution baseline uses depot maintenance BAU Option with one year escalation |  |  | 289559.3732
| Confirmed | Pre-execution baseline uses depot non-maintenance BAU Option with one year escalation |  |  | 598014.8467
| Confirmed | Pre-execution baseline Tesla House maintenance and non-maintenance 12/13 with one year escalation at 4% p.a. |  |  | 331626.88
| Confirmed | Post-execution baseline in Stores maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm |  |  | 44476.4758 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline stores non-maintenance reflective of changes in land tax and increase in rates due to move to ARK building, all other costs remain consistent |  |  | 98977.4706 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm. Correctived costs related to OCCN remain in total |  |  | 98989.7362 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office non-maintenance related to the move to a consolidated open and shared service office efficient floor plan. Four kitchenettes reduced to one kitchen (20% saving in amenities), document destruction bins reduced by half (40% saving in recycling/shredding), electricity usage reduced through removal of buildings and efficiency devices, time sensitive, segmented lights & air-con usage (electricity saving of 50%), lease of donga no longer required (100% saving). |  |  | 444485.9488 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Depot maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm. Grounds maintenance remains. |  |  | 42514.46 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline depot non-maintenance considerable savings quantified through the reduction from 11 buildings to 1 and the centralisation of many staff services and recurring costs. Amenities reduced against staff numbers with a 80% saving (aligned to costs recorded in BG1-Office), cleaning by cost/sqm with a similar saving of 70%, rates & land tax now reflective of 24 Dalrymple Rd (currently BG3), electricity reduced by cost/sqm and a 60% saving (smaller saving due to continuation of workshop tools and devices). |  |  | 237454.5622 | See 'Opex Baseline' worksheet
| Confirmed | Off-site Inventory Storage - Based on current cost for Fleet, Procurement & Logistics to annually lease temporary storage to relieve pressures of inventory at the Garbutt site. In the last twelve months, portions of the ARK Homes site have been utilised on a temporary basis to relieve some of these costs, which will continue in the short-term until the completion of the ARK Homes portion of the redevelopment, where it will be removed |  |  | 182000
| Confirmed | Maintenance & most non-maintenance costs reduced during redevelopment of the relevant stage. All building maintenance ceases, and all non land related non-maintenance is removed |  |  | 0
Option D
| Brief Outline | AER 2010-15 Master Plan Scope - Ingham Rd Redevelopment
| Confirmed | This option represents the original AER 2010-15 Master plan strategy to move blue collar workers to a newly developed Ingham Rd site. Due to the purchase of ARK Homes and the move of white-collar staff to Flinders St, this is no longer a valid choice for the business. This option has been provided as a reference.
Operational Assumptions
| Confirmed | Ingham Rd will operate as the sole 'blue-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | 420 Flinders St will continue to operate as the sole 'white-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | The Garbutt site (exluding Substation/Powerstation) will be sold off |  |  | -
| Confirmed | Hartley St, Townsville will continue to operate as the T&D Centre for Townsville in the near future. |  |  | -
| Confirmed | The existing leased accommodation at Tesla House (15 Dalrymple Rd) will be relinquished |  |  | -
| Confirmed | No other leased accommodation or storage will be required over the next 20 years except what is being phased out as a response to the Flinders St relocation |  |  | -
| Confirmed | The OCCN (Control Centre) portion of the office will be moved to Ingham Rd |  |  | -
| Confirmed | Minor BAU Capex works will be undertaken in the lead-up to the Ingham Rd move |  |  | -
| Confirmed | Due to the limited (if any) impact (financial or otherwise) on 420 Flinders St, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on Hartley St, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Maintenance and non-maintenance costs for OCCN are assumed to retain between sites
| Confirmed | Continue to maintain Garbutt during the development of Ingham Rd |  |  | -
| Confirmed | All Garbutt buildings will continue to operate as they have been (albeit with lower staff numbers) while Ingham Rd is developed |  |  | -
| Confirmed | BAU Minor Capex will be executed each year to maintain and replace aging assets at Garbutt up to the point of relocation |  |  | -
Timing Assumptions
| Confirmed | Detailed Design to commence 3rd Qtr 13/14 |  |  | 13/14
| Confirmed | Shareholding approval will be received by end of 2014 |  |  | 14/15
| Confirmed | Construction of Ingham Rd Development will begin 3rd Qtr 14/15 (Jan 2015) |  |  | 14/15
| Confirmed | Construction of Ingham Rd Development will conclude 2nd Qtr 16/17 (Jan 17) |  |  | 16/17
| Confirmed | Relocation of staff and operations to Ingham Rd will occur 2nd Qtr 16/17 (Jan 17) |  |  | 16/17
| Confirmed | Sale of Garbutt will occur in 2021/22 |  |  | 21/22
| Confirmed | Maintenance and Non-maintenance costs at Ingham Rd will commence 3rd Qtr 16/17 as per baseline |  |  | 16/17
| Confirmed | Maintenance and Non-maintenance costs at Garbutt will continue as per normal in 16/17, reduce in 17/18 prior to sale in 18/19 |  |  | 17/18
| Confirmed | Off-site Inventory Storage no longer required on completion of Ingham Rd 2nd Qtr 16/17 (Jan 17) |  |  | 16/17
| Confirmed | Tesla House - 15 Dalrymple Road will be relinquished 4th Qtr 14/15 (June 2015) |  |  | 14/15
Financial Assumptions
Capex
| Confirmed | No other CAPEX requirements at Garbutt or post-development at Ingham Rd within the 15 year period |  |  | -
| Confirmed | Ingham Rd Development | Based on Bovis Lend Lease Concept Design Cost Plan. Additional costs include EE related expenses as detailed and OCCN Communications CAPEX costs based on Richardson/Glenmore Rd estimate for OCCS |  | 79891600 | See 'OP4-Project Cost'
| Confirmed | EECL Costs based on estimates provided by subsequent providers or where an internal cost, the historical record of similar projects |  |  | 10826275.765
| Confirmed | Escalations not in-built to project costing, estimated at 2.5% p.a. |  |  | 6111921.7985
| Confirmed | Already incurred Project (design) costs as at 30 Nov 2013 with forecast costs up to beginning of new detailed design |  |  | 2233915.3
| Confirmed | Detailed Design for Ingham Rd, Mt St John |  |  | 2233915.3
| Confirmed | Capitalised Interest applied at 7.11% p.a. based on calculated yearly costs |  |  | 6875315.8427 | See 'Itemised Costing' worksheet
| Confirmed | Overheads applied to project |  |  | 50648814.0818 | See 'Cash-flow' worksheet
| Confirmed | Overhead rate applied to Redevelopment |  |  | 50%
| Confirmed | There is no CAPEX impact of the Ingham Rd development on Hartley St or Flinders St sites in Townsville |  |  | 0
| Confirmed | Sale of Garbutt represents the valuations taken 2009-2011 with a forecast 2% p.a. indexation up until sale date |  |  | 45590391.3078
| Opex | Opex escalations applied at consistent rate of 3% p.a. pre and post redevelopment |  |  | 3%
| Confirmed | Pre-execution baseline uses Garbutt stores maintenance BAU Option with one year escalation |  |  | 60637.3772
| Confirmed | Pre-execution baseline uses Garbutt stores non-maintenance BAU Option with one year escalation |  |  | 123121.6989
| Confirmed | Pre-execution baseline uses Garbutt office maintenance BAU Option with one year escalation |  |  | 260661.2245
| Confirmed | Pre-execution baseline uses Garbutt office non-maintenance BAU Option with one year escalation |  |  | 580910.6985
| Confirmed | Pre-execution baseline uses Garbutt depot maintenance BAU Option with one year escalation |  |  | 289559.3732
| Confirmed | Pre-execution baseline uses Garbutt depot non-maintenance BAU Option with one year escalation |  |  | 598014.8467
| Confirmed | Baseline Tesla House maintenance and non-maintenance 12/13 with one year escalation at 4% p.a. |  |  | 331626.88
| Confirmed | Pre-sale Garbutt maintenance and non-maintenance in 17/18 will only retain land tax, grounds & rates costs as per BAU. All other costs will be removed as site not in use |  |  | 342192.69
| Confirmed | Post-execution Ingham Rd Stores maintenance uses Option 1 savings (removal of major plant corrective items) and apportions it against the building sqm |  |  | 59151.5721 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution Ingham Rd Stores non-maintenance consolidated under the Ingham Rd 'Office' |  |  | 0 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution Ingham Rd Office maintenance uses Option 1 savings (removal of major plant corrective items) and apportions it against the building sqm |  |  | 99529.9919 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution Ingham Rd baseline in Office non-maintenance uses and consolidates the costs at Garbutt's three sites calculated in Option 1 as a baseline and applies modifiers based on staff and building sqm. Rates align to the actual rates costs at Ingham Rd with the additional water costs at Garbutt and land tax reflects actual costs at Ingham Rd. Savings forecast within Option 1 reflect consistent design principles if the Ingham Rd development went ahead. |  |  | 598929.1512 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution Ingham Rd Depot maintenance uses Option 1 savings (removal of major plant corrective items) and apportions it against the building sqm |  |  | 205808.5344
| Confirmed | Post-execution Ingham Rd Depot non-maintenance consolidated under the Ingham Rd 'Office', except Grounds Maintenance which is apportioned by sqm of the site |  |  | 90598.562 | See 'Opex Baseline' worksheet
| Confirmed | Off-site Inventory Storage - Based on current cost for Fleet, Procurement & Logistics to annually lease temporary storage to relieve pressures of inventory at the Garbutt site. In the last twelve months, portions of the ARK Homes site have been utilised on a temporary basis to relieve some of these costs, which will continue in the short-term until the completion of the ARK Homes portion of the redevelopment, where it will be removed |  |  | 182000
Option E
| Brief Outline | Do Nothing / BAU
| To Be Confirmed | This option details the 'Business As Usual' / 'Do Nothing' scenario. It assumes the status quo with the continuation of maintenance and capital expenditure to maintain the aging asset base at Garbutt
Operational Assumptions
| Confirmed | Garbutt will operate as the sole 'blue-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | 420 Flinders St will continue to operate as the sole 'white-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | Hartley St, Townsville will continue to operate as the T&D Centre for Townsville in the near future. |  |  | -
| Confirmed | The existing leased accommodation at Tesla House (15 Dalrymple Rd) will be relinquished |  |  | -
| Confirmed | No other leased accommodation or storage will be required over the next 20 years except what is being phased out as a response to the Flinders St relocation |  |  | -
| Confirmed | All temporary staff accommodation at Garbutt will be removed/returned (dongas etc.) |  |  | -
| Confirmed | BAU Capex Works will continue to be undertaken to maintain existing asset base as best as possible |  |  | -
| Confirmed | Continue to maintain all of the Garbutt site over the next twenty years |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on Hartley St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on the OCCN during the Garbutt redevelopment, it will be excluded from the NPV for this option
-
| Confirmed | Land contamination remediation (both known and unknown) will not be addressed |  |  | -
| Confirmed | Asbestos containing material will not be addressed |  |  | -
| Confirmed | All buildings on site will continue to operate as they have been (albeit with lower staff numbers) |  |  | -
| Confirmed | BAU Minor Capex will be executed each year to maintain and replace aging assets |  |  | -
| Confirmed | BAU Major Capex will be executed each year to maintain and replace major plant items where required
Timing Assumptions
| Confirmed | Capex and Opex work will continue to be executed in a timely fashion as per historical trend |  |  | -
Confirmed
| Confirmed | Sale of Ingham Rd will occur in 2017/18 |  |  | 17/18
| Confirmed | Current levels of Off-site Inventory Storage will continue indefinitely |  |  | -
| Confirmed | Tesla House - 15 Dalrymple Road will be relinquished 4th Qtr 14/15 (June 2015) - Current lease term |  |  | 14/15
| Confirmed | BAU Minor Capex will be executed each year indefinitely |  |  | -
| Confirmed | BAU Major Capex will be executed each year indefinitely |  |  | -
Financial Assumptions
| Capex | BAU Capex escalations applied at consistent rate of 6% p.a. based on historical trend due to escalating age of assets, requirement to replace major plant and cost to mitigate existing risks considerable |  |  | 6%
| Confirmed | BAU Minor Capex mitigation based on historical trend from 08/09 to 11/12 escalated 6% p.a. |  |  | 432050.2844 | See 'OP5-Garbutt Projects'
| Confirmed | BAU Major Capex mitigation based on historical trend escalated 6% p.a. Excludes capex 10/11 onwards from calculation as once 10-15 AER program approved, majority of major work ceased |  |  | 899475.5305 | See 'OP5-Garbutt Projects'
| Confirmed | Already incurred Project (design) costs as at 30 Nov 2013 with be expensed to OPEX |  |  | 2233915.3
| Confirmed | Sale of Ingham Rd represents the valuation as at October 2011 with a forecast 2% p.a. indexation up until sale date |  |  | 5292963.3705
| Opex | Opex escalations applied at consistent rate of 3% p.a. pre and post redevelopment |  |  | 3%
| Confirmed | Baseline uses stores maintenance BAU Option with one year escalation |  |  | 60637.3772
| Confirmed | Baseline uses stores non-maintenance BAU Option with one year escalation |  |  | 123121.6989
| Confirmed | Baseline uses office maintenance BAU Option with one year escalation |  |  | 260661.2245
| Confirmed | Baseline uses office non-maintenance BAU Option with one year escalation |  |  | 580910.6985
| Confirmed | Baseline uses depot maintenance BAU Option with one year escalation |  |  | 289559.3732
| Confirmed | Baseline uses depot non-maintenance BAU Option with one year escalation |  |  | 598014.8467
| Confirmed | Baseline Tesla House maintenance and non-maintenance 12/13 with one year escalation at 4% p.a. |  |  | 331626.88
| To Be Confirmed | Forecast escalation for all building maintenance costs from 2017/18 at 0.5% p.a. until additional 4% due to increasing age of asset base reaching critical point in lifecycle |  |  | 0.5% - 4%
| Confirmed | Off-site Inventory Storage - Based on current cost for Fleet, Procurement & Logistics to annually lease temporary storage to relieve pressures of inventory at the Garbutt site. |  |  | 182000
Option F
| Brief Outline | BAU with resolution of BCA Compliance issues
| To Be Confirmed | This option details the 'Business As Usual' / 'Do Nothing' scenario, with the addition of the resolution of the BCA compliance issues. It assumes the status quo with the continuation of maintenance and capital expenditure to maintain the aging asset base at Garbutt, with the addition of a single point of resolution for BCA compliance issues.
Operational Assumptions
| Confirmed | Garbutt will operate as the sole 'blue-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | 420 Flinders St will continue to operate as the sole 'white-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | Hartley St, Townsville will continue to operate as the T&D Centre for Townsville in the near future. |  |  | -
| Confirmed | The existing leased accommodation at Tesla House (15 Dalrymple Rd) will be maintained for decanting purposes until the end of BCA compliance work |  |  | -
| Confirmed | No other leased accommodation or storage will be required over the next 20 years except what is being phased out as a response to the Flinders St relocation |  |  | -
| Confirmed | All temporary staff accommodation at Garbutt will be removed/returned (dongas etc.) |  |  | -
| Confirmed | BAU Capex Works will continue to be undertaken to maintain existing asset base as best as possible |  |  | -
| Confirmed | Capex to resolve outstanding BCA Compliance issues in existing buildings |  |  | -
| Confirmed | Continue to maintain all of the Garbutt site over the next twenty years |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on Hartley St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on the OCCN during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Land contamination remediation (both known and unknown) will not be addressed |  |  | -
| Confirmed | Asbestos containing material will not be addressed |  |  | -
| Confirmed | All buildings on site will continue to operate as they have been (albeit with lower staff numbers) |  |  | -
| Confirmed | BAU Minor Capex will be executed each year to maintain and replace aging assets |  |  | -
| Confirmed | BAU Major Capex will be executed each year to maintain and replace major plant items where required |  |  | - | See 'Garbutt Site Details' worksheet
Timing Assumptions
| Confirmed | Capex and Opex work will continue to be executed in a timely fashion as per historical trend |  |  | -
| Confirmed | Design, documentation and tender will commence February 2014 |  |  | 13/14 | See 'OP6-Item Costs'
| Confirmed | Design, documentation and tender will conclude December 2014 |  |  | 14/15 | See 'OP6-Item Costs'
| Confirmed | Implementation and Construction will commence January 2015 |  |  | 14/15 | See 'OP6-Item Costs'
| Confirmed | Implementation and Construction will conclude June 2016 |  |  | 15/16 | See 'OP6-Item Costs'
| Confirmed | Execution of BCA Compliance resolution capex will result in no BAU Capex being spent those years |  |  | 14/15
| Confirmed | Sale of Ingham Rd will occur in 2017/18 |  |  | 17/18
| Confirmed | Current levels of Off-site Inventory Storage will continue indefinitely |  |  | -
| Confirmed | Tesla House - 15 Dalrymple Road will be relinquished 4th Qtr 14/15 (June 2015) - Current lease term |  |  | 14/15
| Confirmed | BAU Minor Capex will be executed each year indefinitely outside of Compliance work |  |  | -
| Confirmed | BAU Major Capex will be executed each year indefinitely outside of Compliance work |  |  | -
Financial Assumptions
| Capex | BAU Capex escalations applied at consistent rate of 6% p.a. based on historical trend due to escalating age of assets, requirement to replace major plant and cost to mitigate existing risks considerable |  |  | 6%
| Confirmed | BAU Minor Capex mitigation based on historical trend from 08/09 to 11/12 escalated 6% p.a. |  |  | 432050.2844 | See 'OP5-Garbutt Projects'
| Confirmed | BAU Major Capex mitigation based on historical trend escalated 6% p.a. Excludes capex 10/11 onwards from calculation as once 10-15 AER program approved, majority of major work ceased |  |  | 899475.5305 | See 'OP5-Garbutt Projects'
| To be Confirmed | Garbutt Site Compliance | Based on Davis Landgon Preliminary Cost Plan. Additional costs include EE related expenses as detailed (attached) |  | 17501000
| To be Confirmed | EECL Costs based on estimates provided by subsequent providers or where an internal cost, the historical record of similar projects |  |  | 2000000
| Confirmed | There is no CAPEX impact of the Garbutt Redevelopment on Hartley St or Flinders St sites in Townsville |  |  | 0
| Confirmed | Already incurred Project (design) costs as at 30 Nov 2013 |  |  | 1899509
| Confirmed | Garbutt Site Compliance and Refurb costs escalated each year |  |  | 2%
| Confirmed | Capitalised Interest applied at 7.11% p.a. based on supplied monthly cash-flow by S.Hardy |  |  | 3320419.1146
| Confirmed | Overheads applied to project |  |  | 11187779.5
| Confirmed | Overhead rate applied to Redevelopment |  |  | 50%
| Confirmed | Already incurred Project (design) costs as at 31 January 2014 with be expensed to OPEX |  |  | 1899509
| Opex | Opex escalations applied at consistent rate of 3% p.a. pre and post redevelopment |  |  | 3%
| Confirmed | Pre-execution baseline uses stores maintenance BAU Option with one year escalation |  |  | 60637.3772
| Confirmed | Pre-execution baseline uses stores non-maintenance BAU Option with one year escalation |  |  | 123121.6989
| Confirmed | Pre-execution baseline uses office maintenance BAU Option with one year escalation |  |  | 260661.2245
| Confirmed | Pre-execution baseline uses office non-maintenance BAU Option with one year escalation |  |  | 580910.6985
| Confirmed | Pre-execution baseline uses depot maintenance BAU Option with one year escalation |  |  | 289559.3732
| Confirmed | Pre-execution baseline uses depot non-maintenance BAU Option with one year escalation |  |  | 598014.8467
| Confirmed | Pre-execution baseline Tesla House maintenance and non-maintenance 12/13 with one year escalation at 4% p.a. |  |  | 331626.88
| To be confirmed | Post-execution baseline in Stores maintenance inline with pre-execution as removal on non-compliance not expected to influence ongoing costs |  |  | 60637.3772 | See 'Opex Baseline' worksheet
| To be confirmed | Post-execution baseline stores non-maintenance inline with pre-execution as removal on non-compliance not expected to influence ongoing costs |  |  | 123121.6989 | See 'Opex Baseline' worksheet
| To be confirmed | Post-execution baseline in Office maintenance inline with pre-execution as removal on non-compliance not expected to influence ongoing costs |  |  | 260661.2245 | See 'Opex Baseline' worksheet
| To be confirmed | Post-execution baseline in Office non-maintenance inline with pre-execution as removal on non-compliance not expected to influence ongoing costs |  |  | 539531.1983 | See 'Opex Baseline' worksheet
| To be confirmed | Post-execution baseline in Depot maintenance inline with pre-execution as removal on non-compliance not expected to influence ongoing costs |  |  | 289559.3732 | See 'Opex Baseline' worksheet
| To be confirmed | Post-execution baseline depot non-maintenance inline with pre-execution as removal on non-compliance not expected to influence ongoing costs |  |  | 584927.4123 | See 'Opex Baseline' worksheet
| Confirmed | Off-site Inventory Storage - Based on current cost for Fleet, Procurement & Logistics to annually lease temporary storage to relieve pressures of inventory at the Garbutt site. |  |  | 182000
| To Be Confirmed | Forecast escalation for all building maintenance costs from 2017/18 at 0.5% p.a. until additional 4% due to increasing age of asset base reaching critical point in lifecycle |  |  | 0.5% - 4%
Option G
| Brief Outline | Do Nothing / BAU with resolution of BCA Compliance issues and Refurbishment to Accommodation Standard
| To Be Confirmed | This option details the 'Business As Usual' / 'Do Nothing' scenario, with the addition of the resolution of the BCA compliance issues and the upgrade of existing structures at Garbutt. While no site configuration changes are realised, the buildings will be brought up to standard and a portion of the outstanding risk will be addressed.
Operational Assumptions
| Confirmed | Garbutt will operate as the sole 'blue-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | 420 Flinders St will continue to operate as the sole 'white-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | Hartley St, Townsville will continue to operate as the T&D Centre for Townsville in the near future. |  |  | -
| Confirmed | The existing leased accommodation at Tesla House (15 Dalrymple Rd) will be maintained for decanting purposes until the end of BCA & refurb work |  |  | -
| Confirmed | No other leased accommodation or storage will be required over the next 20 years except what is being phased out as a response to the Flinders St relocation |  |  | -
| Confirmed | All temporary staff accommodation at Garbutt will be removed/returned (dongas etc.) |  |  | -
| Confirmed | BAU Capex Works will continue to be undertaken before and after (in a deferred fashion) to maintain existing asset base as best as possible |  |  | -
| Confirmed | Continue to maintain all of the Garbutt site over the next twenty years |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on Hartley St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on the OCCN during the Garbutt redevelopment, it will be excluded from the NPV for this option
-
| Confirmed | Land contamination remediation (both known and unknown) will not be addressed |  |  | -
| Confirmed | Asbestos containing material will be addressed as part of the refurbishments |  |  | -
| Confirmed | All buildings on site will continue to operate as they have been (albeit with lower staff numbers) |  |  | -
| Confirmed | BAU Minor Capex will be executed each year to maintain and replace aging assets |  |  | -
| Confirmed | BAU Major Capex will be executed each year to maintain and replace major plant items where required
Timing Assumptions
| Confirmed | Capex and Opex work will continue to be executed in a timely fashion as per historical trend |  |  | -
| Confirmed | Design, documentation and tender will commence February 2014 |  |  | 13/14 | See 'OP7-Item Costs'
| Confirmed | Design, documentation and tender will conclude June 2015 |  |  | 14/15 | See 'OP7-Item Costs'
| Confirmed | Implementation and Construction will commence July 2016 |  |  | 14/15 | See 'OP7-Item Costs'
| Confirmed | Implementation and Construction will conclude December 2018 |  |  | 18/19 | See 'OP7-Item Costs'
| Confirmed | Execution of BCA Compliance resolution capex will result in no BAU Capex being undertaken during refurbishment years |  |  | 14/15
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Stores will transition between current and new on beginning of 1st Qtr 16/17 |  |  | 16/17
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Office will transition between current and new on beginning of 1st Qtr 16/17 |  |  | 16/17
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Depot will transition between current and new on beginning of 1st Qtr 16/17 |  |  | 16/17
| Confirmed | Sale of Ingham Rd will occur in 2017/18 |  |  | 17/18
| Confirmed | Current levels of Off-site Inventory Storage will continue indefinitely |  |  | -
| Confirmed | Tesla House - 15 Dalrymple Road will be relinquished 4th Qtr 15/16, requiring a one year extension of lease |  |  | 15/16
| Confirmed | BAU Minor Capex will be executed each year indefinitely but at a reduced rate |  |  | -
| Confirmed | BAU Major Capex will not be required for 10 years after refurbishment |  |  | -
Financial Assumptions
| Capex | BAU Capex escalations applied at consistent rate of 6% p.a. due to escalating age of assets, requirement to replace major plant and cost to mitigate existing risks considerable |  |  | 6%
| Confirmed | BAU Minor Capex mitigation based on historical trend from 08/09 to 11/12 escalated 3% p.a. |  |  | 432050.2844 | See 'OP5-Garbutt Projects'
| Confirmed | BAU Major Capex mitigation based on historical trend escalated at a lower rate of 3% p.a. Applies first year expenditure, no expenditure during refurbishment and for 10 years post-refurbishment. Returns at BAU values, but lower escalation rate |  |  | 899475.5305 | See 'OP5-Garbutt Projects'
| To be Confirmed | Garbutt Site Compliance and Refurb | Based on Davis Landgon Preliminary Cost Plan. Additional costs include EE related expenses as detailed (attached) |  | 36357000
| To be Confirmed | EECL Costs based on estimates provided by subsequent providers or where an internal cost, the historical record of similar projects |  |  | 2000000
| Confirmed | There is no CAPEX impact of the Garbutt Redevelopment on Hartley St or Flinders St sites in Townsville |  |  | 0
| Confirmed | Already incurred Project (design) costs as at 30 Nov 2013 |  |  | 1899509
| Confirmed | Garbutt Site Compliance and Refurb costs escalated each year |  |  | 2%
| Confirmed | Capitalised Interest applied at 7.11% p.a. based on supplied monthly cash-flow by S.Hardy |  |  | 4477005.7741
| Confirmed | Overheads applied to project |  |  | 21027924.5256
| Confirmed | Overhead rate applied to Redevelopment |  |  | 50%
| Confirmed | Already incurred Project (design) costs as at 30 Nov 2013 with be expensed to OPEX |  |  | 1899509
| Opex | Opex escalations applied at consistent rate of 3% p.a. pre and post redevelopment |  |  | 3%
| Confirmed | Pre-execution baseline uses stores maintenance BAU Option with one year escalation |  |  | 60637.3772
| Confirmed | Pre-execution baseline uses stores non-maintenance BAU Option with one year escalation |  |  | 123121.6989
| Confirmed | Pre-execution baseline uses office maintenance BAU Option with one year escalation |  |  | 260661.2245
| Confirmed | Pre-execution baseline uses office non-maintenance BAU Option with one year escalation |  |  | 580910.6985
| Confirmed | Pre-execution baseline uses depot maintenance BAU Option with one year escalation |  |  | 289559.3732
| Confirmed | Pre-execution baseline uses depot non-maintenance BAU Option with one year escalation |  |  | 598014.8467
| Confirmed | Pre-execution baseline Tesla House maintenance and non-maintenance 12/13 with one year escalation at 4% p.a. |  |  | 331626.88
| Confirmed | Post-execution baseline in Stores maintenance quantified by removal of forced costs, planned corrective reduced by 75% and major plant unplanned corrective costs. Preventative servicing consistent with BAU |  |  | 44163.4336 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline stores non-maintenance consistent with BAU |  |  | 123121.6989 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office maintenance quantified by removal of forced costs, planned corrective reduced by 75% and major plant unplanned corrective costs. Preventative servicing consistent with BAU. Correctived costs related to OCCN remain in total |  |  | 162646.8262 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office non-maintenance related to the move to a consolidated open and shared service office efficient floor plan. Four kitchenettes reduced to one kitchen (20% saving in amenities), document destruction bins reduced by half (40% saving in recycling/shredding), electricity usage reduced through usage of efficiency devices, time sensitive, segmented lights & air-con usage (electricity saving of 20% - scope of work not as extensive as Option 1, some plant remaining), lease of donga no longer required (100% saving). |  |  | 488125.3961 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Depot maintenance quantified by removal of forced costs, planned corrective reduced by 75% and major plant unplanned corrective costs. Preventative servicing consistent with BAU. Grounds maintenance remains. |  |  | 129700.793 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline depot non-maintenance reflective of staff changes, but costs which are building/sqm driven will remain as BAU. Amenities costs reduced by staffing proportions, cleaning costs reflect 20% saving due to improved building conditions from refurb, electricity usage reduced through usage of efficiency devices, time sensitive, segmented lights & air-con usage (electricity saving of 20% - scope of work not as extensive as Option 1, some plant remaining). |  |  | 525843.993 | See 'Opex Baseline' worksheet
| Confirmed | Off-site Inventory Storage - Based on current cost for Fleet, Procurement & Logistics to annually lease temporary storage to relieve pressures of inventory at the Garbutt site. |  |  | 182000
No forecast increase in maintenance escalation due to executed BAU capex
| Confirmed | Maintenance & most non-maintenance costs reduced during redevelopment of the relevant stage. All building maintenance ceases, and all non land related non-maintenance is removed |  |  | 0
Option H
| Brief Outline | Value Managed - Dalrymple Rd, Garbutt Redevelopment with full deferral to 2015-20
| To Be Confirmed | This is as per Option 1, preferred scope of works, but applies a 36 month postponement to execute the project entirely in the next regulatory period.
Operational Assumptions
| Confirmed | Garbutt will operate as the sole 'blue-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | 420 Flinders St will continue to operate as the sole 'white-collar' site in Townsville over the next 20 years |  |  | -
| Confirmed | Hartley St, Townsville will continue to operate as the T&D Centre for Townsville in the near future. |  |  | -
| Confirmed | The existing leased accommodation at Tesla House (15 Dalrymple Rd) will be maintained for decanting purposes until the end of stage 1 |  |  | -
| Confirmed | No other leased accommodation or storage will be required over the next 20 years except what is being phased out as a response to the Flinders St relocation |  |  | -
| Confirmed | No impact on the OCCN (Control Centre) portion of the office will be experienced |  |  | -
| Confirmed | Minor BAU Capex works will be undertaken in the lead-up and during the Garbutt redevelopment |  |  | -
| Confirmed | Due to the limited (if any) impact (financial or otherwise) on 420 Flinders St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on Hartley St during the Garbutt redevelopment, it will be excluded from the NPV for this option |  |  | -
| Confirmed | Due to no impact (financial or otherwise) on the OCCN during the Garbutt redevelopment, it will be excluded from the NPV for this option
| Confirmed | Continue to maintain unaffected portions of the Garbutt site during the redevelopment |  |  | -
| Confirmed | Land contamination remediation (both known and unknown) is accounted for within the scope of works for the redevelopment |  |  | -
| Confirmed | Removal of asbestos containing material is accounted for within the scope of works for the redevelopment |  |  | -
| Confirmed | The current 'Stores' building (BG3) aka Logistics, will be transitioned to BG18 (ARK) during the Redevelopment and BG3 will become a shared Workshop and office accommodation catering for what is currently known as the 'Depot', inclusive of buildings 4 to 15 |  |  | -
| Confirmed | Staff locations have yet to be finalised, but it is expected staff currently in BGs4-15 will be relocated into the refurbished BG3 building, with some moving to the Office. Forecast staff numbers within the 'Garbutt Site Details' worksheet |  |  | - | See 'Garbutt Site Details' worksheet
Timing Assumptions
| Confirmed | Shareholding approval will be received by end of April 2016 |  |  | 16/17 | Link to Project Delivery Schedule:
| Confirmed | Construction of stage 1 Garbutt Redevelopment (ARK Homes & Office) will begin 4th Qtr 16/17 |  |  | 16/17 | http://esp/ess/ss/Property%20Major%20Projects%20Supporting%20Information/
| Confirmed | Construction of stage 1 Garbutt Redevelopment (ARK Homes & Office) will conclude 4th Qtr 17/18 |  |  | 17/18
| Confirmed | Tender of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will begin 1st Qtr 18/19 |  |  | 18/19
| Confirmed | Construction of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will begin 3rd Qtr 18/19 |  |  | 18/19
| Confirmed | Construction of stage 2 Garbutt Redevelopment (Building 3, external works & demolition) will conclude 3rd Qtr 19/20 |  |  | 19/20
| Confirmed | Relocation of staff and operations to the new Logistics building (ARK) will occur 4th Qtr 17/18 |  |  | 17/18
| Confirmed | Relocation of staff and operations to the Office building will occur 4th Qtr 17/18 |  |  | 17/18
| Confirmed | Relocation of staff and operations to the new Workshop building will occur 2nd Qtr 19/20 |  |  | 19/20
| Confirmed | Final handover and practical completion will occur 3rd Qtr 19/20 |  |  | 19/20
| Confirmed | Sale of Ingham Rd will occur in 2020/21 |  |  | 20/21
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Stores will transition between current and new on beginning of 1st Qtr 18/19 |  |  | 18/19
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Office will transition between current and new on beginning of 1st Qtr 18/19 |  |  | 18/19
| Confirmed | Maintenance and Non-maintenance costs on the Garbutt Depot will transition between current and new on beginning of 3rd Qtr 19/20 (6 months each way) |  |  | 19/20
| Confirmed | Off-site Inventory Storage no longer required on completion of ARK Homes site as Logistics facility - 4th Qtr 17/18 |  |  | 17/18
| Confirmed | Tesla House - 15 Dalrymple Road will be relinquished 4th Qtr 17/18 resulting in a single extension of the lease |  |  | 17/18
Financial Assumptions
Capex
| Confirmed | No CAPEX requirements during the project or within 15 years after completion |  |  | - | Link to Constructed Design Estimate:
| Confirmed | Garbutt Site Redevelopment | Based on Davis Landgon Contract Documentation Cost Plan. Additional costs include EE related expenses as detailed (attached) |  | 37967000 | http://esp/ess/ss/Property%20Major%20Projects%20Supporting%20Information/
| Confirmed | EECL Costs based on estimates provided by subsequent providers or where an internal cost, the historical record of similar projects |  |  | 8786350
| Confirmed | There is no CAPEX impact of the Garbutt Redevelopment on Hartley St or Flinders St sites in Townsville |  |  | 0
| Confirmed | Already incurred Project (design) costs as at 30 Nov 2013 with forecast costs up to beginning of construction |  |  | 2233915.3
| To Be Confirmed | Costs associated with a 36 month delay, including tender extension fee, DA resubmission, internal labour costs and capitalised Interest |  |  | 880849.8722
| Confirmed | Consultant/QS costs associated with thirty-sex month delay, based on Glenmore Rd where multiple reviews, reconfirmation of costs and rework was performed to satisfy the Board and Shareholding Minister requirements. Adds in the half the cost of Detailed design for Garbutt as will need to be revisited and potentially rewritten |  |  | 1689153.65
| Confirmed | Garbutt Redevelopment Construction costs escalated by two years based on yearly escalation documented in Cost Plan |  |  | 2%
| Confirmed | Capitalised Interest applied at 7.11% p.a. based on supplied monthly cash-flow by S.Hardy |  |  | 3373448.0985 | See 'Itemised Costing' worksheet
| Confirmed | Overheads applied to project |  |  | 24493632.65 | See 'Project Cost' worksheet
| Confirmed | Overhead rate applied to Redevelopment |  |  | 50%
| Confirmed | Minor BAU Capex costs based on Option 5 - BAU for two years of the deferral period |  |  | 432050.2844
| Confirmed | Sale of Ingham Rd represents the valuation as at October 2011 with a forecast 2% p.a. indexation up until sale date |  |  | 5616935.0725
| Opex | Opex escalations applied at consistent rate of 3% p.a. pre and post redevelopment |  |  | 3%
| Confirmed | Pre-execution baseline uses stores maintenance BAU Option with one year escalation |  |  | 60637.3772
| Confirmed | Pre-execution baseline uses stores non-maintenance BAU Option with one year escalation |  |  | 123121.6989
| Confirmed | Pre-execution baseline uses office maintenance BAU Option with one year escalation |  |  | 260661.2245
| Confirmed | Pre-execution baseline uses office non-maintenance BAU Option with one year escalation |  |  | 580910.6985
| Confirmed | Pre-execution baseline uses depot maintenance BAU Option with one year escalation |  |  | 289559.3732
| Confirmed | Pre-execution baseline uses depot non-maintenance BAU Option with one year escalation |  |  | 598014.8467
| Confirmed | Pre-execution baseline Tesla House maintenance and non-maintenance 12/13 with one year escalation at 4% p.a. |  |  | 331626.88
| Confirmed | Post-execution baseline in Stores maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm |  |  | 44476.4758 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline stores non-maintenance reflective of changes in land tax and increase in rates due to move to ARK building, all other costs remain consistent |  |  | 98977.4706 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm. Correctived costs related to OCCN remain in total |  |  | 98989.7362 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Office non-maintenance related to the move to a consolidated open and shared service office efficient floor plan. Four kitchenettes reduced to one kitchen (20% saving in amenities), document destruction bins reduced by half (40% saving in recycling/shredding), electricity usage reduced through usage of efficiency devices, time sensitive, segmented lights & air-con usage (electricity saving of 40%), lease of donga no longer required (100% saving). |  |  | 444485.9488 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline in Depot maintenance quantified by removal of planned corrective, forced and major plant unplanned corrective costs. Preventative servicing increased and apportioned to building sqm. Grounds maintenance remains. |  |  | 42514.46 | See 'Opex Baseline' worksheet
| Confirmed | Post-execution baseline depot non-maintenance considerable savings quantified through the reduction from 11 buildings to 1 and the centralisation of many staff services and recurring costs. Amenities reduced against staff numbers with a 80% saving (aligned to costs recorded in BG1-Office), cleaning by cost/sqm with a similar saving of 70%, rates & land tax now reflective of 24 Dalrymple Rd (currently BG3), electricity reduced by cost/sqm and a 60% saving (smaller saving due to continuation of workshop tools and devices). |  |  | 237454.5622 | See 'Opex Baseline' worksheet
| Confirmed | Off-site Inventory Storage - Based on current cost for Fleet, Procurement & Logistics to annually lease temporary storage to relieve pressures of inventory at the Garbutt site. In the last twelve months, portions of the ARK Homes site have been utilised on a temporary basis to relieve some of these costs, which will continue in the short-term until the completion of the ARK Homes portion of the redevelopment, where it will be removed |  |  | 182000
| Confirmed | Maintenance & most non-maintenance costs reduced during redevelopment of the relevant stage. All building maintenance ceases, and all non land related non-maintenance is removed |  |  | 0

## ALL-Opex Baseline
Baseline OPEX Costs for all options | [6 empty] | Done | Done | Done | Done | Done | Done | Done | Done |  |  |  |  | Done | Done | Done | Done | Done | Done | Done | Done
Extrapolated 12/13 post-execution baseline costs for each option for each functional building/site
Historical costs by Functional building/site |  |  |  | Non-Maintenance | [10 empty] | Maintenance
Equip Ref | TOGSPJ | Stores |  | TOGSPJ - Stores | Basis | Actual 12/13 | Option A | Option B | Option C | Option D - Ingham Rd | Option E - BAU | Option F | Option G | Option H | TOGSPJ - Stores | Basis | Actual 11/12 | Actual 12/13 | Option A | Option B | Option C | Option D - Ingham Rd | Option E - BAU | Option F | Option G | Option H
|  |  |  | Waste Removal | flat | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | Corrective - Unplanned | trend & sqm | 34981.24 | 21133.54 | 6120.54 | 6120.54 | 6120.54 | 4098.9414 | 21133.54 | 21133.54 | 16161.54 | 6120.54
Maintenance Type | 12/13 |  |  | Security | flat | 1832.19 | 1832.19 | 1832.19 | 1832.19 | 0 | 1832.19 | 1832.19 | 1832.19 | 1832.19 | Corrective - Planned | trend | 40030 | 0 | 0 | 0 | 0 | 0 | 20015 | 20015 | 10007.5 | 0
Corrective | 21133.54 |  |  | Rates & Water Rates | flat | 40233.12 | 55692 | 55692 | 55692 | 0 | 40233.12 | 40233.12 | 40233.12 | 55692 | Forced | trend | 1084.49 | 944.75 | 0 | 0 | 0 | 0 | 1014.62 | 1014.62 |  | 0
Forced | 944.75 |  |  | Licenses / Permits etc | flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Preventative | sqm | 5613.38 | 16708.08 | 37060.5045 | 37060.5045 | 37060.5045 | 55052.6307 | 16708.08 | 16708.08 | 16708.08 | 37060.5045
Preventative | 16708.08 | 38786.37 | Maintenance | Land Tax | flat | 77036.32 | 38518 | 38518 | 38518 | 0 | 77036.32 | 77036.32 | 77036.32 | 38518 |  |  | 81709.11 | 38786.37 | 43181.0445 | 43181.0445 | 43181.0445 | 59151.5721 | 58871.24 | 58871.24 | 42877.12 | 43181.0445
Non-maintenance | 119535.63 | 119535.63 | Non-maintenance | Indoor Plant Hire | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 158322 |  |  | Furniture | staff | 434 | 52.4417 | 52.4417 | 52.4417 | 0 | 434 | 434 | 434 | 52.4417 |  |  | Note: The cessation of non-priority corrective maintenance commenced from 11/12 & 12/13 due to pending Garbutt Redevelopment
|  |  |  | Bathroom Services | flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | N.B. Electricity costed within Office Amenities & cleaning costing within Depot |  | 119535.63 | 96094.6317 | 96094.6317 | 96094.6317 | 0 | 119535.63 | 119535.63 | 119535.63 | 96094.6317
Equip Ref | TOGOPJ | Office
|  |  |  | TOGOPJ - Office | Basis | Actual 12/13 | Option A | Option B | Option C | Option D - Ingham Rd | Option E - BAU | Option F | Option G | Option H | TOGOPJ - Office | Basis | Actual 11/12 | Actual 12/13 | Option A | Option B | Option C | Option D - Ingham Rd | Option E - BAU | Option F | Option G | Option H
Maintenance Type | 12/13 |  |  | Waste Removal | flat | 0 | 0 | 0 | 0 | 2049.69 | 0 | 0 | 0 | 0 | Corrective - Unplanned | trend & sqm | 150482.17 | 143812.14 | 28146 | 57814.1966 | 28146 | 29148.6006 | 143812.14 | 143812.14 | 84949 | 28146
Corrective | 143812.14 |  |  | Amenities (Tea, Coffee etc) | staff | 26721.64 | 15280.8193 | 17190.9217 | 15280.8193 | 34620.7278 | 19101.0241 | 19101.0241 | 15280.8193 | 15280.8193 | Corrective - Planned | trend | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 5000 | 0
Forced | 5954.56 |  |  | Cleaning | sqm | 36264.1 | 32637.69 | 67040.4969 | 32637.69 | 87253.8361 | 36264.1 | 36264.1 | 32637.69 | 32637.69 | Forced | trend | 36638.38 | 5954.56 | 0 | 0 | 0 | 0 | 21296.47 | 21296.47 | 0 | 0
Preventative | 67960.54 | 217727.24 | Maintenance | Security | flat | 1832.29 | 1832.29 | 1832.29 | 1832.29 | 5548 | 1832.29 | 1832.29 | 1832.29 | 1832.29 | Preventative | sqm | 100154.27 | 67960.54 | 67960.54 | 139596.533 | 67960.54 | 70381.3913 | 67960.54 | 67960.54 | 67960.54 | 67960.54
Non-maintenance | 706260.53 | 706260.53 | Non-maintenance | Secure Document Destruction | staff | 3384.88 | 1451.7374 | 1451.7374 | 1451.7374 | 1451.7374 | 2419.5624 | 2419.5624 | 1451.7374 | 1451.7374 |  |  | 287274.82 | 217727.24 | 96106.54 | 197410.7296 | 96106.54 | 99529.9919 | 253069.15 | 253069.15 | 157909.54 | 96106.54
Grand Total | 923987.77 |  |  | Rates & Water Rates | flat | 112699.98 | 62022 | 62022 | 62022 | 68462 | 62022 | 62022 | 62022 | 62022
|  |  |  | Paper Recycling/Shredding | staff | 4616 | 1979.7511 | 1979.7511 | 1979.7511 | 1979.7511 | 3299.5852 | 3299.5852 | 1979.7511 | 1979.7511
|  |  |  | Lease/Rent Costs/Agent Fees | flat | 46800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equip Ref | TOGDPJ | Depot |  | Land Tax | flat | 67159.86 | 33579.93 | 33579.93 | 33579.93 | 61234 | 33579.93 | 33579.93 | 33579.93 | 33579.93
|  |  |  | Indoor Plant Hire | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance Type | 12/13 |  |  | Furniture | flat | 418 | 418 | 418 | 418 | 1431 | 418 | 418 | 418 | 418
Corrective | 116782.75 |  |  | Electricity | sqm | 401742.72 | 279025.7806 | 510747.4572 | 279025.7806 | 329769.5848 | 401742.72 | 361568.448 | 321394.176 | 279025.7806
Forced | 14453.33 |  |  | Copier Service Agreement | flat | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Preventative | 62495.6 | 193731.68 | Maintenance | Office Accom/Churn | staff | 4591.06 | 3281.7577 | 3281.7577 | 3281.7577 | 5098.824 | 3281.7577 | 3281.7577 | 3281.7577 | 3281.7577
Non-maintenance | 668519.06 | 668519.06 | Non-maintenance | Bathroom Services | flat | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Grand Total | 862250.74 |  |  |  |  | 706260.53 | 431539.7561 | 699574.342 | 431539.7561 | 598929.1512 | 563990.9694 | 523816.6974 | 473908.1516 | 431539.7561
Options: |  |  |  | TOGDPJ - Depot | Basis | Actual 12/13 | Option A | Option B | Option C | Option D - Ingham Rd | Option E - BAU | Option F | Option G | Option H | TOGDPJ - Depot | Basis | Actual 11/12 | Actual 12/13 | Option A | Option B | Option C | Option D - Ingham Rd | Option E - BAU | Option F | Option G | Option H
A) VM Scope – Garbutt Redevelopment |  |  |  | Waste Removal | flat | 2049.69 | 2049.69 | 2049.69 | 2049.69 | 0 | 2049.69 | 2049.69 | 2049.69 | 2049.69 | Corrective - Unplanned | trend & sqm | 207763.13 | 116782.75 | 12472 | 12472 | 12472 | 22827.8558 | 162272.94 | 162272.94 | 54793 | 12472
B) Original Scope – Garbutt Redevelopment |  |  |  | Amenities (Tea, Coffee etc) | staff | 137534.03 | 19339.9085 | 19339.9085 | 19339.9085 | 0 | 96699.5423 | 96699.5423 | 96699.5423 | 19339.9085 | Corrective - Planned | trend | 34538 | 0 | 0 | 0 | 0 | 0 | 34538 | 34538 | 8634.5 | 0
C) VM Scope – 12 months approval delay |  |  |  | Cleaning | sqm | 223281.48 | 52218.3956 | 52218.3956 | 52218.3956 | 0 | 223281.48 | 223281.48 | 178625.184 | 52218.3956 | Forced | trend | 29184.8 | 14453.33 | 0 | 0 | 0 | 0 | 21819.065 | 21819.065 | 0 | 0
D) Scope – Ingham Rd Redevelopment |  |  |  | Security | flat | 1883.52 | 1883.52 | 1883.52 | 1883.52 | 0 | 1883.52 | 1883.52 | 1883.52 | 1883.52 | Preventative | sqm | 107545.13 | 62495.6 | 28804.1747 | 28804.1747 | 28804.1747 | 24299.1146 | 62495.6 | 62495.6 | 62495.6 | 28804.1747
E) Do Nothing / BAU |  |  |  | Secure Document Destruction | staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 379031.06 | 193731.68 | 41276.1747 | 41276.1747 | 41276.1747 | 47126.9704 | 281125.605 | 281125.605 | 125923.1 | 41276.1747
F) BAU with BCA resolution |  |  |  | Rates & Water Rates | flat | 84935.89 | 35192 | 35192 | 35192 | 0 | 84935.89 | 84935.89 | 84935.89 | 35192
G) BAU with BCA resolution & refurbishment |  |  |  | Lease/Rent Costs/Agent Fees | flat | 45054.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 748014.99 | 450245.29 | 180563.7592 | 281867.9488 | 180563.7592 | 205808.5344 | 593065.995 | 593065.995 | 326709.76 | 180563.7592
H) VM Scope - Full Deferral to 2015-20 |  |  |  | Land Tax | flat | 0 | 33580 | 33580 | 33580 | 0 | 0 | 0 | 0 | 33580 |  |  |  |  | 1 | 5 | 1 | 4 | 7 | 7 | 6 | 1
|  |  |  | Indoor Plant Hire | sqm | 169.04 | 77.9104 | 77.9104 | 77.9104 |  | 169.04 | 169.04 | 169.04 | 77.9104
|  |  |  | Grounds | flat | 42119.24 | 42119.24 | 42119.24 | 42119.24 | 90598.562 | 42119.24 | 42119.24 | 42119.24 | 42119.24
|  |  |  | Furniture | flat | 579 | 579 | 579 | 579 | 0 | 579 | 579 | 579 | 579
|  |  |  | Electricity | sqm | 127062.47 | 41681.6791 | 41681.6791 | 41681.6791 | 0 | 127062.47 | 114356.223 | 101649.976 | 41681.6791
|  |  |  | Office Accom/Churn | staff | 3850.45 | 1817.0663 | 1817.0663 | 1817.0663 | 0 | 1817.0663 | 1817.0663 | 1817.0663 | 1817.0663
|  |  |  | Bathroom Services | flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 668519.06 | 230538.4099 | 230538.4099 | 230538.4099 | 90598.562 | 580596.9385 | 567890.6915 | 510528.1485 | 230538.4099
[6 empty] | 1494315.22 | 758172.7977 | 1026207.3836 | 758172.7977 | 689527.7131 | 1264123.538 | 1211243.019 | 1103971.9301 | 758172.7977
[7 empty] | 2 | 5 | 2 | 1 | 8 | 7 | 6 | 2
Note on W6: Removed historical electrical, pluming and other major plant repairs
Note on X6: Removed historical electrical, pluming and other major plant repairs. Apportioned by sqm (same)
Note on Y6: Removed historical electrical, pluming and other major plant repairs
Note on Z6: Removed historical electrical, pluming and other major plant repairs. Apportioned by sqm (same)
Note on AB6: Maintain BAU costs
Note on AC6: Removed historical larger plant repairs.
Note on AD6: Removed historical electrical, pluming and other major plant repairs
Note on J7: Flat-rate
Note on K7: Flat-rate
Note on L7: Flat-rate
Note on M7: All security captured under 'Office'
Note on Q7: Flat-rate
Note on AA7: Reduce by half from 11/12
Note on AB7: Reduce by half from 11/12
Note on AC7: Reduced by 3/4
Note on J8: Reflective of rates at 14 Dalrymple (ARK Homes) moving forward. Water rates based on 24 Dalrymple moving forward. Rates paid 6-monthly, water paid quarterly
Note on K8: Reflective of rates at 14 Dalrymple (ARK Homes) moving forward. Water rates based on 24 Dalrymple moving forward. Rates paid 6-monthly, water paid quarterly.
Note on L8: Reflective of rates at 14 Dalrymple (ARK Homes) moving forward. Water rates based on 24 Dalrymple moving forward. Rates paid 6-monthly, water paid quarterly.
Note on M8: All rates captured under 'Office'
Note on Q8: Reflective of rates at 14 Dalrymple (ARK Homes) moving forward. Water rates based on 24 Dalrymple moving forward. Rates paid 6-monthly, water paid quarterly
Note on U8: Cyclone Yasi costs included
Note on V8: Non-cyclone year
Note on AB8: Maintain BAU Costs
Note on J10: Reflective of land tax at 14 Dalrymple (ARK Homes) moving forward - 12/13 reflects Depot & Stores together
Note on K10: Reflective of land tax at 14 Dalrymple (ARK Homes) moving forward - 12/13 reflects Depot & Stores together
Note on L10: Reflective of land tax at 14 Dalrymple (ARK Homes) moving forward - 12/13 reflects Depot & Stores together
Note on M10: All land tax captured under 'Office'
Note on Q10: Reflective of land tax at 14 Dalrymple (ARK Homes) moving forward - 12/13 reflects Depot & Stores together
Note on J12: Based on change in staff numbers
Note on K12: Based on change in staff numbers
Note on L12: Based on change in staff numbers
Note on M12: All furniture captured under 'Office'
Note on Q12: Based on change in staff numbers
Note on W17: Removed historical lift, electrical, pluming and other major plant repairs. Maintained OCCN repairs in calculation.
Note on X17: Removed historical lift, electrical, pluming and other major plant repairs. Maintained OCCN repairs in calculation. Apportioned by sqm
Note on Y17: Removed historical lift, electrical, pluming and other major plant repairs. Maintained OCCN repairs in calculation.
Note on Z17: Removed historical lift, electrical, pluming and other major plant repairs. Maintained OCCN repairs in calculation. Apportioned by sqm
Note on AB17: Maintain BAU costs
Note on AC17: Removed historical larger plant repairs.
Note on AD17: Removed historical electrical, pluming and other major plant repairs
Note on J18: Applied staff reduction and expected 20% saving based on shared services and centralised kitchen (as opposed to multiple kitchenettes).
Note on K18: Applied staff reduction and expected 20% saving based on shared services and centralised kitchen (as opposed to multiple kitchenettes
Note on L18: Applied staff reduction and expected 20% saving based on shared services and centralised kitchen (as opposed to multiple kitchenettes
Note on M18: Consistent with Garbutt redevelopment as staff driven and consistent design drivers (no separate amenities building).
Note on N18: BAU apportioned by staff changes
Note on P18: Applied staff reduction and expected 20% saving based on shared services and centralised kitchen (as opposed to multiple kitchenettes).
Note on Q18: Applied staff reduction and expected 20% saving based on shared services and centralised kitchen (as opposed to multiple kitchenettes
Note on AA18: Average per year prior to 11/12. Planned Corrective was ceased due to pending redevelopment.
Note on AB18: Maintain BAU costs
Note on AC18: Reduced by 3/4
Note on J19: Based on sqm remaining consistent in office, with 10% saving due to significant change in age of building post-redevelopement
Note on K19: SQM of office and cleaning cost increased proportionally, with 10% saving due to significant change in age of building post-redevelopement
Note on L19: Based on sqm remaining consistent in office, with 10% saving due to significant change in age of building post-redevelopement
Note on M19: Based on Garbutt Redevelopment apportioned for greater SQM profile
Note on P19: Based on sqm remaining consistent in office, with 10% saving due to significant change in age of building post-refurbishment
Note on Q19: Based on sqm remaining consistent in office, with 10% saving due to significant change in age of building post-redevelopement
Note on U19: Cyclone Yasi costs included
Note on V19: Non-cyclone year
Note on AA19: Average of last two years
Note on AB19: Maintain BAU costs
Note on J20: Flat rate
Note on K20: Flat rate
Note on L20: Flat rate
Note on M20: Based on existing costs
Note on Q20: Flat rate
Note on J21: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins
Note on K21: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins
Note on L21: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins
Note on M21: Consistent with Garbutt redevelopment as staff driven and consistent design drivers.
Note on N21: BAU apportioned by staff changes
Note on P21: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins.
Note on Q21: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins
Note on I22: This figure represents a 6-monthly payment of $25k plus a post-amalgamation 6-monthly payment of $59k for Office/Stores/ARK as one lot, plus the associated water rates quarterly.
Note on J22: Represents the original pre-amalgamation rates cost ($25.6k/6monthly) plus associated water rates through year
Note on K22: Represents the original pre-amalgamation rates cost ($25.6k/6monthly) plus associated water rates through year
Note on L22: Represents the original pre-amalgamation rates cost ($25.6k/6monthly) plus associated water rates through year
Note on M22: Based on current rates at 591A Ingham Rd with water costs for Stores, Office & Depot at Garbutt.
Note on N22: Represents the original pre-amalgamation rates cost ($25.6k/6monthly) plus associated water rates through year
Note on Q22: Represents the original pre-amalgamation rates cost ($25.6k/6monthly) plus associated water rates through year
Note on J23: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins
Note on K23: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins
Note on L23: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins
Note on M23: Consistent with Garbutt redevelopment due to staff driven and similar design drivers
Note on N23: BAU apportioned by staff changes
Note on P23: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins.
Note on Q23: Modified in proportion with staff changes in office building with 40% saving based on centralised utility room and significant reduction in no. of document bins
Note on J24: Super donga: 12 * $3900/month
Note on K24: Super donga: 12 * $3900/month
Note on L24: Super donga: 12 * $3900/month
Note on N24: Super donga: 12 * $3900/month
Note on Q24: Super donga: 12 * $3900/month
Note on I25: Cost representative of two years worth
Note on J25: 12/13 actuals reflects two years worth, baseline should be an annual cost
Note on K25: 12/13 actuals reflects two years worth, baseline should be an annual cost
Note on L25: 12/13 actuals reflects two years worth, baseline should be an annual cost
Note on M25: Based on current land tax at 591A Ingham Rd, Mount St John
Note on Q25: 12/13 actuals reflects two years worth, baseline should be an annual cost
Note on K26: Ecolink minimal cost to maintain as per Mackay ecolink (artificial vegetation)
Note on M26: Ecolink minimal cost to maintain as per Mackay ecolink (artificial vegetation)
Note on M27: Based on existing costs
Note on I28: Includes Office, OCCN, S.Donga & Stores (BG3), BG13 & BG14
Note on J28: Based on sqm difference with the removal of buildings 13, 14, and S.Donga. Includes additional 40% reduction due to energy saving devices, reduced comms requirements and time sensitive usage in retained buildings. Although new Stores (ARK) utilises larger under roof profile, staff usage reduced by 91% provides considerable saving in electricity aginst existing stores.
Note on K28: Based on sqm difference with the removal of buildings 13, 14, and S.Donga. Includes larger office sqm profile, and 40% reduction due to energy saving devices, reduced comms requirements and time sensitive usage in retained buildings. Although new Stores (ARK) utilises larger under roof profile, staff usage reduced by 91% provides considerable saving in electricity aginst existing stores.
Note on L28: Based on sqm difference with the removal of buildings 13, 14, and S.Donga. Includes additional 40% reduction due to energy saving devices, reduced comms requirements and time sensitive usage in retained buildings. Although new Stores (ARK) utilises larger under roof profile, staff usage reduced by 91% provides considerable saving in electricity aginst existing stores.
Note on M28: Based on Garbutt Redevelopment apportioned for greater SQM profile
Note on O28: Minor 10% saving in electricity due to A/C plant replacements
Note on P28: Based on consistent site sqm. Includes 20% reduction due to energy saving devices, reduced comms requirements and time sensitive usage in retained buildings.
Note on Q28: Based on sqm difference with the removal of buildings 13, 14, and S.Donga. Includes additional 40% reduction due to energy saving devices, reduced comms requirements and time sensitive usage in retained buildings. Although new Stores (ARK) utilises larger under roof profile, staff usage reduced by 91% provides considerable saving in electricity aginst existing stores.
Note on J30: Modified in proportion with staff changes in office building
Note on K30: Modified in proportion with staff changes in office building
Note on L30: Modified in proportion with staff changes in office building
Note on M30: Consistent with Garbutt Redevelopment as staff driven
Note on N30: BAU apportioned by staff changes
Note on Q30: Modified in proportion with staff changes in office building
Note on J35: Flat-rate
Note on K35: Flat-rate
Note on L35: Flat-rate
Note on Q35: Flat-rate
Note on W35: Removed historical crane, electrical, pluming and other major plant repairs. Maintained general running costs.
Note on Y35: Removed historical crane, electrical, pluming and other major plant repairs. Maintained general running costs.
Note on AB35: Maintain BAU costs
Note on AC35: Removed historical larger plant repairs.
Note on AD35: Removed historical crane, electrical, pluming and other major plant repairs. Maintained general running costs.
Note on I36: Includes BG3, BG4-15 and costs to staff the amenities building
Note on J36: Reduction inline staffing accommodation changes. Includes 80% saving due to relinquish of staffed amenities building (inc labour costs) and significant reductions in the number of depot buildings from 11 to 1. Future Stores (ARK) only maintains 4 office staff. Field staff apportioned at 30% cost of Office staff
Note on K36: Reduction inline staffing accommodation changes. Includes 80% saving due to relinquish of staffed amenities building (inc labour costs) and significant reductions in the number of depot buildings from 11 to 1. Future Stores (ARK) only maintains 4 office staff. Field staff apportioned at 30% cost of Office staff
Note on L36: Reduction inline staffing accommodation changes. Includes 80% saving due to relinquish of staffed amenities building (inc labour costs) and significant reductions in the number of depot buildings from 11 to 1. Future Stores (ARK) only maintains 4 office staff. Field staff apportioned at 30% cost of Office staff
Note on N36: BAU apportioned by staff changes. Most savings not realised due to continuation of Amenities building. Field staff apportioned at 30% cost of Office staff.
Note on O36: BAU apportioned by staff changes. Most savings not realised due to continuation of Amenities building. Field staff apportioned at 30% cost of Office staff.
Note on P36: BAU apportioned by staff changes. Most savings not realised due to continuation of Amenities building. Field staff apportioned at 30% cost of Office staff.
Note on Q36: Reduction inline staffing accommodation changes. Includes 80% saving due to relinquish of staffed amenities building (inc labour costs) and significant reductions in the number of depot buildings from 11 to 1. Future Stores (ARK) only maintains 4 office staff.
Note on AB36: Maintain BAU costs
Note on AC36: Reduced by 3/4
Note on I37: Includes BG3, BG4-15
Note on J37: Reduced proportionally by SQM with 40% saving due to significant reductions in the number of buildings (accounting for majority of the current costs) in addition to improvements in age of BG3 post-redevelopement. Minimal ARK cleaning due to v.small office area
Note on K37: Reduced proportionally by SQM with 40% saving due to significant reductions in the number of buildings (accounting for majority of the current costs) in addition to improvements in age of BG3 post-redevelopement. Minimal ARK cleaning due to v.small office area
Note on L37: Reduced proportionally by SQM with 40% saving due to significant reductions in the number of buildings (accounting for majority of the current costs) in addition to improvements in age of BG3 post-redevelopement. Minimal ARK cleaning due to v.small office area
Note on P37: 20% saving realised on cleaning costs due to improved age of buildings and centralised amenity areas. Number of buildings on site remain.
Note on Q37: Reduced proportionally by SQM with 40% saving due to significant reductions in the number of buildings (accounting for majority of the current costs) in addition to improvements in age of BG3 post-redevelopement. Minimal ARK cleaning due to v.small office area
Note on U37: Cyclone Yasi costs included
Note on V37: Non-cylcone year
Note on AA37: Average of last two years
Note on AB37: Maintain BAU costs
Note on J38: Flat-rate
Note on K38: Flat-rate
Note on L38: Flat-rate
Note on Q38: Flat-rate
Note on J40: Reflective of rates at 24 Dalrymple (Stores) moving forward
Note on K40: Reflective of rates at 24 Dalrymple (Stores) moving forward
Note on L40: Reflective of rates at 24 Dalrymple (Stores) moving forward
Note on Q40: Reflective of rates at 24 Dalrymple (Stores) moving forward
Note on J41: Donga & Temp accommodation now removed
Note on K41: Donga & Temp accommodation now removed
Note on L41: Donga & Temp accommodation now removed
Note on N41: Donga & Temp accommodation now removed
Note on Q41: Donga & Temp accommodation now removed
Note on J42: Reflective of land tax at 24 Dalrymple (Stores) moving forward
Note on K42: Reflective of land tax at 24 Dalrymple (Stores) moving forward
Note on N42: Configuration of Landtax paid as per BAU
Note on Q42: Reflective of land tax at 24 Dalrymple (Stores) moving forward
Note on J43: Reduced proportionally by SQM
Note on K43: Reduced proportionally by SQM
Note on L43: Reduced proportionally by SQM
Note on Q43: Reduced proportionally by SQM
Note on J44: Grounds maintenance will remain consistent
Note on K44: Grounds maintenance will remain consistent
Note on L44: Grounds maintenance will remain consistent
Note on M44: Grounds maintenance apportioned by SQM. Garbutt Redevelopment includes 5,490sqm of landscaped area (as per DD costplan) while lowest Ingham Rd estimate included 11,809sqm of soft landscaping (based on concept design) and included stormwater & flood mitigation detention area.
Note on N44: Grounds maintenance will remain consistent
Note on Q44: Grounds maintenance will continue on site. Redevelopment includes 5,490sqm of landscaped area (as per DD costplan).
Note on J45: No change
Note on K45: No change
Note on L45: No change
Note on Q45: No change
Note on I46: Includes all depot buildings excluding BG13, 14, and 3 (Stores)
Note on J46: Reduced proportionally by SQM with 40% saving due to energy saving devices, reduced comms requirements and time sensitive usage as well as the significant reductions in the number of buildings from 9 to 1.
Note on K46: Reduced proportionally by SQM with 40% saving due to energy saving devices, reduced comms requirements and time sensitive usage as well as the significant reductions in the number of buildings from 9 to 1.
Note on L46: Reduced proportionally by SQM with 40% saving due to energy saving devices, reduced comms requirements and time sensitive usage as well as the significant reductions in the number of buildings from 9 to 1.
Note on O46: Minor 10% saving in electricity due to A/C plant replacements
Note on P46: Based on consistent site BAU sqm. Includes 20% reduction due to energy saving devices, reduced comms requirements and time sensitive usage in retained buildings.
Note on Q46: Reduced proportionally by SQM with 40% saving due to energy saving devices, reduced comms requirements and time sensitive usage as well as the significant reductions in the number of buildings from 9 to 1.
Note on J47: Reduced proportionally by staff numbers
Note on K47: Reduced proportionally by staff numbers
Note on L47: Reduced proportionally by staff numbers
Note on N47: Reduced proportionally by staff numbers
Note on Q47: Reduced proportionally by staff numbers

## ALL-Garbutt Site Details
Garbutt Complex Dalrymple Rd
Building Description | Approx Staff Numbers | Approx Office Floor Area m2
|  |  |  | Current State / BAU: |  |  |  | Future - Option 1,3,5,6,7,8: |  |  |  | Future - Option 2: |  |  |  | Future - Option 4:
Building 1 Corporate Office | 270 | 3846 m2 | Office | UCA Rates | Total | Office subset |  | UCA Rates | Total | Office subset |  | UCA Rates | Total | Office subset |  | UCA Rates | Total | Office subset
(2 storey) |  |  |  | Office - BG2 | 3846 |  | sqm | Office - BG2 | 3846 | 2567 | sqm | Office - BG2 | 7900 | 6069 | sqm | Office - BG2 | 3983 | 3592 | sqm
Building 3 | 48 | Offices: 612 m2 | Stores | Stores - BG3 | 3168 | 612 | sqm | Stores - BG4 | 7027 | 157 | sqm | Stores - BG4 | 7027 | 157 | sqm | Stores - BG4 | 4706 | 4 | sqm
Logistics Building, and Warehouse |  | Total: 2505 m2 |  | Depot - BG4-15 | 6739 | 3752 | sqm | Depot - BG3 | 3106 | 1544 | sqm | Depot - BG3 | 3106 | 1544 | sqm | Depot - BG3 | 5685 | 1104 | sqm
Building 4 | various | 546 m2 | Depot | Qualifications: | Office subset represents the office accommodation areas, a subset of the total figure (excludes workshop, inventory and specialist areas)
Amenities Building |  |  |  |  | Office excludes OCCN sqm & staff
Building 5 | various | 230 m2 | Depot | Staff # | Office | Field |  | F/Cast Staff # | Office | Field |  | F/Cast Staff # | Office | Field |  | F/Cast Staff # | Office | Field
Ablution Block Gymnasium |  |  |  | Office - BG2 | 270 | 0 | staff | Office - BG2 | 193 | 0 | staff | Office - BG2 | 193 | 0 | staff | Office - BG2 | 193 | 0 | staff
Building 6 Workshops (including Transformers, Communications, Test, Project, Meter Test & Laboratories) | 50 | 1950 m2 | Depot | Stores - BG3 | 48 | 0 | staff | Stores - BG4 | 4 | 6 | staff | Stores - BG4 | 4 | 6 | staff | Stores - BG4 | 4 | 6 | staff
|  |  |  | Depot - BG4-15 | 89 | 231 | staff | Depot - BG3 | 42 | 231 | staff | Depot - BG3 | 42 | 231 | staff | Depot - BG3 | 42 | 231 | staff
|  |  |  | Qualifications: | Current state staff represents pre-Flinders St move to ensure consistency with historical costing
Building 7 | 15 | 50 m2 | Depot |  | Field staff apportioned at 30% cost of Office based staff in relation to amenities and other staff driven expenditure
Transmission Line Office
Building 9 | 60 | 624 m2 | Depot | Current State / BAU: | [14 empty] | Option 4 - Ingham Rd Concept:
Transmission and Distribution Services Building
Building 10 | 50 | 90 m2 | Depot
Line Vehicle Storage
Field Operations Office - 10A
Building 11 | 6 | 55 m2 | Depot
Lines – Team Leaders Office
Building 13 | 15 | 95 m2 | Depot
Shift Hut Office
Building 14 | 15 | 112 m2 | Depot
Substation workshop office and meeting room
Building 16 OCCN Control centre manned - Unchanged | 20 | 560 m2
Building 18 ARK Homes (unused, future Stores/Logisitics building) | 0 | Gnd Flr: 4366 | Unused
Mid Mezz: 1436
Top Mezz: 751
Future State - Options 1,3,5,6,7,8:

## OP1,3,8-Item Costs
Area Schedule | Constructed Design Cost Plan Nov 2013 $
Construction
Site Preparation
Building 2 | 9487000
Building 3 | 12840000
Building 4 | 5865000
Carparks & Roads, External Works | 7705000
Sub-Total: | 35897000
Garbutt Design and PQS Fees | 2070000
Sub-Total: | 37967000
EECL Associated and Other Costs
HV Transformer & Electrical Works | 160000
Sparq | 2150000
Staging/Decanting | 1000000
Int, External Racking to Warehouse | 1500000
Underground tank removal | 100000
DA Requirements (outside fence) | 250000
Authority Fee, Op Works, DA | 150000
Temporary Services | 250000
Staff Relocation | 400000
Internal Management | 600000
Civil and Technical Allowances | 2226350
EECL Sub-Total: | 8786350
Total: | 46753350
Expenditure to date plus forecast up to construct | 2233915.3
Overheads | 24493632.65
Capitalised Interest | 3373448.0985
GRAND TOTAL PROJECT ESTIMATE: | 76854346.0485

## OP1,3,8-Project Cost
Estimating Tool - High Level Cost to the Business
v0.3
[13 empty] | Workings: | [7 empty] | No | 2
| Enter the known estimate costs for the following items: | [11 empty] | 1 | 2 | 3 | 4 | 5 | Total |  |  | Yes | 3
1 | 2233915.3 | Design Estimate | [19 empty] | 4
| 37967000 | Contruction Estimate | [10 empty] | 1420630.6937 | 1255053.737 | 18155660.2655 | 21799333.0585 | 6356587.5453 | 48987265.3 |  |  |  | 5
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Escalations
[13 empty] | 710315.3468 | 627526.8685 | 9077830.1327 | 10899666.5292 | 3178293.7727 | 24493632.65 | Overheads
| Enter any other assumptions: | [11 empty] | 83877.6815 | 236809.9574 | 1390362.6589 | 1287088.561 | 375309.2397 | 3373448.0985 | Capitalised Interest
2 | 8786350 | EECL Allowances | [15 empty] | 76854346.0485
3 | [12 empty] | FALSE |  | FALSE |  | TRUE |  | TRUE
4 | [12 empty] | 2130946.0406 |  | 1882580.6055 |  | 27233490.3982 |  | 32698999.5877 |  | 9534881.318
| 48987265.3 | Sub-total | [10 empty] | 177578.8367 | 1052.1546 | 2371705.4392 | 14052.3547 | 6603671.8181 | 39126.7555 | 2724916.6323 | 16145.131 | 794573.4432 | 4707.8477
[13 empty] | 356209.828 | 2110.5432 | 2542639.511 | 15065.1391 | 8912256.1068 | 52805.1174 | 5465978.3957 | 32385.922 | 1593854.734 | 9443.5893
| Over how many financial years will the project run for (2-5): | [11 empty] | 535899.208 | 3175.2028 | 2714586.3673 | 16083.9242 | 11234518.7574 | 66564.5236 | 8223280.95 | 48722.9396 | 2397871.7664 | 14207.3902
5 | 5 | years | [10 empty] | 716653.2475 | 4246.1705 | 2887552.0086 | 17108.7457 | 13570540.8143 | 80405.4543 | 10996920.5219 | 65156.7541 | 3206652.5998 | 18999.4167
[7 empty] | 0% | [5 empty] | 898478.2547 | 5323.4837 | 3061542.4714 | 18139.6391 | 15920403.8018 | 94328.3925 | 13786993.9083 | 81687.9389 | 4020225.4596 | 23819.8358
| Enter the expected % split of costs over the years: | [11 empty] | 1081380.5751 | 6407.1799 | 3236563.8276 | 19176.6407 | 18284189.7275 | 108333.8241 | 16593598.4795 | 98317.071 | 4838618.7387 | 28668.816
6 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | [7 empty] | 1265366.5917 | 7497.2971 | 3412622.1854 | 20219.7864 | 20661981.0848 | 122422.2379 | 19416832.1828 | 115044.7307 | 5661860.9979 | 33546.5264
| 2.9% | 2.562% | 37.06% | 44.5% | 12.98% | 100% | < Needs to equal 100% | [5 empty] | 1450442.7255 | 8593.8731 | 3589723.689 | 21269.1129 | 23053860.8559 | 136594.1256 | 22256793.5458 | 131871.5018 | 6489980.9674 | 38453.1372
[13 empty] | 1636615.4353 | 9696.9465 | 3767874.519 | 22324.6565 | 25459912.5147 | 150849.9816 | 25113581.6799 | 148797.9715 | 7323007.5478 | 43388.8197
7 | No |  |  |  | Partial Capitalisation at year end? | [7 empty] | 1823891.2185 | 10806.5555 | 3947080.8926 | 23386.4543 | 27880220.0295 | 165190.3037 | 27987296.2837 | 165824.7305 | 8160969.8107 | 48353.7461
[13 empty] | 2012276.6107 | 11922.7389 | 4127349.0641 | 24454.5432 | 30314867.8664 | 179615.5921 | 30878037.6465 | 182952.3731 | 9003897 | 53348.0897
| Enter the overhead rate to be used throughout the project: | [8 empty] | Business Overheads: |  |  | 2201778.1863 | 13045.5358 | 4308685.3244 | 25528.9605 | 32763940.9917 | 194126.3504 | 33785906.6518 | 200181.4969 | 9851818.5329 | 58372.0248
8 | 50% | [8 empty] | Regulated Capex Overhead Rate as per FSS History |  |  | CI Calculation | 83877.6815 |  | 236809.9574 |  | 1390362.6589 |  | 1287088.561 |  | 375309.2397
[11 empty] | 0.5356 | Average Rate 0910
| Enter an escalation rate (%): | [9 empty] | 0.5105 | Average Rate 1011
9 | [10 empty] | 0.5167 | Average Rate 1112
If not included in Construction estimate | [10 empty] | 0.529 | Average Rate 1213
[11 empty] | 0.486 | Budgeted Rate 1314
[11 empty] | 0.51556 | Average Rate
| Cost to the Business | [9 empty] | 0.5 | Adopted Rate during project
| Yearly Split: | [5 empty] | Total Project Cost:
| 12/13 | 13/14 | 14/15 | 15/16 | 16/17
| 1420630.6937 | 1255053.737 | 18155660.2655 | 21799333.0585 | 6356587.5453 | Construction |  | 48987265.3
| 0 | 0 | 0 | 0 | 0 | Escalations | Escalations | 0
| 710315.3468 | 627526.8685 | 9077830.1327 | 10899666.5292 | 3178293.7727 | Overheads | Overheads | 24493632.65
| 83877.6815 | 236809.9574 | 1390362.6589 | 1287088.561 | 375309.2397 | C. Interest | C.Interest | 3373448.0985
| 2214823.7221 | 2119390.5629 | 28623853.0571 | 33986088.1488 | 9910190.5577 | Total |  | 76854346.0485
| 2214401 |  | 20831344.6962 |  | 28155920.6038
|  |  | 32958067.342 |  | 43896278.7065
| Additional Workings - Design | [8 empty] | Greenfield Site:
[5 empty] | 30.38% | 54.13% | 15.49%
| 41602063 |  |  |  | 28275000 | 50372000 | 14419000 | 93066000 |  | Bulk Exc | 131440
| 4712741 |  |  |  | 18568989.2953 | 33080711.8933 | 9469363.6304 | 61119064.8191 |  | Found | 469601
| 2639135 | 48953939 | [7 empty] | Slab | 312802
| 3426775.73 | 7% |  |  | 25439515.3346 | 45320575.2939 | 12973028.1736 | 83733118.8021 | 83733118.8021 | Landscaping | 281380 | 60%
| 1047614.2946 | 2% |  |  | 38736750 | 69009640 | 19754030 | 127500420 |  | Surface & Roads | 2231569 | 60%
| 4474390.0246 |  |  |  | 28737000 | 49010000 | 49753420 | 0 |  | External Works | 707673 | 80%
| 447439.0025 | 10% cont | [7 empty] | Sub-total | 2987750.8
| 2572640.0324 | overheads | 4921829.0271 | 4921829.0271 | [5 empty] | Total Project | 8075641
| 188054.8841 | Cap interest
| 7682523.9436 | TOTAL |  | 246091.4514 | 246091.4514 | 1435.5335 |  |  |  | % | 37%
|  |  |  | 246091.4514 | 492182.9027 | 2871.0669
|  |  |  | 246091.4514 | 738274.3541 | 4306.6004
|  |  |  | 492182.9027 | 1230457.2568 | 7177.6673
|  |  |  | 492182.9027 | 1722640.1595 | 10048.7343
|  |  |  | 738274.3541 | 2460914.5135 | 14355.3347
|  |  |  | 738274.3541 | 3199188.8676 | 18661.9351
|  |  |  | 738274.3541 | 3937463.2216 | 22968.5355
|  |  |  | 246091.4514 | 4183554.673 | 24404.0689
|  |  |  | 246091.4514 | 4429646.1244 | 25839.6024
|  |  |  | 246091.4514 | 4675737.5757 | 27275.1359
|  |  |  | 246091.4514 | 4921829.0271 | 28710.6693
[6 empty] | 188054.8841 | CI

## OP2-Item Costs
Area Schedule | Schematic Design Estimate Jun 2013 $
Construction
Site Preparation | 1881140
Building 2 | 18743781.83
Building 3 | 7781516.81
Building 4 | 884166.75
Carparks & Roads, External Works | 14906105
Sub-Total: | 44196710.39
Garbutt Design and PQS Fees | 2070000
Sub-Total: | 46266710.39
EECL Associated and Other Costs
HV Transformer & Electrical Works | 160000
Sparq | 2150000
Staging/Decanting | 1000000
Int, External Racking to Warehouse | 1500000
Underground tank removal | 100000
DA Requirements (outside fence) | 250000
Authority Fee, Op Works, DA | 150000
Temporary Services | 250000
Staff Relocation | 400000
Internal Management | 600000
Civil and Technical Allowances | 2641335.5195
EECL Sub-Total: | 9201335.5195
Total: | 55468045.9095
Expenditure to date plus forecast up to construct | 2233915.3
Overheads | 28850980.6047
Capitalised Interest | 3908797.5371
GRAND TOTAL PROJECT ESTIMATE: | 90461739.3514

## OP2-Project Cost
Estimating Tool - High Level Cost to the Business
v0.3
[13 empty] | Workings: | [7 empty] | No | 2
| Enter the known estimate costs for the following items: | [11 empty] | 1 | 2 | 3 | 4 | 5 | Total |  |  | Yes | 3
1 | 2233915.3 | Design Estimate | [19 empty] | 4
| 46266710.39 | Contruction Estimate | [10 empty] | 1420622.285 | 1436778.8341 | 21286253.4902 | 19618666.8112 | 13939639.789 | 57701961.2095 |  |  |  | 5
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Escalations
[13 empty] | 710311.1425 | 718389.4171 | 10643126.7451 | 9809333.4056 | 6969819.8945 | 28850980.6047 | Overheads
| Enter any other assumptions: | [11 empty] | 83877.185 | 247538.5104 | 1596013.3092 | 1158336.4302 | 823032.1023 | 3908797.5371 | Capitalised Interest
2 | 9201335.5195 | EECL Allowances | [15 empty] | 90461739.3514
3 | [12 empty] | FALSE |  | FALSE |  | TRUE |  | TRUE
4 | [12 empty] | 2130933.4275 |  | 2155168.2512 |  | 31929380.2353 |  | 29428000.2168 |  | 20909459.6835
| 57701961.2095 | Sub-total | [10 empty] | 177577.7856 | 1052.1484 | 2394407.9668 | 14186.8672 | 7278299.0603 | 43123.9219 | 2452333.3514 | 14530.0751 | 1742454.9736 | 10324.0457
[13 empty] | 356207.7196 | 2110.5307 | 2588192.1882 | 15335.0387 | 9982204.6685 | 59144.5627 | 4919196.7779 | 29146.2409 | 3495233.993 | 20709.2614
| Over how many financial years will the project run for (2-5): | [11 empty] | 535896.036 | 3175.184 | 2783124.5812 | 16490.0131 | 12702130.9175 | 75260.1257 | 7400676.3702 | 43849.0075 | 5258398.228 | 31156.0095
5 | 5 | years | [10 empty] | 716649.0056 | 4246.1454 | 2979211.9486 | 17651.8308 | 15438172.7294 | 91471.1734 | 9896858.7291 | 58638.888 | 7032009.2111 | 41664.6546
[7 empty] | 0% | [5 empty] | 898472.9366 | 5323.4521 | 3176461.1337 | 18820.5322 | 18190425.5891 | 107778.2716 | 12407830.9685 | 73516.3985 | 8816128.8393 | 52235.5634
| Enter the expected % split of costs over the years: | [11 empty] | 1081374.1744 | 6407.142 | 3374879.0202 | 19996.1582 | 20958985.547 | 124181.9894 | 14933680.7184 | 88482.0583 | 10610819.3763 | 62869.1048
6 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | [7 empty] | 1265359.102 | 7497.2527 | 3574472.5326 | 21178.7498 | 23743949.2226 | 140682.8991 | 17474496.1281 | 103536.3896 | 12416143.4547 | 73565.65
| 2.462% | 2.49% | 36.89% | 34% | 24.16% | 100% | < Needs to equal 100% | [5 empty] | 1450434.1403 | 8593.8223 | 3775248.6366 | 22368.3482 | 26545413.8081 | 157281.5768 | 20030365.869 | 118679.9178 | 14232164.0783 | 84325.5722
[13 empty] | 1636605.7482 | 9696.8891 | 3977214.3391 | 23564.995 | 29363477.0711 | 173978.6016 | 22601379.1382 | 133913.1714 | 16058944.6241 | 95149.2469
7 | No |  |  |  | Partial Capitalisation at year end? | [7 empty] | 1823880.4229 | 10806.4915 | 4180376.6883 | 24768.7319 | 32198237.3591 | 190774.5564 | 25187625.661 | 149236.682 | 17896548.8447 | 106037.0519
[13 empty] | 2012264.7 | 11922.6683 | 4384742.7744 | 25979.6009 | 35049793.6017 | 207670.0271 | 27789195.6944 | 164650.9845 | 19745040.8702 | 116989.3672
| Enter the overhead rate to be used throughout the project: | [8 empty] | Business Overheads: |  |  | 2201765.154 | 13045.4585 | 4590319.7296 | 27197.6444 | 37918245.315 | 224665.6035 | 30406180.0303 | 180156.6167 | 21604485.211 | 128006.5749
8 | 50% | [8 empty] | Regulated Capex Overhead Rate as per FSS History |  |  | CI Calculation | 83877.185 |  | 247538.5104 |  | 1596013.3092 |  | 1158336.4302 |  | 823032.1023
[11 empty] | 0.5356 | Average Rate 0910
| Enter an escalation rate (%): | [9 empty] | 0.5105 | Average Rate 1011
9 | [10 empty] | 0.5167 | Average Rate 1112
If not included in Construction estimate | [10 empty] | 0.529 | Average Rate 1213
[11 empty] | 0.486 | Budgeted Rate 1314
[11 empty] | 0.51556 | Average Rate
| Cost to the Business | [9 empty] | 0.5 | Adopted Rate during project
| Yearly Split: | [5 empty] | Total Project Cost:
| 12/13 | 13/14 | 14/15 | 15/16 | 16/17
| 1420622.285 | 1436778.8341 | 21286253.4902 | 19618666.8112 | 13939639.789 | Construction |  | 57701961.2095
| 0 | 0 | 0 | 0 | 0 | Escalations | Escalations | 0
| 710311.1425 | 718389.4171 | 10643126.7451 | 9809333.4056 | 6969819.8945 | Overheads | Overheads | 28850980.6047
| 83877.185 | 247538.5104 | 1596013.3092 | 1158336.4302 | 823032.1023 | C. Interest | C.Interest | 3908797.5371
| 2214810.6125 | 2402706.7615 | 33525393.5445 | 30586336.647 | 21732491.7858 | Total |  | 90461739.3514
| 2214401 |  | 24143654.6093 |  | 33558306.6002
| Additional Workings - Design | [8 empty] | Greenfield Site:
[5 empty] | 30.38% | 54.13% | 15.49%
| 41602063 |  |  |  | 28275000 | 50372000 | 14419000 | 93066000 |  | Bulk Exc | 131440
| 4712741 |  |  |  | 18568989.2953 | 33080711.8933 | 9469363.6304 | 61119064.8191 |  | Found | 469601
| 2639135 | 48953939 | [7 empty] | Slab | 312802
| 3426775.73 | 7% |  |  | 25439515.3346 | 45320575.2939 | 12973028.1736 | 83733118.8021 | 83733118.8021 | Landscaping | 281380 | 60%
| 1047614.2946 | 2% |  |  | 38736750 | 69009640 | 19754030 | 127500420 |  | Surface & Roads | 2231569 | 60%
| 4474390.0246 |  |  |  | 28737000 | 49010000 | 49753420 | 0 |  | External Works | 707673 | 80%
| 447439.0025 | 10% cont | [7 empty] | Sub-total | 2987750.8
| 2572640.0324 | overheads | 4921829.0271 | 4921829.0271 | [5 empty] | Total Project | 8075641
| 188054.8841 | Cap interest
| 7682523.9436 | TOTAL |  | 246091.4514 | 246091.4514 | 1435.5335 |  |  |  | % | 37%
|  |  |  | 246091.4514 | 492182.9027 | 2871.0669
|  |  |  | 246091.4514 | 738274.3541 | 4306.6004
|  |  |  | 492182.9027 | 1230457.2568 | 7177.6673
|  |  |  | 492182.9027 | 1722640.1595 | 10048.7343
|  |  |  | 738274.3541 | 2460914.5135 | 14355.3347
|  |  |  | 738274.3541 | 3199188.8676 | 18661.9351
|  |  |  | 738274.3541 | 3937463.2216 | 22968.5355
|  |  |  | 246091.4514 | 4183554.673 | 24404.0689
|  |  |  | 246091.4514 | 4429646.1244 | 25839.6024
|  |  |  | 246091.4514 | 4675737.5757 | 27275.1359
|  |  |  | 246091.4514 | 4921829.0271 | 28710.6693
[6 empty] | 188054.8841 | CI

## OP4-Item Costs
Area Schedule | Schematic Design Estimate Jun 2013 $
Construction
Recompletion of Detailed Design | 2233915.3
Total Construction Costs | 70430600
OCCN Build & Comms relocation | 9461000
Sub-Total: | 82125515.3
EECL Associated and Other Costs
Sparq | 2150000
Staging/Decanting | 1000000
Int, External Racking to Warehouse | 1500000
Underground tank removal | 100000
DA Requirements (outside fence) | 250000
Authority Fee, Op Works, DA | 150000
Temporary Services | 250000
Staff Relocation | 400000
Internal Management | 600000
EECL Sub-Total: | 6400000
EE Contingency included in project | 4426275.765
Total: | 92951791.065
Expenditure to date plus forecast up to construct | 2233915.3
Escalations to Delivery date | 6111921.7985
Overheads | 50648814.0818
Capitalised Interest | 6875315.8427
GRAND TOTAL PROJECT ESTIMATE: | 158821758.088
Note on B5: Based on costing performed at Richo/Glenmore Rd for OCCS

## OP4-Project Cost
Estimating Tool - High Level Cost to the Business
v0.3
[13 empty] | Workings: | [7 empty] | No | 2
| Enter the known estimate costs for the following items: | [11 empty] | 1 | 2 | 3 | 4 | 5 | Total |  |  | Yes | 3
1 | [21 empty] | 4
| 82125515.3 | Design & Contruction Estimate | [10 empty] | 2594762.3555 | 2370124.0885 | 28555711.9095 | 30459426.0368 | 31205681.9747 | 95185706.365 |  |  |  | 5
[13 empty] | 0 | 59253.1022 | 1427785.5955 | 2284456.9528 | 2340426.1481 | 6111921.7985 | Escalations
[13 empty] | 1297381.1778 | 1214688.5954 | 14991748.7525 | 16371941.4948 | 16773054.0614 | 50648814.0818 | Overheads
| Enter any other assumptions: | [11 empty] | 153201.4276 | 440621.2449 | 2367561.9943 | 1933282.8727 | 1980648.3031 | 6875315.8427 | Capitalised Interest
2 | 6400000 | EECL Allowances | [15 empty] | 158821758.088
3 | 4426275.765 | Contingency | [10 empty] | FALSE |  | FALSE |  | TRUE |  | TRUE
4 | 2233915.3 | [11 empty] | 3892143.5333 |  | 3644065.7861 |  | 44975246.2575 |  | 49115824.4843 |  | 50319162.1842
| 95185706.365 | Sub-total | [10 empty] | 324345.2944 | 1921.7459 | 4349017.1097 | 25767.9264 | 11877969.18 | 70376.9674 | 4092985.3737 | 24250.9383 | 4193263.5154 | 24845.0863
[13 empty] | 650612.3347 | 3854.8781 | 4678457.185 | 27719.8588 | 15696283.3355 | 93000.4788 | 8210221.6857 | 48645.5635 | 8411372.117 | 49837.3798
| Over how many financial years will the project run for (2-5): | [11 empty] | 978812.5073 | 5799.4641 | 5009849.1926 | 29683.3565 | 19537221.0024 | 115758.0344 | 12351852.6229 | 73184.7268 | 12654473.0122 | 74977.7526
5 | 5 | years | [10 empty] | 1308957.2658 | 7755.5718 | 5343204.6979 | 31658.4878 | 23400916.225 | 138650.4286 | 16518022.7234 | 97869.2846 | 16922714.2801 | 100267.0821
[7 empty] | 0% | [5 empty] | 1641058.1321 | 9723.2694 | 5678535.3346 | 33645.3219 | 27287503.8417 | 161678.4603 | 20708877.3817 | 122700.0985 | 21216244.8776 | 125706.2509
| Enter the expected % split of costs over the years: | [11 empty] | 1975126.6959 | 11702.6257 | 6015852.8053 | 35643.9279 | 31197119.4901 | 184842.933 | 24924562.8539 | 147678.0349 | 25535214.6438 | 151296.1468
6 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | [7 empty] | 2311174.616 | 13693.7096 | 6355168.882 | 37654.3756 | 35129899.6112 | 208144.6552 | 29165226.2625 | 172803.9656 | 29879774.3059 | 177037.6628
| 2.726% | 2.49% | 30% | 32% | 32.78% | 100% | < Needs to equal 100% | [5 empty] | 2649213.6201 | 15696.5907 | 6696495.4065 | 39676.7353 | 39085981.4545 | 231584.4401 | 33431015.6018 | 198078.7674 | 34250075.4841 | 202931.6972
[13 empty] | 2989255.5052 | 17711.3389 | 7039844.2906 | 41711.0774 | 43065503.0828 | 255163.1058 | 37722079.743 | 223503.3225 | 38646270.6967 | 228979.1539
7 | No |  |  |  | Partial Capitalisation at year end? | [7 empty] | 3331312.1385 | 19738.0244 | 7385227.5168 | 43757.473 | 47068603.3767 | 278881.475 | 42038568.4391 | 249078.518 | 43068513.3659 | 255180.9417
[13 empty] | 3675395.4574 | 21776.7181 | 7732657.1387 | 45815.9935 | 51095422.0398 | 302740.3756 | 46380632.3308 | 274805.2466 | 47516957.8229 | 281537.9751
| Enter the overhead rate to be used throughout the project: | [8 empty] | Business Overheads: |  |  | 4021517.4699 | 23827.491 | 8082145.2811 | 47886.7108 | 55146099.6035 | 326740.6402 | 50748422.9511 | 300684.406 | 51991759.3134 | 308051.1739
8 | 50% | [8 empty] | Regulated Capex Overhead Rate as per FSS History |  |  | CI Calculation | 153201.4276 |  | 440621.2449 |  | 2367561.9943 |  | 1933282.8727 |  | 1980648.3031
[11 empty] | 0.5356 | Average Rate 0910
| Enter an escalation rate (%): | [9 empty] | 0.5105 | Average Rate 1011
9 | 2.5% | [9 empty] | 0.5167 | Average Rate 1112
If not included in Construction estimate | [10 empty] | 0.529 | Average Rate 1213
[11 empty] | 0.486 | Budgeted Rate 1314
[11 empty] | 0.51556 | Average Rate
| Cost to the Business | [9 empty] | 0.5 | Adopted Rate during project
| Yearly Split: | [5 empty] | Total Project Cost:
| 13/14 | 14/15 | 15/16 | 16/17 | 17/18
| 2594762.3555 | 2370124.0885 | 28555711.9095 | 30459426.0368 | 31205681.9747 | Construction |  | 95185706.365
| 0 | 59253.1022 | 1427785.5955 | 2284456.9528 | 2340426.1481 | Escalations | Escalations | 6111921.7985
| 1297381.1778 | 1214688.5954 | 14991748.7525 | 16371941.4948 | 16773054.0614 | Overheads | Overheads | 50648814.0818
| 153201.4276 | 440621.2449 | 2367561.9943 | 1933282.8727 | 1980648.3031 | C. Interest | C.Interest | 6875315.8427
| 4045344.9609 | 4084687.031 | 47342808.2518 | 51049107.3571 | 52299810.4873 | Total |  | 158821758.088
2214401 |  |  | 33520598.3535 |  | 61665108.0115
| Additional Workings - Design | [8 empty] | Greenfield Site:
[5 empty] | 30.38% | 54.13% | 15.49%
| 41602063 |  |  |  | 28275000 | 50372000 | 14419000 | 93066000 |  | Bulk Exc | 131440
| 4712741 |  |  |  | 18568989.2953 | 33080711.8933 | 9469363.6304 | 61119064.8191 |  | Found | 469601
| 2639135 | 48953939 | [7 empty] | Slab | 312802
| 3426775.73 | 7% |  |  | 25439515.3346 | 45320575.2939 | 12973028.1736 | 83733118.8021 | 83733118.8021 | Landscaping | 281380 | 60%
| 1047614.2946 | 2% |  |  | 38736750 | 69009640 | 19754030 | 127500420 |  | Surface & Roads | 2231569 | 60%
| 4474390.0246 |  |  |  | 28737000 | 49010000 | 49753420 | 0 |  | External Works | 707673 | 80%
| 447439.0025 | 10% cont | [7 empty] | Sub-total | 2987750.8
| 2572640.0324 | overheads | 4921829.0271 | 4921829.0271 | [5 empty] | Total Project | 8075641
| 188054.8841 | Cap interest
| 7682523.9436 | TOTAL |  | 246091.4514 | 246091.4514 | 1435.5335 |  |  |  | % | 37%
|  |  |  | 246091.4514 | 492182.9027 | 2871.0669
|  |  |  | 246091.4514 | 738274.3541 | 4306.6004
|  |  |  | 492182.9027 | 1230457.2568 | 7177.6673
|  |  |  | 492182.9027 | 1722640.1595 | 10048.7343
|  |  |  | 738274.3541 | 2460914.5135 | 14355.3347
|  |  |  | 738274.3541 | 3199188.8676 | 18661.9351
|  |  |  | 738274.3541 | 3937463.2216 | 22968.5355
|  |  |  | 246091.4514 | 4183554.673 | 24404.0689
|  |  |  | 246091.4514 | 4429646.1244 | 25839.6024
|  |  |  | 246091.4514 | 4675737.5757 | 27275.1359
|  |  |  | 246091.4514 | 4921829.0271 | 28710.6693
[6 empty] | 188054.8841 | CI

## OP5-Garbutt Projects
Work Request Number | Project Number | Project Opened | Program Category - Version 1 Forecast | Project Code | Financial Year Project Opened | Project Location | Project Description (Data from Ellipse) | Comments | Region | Work Category | Residential | Project Supervisor | Project Type | Project Planned Start Date | Project Planned Finish Date | Project Status | Pratical Completion / Closed Date | Initial Project Estimate Excl OH's | Initial Project Estimate Incl OH's* | Budget (Excl O/H's) | Budget (Incl O/H's @ 41.95 / 45.73%)* | Forecast V1 (Excl O/H's) | Forecast V1 (Incl O/H's @ 48.6%) | AP Estimate Excl OH's | AP Estimate | LTD Spend
- | - | - | MP< |  | 05/06 | Garbutt | 05/06 Minor Projects | [17 empty] | 29938
- | - | - | MP |  | 05/06 | Garbutt | 05/06 Major Projects | [17 empty] | 197538
- | - | - | MP< |  | 06/07 | Garbutt | 06/07 Minor Projects | [17 empty] | 100000
- | - | - | MP |  | 06/07 | Garbutt | 06/07 Major Projects | [17 empty] | 2000000
139687 | 61743 | - | MP |  | 07/08 | Garbutt | PJTOGD Mster Site Planning Garbutt |  | N |  |  | L. Olsen | Carry Over |  | 0 | Closed | 2009-08-31 |  |  |  |  | 0 | 0 |  | 143690 | 142130.5
252703 | 81476 | 2008-09-09 | MP< |  | 08/09 | Garbutt | Garbutt Depot- Heavy duty racking for storage shed |  | N |  |  | D. Dixon | Carry Over |  | 2008-10-05 | Closed | 2009-10-31 |  |  |  |  | 15500 | 22271.95 |  | 27574 | 27724.61
253937 | 81803 | 2008-09-15 | MP< |  | 08/09 | Garbutt | Garbutt, Pandora Rm Video Conferencing Upg |  | N |  |  | R. Rhead | Carry Over | 2008-09-01 | 2008-11-01 | Closed | 2009-11-30 |  |  |  |  | 48500 | 69689.65 |  | 107768 | 102275.19
256834 | 82604 | 2008-10-06 | MP< |  | 08/09 | Garbutt | Garbutt install Dexion heavy duty shelving required for Carpenters shed |  | N |  |  | D. Dixon | Carry Over | 2008-09-09 | 2008-09-30 | Closed | 2009-09-30 |  |  |  |  | 11765 | 16905.1285 |  | 19154 | 19751.44
264674 | 83257 | 2008-10-16 | MP< |  | 08/09 | Garbutt | Garbutt, Upgrade of Switchboard |  | N |  |  | R. Rhead | Carry Over | 2008-12-10 | 2008-12-31 | Active | [5 empty] | 20000 | 28738 |  | 28738 | 2892.07
264678 | 83261 | 2008-10-16 | MP< |  | 08/09 | Garbutt | Garbutt, Control Room Accommodation Upgrade |  | N |  |  | R. Rhead | Carry Over | 2008-12-10 | 31/2/08 | Closed | 2010-02-28 |  |  |  |  | 80000 | 114952 |  | 163807 | 146277.24
269821 | 84130 | 2008-10-30 | MP< |  | 08/09 | Garbutt | Garbutt - Airconditioner in Comms Room, Old Control Room |  | N |  |  | D. Dixon | Carry Over | 2008-10-28 | 2008-11-05 | Closed | 2009-10-31 |  |  |  |  | 10255 | 14735.4095 |  | 14735 | 10896.6
281753 | 85691 | 2008-12-04 | MP< |  | 08/09 | Garbutt | Relocation Control Computer 1st Garbutt |  | N |  |  | D. Dixon | Carry Over | 2008-07-19 | 2008-10-01 | Closed | 2009-10-31 |  |  |  |  | 6743 | 9689.0167 |  | 9689 | 0
302955 | 87712 | 2009-01-21 | MP< |  | 08/09 | Garbutt | Garbutt Muster Room fit out & adjoining Office Area for training |  | N |  |  | R. Rhead | Carry Over | 2009-01-19 | 2009-02-28 | Closed | 2009-09-30 |  |  |  |  | 40000 | 57476 |  | 74719 | 72224.8
327109 | 91151 | 2009-03-30 | MP |  | 08/09 | Garbutt | Garbutt - Replace Roof above old control room |  | N |  |  | R. Rhead | Carry Over |  |  | Closed | 2010-05-31 |  |  |  |  | 145000 | 232000 |  | 221850 | 242324.41
331146 | 91636 | 2009-04-07 | MP< |  | 08/09 | Garbutt | Garbutt - HR Management Area Electronic Access |  | N |  |  | D. Dixon | Carry Over |  |  | Closed | 2009-09-30 |  |  |  |  | 4120 | 6592 |  | 6304 | 6695
330552 | 92426 | 2009-04-23 | MP< |  | 08/09 | Garbutt | Garbutt - Pedestrian access to the OCCN Secure Parking Area |  | N |  |  | D. Dixon | Carry Over |  |  | Closed | 2009-10-31 |  |  |  |  | 2350 | 3760 |  | 3377 | 2193.75
337681 | 92835 | 2009-04-30 | MP< |  | 08/09 | Garbutt | Garbutt - Additional Shelving Line Services |  | N |  |  | D. Dixon | Carry Over |  |  | Closed | 2009-10-31 |  |  |  |  | 18452 | 29523.2 |  | 32966 | 32963.2
343334 | 93957 | 2009-05-20 | MP< |  | 08/09 | Garbutt | Additional Shelving Logistics Ext Store |  | N |  |  | D. Dixon | Carry Over |  |  | Closed | 2009-09-30 |  |  |  |  | 11765 | 18824 |  | 12617 | 12640.99
350354 | 97001 | 2009-06-26 | MP |  | 09/10 | Garbutt | Roof Upgrade Bldg 6 Workshops Garbutt |  | N |  |  | R. Rhead | New Project | 2009-07-03 | 2009-07-31 | Active | [5 empty] | 266574 | 384026.5044 |  | 497007 | 523758.1
354769 | 98430 | 2009-07-22 | MP< |  | 09/10 | Garbutt | Repair Garbutt Admin Control Rm Ceiling |  | N |  |  | R. Rhead | New Project | 2009-07-12 | 2009-08-30 | Closed | 2010-03-31 |  |  |  |  | 30000 | 43218 |  | 78138 | 70569.96
402748 | 107902 | 2009-12-15 | MP< |  | 09/10 | Garbutt | Workstns Additions & upgrd Garbutt Bld14 | 5/7 - Completed CP sent to Damian Dixon for approval | N |  |  | D. Dixon | New Project | 2009-12-07 | 2010-01-11 | Practical Completion | 2010-06-30 |  |  |  |  | 12000 | 17287.2 |  | 17287 | 14608.1
407054 | 107903 | 2009-12-15 | MP< |  | 09/10 | Garbutt | Pallet Racking Replacement Program 2010 |  | N |  |  | D. Dixon | New Project | 2010-02-12 | 2010-02-17 | Closed | 2010-05-31 |  |  |  |  | 33938 | 48891.0828 |  | 48891 | 49888.86
417415 | 110890 | 2010-02-17 | MP< |  | 09/10 | Garbutt | Board Room Kitchenette Annex Upgrade | 21/6 - CP sent to Rowan Rhead | N |  |  | R. Rhead | New Project | 2010-02-02 | 2010-02-28 | Practical Completion | 2010-06-30 |  |  |  |  | 30000 | 44100 |  | 44100 | 48519.32
436304 | 111869 | 2010-03-10 | MP |  | 09/10 | Garbutt | Generator Upgrade Garbutt Admin |  | N |  |  | D. Dixon | New Project | 2010-03-03 | 2010-06-30 | Active | [5 empty] | 300000 | 441000 |  | 441000 | 331488.17
450997 | 113952 | 2010-04-21 | MP< |  | 09/10 | Garbutt | Upgrade External Racking Garbutt Stores |  | N |  |  | D. Dixon | New Project | 2010-06-21 | 2010-06-25 | Active | [5 empty] | 67469 | 105926.33 |  | 105926 | 28009.6
457722 | 115317 | 2010-05-20 | MP< |  | 09/10 | Garbutt | Add/Upgrade Workstations Bld 7 Garbutt | 5/7 - Completed CP sent to Damian Dixon for approval | N |  |  | D. Dixon | New Project | 2010-05-17 | 2010-06-04 | Practical Completion | 2010-06-30 |  |  |  |  | 8300 | 13238.5 |  | 13239 | 17844.72
462298 | 115936 | 2010-06-02 | MP< |  | 09/10 | Garbutt | Add Wrkstations Bld 6 Garbutt Depot |  | N |  |  | D. Dixon | New Project | 2010-06-01 | 2010-06-28 | Active | [5 empty] | 30000 | 66000 |  | 66000 | 34355.56
465524 | 117044 | 2010-06-10 | MP |  | 09/10 | Garbutt | Construct Roadway Heavy Vehicles Garbutt |  | N |  |  | R. Rhead | New Project | 2010-06-07 | 2010-06-30 | Active | [5 empty] | 125000 | 275000 |  | 275000 | 85118.76
468884 | 118439 | 2010-06-28 | MP< |  | 09/10 | Garbutt | Storage Upgrade Fld Ops Garbutt Depot |  | N |  |  | D. Dixon | New Project | 2010-06-24 | 2010-06-29 | Active | [5 empty] | 8002 | 12803.2 |  | 12803 | 0
469083 | 118474 | 2010-06-28 | MP< |  | 09/10 | Garbutt | Upgrade Road Pavement Garbutt Stores |  | N |  |  | D. Dixon | New Project | 2010-05-29 | 2010-06-03 | Active | [5 empty] | 21258 | 34012.8 |  | 34013 | 34012.8
470222 | 118593 | 2010-06-29 | MP< |  | 09/10 | Garbutt | Supply & Install Path Superdonga Garbutt |  | N |  |  | D. Dixon | New Project | 2010-06-15 | 2010-06-21 | Active | [5 empty] | 3931 | 6289.6 |  | 6290 | 6289.6
472203 | 118997 | 2010-07-05 | MP< |  | 09/10 | Garbutt | Ugrade CBUS Lighting Sys Garbutt Depot |  | N |  |  | D. Dixon | New Project | 2010-06-15 | 2010-07-02 | Active | [5 empty] | 16925 | 24553.0975 |  | 24553 | 0
557398 | 133031 | 2011-03-23 | MP |  | 10/11 | Townsville, Garbutt | TSV Garbutt-TAPS Soil Test Lab |  | N |  |  | Dixon, D | Carry Over | 2011-03-10 | 2011-03-30 | Closed | 2012-06-30 | 26000 | 41600 |  |  | 10254 | 15235.81 |  | 41600 | 46385.95
562704 | 134030 | 2011-04-07 | MP< |  | 10/11 | Townsville, Garbutt | TSV Garbutt-Mezzaine Flr & Racking Upgr |  | N | FU |  | Rhead, R | Carry Over | 2011-05-03 | 2011-05-13 | Closed | 2012-08-31 | 100000 | 170000 | 0 | 0 | 0 | 0 | 100000 | 170000 | 78824.93
564876 | 134032 | 2011-04-07 | MP< |  | 10/11 | Townsville, Garbutt | TSV Garbutt Depot-Storage Demountable |  | N | FU |  | Dixon, D | Carry Over | 2011-04-09 | 2011-05-31 | Closed | 2012-04-30 | 15000 | 25500 |  |  | 8346.94 | 12210.76 |  | 25500 | 25407.12
577551 | 136656 | 2011-05-31 | MP< |  | 10/11 | Townsville, Garbutt | TSV Garbutt-Install Additional Workstati |  | N | FU |  | Dixon, D | Carry Over | 2011-05-21 | 2011-06-10 | Closed | 2011-10-31 | 13800 | 20010 |  |  | 1900 | 2893.13 |  | 20010 | 19624.61
577529 | 136659 | 2011-05-31 | MP< |  | 10/11 | Townsville, Garbutt | TSV Garbutt-Install Workstn Trans Test |  | N | FU |  | Dixon, D | Carry Over | 2011-05-23 | 2011-06-28 | Closed | 2012-05-31 | 10000 | 14500 |  |  | 0 | 0 |  | 14500 | 13396.82
576989 | 136668 | 2011-05-31 | MP< |  | 10/11 | Townsville, Garbutt | TOGDPJ-Line Services Roller Shutter Upg |  | N |  |  | Dixon, D | Carry Over | 2011-05-17 | 2011-05-20 | Closed | 2012-05-31 | 35576 | 51585.2 |  |  | 0 | 0 |  | 51585 | 71641.9
579439 | 136671 | 2011-05-31 | MP< |  | 10/11 | Townsville, Garbutt | TSV Garbutt-Hdrive Recorder & Sec Cam |  | N | FS |  | Dixon, D | Carry Over | 2011-06-06 | 2011-06-24 | Closed | 2012-08-31 | 9575 | 13883.75 | 0 | 0 | 0 | 0 | 9575 | 13884 | 11592
709297 | 159420 | 2012-08-02 | MP< |  | 12/13 | Townsville, Garbutt | Garbutt Depot-Install OCCN Street Light |  | N |  |  | Webley, A | Outside Program | 2012-07-30 | 2012-08-31 | Closed | 2012-11-30 | 8789 | 12808 | 0 | 0 | 5927.16 | 8619.44 | 8789 | 12808 | 8619.44
740305 | 168151 | 2013-03-15 | MP< |  | 12/13 | Townsville, Garbutt | TSV Garbutt OCCN-Sounding Ugrad |  | N | C |  | Rhead, R | Carry Over | 2012-11-19 | 2013-06-30 | Closed | 2013-08-31 | 100000 | 145730 | 0 | 0 | 28476.66 | 42316.03 | 100000 | 145730 | 162462.51
620199 | 144643 | 2011-10-19 | MP< |  | 11/12 | Townsville, Garbutt | TSV Garbutt Bld 3-Add Workstations |  | N | FU |  | Dixon, D | Carry Over | 2011-10-17 | 2011-11-07 | Closed | 2012-08-31 | 6500 | 9897.55 | 0 | 0 | 0 | 0 | 6500 | 9898 | 15073.15
640004 | 147320 | 2011-12-14 | MP< |  | 11/12 | Townsville, Garbutt | TSV Garbutt Dot - Designated Smoking Areas |  | N | FU |  | Dixon, D | Carry Over | 2011-12-12 | 2012-02-29 | Closed | 2012-08-31 | 54675 | 83253.6225 | 0 | 0 | 0 | 0 | 54675 | 83254 | 92334.05
652300 | 148663 | 2012-01-19 | MP< |  | 11/12 | Townsville, Garbutt | TSV Garbutt - Careers workstation upgrade |  | N | FU |  | Dixon, D | Carry Over | 2012-01-20 | 2012-03-30 | Closed | 2012-08-31 | 17906 | 25784.64 | 0 | 0 | 0 | 0 | 17906 | 25785 | 24637.53
673148 | 151729 | 2012-03-20 | MP |  | 11/12 | Townsville, Garbutt | TSV Garbutt-OCCN Generator Roof |  | N | FU |  | Dixon, D | Carry Over | 2012-03-19 | 2012-04-20 | Closed | 2012-09-30 | 55000 | 79200 | 0 | 0 | 1297.44 | 2241.68 | 55000 | 79200 | 100212.56
673018 | 151846 | 2012-03-21 | MP< |  | 11/12 | Townsville, Garbutt | TSV-Generation W/shop & Office Accom |  | N | FU |  | Dixon, D | Carry Over | 2012-03-01 | 2012-04-27 | Closed | 2013-01-31 | 45000 | 64800 | 0 | 0 | 9468.71 | 13798.72 | 45000 | 64800 | 17569.29
665782 | 151848 | 2012-03-21 | MP< |  | 11/12 | Townsville, Garbutt | Garbutt-Admin Building Fire Panel Upgrad |  | N |  |  | Dixon, D | Outside Program | 2012-03-01 | 2012-04-30 | Closed |  | 13282.5 | 19126.8 |  |  | 12321.62 | 18467.63 |  | 19127 | 18467.63
Sum of AP Estimate | Column Labels
Row Labels | MP | MP< | Grand Total
05/06 | 197538 | 29938 | 227476
06/07 | 2000000 | 100000 | 2100000
07/08 | 143690 |  | 143690
08/09 | 221850 | 501448 | 723298
09/10 | 1213007 | 451240 | 1664247
10/11 | 41600 | 295479 | 337079
11/12 | 79200 | 202864 | 282064
Grand Total | 3896885 | 1580969 | 5477854
Average: | 755217 | 362757.75 | 875063
Note on D1: As per version 1 forecast. ---------------------------------------- Major Program - MP Minor Program => $500k - MP> Minor Program = <$500k - MP< Projects Outside Approved Program - OP Capital Purchases - CP
Note on E1: Program Support Analyst reference: CP - Closure Pack FU - Follow Up J - Journal V - Variations NP - Project not Proceeding D - Project opened for Design only
Note on K1: Category allocation as per PoW ------------------------------------------------------- O = Operational HS= Health & Safety C= Compliance E= Environmental G= Growth
Note on N1: As per the 13/14 FY Property PoW Business Case submission
Note on B45: taevans: Estimate is for design & construction. Forecast for construct project has now been rolled into this project

## OP6-Item Costs
Area Schedule | Preliminary Cost Plan Dec 2013 $
Construction
Building 1 | excluded
Building 2 | 4623000
Building 3 | 1880000
Building 4 | 580000
Building 5 | 655000
Building 6 | 2149000
Building 7 | 760000
Building 9 | 756000
Building 10 & 11 | 618000
Building 13 | 164000
Building 14 | 690000
Building 15 | 140000
Building 17 | 2114000
Building 18 | 413000
Building 19 | 682000
Site Works | 1277000
Sub-Total: | 17501000
Garbutt Design and PQS Fees
Sub-Total: | 17501000
EECL Associated and Other Costs
Staging/Decanting | 500000
Underground tank removal | 100000
Authority Fee, Op Works, DA | 150000
Temporary Services | 250000
Staff Relocation | 400000
Internal Management | 600000
EECL Sub-Total: | 2000000
EE Contingency included in project | 975050
Total: | 20476050
Expenditure to date plus forecast up to construct | 1899509
Escalations to 2012/13 | 0
Overheads | 11187779.5
Capitalised Interest | 3320419.1146
GRAND TOTAL PROJECT ESTIMATE: | 36883757.6146

## OP6-Project Cost
Estimating Tool - High Level Cost to the Business
v0.3
[13 empty] | Workings: | [7 empty] | No | 2
| Enter the known estimate costs for the following items: | [11 empty] | 1 | 2 | 3 | 4 | 5 | Total |  |  | Yes | 3
1 | 1899509 | Design Estimate | [19 empty] | 4
| 17501000 | Contruction Estimate | [10 empty] | 1420176.7297 | 1342533.54 | 10091377.109 | 9521471.6213 | 0 | 22375559 |  |  |  | 5
As provided by formal estimate through consultancy or Rawlinsons cost guide | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Escalations
[13 empty] | 710088.3649 | 671266.77 | 5045688.5545 | 4760735.8106 | 0 | 11187779.5 | Overheads
| Enter any other assumptions: | [11 empty] | 83850.8783 | 241922.9958 | 924190.1543 | 2070455.0861 | 0 | 3320419.1146 | Capitalised Interest
2 | 2000000 | EECL Allowances | [15 empty] | 36883757.6146
3 | 975050 | Contingency | [10 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
4 | [12 empty] | 2130265.0946 |  | 2013800.31 |  | 15137065.6635 |  | 14282207.4319 |  | 0
| 22375559 | Sub-total | [10 empty] | 177522.0912 | 1051.8184 | 2381932.6654 | 14112.951 | 5731261.4173 | 33957.7239 | 21721279.0492 | 128698.5784 | 0 | 0
[13 empty] | 356096.0008 | 2109.8688 | 2563862.3089 | 15190.8842 | 7026641.2799 | 41632.8496 | 23040161.5803 | 136512.9574 | 0 | 0
| Over how many financial years will the project run for (2-5): | [11 empty] | 535727.9608 | 3174.1882 | 2746869.8856 | 16275.2041 | 8329696.2681 | 49353.4504 | 24366858.4903 | 144373.6366 | 0 | 0
5 | 4 | years | [10 empty] | 716424.2402 | 4244.8136 | 2930961.7822 | 17365.9486 | 9640471.8571 | 57119.7958 | 25701416.0795 | 152280.8903 | 0 | 0
[7 empty] | 0% | [5 empty] | 898191.1451 | 5321.7825 | 3116144.4233 | 18463.1557 | 10959013.7915 | 64932.1567 | 27043880.9224 | 160234.9945 | 0 | 0
| Enter the expected % split of costs over the years: | [11 empty] | 1081035.0188 | 6405.1325 | 3302424.2715 | 19566.8638 | 12285368.0868 | 72790.8059 | 28394299.8695 | 168236.2267 | 0 | 0
6 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | [7 empty] | 1264962.2425 | 7494.9013 | 3489807.8278 | 20677.1114 | 13619581.0313 | 80696.0176 | 29752720.0489 | 176284.8663 | 0 | 0
| 6.347% | 6% | 45.1% | 42.55% |  | 100% | < Needs to equal 100% | [5 empty] | 1449979.235 | 8591.127 | 3678301.6317 | 21793.9372 | 14961699.1876 | 88648.0677 | 31119188.8679 | 184381.194 | 0 | 0
[13 empty] | 1636092.4532 | 9693.8478 | 3867912.2613 | 22917.3801 | 16311769.3939 | 96647.2337 | 32493754.0146 | 192525.4925 | 0 | 0
7 | No |  |  |  | Partial Capitalisation at year end? | [7 empty] | 1823308.3922 | 10803.1022 | 4058646.334 | 24047.4795 | 17669838.7662 | 104693.7947 | 33876463.4598 | 200718.046 | 0 | 0
[13 empty] | 2011633.5857 | 11918.929 | 4250510.506 | 25184.2747 | 19035954.6995 | 112788.0316 | 35267365.4584 | 208959.1403 | 0 | 0
| Enter the overhead rate to be used throughout the project: | [8 empty] | Business Overheads: |  |  | 2201074.6059 | 13041.367 | 4443511.4732 | 26327.8055 | 20410164.8697 | 120930.2269 | 36666508.5514 | 217249.0632 | 0 | 0
8 | 50% | [8 empty] | Regulated Capex Overhead Rate as per FSS History |  |  | CI Calculation | 83850.8783 |  | 241922.9958 |  | 924190.1543 |  | 2070455.0861 |  | 0
[11 empty] | 0.5356 | Average Rate 0910
| Enter an escalation rate (%): | [9 empty] | 0.5105 | Average Rate 1011
9 | [10 empty] | 0.5167 | Average Rate 1112
If not included in Construction estimate | [10 empty] | 0.529 | Average Rate 1213
[11 empty] | 0.486 | Budgeted Rate 1314
[11 empty] | 0.51556 | Average Rate
| Cost to the Business | [9 empty] | 0.5 | Adopted Rate during project
| Yearly Split: | [5 empty] | Total Project Cost:
| 12/13 | 13/14 | 14/15 | 15/16 | 16/17
| 1420176.7297 | 1342533.54 | 10091377.109 | 9521471.6213 | 0 | Construction |  | 22375559
| 0 | 0 | 0 | 0 | 0 | Escalations | Escalations | 0
| 710088.3649 | 671266.77 | 5045688.5545 | 4760735.8106 | 0 | Overheads | Overheads | 11187779.5
| 83850.8783 | 241922.9958 | 924190.1543 | 2070455.0861 | 0 | C. Interest | C.Interest | 3320419.1146
| 2214115.9729 | 2255723.3058 | 16061255.8178 | 16352662.518 | 0 | Total |  | 36883757.6146
| 2214401 |  | 12854087.3787 |  | 9521471.6213
| Additional Workings - Design | [8 empty] | Greenfield Site:
[5 empty] | 30.38% | 54.13% | 15.49%
| 41602063 |  |  |  | 28275000 | 50372000 | 14419000 | 93066000 |  | Bulk Exc | 131440
| 4712741 |  |  |  | 18568989.2953 | 33080711.8933 | 9469363.6304 | 61119064.8191 |  | Found | 469601
| 2639135 | 48953939 | [7 empty] | Slab | 312802
| 3426775.73 | 7% |  |  | 25439515.3346 | 45320575.2939 | 12973028.1736 | 83733118.8021 | 83733118.8021 | Landscaping | 281380 | 60%
| 1047614.2946 | 2% |  |  | 38736750 | 69009640 | 19754030 | 127500420 |  | Surface & Roads | 2231569 | 60%
| 4474390.0246 |  |  |  | 28737000 | 49010000 | 49753420 | 0 |  | External Works | 707673 | 80%
| 447439.0025 | 10% cont | [7 empty] | Sub-total | 2987750.8
| 2572640.0324 | overheads | 4921829.0271 | 4921829.0271 | [5 empty] | Total Project | 8075641
| 188054.8841 | Cap interest
| 7682523.9436 | TOTAL |  | 246091.4514 | 246091.4514 | 1435.5335 |  |  |  | % | 37%
|  |  |  | 246091.4514 | 492182.9027 | 2871.0669
|  |  |  | 246091.4514 | 738274.3541 | 4306.6004
|  |  |  | 492182.9027 | 1230457.2568 | 7177.6673
|  |  |  | 492182.9027 | 1722640.1595 | 10048.7343
|  |  |  | 738274.3541 | 2460914.5135 | 14355.3347
|  |  |  | 738274.3541 | 3199188.8676 | 18661.9351
|  |  |  | 738274.3541 | 3937463.2216 | 22968.5355
|  |  |  | 246091.4514 | 4183554.673 | 24404.0689
|  |  |  | 246091.4514 | 4429646.1244 | 25839.6024
|  |  |  | 246091.4514 | 4675737.5757 | 27275.1359
|  |  |  | 246091.4514 | 4921829.0271 | 28710.6693
[6 empty] | 188054.8841 | CI

## OP7-Item Costs
Area Schedule | Preliminary Cost Plan Dec 2013 $ | Preliminary Cost Plan Dec 2013 $
Construction | Compliance | Refurbishment
Building 1 | excluded | excluded
Building 2 | 4623000 | 6536000
Building 3 | 1880000 | 2672000
Building 4 | 580000 | 544000
Building 5 | 655000 | 1043000
Building 6 | 2149000 | 1557000
Building 7 | 760000 | 393000
Building 9 | 756000 | 890000
Building 10 & 11 | 618000 | 564000
Building 13 | 164000 | 152000
Building 14 | 690000 | 410000
Building 15 | 140000 | 83000
Building 17 | 2114000 | 3421000
Building 18 | 413000 | 138000
Building 19 | 682000 | 453000
Site Works | 1277000 | 0
Sub-Total: | 17501000 | 18856000
Garbutt Design and PQS Fees
Sub-Total: | 36357000
EECL Associated and Other Costs
Staging/Decanting | 500000
Underground tank removal | 100000
Authority Fee, Op Works, DA | 150000
Temporary Services | 250000
Staff Relocation | 400000
Internal Management | 600000
EECL Sub-Total: | 2000000
EE Contingency included in project | 1917850
Total: | 40274850
Expenditure to date plus forecast up to construct | 1899509
Escalations to 2012/13 | 0
Overheads | 21027924.5256
Capitalised Interest | 4477005.7741
GRAND TOTAL PROJECT ESTIMATE: | 67679289.2997

## OP7-Project Cost
Estimating Tool - High Level Cost to the Business
v0.3
[13 empty] | Workings: | [7 empty] | No | 2
| Enter the known estimate costs for the following items: | [11 empty] | 1 | 2 | 3 | 4 | 5 | Total |  |  | Yes | 3
1 | 1899509 | Design Estimate | [19 empty] | 4
| 36357000 | Contruction Estimate | [10 empty] | 1436036.9239 | 1357592.6162 | 13074051.29 | 13074051.29 | 13114116.9311 | 42055849.0512 |  |  |  | 5
As provided by formal estimate through consultancy or Rawlinsons cost guide | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Escalations
[13 empty] | 718018.462 | 678796.3081 | 6537025.645 | 6537025.645 | 6557058.4655 | 21027924.5256 | Overheads
| Enter any other assumptions: | [11 empty] | 84787.3049 | 244628.6298 | 1103969.5992 | 771925.5363 | 2271694.704 | 4477005.7741 | Capitalised Interest
2 | 2000000 | EECL Allowances | [15 empty] | 67560779.3509
3 | 1917850 | Contingency | [10 empty] | FALSE |  | FALSE |  | TRUE |  | FALSE
4 | [12 empty] | 2154055.3859 |  | 2036388.9243 |  | 19611076.935 |  | 19611076.935 |  | 19671175.3966
| 42174359 | Sub-total | [10 empty] | 179504.6155 | 1063.5648 | 2408541.7678 | 14270.61 | 6154116.6561 | 36463.1412 | 1634256.4112 | 9682.9692 | 22022267.0876 | 130481.9325
[13 empty] | 360072.7958 | 2133.4313 | 2592511.4548 | 15360.6304 | 7824836.2086 | 46362.1545 | 3278195.7917 | 19423.3101 | 23792013.6365 | 140967.6808
| Over how many financial years will the project run for (2-5): | [11 empty] | 541710.8426 | 3209.6367 | 2777571.1622 | 16457.1091 | 9505454.7744 | 56319.8195 | 4931875.5131 | 29221.3624 | 25572245.9337 | 151515.5572
5 | 5 | years | [10 empty] | 724425.0949 | 4292.2187 | 2963727.3484 | 17560.0845 | 11196031.0052 | 66336.4837 | 6595353.2867 | 39077.4682 | 27363026.1072 | 162125.9297
[7 empty] | 0.281% | [5 empty] | 908221.9291 | 5381.2149 | 3150986.5099 | 18669.5951 | 12896623.9001 | 76412.4966 | 8268687.1662 | 48991.9715 | 29164416.6533 | 172799.1687
| Enter the expected % split of costs over the years: | [11 empty] | 1093107.7595 | 6476.6635 | 3339355.182 | 19785.6795 | 14607292.808 | 86548.2099 | 9951935.5489 | 58965.2181 | 30976480.4384 | 183535.6466
6 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | [7 empty] | 1279089.0385 | 7578.6026 | 3528839.9385 | 20908.3766 | 16328097.4291 | 96743.9773 | 11645157.1783 | 68997.5563 | 32799280.7013 | 194335.7382
| 3.405% | 3.219% | 31% | 31% | 31.09% | 99.72% | < Needs to equal 100% | [5 empty] | 1466172.2565 | 8687.0706 | 3719447.3922 | 22037.7258 | 18059097.8176 | 107000.1546 | 13348411.1458 | 79089.336 | 34632881.0559 | 205199.8203
[13 empty] | 1654363.9426 | 9802.1064 | 3911184.195 | 23173.7664 | 19800354.3834 | 117317.0997 | 15061756.8931 | 89240.9096 | 36477345.4925 | 216128.272
7 | No |  |  |  | Partial Capitalisation at year end? | [7 empty] | 1843670.6645 | 10923.7487 | 4104057.0384 | 24316.538 | 21551927.8944 | 127695.1728 | 16785254.2139 | 99452.6312 | 38332738.3809 | 227121.4749
[13 empty] | 2034099.0286 | 12052.0367 | 4298072.6534 | 25466.0805 | 23313879.4784 | 138134.7359 | 18518963.2564 | 109724.8573 | 40199124.4722 | 238179.8125
| Enter the overhead rate to be used throughout the project: | [8 empty] | Business Overheads: |  |  | 2225655.6809 | 13187.0099 | 4493237.8109 | 26622.434 | 25086270.6256 | 148636.1535 | 20262944.525 | 120057.9463 | 42076568.9011 | 249303.6707
8 | 50% | [8 empty] | Regulated Capex Overhead Rate as per FSS History |  |  | CI Calculation | 84787.3049 |  | 244628.6298 |  | 1103969.5992 |  | 771925.5363 |  | 2271694.704
[11 empty] | 0.5356 | Average Rate 0910
| Enter an escalation rate (%): | [9 empty] | 0.5105 | Average Rate 1011
9 | [10 empty] | 0.5167 | Average Rate 1112
If not included in Construction estimate | [10 empty] | 0.529 | Average Rate 1213
[11 empty] | 0.486 | Budgeted Rate 1314
[11 empty] | 0.51556 | Average Rate
| Cost to the Business | [9 empty] | 0.5 | Adopted Rate during project
| Yearly Split: | [5 empty] | Total Project Cost:
| 12/13 | 13/14 | 14/15 | 15/16 | 16/17
| 1436036.9239 | 1357592.6162 | 13074051.29 | 13074051.29 | 13114116.9311 | Construction |  | 42055849.0512
| 0 | 0 | 0 | 0 | 0 | Escalations | Escalations | 0
| 718018.462 | 678796.3081 | 6537025.645 | 6537025.645 | 6557058.4655 | Overheads | Overheads | 21027924.5256
| 84787.3049 | 244628.6298 | 1103969.5992 | 771925.5363 | 2271694.704 | C. Interest | C.Interest | 4477005.7741
| 2238842.6908 | 2281017.5541 | 20715046.5342 | 20383002.4713 | 21942870.1006 | Total |  | 67560779.3509
| 2214401 |  | 15867680.8302 |  | 26188168.2211
| Additional Workings - Design | [8 empty] | Greenfield Site:
[5 empty] | 30.38% | 54.13% | 15.49%
| 41602063 |  |  |  | 28275000 | 50372000 | 14419000 | 93066000 |  | Bulk Exc | 131440
| 4712741 |  |  |  | 18568989.2953 | 33080711.8933 | 9469363.6304 | 61119064.8191 |  | Found | 469601
| 2639135 | 48953939 | [7 empty] | Slab | 312802
| 3426775.73 | 7% |  |  | 25439515.3346 | 45320575.2939 | 12973028.1736 | 83733118.8021 | 83733118.8021 | Landscaping | 281380 | 60%
| 1047614.2946 | 2% |  |  | 38736750 | 69009640 | 19754030 | 127500420 |  | Surface & Roads | 2231569 | 60%
| 4474390.0246 |  |  |  | 28737000 | 49010000 | 49753420 | 0 |  | External Works | 707673 | 80%
| 447439.0025 | 10% cont | [7 empty] | Sub-total | 2987750.8
| 2572640.0324 | overheads | 4921829.0271 | 4921829.0271 | [5 empty] | Total Project | 8075641
| 188054.8841 | Cap interest
| 7682523.9436 | TOTAL |  | 246091.4514 | 246091.4514 | 1435.5335 |  |  |  | % | 37%
|  |  |  | 246091.4514 | 492182.9027 | 2871.0669
|  |  |  | 246091.4514 | 738274.3541 | 4306.6004
|  |  |  | 492182.9027 | 1230457.2568 | 7177.6673
|  |  |  | 492182.9027 | 1722640.1595 | 10048.7343
|  |  |  | 738274.3541 | 2460914.5135 | 14355.3347
|  |  |  | 738274.3541 | 3199188.8676 | 18661.9351
|  |  |  | 738274.3541 | 3937463.2216 | 22968.5355
|  |  |  | 246091.4514 | 4183554.673 | 24404.0689
|  |  |  | 246091.4514 | 4429646.1244 | 25839.6024
|  |  |  | 246091.4514 | 4675737.5757 | 27275.1359
|  |  |  | 246091.4514 | 4921829.0271 | 28710.6693
[6 empty] | 188054.8841 | CI

## NPVData
| Year | 30 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Baseline Risk: | Discount Factor |  | 1 | 0.91141 | 0.83067 | 0.75708 | 0.69001 | 0.62888 | 0.57317 | 0.5224 | 0.47612 | 0.43394 | 0.3955 | 0.36046 | 0.32853 | 0.29942 | 0.2729 | 0.24872 | 0.22669 | 0.20661 | 0.1883 | 0.17162 | 0.15642 | 0.14256 | 0.12993 | 0.11842 | 0.10793 | 0.098368 | 0.089654 | 0.081712 | 0.074473 | 0.067875
17 |  |  | 13/14 | 14/15 | 15/16 | 16/17 | 17/18 | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | 31/32 | 32/33 | 33/34 | 34/35 | 35/36 | 36/37 | 37/38 | 38/39 | 39/40 | 40/41 | 41/42 | 42/43
Option A |  |  | 33/34: Hard-coded based on consistent escalation rates
Risk Score: | Implementation | 25 | 2.6762 | 18.1557 | 21.7993 | 6.3561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.9873
0 | Lifecycle |  | 2.4526 | 1.6714 | 0.86356 | 0.90359 | 1.0883 | 1.1209 | 1.1545 | 1.1892 | 1.2248 | 1.2616 | 1.2994 | 1.3384 | 1.3786 | 1.4199 | 1.4625 | 1.5064 | 1.5516 | 1.5981 | 1.6461 | 1.6955 | 1.7463 | 1.7987 | 1.8527 | 1.9083 | 1.9655 | 2.0245 | 2.0852 | 2.1478 | 2.2122 | 2.2786 | 47.8466
| Benefits |  | 0 | 0 | 0 | 0 | 5.293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.293
| Residual Value |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Benefit |  | -5.1288 | -19.8271 | -22.6629 | -7.2597 | 4.2047 | -1.1209 | -1.1545 | -1.1892 | -1.2248 | -1.2616 | -1.2994 | -1.3384 | -1.3786 | -1.4199 | -1.4625 | -1.5064 | -1.5516 | -1.5981 | -1.6461 | -1.6955 | -1.7463 | -1.7987 | -1.8527 | -1.9083 | -1.9655 | -2.0245 | -2.0852 | -2.1478 | -2.2122 | -2.2786 | 91.5409
| Cumulative Net Benefit |  | -5.1288 | -24.9559 | -47.6188 | -54.8785 | -50.6737 | -51.7946 | -52.9492 | -54.1383 | -55.3632 | -56.6248 | -57.9242 | -59.2626 | -60.6412 | -62.0611 | -63.5236 | -65.03 | -66.5816 | -68.1797 | -69.8258 | -71.5213 | -73.2676 | -75.0663 | -76.919 | -78.8272 | -80.7927 | -82.8172 | -84.9024 | -87.0502 | -89.2624 | -91.5409
| D/Cashflow |  | -5.1288 | -18.0706 | -18.8254 | -5.4962 | 2.9013 | -0.70492 | -0.66174 | -0.62121 | -0.58317 | -0.54745 | -0.51392 | -0.48244 | -0.4529 | -0.42516 | -0.39912 | -0.37467 | -0.35173 | -0.33018 | -0.30996 | -0.29098 | -0.27316 | -0.25643 | -0.24072 | -0.22598 | -0.21214 | -0.19914 | -0.18695 | -0.1755 | -0.16475 | -0.15466
| Cumulative D/Cashflow |  | -5.1288 | -23.1994 | -42.0248 | -47.521 | -44.6197 | -45.3246 | -45.9863 | -46.6075 | -47.1907 | -47.7381 | -48.2521 | -48.7345 | -49.1874 | -49.6126 | -50.0117 | -50.3864 | -50.7381 | -51.0683 | -51.3782 | -51.6692 | -51.9424 | -52.1988 | -52.4395 | -52.6655 | -52.8776 | -53.0768 | -53.2637 | -53.4392 | -53.6039 | -53.7586
| Cumulative Cashflow |  | 5.1288 | 24.9559 | 47.6188 | 54.8785 | 50.6737 | 51.7946 | 52.9492 | 54.1383 | 55.3632 | 56.6248 | 57.9242 | 59.2626 | 60.6412 | 62.0611 | 63.5236 | 65.03 | 66.5816 | 68.1797 | 69.8258 | 71.5213 | 73.2676 | 75.0663 | 76.919 | 78.8272 | 80.7927 | 82.8172 | 84.9024 | 87.0502 | 89.2624 | 91.5409
| Cumulative Implementation |  | 2.6762 | 20.8318 | 42.6312 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873 | 48.9873
| Cumulative Lifecycle |  | 2.4526 | 4.124 | 4.9876 | 5.8912 | 6.9794 | 8.1003 | 9.2549 | 10.444 | 11.6689 | 12.9304 | 14.2299 | 15.5683 | 16.9469 | 18.3668 | 19.8293 | 21.3357 | 22.8873 | 24.4854 | 26.1315 | 27.827 | 29.5733 | 31.372 | 33.2247 | 35.1329 | 37.0984 | 39.1229 | 41.2081 | 43.3559 | 45.5681 | 47.8466
| Cumulative Benefits |  | 0 | 0 | 0 | 0 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293
| Present value of Implementation |  | 2.6762 | 16.5051 | 18.016 | 4.7754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41.9727
| Present value of Lifecycle |  | 2.4526 | 1.5195 | 0.71368 | 0.67888 | 0.74329 | 0.69599 | 0.6517 | 0.61023 | 0.5714 | 0.53503 | 0.50099 | 0.46911 | 0.43925 | 0.4113 | 0.38513 | 0.36062 | 0.33767 | 0.31618 | 0.29606 | 0.27722 | 0.25958 | 0.24306 | 0.22759 | 0.21311 | 0.19955 | 0.18685 | 0.17496 | 0.16383 | 0.1534 | 0.14364 | -14.9314
| Present value of Benefits |  | 0 | 0 | 0 | 0 | 3.6152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6152
Option B
Risk Score: | Implementation | 25 | 5.0919 | 21.2863 | 19.6187 | 13.9391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.9359
0 | Lifecycle |  | 2.4526 | 1.6714 | 0.88538 | 1.3469 | 1.5164 | 1.5619 | 1.6088 | 1.657 | 1.7067 | 1.7579 | 1.8107 | 1.865 | 1.921 | 1.9786 | 2.0379 | 2.0991 | 2.162 | 2.2269 | 2.2937 | 2.3625 | 2.4334 | 2.5064 | 2.5816 | 2.659 | 2.7388 | 2.821 | 2.9056 | 2.9928 | 3.0826 | 3.175 | 64.8188
| Benefits |  | 0 | 0 | 0 | 0 | 5.293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.293
| Residual Value |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Benefit |  | -7.5445 | -22.9577 | -20.504 | -15.286 | 3.7765 | -1.5619 | -1.6088 | -1.657 | -1.7067 | -1.7579 | -1.8107 | -1.865 | -1.921 | -1.9786 | -2.0379 | -2.0991 | -2.162 | -2.2269 | -2.2937 | -2.3625 | -2.4334 | -2.5064 | -2.5816 | -2.659 | -2.7388 | -2.821 | -2.9056 | -2.9928 | -3.0826 | -3.175 | 119.4618
| Cumulative Net Benefit |  | -7.5445 | -30.5022 | -51.0062 | -66.2922 | -62.5157 | -64.0776 | -65.6864 | -67.3434 | -69.0501 | -70.8081 | -72.6188 | -74.4838 | -76.4047 | -78.3833 | -80.4212 | -82.5203 | -84.6823 | -86.9093 | -89.203 | -91.5655 | -93.9989 | -96.5053 | -99.0869 | -101.746 | -104.4848 | -107.3058 | -110.2114 | -113.2042 | -116.2867 | -119.4618
| D/Cashflow |  | -7.5445 | -20.9239 | -17.0321 | -11.5727 | 2.6059 | -0.98226 | -0.9221 | -0.86562 | -0.81261 | -0.76284 | -0.71612 | -0.67226 | -0.63108 | -0.59243 | -0.55615 | -0.52208 | -0.49011 | -0.46009 | -0.43191 | -0.40546 | -0.38063 | -0.35731 | -0.33543 | -0.31489 | -0.2956 | -0.2775 | -0.2605 | -0.24454 | -0.22957 | -0.21551
| Cumulative D/Cashflow |  | -7.5445 | -28.4684 | -45.5005 | -57.0732 | -54.4674 | -55.4496 | -56.3717 | -57.2373 | -58.0499 | -58.8128 | -59.5289 | -60.2012 | -60.8322 | -61.4247 | -61.9808 | -62.5029 | -62.993 | -63.4531 | -63.885 | -64.2905 | -64.6711 | -65.0284 | -65.3638 | -65.6787 | -65.9743 | -66.2518 | -66.5123 | -66.7569 | -66.9864 | -67.2019
| Cumulative Cashflow |  | 7.5445 | 30.5022 | 51.0062 | 66.2922 | 62.5157 | 64.0776 | 65.6864 | 67.3434 | 69.0501 | 70.8081 | 72.6188 | 74.4838 | 76.4047 | 78.3833 | 80.4212 | 82.5203 | 84.6823 | 86.9093 | 89.203 | 91.5655 | 93.9989 | 96.5053 | 99.0869 | 101.746 | 104.4848 | 107.3058 | 110.2114 | 113.2042 | 116.2867 | 119.4618
| Cumulative Implementation |  | 5.0919 | 26.3781 | 45.9968 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359 | 59.9359
| Cumulative Lifecycle |  | 2.4526 | 4.124 | 5.0094 | 6.3563 | 7.8728 | 9.4347 | 11.0434 | 12.7005 | 14.4072 | 16.1652 | 17.9758 | 19.8408 | 21.7618 | 23.7404 | 25.7783 | 27.8774 | 30.0394 | 32.2663 | 34.5601 | 36.9226 | 39.356 | 41.8624 | 44.444 | 47.103 | 49.8419 | 52.6628 | 55.5685 | 58.5612 | 61.6438 | 64.8188
| Cumulative Benefits |  | 0 | 0 | 0 | 0 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293
| Present value of Implementation |  | 5.0919 | 19.3511 | 16.2138 | 10.4726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51.1294
| Present value of Lifecycle |  | 2.4526 | 1.5195 | 0.73172 | 1.012 | 1.0357 | 0.96982 | 0.90811 | 0.85032 | 0.79621 | 0.74554 | 0.6981 | 0.65367 | 0.61207 | 0.57312 | 0.53665 | 0.5025 | 0.47052 | 0.44058 | 0.41255 | 0.38629 | 0.36171 | 0.33869 | 0.31714 | 0.29696 | 0.27806 | 0.26037 | 0.2438 | 0.22828 | 0.21376 | 0.20015 | -19.0465
| Present value of Benefits |  | 0 | 0 | 0 | 0 | 3.6152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6152
Option C
Risk Score: | Implementation | 25 | 3.1095 | 4.9852 | 19.2708 | 18.1838 | 4.8386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.3879
0 | Lifecycle |  | 2.6686 | 2.7585 | 1.7216 | 0.88542 | 1.0883 | 1.1209 | 1.1545 | 1.1892 | 1.2248 | 1.2616 | 1.2994 | 1.3384 | 1.3786 | 1.4199 | 1.4625 | 1.5064 | 1.5516 | 1.5981 | 1.6461 | 1.6955 | 1.7463 | 1.7987 | 1.8527 | 1.9083 | 1.9655 | 2.0245 | 2.0852 | 2.1478 | 2.2122 | 2.2786 | 49.9896
| Benefits |  | 0 | 0 | 0 | 0 | 5.293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.293
| Residual Value |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Benefit |  | -5.7781 | -7.7437 | -20.9924 | -19.0692 | -0.63387 | -1.1209 | -1.1545 | -1.1892 | -1.2248 | -1.2616 | -1.2994 | -1.3384 | -1.3786 | -1.4199 | -1.4625 | -1.5064 | -1.5516 | -1.5981 | -1.6461 | -1.6955 | -1.7463 | -1.7987 | -1.8527 | -1.9083 | -1.9655 | -2.0245 | -2.0852 | -2.1478 | -2.2122 | -2.2786 | 95.0845
| Cumulative Net Benefit |  | -5.7781 | -13.5219 | -34.5143 | -53.5835 | -54.2173 | -55.3382 | -56.4927 | -57.6819 | -58.9067 | -60.1683 | -61.4678 | -62.8062 | -64.1847 | -65.6047 | -67.0672 | -68.5736 | -70.1252 | -71.7233 | -73.3694 | -75.0648 | -76.8112 | -78.6099 | -80.4626 | -82.3708 | -84.3363 | -86.3608 | -88.446 | -90.5938 | -92.8059 | -95.0845
| D/Cashflow |  | -5.7781 | -7.0577 | -17.4378 | -14.4369 | -0.43738 | -0.70492 | -0.66174 | -0.62121 | -0.58317 | -0.54745 | -0.51392 | -0.48244 | -0.4529 | -0.42516 | -0.39912 | -0.37467 | -0.35173 | -0.33018 | -0.30996 | -0.29098 | -0.27316 | -0.25643 | -0.24072 | -0.22598 | -0.21214 | -0.19914 | -0.18695 | -0.1755 | -0.16475 | -0.15466
| Cumulative D/Cashflow |  | -5.7781 | -12.8359 | -30.2736 | -44.7105 | -45.1479 | -45.8528 | -46.5146 | -47.1358 | -47.7189 | -48.2664 | -48.7803 | -49.2628 | -49.7157 | -50.1408 | -50.5399 | -50.9146 | -51.2663 | -51.5965 | -51.9065 | -52.1974 | -52.4706 | -52.727 | -52.9677 | -53.1937 | -53.4059 | -53.605 | -53.792 | -53.9674 | -54.1322 | -54.2869
| Cumulative Cashflow |  | 5.7781 | 13.5219 | 34.5143 | 53.5835 | 54.2173 | 55.3382 | 56.4927 | 57.6819 | 58.9067 | 60.1683 | 61.4678 | 62.8062 | 64.1847 | 65.6047 | 67.0672 | 68.5736 | 70.1252 | 71.7233 | 73.3694 | 75.0648 | 76.8112 | 78.6099 | 80.4626 | 82.3708 | 84.3363 | 86.3608 | 88.446 | 90.5938 | 92.8059 | 95.0845
| Cumulative Implementation |  | 3.1095 | 8.0947 | 27.3656 | 45.5493 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879 | 50.3879
| Cumulative Lifecycle |  | 2.6686 | 5.4271 | 7.1487 | 8.0341 | 9.1224 | 10.2433 | 11.3978 | 12.587 | 13.8118 | 15.0734 | 16.3728 | 17.7112 | 19.0898 | 20.5097 | 21.9722 | 23.4786 | 25.0302 | 26.6283 | 28.2744 | 29.9699 | 31.7162 | 33.5149 | 35.3676 | 37.2759 | 39.2414 | 41.2658 | 43.351 | 45.4988 | 47.711 | 49.9896
| Cumulative Benefits |  | 0 | 0 | 0 | 0 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293 | 5.293
| Present value of Implementation |  | 3.1095 | 4.532 | 15.9263 | 13.6617 | 3.3048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40.5344
| Present value of Lifecycle |  | 2.6686 | 2.5077 | 1.4228 | 0.66523 | 0.74329 | 0.69599 | 0.6517 | 0.61023 | 0.5714 | 0.53503 | 0.50099 | 0.46911 | 0.43925 | 0.4113 | 0.38513 | 0.36062 | 0.33767 | 0.31618 | 0.29606 | 0.27722 | 0.25958 | 0.24306 | 0.22759 | 0.21311 | 0.19955 | 0.18685 | 0.17496 | 0.16383 | 0.1534 | 0.14364 | -16.8311
| Present value of Benefits |  | 0 | 0 | 0 | 0 | 3.6152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6152
Option D
Risk Score: | Implementation | 40 | 2.5948 | 2.4294 | 29.9835 | 32.7439 | 33.5461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101.2976
-9 | Lifecycle |  | 2.4526 | 2.5295 | 2.2501 | 2.7911 | 1.5755 | 1.2219 | 1.2586 | 1.2963 | 1.3352 | 1.3753 | 1.4165 | 1.459 | 1.5028 | 1.5479 | 1.5943 | 1.6421 | 1.6914 | 1.7421 | 1.7944 | 1.8482 | 1.9037 | 1.9608 | 2.0196 | 2.0802 | 2.1426 | 2.2069 | 2.2731 | 2.3413 | 2.4115 | 2.4839 | 56.1483
| Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.5647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.6947 | 75.2594
| Residual Value |  | 0.64869 | 0.66808 | 8.995 | 10.6418 | 11.7411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.6947
| Net Benefit |  | -5.0474 | -4.9589 | -32.2336 | -35.535 | -35.1216 | -1.2219 | -1.2586 | -1.2963 | 41.2295 | -1.3753 | -1.4165 | -1.459 | -1.5028 | -1.5479 | -1.5943 | -1.6421 | -1.6914 | -1.7421 | -1.7944 | -1.8482 | -1.9037 | -1.9608 | -2.0196 | -2.0802 | -2.1426 | -2.2069 | -2.2731 | -2.3413 | -2.4115 | 30.2109 | 82.1865
| Cumulative Net Benefit |  | -5.0474 | -10.0062 | -42.2399 | -77.7749 | -112.8965 | -114.1184 | -115.3769 | -116.6732 | -75.4438 | -76.819 | -78.2355 | -79.6945 | -81.1973 | -82.7452 | -84.3395 | -85.9816 | -87.673 | -89.4151 | -91.2095 | -93.0577 | -94.9614 | -96.9222 | -98.9418 | -101.022 | -103.1646 | -105.3715 | -107.6446 | -109.9859 | -112.3974 | -82.1865
| D/Cashflow |  | -5.0474 | -4.5196 | -26.7755 | -26.9029 | -24.2343 | -0.76843 | -0.72137 | -0.67719 | 19.6301 | -0.59678 | -0.56023 | -0.52591 | -0.4937 | -0.46347 | -0.43508 | -0.40843 | -0.38342 | -0.35993 | -0.33789 | -0.31719 | -0.29777 | -0.27953 | -0.26241 | -0.24634 | -0.23125 | -0.21709 | -0.20379 | -0.19131 | -0.17959 | 2.0506
| Cumulative D/Cashflow |  | -5.0474 | -9.5669 | -36.3425 | -63.2453 | -87.4797 | -88.2481 | -88.9695 | -89.6467 | -70.0166 | -70.6134 | -71.1736 | -71.6995 | -72.1932 | -72.6567 | -73.0918 | -73.5002 | -73.8836 | -74.2435 | -74.5814 | -74.8986 | -75.1964 | -75.4759 | -75.7383 | -75.9847 | -76.2159 | -76.433 | -76.6368 | -76.8281 | -77.0077 | -74.9571
| Cumulative Cashflow |  | 5.0474 | 10.0062 | 42.2399 | 77.7749 | 112.8965 | 114.1184 | 115.3769 | 116.6732 | 75.4438 | 76.819 | 78.2355 | 79.6945 | 81.1973 | 82.7452 | 84.3395 | 85.9816 | 87.673 | 89.4151 | 91.2095 | 93.0577 | 94.9614 | 96.9222 | 98.9418 | 101.022 | 103.1646 | 105.3715 | 107.6446 | 109.9859 | 112.3974 | 82.1865
| Cumulative Implementation |  | 2.5948 | 5.0241 | 35.0076 | 67.7515 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976 | 101.2976
| Cumulative Lifecycle |  | 2.4526 | 4.9821 | 7.2323 | 10.0234 | 11.5989 | 12.8208 | 14.0793 | 15.3756 | 16.7108 | 18.0861 | 19.5026 | 20.9616 | 22.4644 | 24.0122 | 25.6065 | 27.2487 | 28.9401 | 30.6822 | 32.4766 | 34.3248 | 36.2285 | 38.1893 | 40.2089 | 42.2891 | 44.4317 | 46.6386 | 48.9117 | 51.2529 | 53.6645 | 56.1483
| Cumulative Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 42.5647 | 75.2594
| Present value of Implementation |  | 2.5948 | 2.2085 | 24.7798 | 24.601 | 22.9124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -77.0964
| Present value of Lifecycle |  | 2.4526 | 2.2995 | 1.8596 | 2.097 | 1.0761 | 0.7587 | 0.71042 | 0.66521 | 0.62288 | 0.58324 | 0.54613 | 0.51137 | 0.47883 | 0.44836 | 0.41983 | 0.39311 | 0.3681 | 0.34467 | 0.32274 | 0.3022 | 0.28297 | 0.26496 | 0.2481 | 0.23231 | 0.21753 | 0.20369 | 0.19072 | 0.17859 | 0.16722 | 0.15658 | -19.4033
| Present value of Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.8567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0611 | 21.9178
Business As Usual
Risk Score: | Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-43 | Lifecycle |  | 3.7841 | 3.9409 | 3.7463 | 3.9035 | 4.0717 | 4.2514 | 4.4435 | 4.649 | 4.8689 | 5.1044 | 5.357 | 5.628 | 5.9142 | 6.2165 | 6.5358 | 6.873 | 7.2294 | 7.606 | 8.0041 | 8.425 | 8.8665 | 9.3311 | 9.82 | 10.3346 | 10.8761 | 11.446 | 12.0458 | 12.677 | 13.3413 | 14.0403 | 223.3315
| Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Residual Value |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
| Net Benefit |  | -3.7841 | -3.9409 | -3.7463 | -3.9035 | -4.0717 | -4.2514 | -4.4435 | -4.649 | -4.8689 | -5.1044 | -5.357 | -5.628 | -5.9142 | -6.2165 | -6.5358 | -6.873 | -7.2294 | -7.606 | -8.0041 | -8.425 | -8.8665 | -9.3311 | -9.82 | -10.3346 | -10.8761 | -11.446 | -12.0458 | -12.677 | -13.3413 | -14.0403 | 223.3315
| Cumulative Net Benefit |  | -3.7841 | -7.7251 | -11.4713 | -15.3748 | -19.4465 | -23.6979 | -28.1414 | -32.7904 | -37.6593 | -42.7637 | -48.1207 | -53.7487 | -59.663 | -65.8795 | -72.4153 | -79.2883 | -86.5177 | -94.1238 | -102.1279 | -110.5529 | -119.4194 | -128.7504 | -138.5704 | -148.905 | -159.7811 | -171.2271 | -183.2729 | -195.9499 | -209.2912 | -223.3315
| D/Cashflow |  | -3.7841 | -3.5918 | -3.1119 | -2.9553 | -2.8095 | -2.6736 | -2.5469 | -2.4286 | -2.3182 | -2.215 | -2.1187 | -2.0287 | -1.943 | -1.8614 | -1.7836 | -1.7095 | -1.6388 | -1.5714 | -1.5072 | -1.4459 | -1.3869 | -1.3302 | -1.2759 | -1.2238 | -1.1739 | -1.1259 | -1.08 | -1.0359 | -0.99356 | -0.95299
| Cumulative D/Cashflow |  | -3.7841 | -7.3759 | -10.4878 | -13.4431 | -16.2526 | -18.9262 | -21.4731 | -23.9017 | -26.2199 | -28.4349 | -30.5536 | -32.5823 | -34.5253 | -36.3866 | -38.1702 | -39.8797 | -41.5185 | -43.09 | -44.5971 | -46.0431 | -47.4299 | -48.7602 | -50.0361 | -51.2599 | -52.4338 | -53.5597 | -54.6396 | -55.6755 | -56.6691 | -57.622
| Cumulative Cashflow |  | 3.7841 | 7.7251 | 11.4713 | 15.3748 | 19.4465 | 23.6979 | 28.1414 | 32.7904 | 37.6593 | 42.7637 | 48.1207 | 53.7487 | 59.663 | 65.8795 | 72.4153 | 79.2883 | 86.5177 | 94.1238 | 102.1279 | 110.5529 | 119.4194 | 128.7504 | 138.5704 | 148.905 | 159.7811 | 171.2271 | 183.2729 | 195.9499 | 209.2912 | 223.3315
| Cumulative Implementation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Lifecycle |  | 3.7841 | 7.7251 | 11.4713 | 15.3748 | 19.4465 | 23.6979 | 28.1414 | 32.7904 | 37.6593 | 42.7637 | 48.1207 | 53.7487 | 59.663 | 65.8795 | 72.4153 | 79.2883 | 86.5177 | 94.1238 | 102.1279 | 110.5529 | 119.4194 | 128.7504 | 138.5704 | 148.905 | 159.7811 | 171.2271 | 183.2729 | 195.9499 | 209.2912 | 223.3315
| Cumulative Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Present value of Implementation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Present value of Lifecycle |  | 3.7841 | 3.5827 | 3.0961 | 2.9328 | 2.781 | 2.6398 | 2.5082 | 2.3857 | 2.2714 | 2.1648 | 2.0653 | 1.9726 | 1.8845 | 1.8007 | 1.7211 | 1.6454 | 1.5733 | 1.5048 | 1.4396 | 1.3776 | 1.3179 | 1.2609 | 1.2063 | 1.1541 | 1.1042 | 1.0564 | 1.0107 | 0.96697 | 0.92513 | 0.88509 | -56.0192
| Present value of Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option F
Risk Score: | Implementation | 10 | 2.763 | 10.2928 | 9.9067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.9625
-29 | Lifecycle |  | 3.7841 | 2.5295 | 3.6616 | 3.8138 | 3.9765 | 4.1505 | 4.3366 | 4.5357 | 4.7488 | 4.9771 | 5.222 | 5.485 | 5.7626 | 6.0557 | 6.3654 | 6.6924 | 7.038 | 7.4031 | 7.789 | 8.197 | 8.6265 | 9.0785 | 9.5542 | 10.0549 | 10.5817 | 11.1362 | 11.7197 | 12.3339 | 12.9802 | 13.6603 | 216.2503
| Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Residual Value |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Benefit |  | -6.5471 | -12.8223 | -13.5683 | -3.8138 | -3.9765 | -4.1505 | -4.3366 | -4.5357 | -4.7488 | -4.9771 | -5.222 | -5.485 | -5.7626 | -6.0557 | -6.3654 | -6.6924 | -7.038 | -7.4031 | -7.789 | -8.197 | -8.6265 | -9.0785 | -9.5542 | -10.0549 | -10.5817 | -11.1362 | -11.7197 | -12.3339 | -12.9802 | -13.6603 | 239.2128
| Cumulative Net Benefit |  | -6.5471 | -19.3695 | -32.9377 | -36.7515 | -40.728 | -44.8785 | -49.2151 | -53.7508 | -58.4996 | -63.4767 | -68.6987 | -74.1836 | -79.9462 | -86.002 | -92.3673 | -99.0597 | -106.0977 | -113.5008 | -121.2898 | -129.4867 | -138.1132 | -147.1917 | -156.7459 | -166.8008 | -177.3825 | -188.5187 | -200.2385 | -212.5723 | -225.5525 | -239.2128
| D/Cashflow |  | -6.5471 | -11.6864 | -11.2707 | -2.8873 | -2.7438 | -2.6102 | -2.4856 | -2.3694 | -2.261 | -2.1598 | -2.0653 | -1.9771 | -1.8932 | -1.8132 | -1.7371 | -1.6645 | -1.5954 | -1.5295 | -1.4667 | -1.4068 | -1.3493 | -1.2942 | -1.2414 | -1.1907 | -1.1421 | -1.0954 | -1.0507 | -1.0078 | -0.96667 | -0.9272
| Cumulative D/Cashflow |  | -6.5471 | -18.2335 | -29.5043 | -32.3916 | -35.1354 | -37.7456 | -40.2313 | -42.6007 | -44.8616 | -47.0214 | -49.0867 | -51.0638 | -52.957 | -54.7702 | -56.5073 | -58.1718 | -59.7672 | -61.2967 | -62.7634 | -64.1702 | -65.5195 | -66.8138 | -68.0551 | -69.2458 | -70.3879 | -71.4834 | -72.5341 | -73.5419 | -74.5086 | -75.4358
| Cumulative Cashflow |  | 6.5471 | 19.3695 | 32.9377 | 36.7515 | 40.728 | 44.8785 | 49.2151 | 53.7508 | 58.4996 | 63.4767 | 68.6987 | 74.1836 | 79.9462 | 86.002 | 92.3673 | 99.0597 | 106.0977 | 113.5008 | 121.2898 | 129.4867 | 138.1132 | 147.1917 | 156.7459 | 166.8008 | 177.3825 | 188.5187 | 200.2385 | 212.5723 | 225.5525 | 239.2128
| Cumulative Implementation |  | 2.763 | 13.0558 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625 | 22.9625
| Cumulative Lifecycle |  | 3.7841 | 6.3136 | 9.9752 | 13.789 | 17.7655 | 21.916 | 26.2526 | 30.7883 | 35.537 | 40.5142 | 45.7361 | 51.2211 | 56.9837 | 63.0394 | 69.4048 | 76.0972 | 83.1352 | 90.5383 | 98.3273 | 106.5242 | 115.1507 | 124.2292 | 133.7834 | 143.8383 | 154.42 | 165.5562 | 177.276 | 189.6098 | 202.59 | 216.2503
| Cumulative Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Present value of Implementation |  | 2.763 | 9.3571 | 8.1873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20.3075
| Present value of Lifecycle |  | 3.7841 | 2.2995 | 3.0261 | 2.8653 | 2.716 | 2.5771 | 2.4479 | 2.3275 | 2.2153 | 2.1108 | 2.0133 | 1.9224 | 1.8361 | 1.7541 | 1.6762 | 1.6021 | 1.5317 | 1.4647 | 1.4009 | 1.3403 | 1.2823 | 1.2268 | 1.1737 | 1.1229 | 1.0743 | 1.0278 | 0.98335 | 0.9408 | 0.90009 | 0.86114 | -53.5048
| Present value of Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option G
Risk Score: | Implementation | 10 | 2.763 | 13.1911 | 13.4549 | 13.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.1751
-21 | Lifecycle |  | 3.7841 | 0.8881 | 0.91819 | 2.6016 | 2.6797 | 2.76 | 2.8428 | 2.9281 | 3.016 | 3.1065 | 3.1996 | 3.2956 | 4.7143 | 4.8557 | 5.0014 | 5.1514 | 5.306 | 5.4652 | 5.6291 | 5.798 | 5.9719 | 6.1511 | 6.3356 | 6.5257 | 6.7215 | 6.9231 | 7.1308 | 7.3447 | 7.5651 | 7.792 | 142.403
| Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Residual Value |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Benefit |  | -6.5471 | -14.0792 | -14.3731 | -16.3677 | -2.6797 | -2.76 | -2.8428 | -2.9281 | -3.016 | -3.1065 | -3.1996 | -3.2956 | -4.7143 | -4.8557 | -5.0014 | -5.1514 | -5.306 | -5.4652 | -5.6291 | -5.798 | -5.9719 | -6.1511 | -6.3356 | -6.5257 | -6.7215 | -6.9231 | -7.1308 | -7.3447 | -7.5651 | -7.792 | 185.5781
| Cumulative Net Benefit |  | -6.5471 | -20.6263 | -34.9995 | -51.3672 | -54.0468 | -56.8069 | -59.6497 | -62.5778 | -65.5938 | -68.7003 | -71.8999 | -75.1955 | -79.9098 | -84.7656 | -89.7669 | -94.9184 | -100.2244 | -105.6895 | -111.3186 | -117.1166 | -123.0886 | -129.2396 | -135.5753 | -142.1009 | -148.8224 | -155.7455 | -162.8763 | -170.221 | -177.7861 | -185.5781
| D/Cashflow |  | -6.5471 | -12.8319 | -11.9393 | -12.3917 | -1.849 | -1.7357 | -1.6294 | -1.5296 | -1.436 | -1.348 | -1.2654 | -1.1879 | -1.5488 | -1.4539 | -1.3649 | -1.2813 | -1.2028 | -1.1291 | -1.06 | -0.99506 | -0.93411 | -0.8769 | -0.82319 | -0.77277 | -0.72544 | -0.68101 | -0.6393 | -0.60015 | -0.56339 | -0.52889
| Cumulative D/Cashflow |  | -6.5471 | -19.3791 | -31.3184 | -43.7101 | -45.5591 | -47.2948 | -48.9243 | -50.4539 | -51.8898 | -53.2379 | -54.5033 | -55.6912 | -57.24 | -58.6939 | -60.0588 | -61.3401 | -62.5429 | -63.672 | -64.732 | -65.727 | -66.6611 | -67.538 | -68.3612 | -69.134 | -69.8595 | -70.5405 | -71.1798 | -71.7799 | -72.3433 | -72.8722
| Cumulative Cashflow |  | 6.5471 | 20.6263 | 34.9995 | 51.3672 | 54.0468 | 56.8069 | 59.6497 | 62.5778 | 65.5938 | 68.7003 | 71.8999 | 75.1955 | 79.9098 | 84.7656 | 89.7669 | 94.9184 | 100.2244 | 105.6895 | 111.3186 | 117.1166 | 123.0886 | 129.2396 | 135.5753 | 142.1009 | 148.8224 | 155.7455 | 162.8763 | 170.221 | 177.7861 | 185.5781
| Cumulative Implementation |  | 2.763 | 15.9541 | 29.409 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751 | 43.1751
| Cumulative Lifecycle |  | 3.7841 | 4.6722 | 5.5904 | 8.192 | 10.8717 | 13.6317 | 16.4746 | 19.4027 | 22.4187 | 25.5251 | 28.7248 | 32.0204 | 36.7347 | 41.5904 | 46.5918 | 51.7433 | 57.0492 | 62.5144 | 68.1435 | 73.9415 | 79.9134 | 86.0645 | 92.4001 | 98.9258 | 105.6473 | 112.5704 | 119.7012 | 127.0459 | 134.6109 | 142.403
| Cumulative Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Present value of Implementation |  | 2.763 | 11.9919 | 11.1198 | 10.3427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36.2174
| Present value of Lifecycle |  | 3.7841 | 0.80736 | 0.75884 | 1.9546 | 1.8302 | 1.7138 | 1.6047 | 1.5026 | 1.407 | 1.3174 | 1.2336 | 1.1551 | 1.5021 | 1.4065 | 1.317 | 1.2332 | 1.1547 | 1.0813 | 1.0124 | 0.94802 | 0.88769 | 0.8312 | 0.77831 | 0.72878 | 0.6824 | 0.63897 | 0.59831 | 0.56024 | 0.52459 | 0.4912 | -35.4464
| Present value of Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option H
Risk Score: | Implementation | 25 | 2.6762 | 0.23903 | 0.32179 | 2.3565 | 19.2669 | 23.1336 | 6.7451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.7392
-4 | Lifecycle |  | 2.6686 | 2.9875 | 3.0943 | 3.2053 | 2.3919 | 1.6599 | 1.3444 | 1.1892 | 1.2248 | 1.2616 | 1.2994 | 1.3384 | 1.3786 | 1.4199 | 1.4625 | 1.5064 | 1.5516 | 1.5981 | 1.6461 | 1.6955 | 1.7463 | 1.7987 | 1.8527 | 1.9083 | 1.9655 | 2.0245 | 2.0852 | 2.1478 | 2.2122 | 2.2786 | 55.9436
| Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26981 | 5.8867
| Residual Value |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.26981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26981
| Net Benefit |  | -5.3448 | -3.2265 | -3.4161 | -5.5618 | -21.6588 | -24.7935 | -8.0896 | 4.4278 | -1.2248 | -1.2616 | -1.2994 | -1.3384 | -1.3786 | -1.4199 | -1.4625 | -1.5064 | -1.5516 | -1.5981 | -1.6461 | -1.6955 | -1.7463 | -1.7987 | -1.8527 | -1.9083 | -1.9655 | -2.0245 | -2.0852 | -2.1478 | -2.2122 | -2.0088 | 104.7961
| Cumulative Net Benefit |  | -5.3448 | -8.5713 | -11.9874 | -17.5492 | -39.208 | -64.0015 | -72.0911 | -67.6633 | -68.8881 | -70.1497 | -71.4491 | -72.7876 | -74.1661 | -75.586 | -77.0486 | -78.555 | -80.1066 | -81.7047 | -83.3508 | -85.0462 | -86.7926 | -88.5913 | -90.4439 | -92.3522 | -94.3177 | -96.3422 | -98.4274 | -100.5751 | -102.7873 | -104.7961
| D/Cashflow |  | -5.3448 | -2.9407 | -2.8376 | -4.2107 | -14.9449 | -15.5923 | -4.6367 | 2.313 | -0.58317 | -0.54745 | -0.51392 | -0.48244 | -0.4529 | -0.42516 | -0.39912 | -0.37467 | -0.35173 | -0.33018 | -0.30996 | -0.29098 | -0.27316 | -0.25643 | -0.24072 | -0.22598 | -0.21214 | -0.19914 | -0.18695 | -0.1755 | -0.16475 | -0.13634
| Cumulative D/Cashflow |  | -5.3448 | -8.2855 | -11.1231 | -15.3338 | -30.2787 | -45.871 | -50.5077 | -48.1946 | -48.7778 | -49.3252 | -49.8391 | -50.3216 | -50.7745 | -51.1996 | -51.5988 | -51.9734 | -52.3252 | -52.6553 | -52.9653 | -53.2563 | -53.5294 | -53.7859 | -54.0266 | -54.2526 | -54.4647 | -54.6638 | -54.8508 | -55.0263 | -55.191 | -55.3274
| Cumulative Cashflow |  | 5.3448 | 8.5713 | 11.9874 | 17.5492 | 39.208 | 64.0015 | 72.0911 | 67.6633 | 68.8881 | 70.1497 | 71.4491 | 72.7876 | 74.1661 | 75.586 | 77.0486 | 78.555 | 80.1066 | 81.7047 | 83.3508 | 85.0462 | 86.7926 | 88.5913 | 90.4439 | 92.3522 | 94.3177 | 96.3422 | 98.4274 | 100.5751 | 102.7873 | 104.7961
| Cumulative Implementation |  | 2.6762 | 2.9152 | 3.237 | 5.5935 | 24.8604 | 47.9941 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392 | 54.7392
| Cumulative Lifecycle |  | 2.6686 | 5.6561 | 8.7504 | 11.9557 | 14.3476 | 16.0075 | 17.3519 | 18.541 | 19.7659 | 21.0274 | 22.3269 | 23.6653 | 25.0439 | 26.4638 | 27.9263 | 29.4327 | 30.9843 | 32.5824 | 34.2285 | 35.924 | 37.6703 | 39.469 | 41.3217 | 43.2299 | 45.1954 | 47.2199 | 49.3051 | 51.4529 | 53.6651 | 55.9436
| Cumulative Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.6169 | 5.8867
| Present value of Implementation |  | 2.6762 | 0.2173 | 0.26594 | 1.7705 | 13.1596 | 14.3642 | 3.8075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36.2611
| Present value of Lifecycle |  | 2.6686 | 2.7159 | 2.5573 | 2.4082 | 1.6337 | 1.0307 | 0.75888 | 0.61023 | 0.5714 | 0.53503 | 0.50099 | 0.46911 | 0.43925 | 0.4113 | 0.38513 | 0.36062 | 0.33767 | 0.31618 | 0.29606 | 0.27722 | 0.25958 | 0.24306 | 0.22759 | 0.21311 | 0.19955 | 0.18685 | 0.17496 | 0.16383 | 0.1534 | 0.14364 | -21.2489
| Present value of Benefits |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017008 | 2.8994