## Overview
Overview of this model
This model is a supporting document to the 'TransGrid - PEC Corporate and Network Overhead forecast' document, dated September 2020 This model substantiates values documented in the report in relation to the ‘Corporate and Network Overhead’ capital expenditure (Capex) for Project Energy Connect (PEC) for the remainder of the current regulatory period 2018-19 to 2023-24 (2018-24).
Model structure / Naviation instructions
Below outlines the key components of this model which map to the respective section of the written report (for example, section 4 of the report relates to 'Works Delivery' and this is reflected in the worksheet titled 's4. Works Delivery'.
Reference to PEC Forecast Indirect Capex CPA report | Header worksheets | Description of worksheet | Key Contact
Section 7 | Key assumptions | The Key assumptions worksheet outlines the key assumptions and rates which apply across the below listed categories. With the exception of allocation rates applied to discrete major projects, the rates applied highlighted in Yellow shade are global assumptions as referenced in the Key assumptions worksheet. | Manager People & Culture Operations - TransGrid; Manager, Management Accounting - TransGrid; Service Transition Manager
Section 2 | s2. Historical Indirect Capex | The s2. Historical Indirect Capex worksheet provides a summarised view of the 'costs incurred to date' (i.e. the 'Actuals') that have already been incurred to progress the PEC project. The Actuals have been incurred since FY18 through to 31 July 2020 (afterwhich the PEC Forecast costs commence, i.e. from 1 August 2020). | Manager, Management Accounting - TransGrid
Section 3 | s3. PEC Summary forecast | The s3. PEC Summary forecast worksheet consolidates details from Section 4 through to Section 9 to provide a summarised overview of the total forecast corporate and network overhead costs for PEC through to the commissioning of the project. Further capex is expected post commissioning which is separately identified in the summary. | Manager, Management Accounting - TransGrid
Section 4 | s4. Works Delivery | The s4. Works Delivery worsheet provides a summarised view of the forecast costs of the Works Delivery team to complete the PEC project. The Works Delivery team have provided supporting workpapers, including the Works Deliery project schedule which supports the detailed calculations. | PEC Project Director - TransGrid; Service Management, Works Delivery - TransGrid; Senior Program Manager, Major Projects Delivery - TransGrid
| - Works Delivery Res Cost | This worksheet summarises details from the WD Labour Data worksheet and also leverages information from the Works Delivery Labour FTEs worksheet which drive calculations for the labour-related costs (i.e. recruitment, training and IT Hardware). | Manager, Management Accounting - TransGrid
| - WD Labour Data | This worksheet captures the Works Delivery Bottom-up Labour Estimate, provided by the PEC Project team. | PEC Project Director - TransGrid
Section 5 | s5. Project Development | The s5. Project Development worksheet provides a summarised view of Project Development costs. Details of cost estimates have been captured in the supporting PD-Labour(&related) and PD-Non-Labour worksheets. | PEC Project Director - TransGrid; PEC Senior Project Manager - TransGrid
| - PD-Labour(&related) | This worksheet captures the Project Development labour and labour related resource requirements to support the delivery of the PEC project. | Manager, Management Accounting - TransGrid
| - PD-NonLabour | This worksheet captures the Project Development non-labour related resource requirements to support the delivery of the PEC project. | Manager, Management Accounting - TransGrid
Section 6 | s6. Land & Environment | The s6. Land & Environment worksheet provides a summarised view of the Land and Environment related costs. Details of cost estimates have been captured in the supporting L&E-Labour(&related) and L&E-Non-Labour worksheets. | Property Portfolio Manager - TransGrid
| - L&E-Labour(&related) | This worksheet captures the Land and Environment labour and labour related resource requirements to support the delivery of the PEC project. | Manager, Management Accounting - TransGrid
| - L&E-NonLabour | This worksheet captures the Land and Environment non-labour related resource requirements to support the delivery of the PEC project. | Manager, Management Accounting - TransGrid
Section 7 | s7. Stakeholder & Comm Egmt | The s7. Stakeholder & Comm Egmt worksheet provides a summarised view of the Stakeholder and Community Engagement related costs. Details of cost estimates have been captured in the supporting SHC-Labour(&related) and SHC-Non-Labour worksheets. | Community Engagement Manager- TransGrid
| - SHC-Labour(&related) | This worksheet captures the Stakeholder and Community Engagement labour and labour related resource requirements to support the delivery of the PEC project. | Manager, Management Accounting - TransGrid
| - SHC-NonLabour | This worksheet captures the Stakeholder and Community Engagement non-labour related resource requirements to support the delivery of the PEC project. | Manager, Management Accounting - TransGrid
Section 8 | s8. Insurance | Worksheet s8 Insurance contains calculations relating to Insurance required during the Construction period of PEC. No summary sheet is required as there is only a single line item listed for Insurance. | Head of Risk - TransGrid
Section 9 | s9. Bidder Payments | Worksheet s9 Bidder Payments contains calculations relating to bidder payments for PEC. No summary sheet is required as there is only a single line item listed for Bidder Payments. | PEC Project Director - TransGrid; PEC Senior Project Manager - TransGrid

## Key assumptions
RATES / ASSUMPTIONS
The following rates have been applied across the categories of cost estimates.
Any changes should be made in the Black cells which link to the corresponding calculations
Escalation and Labour Rate restatement
Costs have been collected in current year rates.
TransGrid's standard labour rates as at 1 July 2019 have been used in labour costing estimates.
In order to restate these figures in 2017/8 costs, discounts have been applied as follows:
| Labour real cost de-escalation | -0.8111% | 0.8111% | Applied to all labour costs to restate the cost estimate in 2017/8 rates
| CPI discount | -1.239% | 1.239% | Applied to all non-labour costs
| CPI discount - Labour & Labour related | -1.593% | 1.593% | Applied to Labour and Labour related costs post de-escalation
Allocation of costs to Major Projects
Project | Major Projects Portfolio | Value | % of Portfolio
A | Project Energy Connect (PEC) | 1500000000 | 45.73%
B | Hume Link (Snowy 2.0) | 1500000000 | 45.73%
C | Queensland Interconnector (QNI) | 180000000 | 5.488%
D | Victorian Interconnector (VNI) | 50000000 | 1.524%
|  | 3280000000 | 100%
Salary assumptions
| Oncosts - contract | 24%
| Oncosts - Enterprise Agreement | 41%
Recruitment fees assumptions
| Recruitment fees as % of annual salary | 15%
| Roles recruited using external recruiter | 50%
Training cost assumptions
| Training cost per annum per employee | 1500
Travel rate assumptions
| Cost per return flight to PEC sites | 1000
| ATO rates for Accom & Meals | 293.65
IT hardware cost assumptions
| IT hardware cost per annum per employee | 2650
Direct cost assumptions
| Share of labour costs that are direct | 65%
| Share of labour related costs that are direct | 65%
| Share of non-labour costs that are direct | 0%
Rates per capex forecast model
Rates
|  |  | 2019 | 2020 | 2021 | 2022 | 2023
| CPI escalation |  | 1.593% | -0.3484% | 2.45% | 2.45% | 2.45%
| Labour Rate escalation |  | 0.8111% | 0.9547% | 1.206% | 1.464% | 1.488%
Cumulative factors
|  | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| Cumulative CPI | 1 | 1.0159 | 1.0124 | 1.0372 | 1.0626 | 1.0886
| Cumulative Labour rate | 1 | 1.0081 | 1.0177 | 1.03 | 1.0451 | 1.0606
CPI Adjustment |  | 2018/9 | 2019/20 | June18 to Jul20
| Actual inflation rate | 1.593% | -0.3484% | 1.239%
(based on RBA CPI rates by quarter)

## s2. Historical Indirect Capex
Historical Labour and Indirect capex costs incurred between 1 July 2018 to 1 August 2020:
|  | Nominal values |  |  |  | Restatement to 30 June 2018 Labour rates |  |  |  | Restatement to 2017/8 dollars |  |  |  | ROUNDED $ M
| s2. Historical Indirect Capex | 2018-19 | 2019-20 | 2020 - 21 (July 20) | Total Historical Labour and Indirect Capex | 2018-19 | 2019-20 | 2020 - 21 (July 20) | Total Historical Labour and Indirect Capex | 2018-19 | 2019-20 | 2020 - 21 (July 20) | Total Historical Labour and Indirect Capex | 2018-19 | 2019-20 | 2020 - 21 (July 20) | Total Historical Labour and Indirect Capex
| Total labour | 1458997.17 | 4571709 | 397815 | 1856812.17 | 1447258.4267 | 4534926.1195 | 390882.7016 | 6373067.2478 | 1424566.2214 | 4479428.7719 | 386099.172 | 6290094.1653 | 1.4246 | 4.4794 | 0.3861 | 6.2901
| Labour Related | 114749.6 | 201293 | 9285 | 124034.6 | 114749.6 | 199673.4445 | 9123.2002 | 123872.8002 | 112950.3902 | 198829.6241 | 9171.3724 | 122121.7626 | 0.11295 | 0.19883 | 0.0091714 | 0.12212
| Travel | 88217 | 165142 | 4030 | 92247 | 88217 | 165142 | 4030 | 257389 | 86833.8066 | 163121.0315 | 3980.6818 | 253935.5199 | 0.086834 | 0.16312 | 0.0039807 | 0.25394
| Sustenance | 26532.6 | 21365 | 5255 | 31787.6 | 26532.6 | 21365 | 5255 | 53152.6 | 26116.5836 | 21103.5402 | 5190.6906 | 52410.8144 | 0.026117 | 0.021104 | 0.0051907 | 0.052411
| Training |  | 14786 | 0 | 0 | 0 | 14786 | 0 | 14786 | 0 | 14605.0524 | 0 | 14605.0524
| Non-Labour | 1919368.81 | 17948437 | 1617198 | 3536566.81 | 1919368.81 | 17804028.1557 | 1589016.8125 | 3508385.6225 | 1889274.1771 | 17728788.2955 | 1597407.1154 | 3486681.2925 | 1.8893 | 17.7288 | 1.5974 | 3.4867
| Legal | 61386.7 | 1727458 | 14835 | 76221.7 | 61386.7 | 1727458 | 14835 | 1803679.7 | 60424.1908 | 1706317.7797 | 14653.4528 | 1781395.4233 | 0.060424 | 1.7063 | 0.014653 | 1.7814
| O/S – consulting | 510976.26 | 9722788 | 881725 | 1392701.26 | 510976.26 | 9722788 | 881725 | 11115489.26 | 502964.4371 | 9603802.8322 | 870934.6591 | 10977701.9284 | 0.50296 | 9.6038 | 0.87093 | 10.9777
| O/S – engineering | 1046646.62 | 3859851 | 288876 | 1335522.62 | 1046646.62 | 3859851 | 288876 | 5195373.62 | 1030235.7845 | 3812615.0612 | 285340.8042 | 5128191.6499 | 1.0302 | 3.8126 | 0.28534 | 5.1282
| O/S – network / property | 249469.23 | 646465 | 119389 | 368858.23 | 249469.23 | 646465 | 119389 | 1015323.23 | 245557.6916 | 638553.715 | 117927.9458 | 1002039.3524 | 0.24556 | 0.63855 | 0.11793 | 1.002
| Other | 50890 | 1991875 | 312373 | 363263 | 50890 | 1991875 | 312373 | 2355138 | 50092.0732 | 1967498.9073 | 308550.2535 | 2326141.234 | 0.050092 | 1.9675 | 0.30855 | 2.3261
| Total costs incurred | 3493115.58 | 22721439 | 2024298 | 5517413.58 | 3481376.8367 | 22538627.7197 | 1989022.7143 | 5470399.551 | 3426790.7887 | 22407046.6915 | 1992677.6598 | 5419468.4485 | 3.4268 | 22.407 | 1.9927 | 5.4195

## FCST O-M (hidden)
2019/20
Actual to Sept 19 |  |  |  | #REF!
Previous forecast Oct19 - July20 |  |  |  | #REF!
Total |  |  |  | #REF!
|  |  |  | Forecast… | Actuals
| Oct 19 - Mar 20 Period | Unphased | Apr - Jun 20 Period | 2019/20 | Oct19-Mar20 ACTUALS | Current Forecast Apr 20 - | Revised forecast Apr20 -
Works Delivery
Labour | #REF! |  | #REF! | 0 |  | #REF! | #REF!
Labour Related |  | 0 |  | 0
Project Development | [6 empty] | 10814341
Labour | #REF! |  | #REF! | #REF! | 1757881 | #REF! | 10791530
Labour related - recruitment | #REF! |  | #REF! | 0
Labour related - training | #REF! |  | #REF! | 0 | 14786
Labour related - office | #REF! |  | #REF! | 0 | 121356
Labour related - travel | #REF! |  | #REF! | 0 | 148506
Geo technical |  | #REF! |  | 0 | 3514145
Legal fees | #REF! | #REF! | 60000 | 0 | 984496
Consulting costs |  | #REF! |  | 0
Land & Environment
Labour | #REF! |  | #REF! | 0
Labour related costs - recruitment & training | #REF! |  | #REF! | 0
travel | #REF! |  | #REF! | 0
Consulting |  | #REF! | #REF! | #REF!
EIS | #REF! |  | #REF! | #REF! | 1184987
Non-phased consulting |  | #REF! |  | #REF! | 2918907
Stakeholder & Comms
Labour | #REF! |  | #REF! | 0
travel | #REF! |  | #REF! | 0
Community engagement | #REF! |  | #REF! | 0 | 371000
Insurance | #REF! |  | #REF! | 0
Bidder Payments |  | #REF! |  | 8750000
Miscellaneous |  |  |  |  | 468307
Total Forecast - Nominal | #REF! | #REF! | #REF! | #REF! | 11484371
Restated |  |  |  | #REF!
Labour | #REF! | 0 | #REF!
Non-Labour | #REF! | #REF! | #REF!

## FCST O-M (2) (hidden)
2019/20
| Actual to Sept 19 | #REF!
| Previous forecast Oct19 - July20 | #REF!
| Total | #REF!
|  | Current Forecast… |  |  |  | Q2/3 FY20 |  |  | Q4FY20 - forecast comparison
|  | 2019/20 | Oct 19 - Mar 20 Period | Unphased | Apr - Jun 20 Period | Q2-Q3 - Forecast | Q2-Q3 Actuals | Variance | Current Forecast Apr 20 - | Forecast per Project Schedule Apr20 - | Variance
LABOUR
WD | Labour | 0 | #REF! |  | #REF! | #REF! |  | #REF! | #REF! | 42842733 | #REF!
L&E | Labour | 0 | #REF! |  | #REF! | #REF! |  | #REF! | #REF! |  | #REF!
PD | Labour | #REF! | #REF! |  | #REF! | #REF! | 1757881 | #REF! | #REF! | 10791530 | #REF!
SH&C | Labour | 0 | #REF! |  | #REF! | #REF! |  | #REF! | #REF! | 10814341 | #REF!
|  | #REF! | #REF! | 0 | #REF! | #REF! | 1757881 | #REF! | #REF! | 64448604 | #REF!
Project Development
WD | Labour Related | 0 |  | 0
| Labour related - recruitment | 0 | #REF! |  | #REF!
| Labour related - training | 0 | #REF! |  | #REF! |  | 14786
| Labour related - office | 0 | #REF! |  | #REF! |  | 121356
| Labour related - travel | 0 | #REF! |  | #REF! |  | 148506
| Geo technical | 0 |  | #REF! |  |  | 3514145
| Legal fees | 0 | #REF! | #REF! | 60000 |  | 984496
| Consulting costs | 0 |  | #REF!
Land & Environment
| Labour related costs - recruitment & training | 0 | #REF! |  | #REF!
| travel | 0 | #REF! |  | #REF!
| Consulting | #REF! |  | #REF! | #REF!
| EIS | #REF! | #REF! |  | #REF! |  | 1184987
| Non-phased consulting | #REF! |  | #REF! |  |  | 2918907
Stakeholder & Comms
| travel | 0 | #REF! |  | #REF!
| Community engagement | 0 | #REF! |  | #REF! |  | 371000
| Insurance | 0 | #REF! |  | #REF!
| Bidder Payments | 8750000 |  | #REF!
| Miscellaneous | [5 empty] | 468307
| Total Forecast - Nominal | #REF! | #REF! | #REF! | #REF! |  | 13242252
| Restated | #REF!
| Labour |  | #REF! | 0 | #REF!
| Non-Labour |  | #REF! | #REF! | #REF!

## Oct-Mar (hidden)
Forecast costs - October 19 to March 20
|  | Per Forecast | Per Actuals | Variance | Comments on Forecast: | Comments on Actuals
Works Delivery
| Labour | #REF! |  | #REF! | Costs in Oct - Jan period relate to 4 roles, with Feb-March costs much higher (X roles). Project timing has been delayed, impacting the phasing of these roles. Hence, majority of this is likely to be a timing difference.
| Labour related costs | 0 |  | 0 | Note - the fcast is the full 2019/20 year costs (it is not calculated by month).
|  | #REF! |  | #REF!
Project Development
| Labour | #REF! | 1757881 | #REF! | X roles anticipated to be in place from 1 October, many for duration of project.
| Labour related - recruitment | #REF! |  | #REF!
| Labour related - training | #REF! | 14786 | #REF!
| Labour related - office | #REF! | 121356 | #REF!
| Labour related - travel | #REF! | 148506 | #REF!
| Legal fees | #REF! | 984496 | #REF! |  | Allens costs
0
| Consulting costs | #REF! | 3514145 | #REF! | Note - the fcast is the full 2019/20 year costs (it is not calculated by month).
| Geo technical | #REF! |  | #REF! | Note - the fcast is the full 2019/20 year costs (it is not calculated by month).
|  | #REF! | 6541170 | #REF!
Land & Environment
| Labour | #REF! |  | #REF!
| Labour related costs - recruitment & training | #REF! |  | #REF!
| travel | #REF! |  | #REF!
0
| Consulting | #REF! |  | #REF! | Note - the fcast is the full 2019/20 year costs (it is not calculated by month).
| EIS | #REF! | 1184987 | #REF! |  | WSP costs for Enviro Assessment
| Non-phased consulting | #REF! | 2918907 | #REF! | Note - the fcast is the full 2019/20 year costs (it is not calculated by month).
|  | #REF! | 4103894 | #REF!
Stakeholder & Comms |  |  |  | 0
| Labour | #REF! |  | #REF!
| Labour related costs - recruitment & training |  |  | 0
| travel | #REF! |  | #REF!
0
| Community engagement | #REF! | 371000 | #REF! | Phased from Nov - ongoing | Kathy Jones consulting costs
0
0
0
|  | #REF! | 371000 | #REF!
Insurance |  | #REF! |  | #REF! | Total amount was estimated, then phased over duration of project. Based on this, there is an argument for rephasing.
Bidder Payments |  | #REF! |  | #REF! | Not phased - this is the total Year 1 cost
MISC |  |  | 468307 | 468307 |  | FTI and MBB costs have been allocated to Misc account.
Total |  | #REF! | 11484371 | #REF!
Excl Bidder Pmts & Insurance |  | #REF! | 11484371 | #REF!
| Labour | #REF! | 1757881 | #REF!
| Ex Labour | #REF! | 9726490 | #REF!
| Directly related to March - Sept | #REF!
| Not phased | #REF!
32001486

## s3. PEC Summary forecast
Summary PEC Indirect Capex costs
Total - Forecast and Actual TransGrid Labour and Indirect Costs
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY19-FY23 | Post commissioning costs (FY24) | TOTAL FY19-FY24 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY19-FY23 | Post commissioning costs (FY24) | TOTAL FY19-FY24
| Total estimate: Actuals + Forecast | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Historical Indirect Capex - actuals | 3426790.7887 | 22407046.6915 | 1992677.6598 |  |  | 27826515.14 |  | 27826515.14 |  | 3.4268 | 22.407 | 1.9927 | 0 | 0 | 27.8265 | 0 | 27.8265
| Forecast |  | 0 | 45832095.7664 | 27898866.1697 | 23920218.8131 | 97651180.7492 | 10322516.8778 | 107973697.627 |  | 0 | 0 | 45.8321 | 27.8989 | 23.9202 | 97.6512 | 10.3225 | 107.9737
| Total estimate of PEC Costs - Actuals + Forecast | 3426790.7887 | 22407046.6915 | 47824773.4262 | 27898866.1697 | 23920218.8131 | 125477695.8892 | 10322516.8778 | 135800212.767 |  | 3.4268 | 22.407 | 47.8248 | 27.8989 | 23.9202 | 125.4777 | 10.3225 | 135.8002
Forecast TransGrid Labour and Indirect Costs
| Total Estimate of Incremental Corporate Costs | 107973697.627 | 137796921.252
| Works Delivery | 19920639.307
| Project Development | 40600886.4898
| Land and Environment Costs | 18376538.5705
| Stakeholder and Community Engagement | 8181454.88
| Insurance Costs | 8590171.4111
| Bidder Payments and Data Portal | 12304006.9686
Rounded ($M)
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL | CHECK: |  | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL
| Phased |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Works Delivery |  | 0 | 2200773.1296 | 6044502.7639 | 7718980.179 | 15964256.0725 | 3956383.2344 | 19920639.307 | 0 |  | 0 | 2.2008 | 6.0445 | 7.719 | 15.9643 | 3.9564 | 19.9206 | 18.45%
| Project Development |  | 0 | 13916708.0839 | 10905831.4608 | 10449310.5274 | 35271850.0722 | 5329036.4176 | 40600886.4898 | 0 |  | 0 | 13.9167 | 10.9058 | 10.4493 | 35.2719 | 5.329 | 40.6009 | 37.6%
| Other indirect Capex |  | 0 | 29714614.5529 | 10948531.9449 | 5751928.1067 | 46415074.6045 | 1037097.2258 | 47452171.8303 |  |  | 0 | 29.7146 | 10.9485 | 5.7519 | 46.4151 | 1.0371 | 47.4522 | 43.95%
| Land and Environment Costs |  | 0 | 10990334.2254 | 5724673.8356 | 1172845.0655 | 17887853.1266 | 488685.444 | 18376538.5705 | 0 |  | 0 | 10.9903 | 5.7247 | 1.1728 | 17.8879 | 0.48869 | 18.3765 | 17.02%
| Stakeholder and Community Engagement |  | 0 | 3893752.3555 | 2192032.9054 | 1547257.8373 | 7633043.0982 | 548411.7818 | 8181454.88 | 0 |  | 0 | 3.8938 | 2.192 | 1.5473 | 7.633 | 0.54841 | 8.1815 | 7.577%
| Insurance Costs |  | 0 | 2526521.0033 | 3031825.2039 | 3031825.2039 | 8590171.4111 | 0 | 8590171.4111 | 0 |  | 0 | 2.5265 | 3.0318 | 3.0318 | 8.5902 | 0 | 8.5902 | 7.956%
| Bidder Payments and Data Portal |  | 0 | 12304006.9686 | 0 | 0 | 12304006.9686 | 0 | 12304006.9686 | 0 |  | 0 | 12.304 | 0 | 0 | 12.304 | 0 | 12.304 | 11.4%
| Total forecast indirect costs |  | 0 | 45832095.7664 | 27898866.1697 | 23920218.8131 | 97651180.7492 | 10322516.8778 | 107973697.627 |  |  | 0 | 45.8321 | 27.8989 | 23.9202 | 97.6512 | 10.3225 | 107.9737 | 100%
|  | 2018-9 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL |  |  | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL
| Labour component |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Works Delivery |  | 0 | 2118736.1946 | 5606859.8854 | 7338758.4306 | 15064354.5105 | 3819422.0981 | 18883776.6086 |  |  | 0 | 2.1187 | 5.6069 | 7.3388 | 15.0644 | 3.8194 | 18.8838
| Project Development |  | 0 | 8401764.4398 | 8179326.7086 | 8230600.4243 | 24811691.5727 | 3856898.0172 | 28668589.5899 |  |  | 0 | 8.4018 | 8.1793 | 8.2306 | 24.8117 | 3.8569 | 28.6686
| Other indirect Capex |  | 0 | 3101024.4337 | 2277780.4278 | 1852717.1 | 7231521.9615 | 898700.4916 | 8130222.4531 |  |  | 0 | 3.101 | 2.2778 | 1.8527 | 7.2315 | 0.8987 | 8.1302
| Land and Environment Costs |  | 0 | 2129287.0606 | 1471173.3601 | 1172845.0655 | 4773305.4863 | 488685.444 | 5261990.9302 |  |  | 0 | 2.1293 | 1.4712 | 1.1728 | 4.7733 | 0.48869 | 5.262
| Stakeholder and Community Engagement |  | 0 | 971737.3731 | 806607.0677 | 679872.0344 | 2458216.4752 | 410015.0476 | 2868231.5229 |  |  | 0 | 0.97174 | 0.80661 | 0.67987 | 2.4582 | 0.41002 | 2.8682
| Insurance Costs | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bidder Payments and Data Portal | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total forecast Labour and Labour related costs |  | 0 | 13621525.0681 | 16063967.0218 | 17422075.9549 | 47107568.0447 | 8575020.6068 | 55682588.6515 |  |  | 0 | 13.6215 | 16.064 | 17.4221 | 47.1076 | 8.575 | 55.6826
| Total forecast Non-Labour costs |  | 0 | 32210570.6983 | 11834899.1479 | 6498142.8583 | 50543612.7045 | 1747496.271 | 52291108.9755 |  |  | 0 | 32.2106 | 11.8349 | 6.4981 | 50.5436 | 1.7475 | 52.2911
Forecast TransGrid Labour and Indirect Costs
|  | Forecast TransGrid Labour and Indirect Costs | [8 empty] | Forecast Direct Costs | [8 empty] | Forecast Indirect Costs
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL FY19-FY24 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL FY19-FY24 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL FY20-FY23
| Labour component | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ |  |  |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Works Delivery | 0 | 0 | 2118736.1946 | 5606859.8854 | 7338758.4306 | 15064354.5105 | 3819422.0981 | 18883776.6086 |  | 0 | 0 | 1377178.5265 | 3644458.9255 | 4770192.9799 | 9791830.4318 | 2482624.3637 | 12274454.7956 |  | 0 | 0 | 741557.6681 | 1962400.9599 | 2568565.4507 | 5272524.0787 | 1336797.7343 | 6609321.813
| Project Development |  | 0 | 8401764.4398 | 8179326.7086 | 8230600.4243 | 24811691.5727 | 3856898.0172 | 28668589.5899 |  | 0 | 0 | 5461146.8859 | 5316562.3606 | 5349890.2758 | 16127599.5223 | 2506983.7111 | 18634583.2334 |  | 0 | 0 | 2940617.5539 | 2862764.348 | 2880710.1485 | 8684092.0504 | 1349914.306 | 10034006.3565
| Other Indirect Capex | 0 | 0 | 3101024.4337 | 2277780.4278 | 1852717.1 | 7231521.9615 | 898700.4916 | 8130222.4531 |  | 0 | 0 | 2015665.8819 | 1480557.2781 | 1204266.115 | 4700489.275 | 584155.3195 | 5284644.5945 |  | 0 | 0 | 1085358.5518 | 797223.1497 | 648450.985 | 2531032.6865 | 314545.1721 | 2845577.8586
| Land and Environment Costs |  | 0 | 2129287.0606 | 1471173.3601 | 1172845.0655 | 4773305.4863 | 488685.444 | 5261990.9302 |  | 0 | 0 | 1384036.5894 | 956262.6841 | 762349.2926 | 3102648.5661 | 317645.5386 | 3420294.1047 |  | 0 | 0 | 745250.4712 | 514910.676 | 410495.7729 | 1670656.9202 | 171039.9054 | 1841696.8256
| Stakeholder and Community Engagement |  | 0 | 971737.3731 | 806607.0677 | 679872.0344 | 2458216.4752 | 410015.0476 | 2868231.5229 |  | 0 | 0 | 631629.2925 | 524294.594 | 441916.8224 | 1597840.7089 | 266509.781 | 1864350.4899 |  | 0 | 0 | 340108.0806 | 282312.4737 | 237955.2121 | 860375.7663 | 143505.2667 | 1003881.033
| Insurance Costs | [5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bidder Payments | [5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| Total | 0 | 0 | 13621525.0681 | 16063967.0218 | 17422075.9549 | 47107568.0447 | 8575020.6068 | 55682588.6515 |  | 0 | 0 | 8853991.2943 | 10441578.5641 | 11324349.3707 | 30619919.2291 | 5573763.3944 | 36193682.6235 |  | 0 | 0 | 4767533.7738 | 5622388.4576 | 6097726.5842 | 16487648.8157 | 3001257.2124 | 19488906.028
[18 empty] | 65% | [8 empty] | 35%
Labour Related component
| Works Delivery |  | 0 | 82036.935 | 437642.8786 | 380221.7484 | 899901.562 | 136961.1364 | 1036862.6984 | ` | 0 | 0 | 53324.0078 | 284467.8711 | 247144.1365 | 584936.0153 | 89024.7386 | 673960.7539 |  | 0 | 0 | 28712.9273 | 153175.0075 | 133077.6119 | 314965.5467 | 47936.3977 | 362901.9444
| Project Development |  | 0 | 1936343.4943 | 1368142.3829 | 1332821.6014 | 4637307.4785 | 881546.0659 | 5518853.5445 |  | 0 | 0 | 1258623.2713 | 889292.5489 | 866334.0409 | 3014249.8611 | 573004.9429 | 3587254.8039 |  | 0 | 0 | 677720.223 | 478849.834 | 466487.5605 | 1623057.6175 | 308541.1231 | 1931598.7406
| Other Indirect Capex | 0 | 0 | 517347.804 | 389883.3864 | 178361.4126 | 1085592.603 | 89180.7063 | 1174773.3093 |  | 0 | 0 | 336276.0726 | 253424.2011 | 115934.9182 | 705635.1919 | 57967.4591 | 763602.651 |  | 0 | 0 | 181071.7314 | 136459.1852 | 62426.4944 | 379957.411 | 31213.2472 | 411170.6582
| Land and Environment Costs |  | 0 | 353849.8425 | 211521.9738 | 0 | 565371.8163 | 0 | 565371.8163 |  | 0 | 0 | 230002.3976 | 137489.283 | 0 | 367491.6806 | 0 | 367491.6806 |  | 0 | 0 | 123847.4449 | 74032.6908 | 0 | 197880.1357 | 0 | 197880.1357
| Stakeholder and Community Engagement |  | 0 | 163497.9615 | 178361.4126 | 178361.4126 | 520220.7867 | 89180.7063 | 609401.493 |  | 0 | 0 | 106273.675 | 115934.9182 | 115934.9182 | 338143.5114 | 57967.4591 | 396110.9705 |  | 0 | 0 | 57224.2865 | 62426.4944 | 62426.4944 | 182077.2753 | 31213.2472 | 213290.5226
| Insurance Costs | [5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bidder Payments | [5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| Total | 0 | 0 | 2535728.2333 | 2195668.6478 | 1891404.7624 | 6622801.6435 | 1107687.9086 | 7730489.5521 |  | 0 | 0 | 1648223.3517 | 1427184.6211 | 1229413.0955 | 4304821.0683 | 719997.1406 | 5024818.2089 |  | 0 | 0 | 887504.8817 | 768484.0267 | 661991.6668 | 2317980.5752 | 387690.768 | 2705671.3432
[18 empty] | 65% | [8 empty] | 35%
Non-Labour component
| Works Delivery |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Development |  | 0 | 3578600.1498 | 1358362.3693 | 885888.5017 | 5822851.0209 | 590592.3345 | 6413443.3554 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3578600.1498 | 1358362.3693 | 885888.5017 | 5822851.0209 | 590592.3345 | 6413443.3554
| Other Indirect Capex | 0 | 0 | 26096242.3151 | 8280868.1308 | 3720849.5942 | 38097960.0401 | 49216.0279 | 38147176.0679 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 26096242.3151 | 8280868.1308 | 3720849.5942 | 38097960.0401 | 49216.0279 | 38147176.0679
| Land and Environment Costs |  | 0 | 8507197.3223 | 4041978.5017 | 0 | 12549175.824 | 0 | 12549175.824 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8507197.3223 | 4041978.5017 | 0 | 12549175.824 | 0 | 12549175.824
| Stakeholder and Community Engagement |  | 0 | 2758517.0209 | 1207064.4251 | 689024.3902 | 4654605.8362 | 49216.0279 | 4703821.8641 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2758517.0209 | 1207064.4251 | 689024.3902 | 4654605.8362 | 49216.0279 | 4703821.8641
| Insurance Costs |  | 0 | 2526521.0033 | 3031825.2039 | 3031825.2039 | 8590171.4111 | 0 | 8590171.4111 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2526521.0033 | 3031825.2039 | 3031825.2039 | 8590171.4111 | 0 | 8590171.4111
| Bidder Payments |  | 0 | 12304006.9686 | 0 | 0 | 12304006.9686 |  | 12304006.9686 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 12304006.9686 | 0 | 0 | 12304006.9686 | 0 | 12304006.9686
| Total | 0 | 0 | 29674842.465 | 9639230.5001 | 4606738.0959 | 43920811.061 | 639808.3624 | 44560619.4233 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 29674842.465 | 9639230.5001 | 4606738.0959 | 43920811.061 | 639808.3624 | 44560619.4233
[18 empty] | 0% | [8 empty] | 100%
Total Labour and Non-Labour
| Total | 0 | 0 | 45832095.7664 | 27898866.1697 | 23920218.8131 | 97651180.7492 | 10322516.8778 | 107973697.627 |  | 0 | 0 | 10502214.6459 | 11868763.1852 | 12553762.4662 | 34924740.2974 | 6293760.535 | 41218500.8324 |  | 0 | 0 | 35329881.1205 | 16030102.9845 | 11366456.3469 | 62726440.4519 | 4028756.3428 | 66755196.7946
Actual TransGrid Labour and Indirect Costs
|  | Actual TransGrid Labour and Indirect Costs | [8 empty] | Actual Direct Costs | [8 empty] | Actual Indirect Costs
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL FY19-FY24 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL FY19-FY24 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY20-FY23 | Post commissioning costs (FY24) | TOTAL FY20-FY23
| Labour component | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Labour | 1424566.2214 | 4479428.7719 | 386099.172 | 0 | 0 | 6290094.1653 | 0 | 6290094.1653 |  | 925968.0439 | 2911628.7017 | 250964.4618 | 0 | 0 | 4088561.2075 | 0 | 4088561.2075 |  | 498598.1775 | 1567800.0702 | 135134.7102 | 0 | 0 | 2201532.9579 | 0 | 2201532.9579
| Labour Related | 112950.3902 | 198829.6241 | 9171.3724 | 0 | 0 | 320951.3867 | 0 | 320951.3867 |  | 73417.7537 | 129239.2557 | 5961.392 | 0 | 0 | 208618.4014 | 0 | 208618.4014 |  | 39532.6366 | 69590.3684 | 3209.9803 | 0 | 0 | 112332.9854 | 0 | 112332.9854
| Non-Labour | 1889274.1771 | 17728788.2955 | 1597407.1154 | 0 | 0 | 21215469.5879 | 0 | 21215469.5879 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1889274.1771 | 17728788.2955 | 1597407.1154 | 0 | 0 | 21215469.5879 | 0 | 21215469.5879
| Total | 3426790.7887 | 22407046.6915 | 1992677.6598 | 0 | 0 | 27826515.14 | 0 | 27826515.14 |  | 999385.7976 | 3040867.9574 | 256925.8539 | 0 | 0 | 4297179.6088 | 0 | 4297179.6088 |  | 2427404.9912 | 19366178.7341 | 1735751.8059 | 0 | 0 | 23529335.5311 | 0 | 23529335.5311
Actual and Forecast TransGrid Labour and Indirect Costs
|  | Actual and Forecast TransGrid Labour and Indirect Costs | [8 empty] | Actual and Forecast Direct Costs | [8 empty] | Actual and Forecast Indirect Costs
|  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY19-FY23 | Post commissioning costs (FY24) | TOTAL FY19-FY24 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY19-FY23 | Post commissioning costs (FY24) | TOTAL FY19-FY23 |  | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | TOTAL FY19-FY23 | Post commissioning costs (FY24) | TOTAL FY20-FY23
| Total estimate: Actuals + Forecast | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ |  |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ |  | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $ | 2017/8 $
| Actuals | 3426790.7887 | 22407046.6915 | 1992677.6598 | 0 | 0 | 27826515.14 | 0 | 27826515.14 |  | 999385.7976 | 3040867.9574 | 256925.8539 | 0 | 0 | 4297179.6088 | 0 | 4297179.6088 |  | 2427404.9912 | 19366178.7341 | 1735751.8059 | 0 | 0 | 23529335.5311 | 0 | 23529335.5311
| Forecast | 0 | 0 | 45832095.7664 | 27898866.1697 | 23920218.8131 | 97651180.7492 | 10322516.8778 | 107973697.627 |  | 0 | 0 | 10502214.6459 | 11868763.1852 | 12553762.4662 | 34924740.2974 | 6293760.535 | 41218500.8324 |  | 0 | 0 | 35329881.1205 | 16030102.9845 | 11366456.3469 | 62726440.4519 | 4028756.3428 | 66755196.7946
| Total | 3426790.7887 | 22407046.6915 | 47824773.4262 | 27898866.1697 | 23920218.8131 | 125477695.8892 | 10322516.8778 | 135800212.767 |  | 999385.7976 | 3040867.9574 | 10759140.4998 | 11868763.1852 | 12553762.4662 | 39221919.9062 | 6293760.535 | 45515680.4412 |  | 2427404.9912 | 19366178.7341 | 37065632.9264 | 16030102.9845 | 11366456.3469 | 86255775.983 | 4028756.3428 | 90284532.3258
135800212.767

## s4. Works Delivery
|  |  |  | Current / Nominal values (2018/9) | [6 empty] | Restatement to 2017-18 LABOUR rates | [6 empty] | Restatement to 2017/8 $ | [6 empty] | Rounded ($M)
s4. Works Delivery | Nominal values | Labour adjusted | Restated estimates | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-4) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-4) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-4) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-4) | TOTAL
Labour costs | Estimate
Works Delivery Project Management | 1676706.85 | 1663216.4665 | 1642862.4188 | 0 | 651666.05 | 376084.8 | 383997.6 | 1411748.45 | 264958.4 | 1676706.85 | 0 | 646422.9004 | 373058.9114 | 380908.0469 | 1400389.8586 | 262826.6079 | 1663216.4665 | 0 | 638512.1306 | 368493.5051 | 376246.5848 | 1383252.2205 | 259610.1984 | 1642862.4188 | 0 | 0.63851 | 0.36849 | 0.37625 | 1.3833 | 0.25961 | 1.6429
Site Management | 9402962.7 | 9327308.7043 | 9213163.318 | 0 | 873560.5 | 3067815 | 3728748.2 | 7670123.7 | 1732839 | 9402962.7 | 0 | 866532.0405 | 3043132.092 | 3698747.5811 | 7608411.7137 | 1718896.9906 | 9327308.7043 | 0 | 855927.6274 | 3005890.965 | 3653483.1876 | 7515301.7801 | 1697861.5379 | 9213163.318 | 0 | 0.85593 | 3.0059 | 3.6535 | 7.5153 | 1.6979 | 9.2132
Technical Fitters | 4417455.7 | 4381913.9048 | 4328289.0843 | 0 | 608005.3 | 1451662.8 | 1660293.6 | 3719961.7 | 697494 | 4417455.7 | 0 | 603113.4343 | 1439983.0673 | 1646935.2736 | 3690031.7752 | 691882.1296 | 4381913.9048 | 0 | 595732.6755 | 1422360.8969 | 1626780.4713 | 3644874.0437 | 683415.0406 | 4328289.0843 | 0 | 0.59573 | 1.4224 | 1.6268 | 3.6449 | 0.68342 | 4.3283
Support | 3775674 | 3745295.8273 | 3699461.7875 | 0 | 29152.2 | 826803.6 | 1716904 | 2572859.8 | 1202814.2 | 3775674 | 0 | 28917.6484 | 820151.3354 | 1703090.1998 | 2552159.1835 | 1193136.6438 | 3745295.8273 | 0 | 28563.761 | 810114.5183 | 1682248.1869 | 2520926.4663 | 1178535.3212 | 3699461.7875 | 0 | 0.028564 | 0.81011 | 1.6822 | 2.5209 | 1.1785 | 3.6995
Works Delivery - Labour costs | 19272799.25 | 19117734.9028 | 18883776.6086 | 0 | 2162384.05 | 5722366.2 | 7489943.4 | 15374693.65 | 3898105.6 | 19272799.25 | 0 | 2144986.0236 | 5676325.4061 | 7429681.1014 | 15250992.531 | 3866742.3718 | 19117734.9028 | 0 | 2118736.1946 | 5606859.8854 | 7338758.4306 | 15064354.5105 | 3819422.0981 | 18883776.6086 | 0 | 2.1187 | 5.6069 | 7.3388 | 15.0644 | 3.8194 | 18.8838
Labour Related costs
Sustenance | 515790 | 515790 | 509477.8846 | 0 | 0 | 165052.8 | 247579.2 | 412632 | 103158 | 515790 | 0 | 0 | 165052.8 | 247579.2 | 412632 | 103158 | 515790 | 0 | 0 | 163032.9231 | 244549.3846 | 407582.3077 | 101895.5769 | 509477.8846 | 0 | 0 | 0.16303 | 0.24455 | 0.40758 | 0.1019 | 0.50948
Training | 96000 | 96000 | 94825.1748 | 0 | 31500 | 21000 | 24000 | 76500 | 19500 | 96000 | 0 | 31500 | 21000 | 24000 | 76500 | 19500 | 96000 | 0 | 31114.5105 | 20743.007 | 23706.2937 | 75563.8112 | 19261.3636 | 94825.1748 | 0 | 0.031115 | 0.020743 | 0.023706 | 0.075564 | 0.019261 | 0.094825
Recruitment | 323420.9528 | 320818.7849 | 316892.6809 | 0 | 38614.0009 | 214588.7325 | 70218.2194 | 323420.9528 | 0 | 323420.9528 | 0 | 38303.3218 | 212862.2027 | 69653.2603 | 320818.7849 | 0 | 320818.7849 | 0 | 37834.5749 | 210257.2457 | 68800.8603 | 316892.6809 | 0 | 316892.6809 | 0 | 0.037835 | 0.21026 | 0.068801 | 0.31689 | 0 | 0.31689
Travel & Expenses | 80000 | 80000 | 79020.979 | 0 | 0 | 25600 | 38400 | 64000 | 16000 | 80000 | 0 | 0 | 25600 | 38400 | 64000 | 16000 | 80000 | 0 | 0 | 25286.7133 | 37930.0699 | 63216.7832 | 15804.1958 | 79020.979 | 0 | 0 | 0.025287 | 0.03793 | 0.063217 | 0.015804 | 0.079021
IT hardware | 37100 | 37100 | 36645.979 | 0 | 13250 | 18550 | 5300 | 37100 | 0 | 37100 | 0 | 13250 | 18550 | 5300 | 37100 | 0 | 37100 | 0 | 13087.8497 | 18322.9895 | 5235.1399 | 36645.979 | 0 | 36645.979 | 0 | 0.013088 | 0.018323 | 0.0052351 | 0.036646 | 0 | 0.036646
Works Delivery - Labour Related Costs | 1052310.9528 | 1049708.7849 | 1036862.6984 | 0 | 83364.0009 | 444791.5325 | 385497.4194 | 913652.9528 | 138658 | 1052310.9528 | 0 | 83053.3218 | 443065.0027 | 384932.4603 | 911050.7849 | 138658 | 1049708.7849 | 0 | 82036.935 | 437642.8786 | 380221.7484 | 899901.562 | 136961.1364 | 1036862.6984 | 0 | 0.082037 | 0.43764 | 0.38022 | 0.8999 | 0.13696 | 1.0369
TOTAL WORKS DELIVERY | 20325110.2028 | 20167443.6877 | 19920639.307 | 0 | 2245748.0509 | 6167157.7325 | 7875440.8194 | 16288346.6028 | 4036763.6 | 20325110.2028 | 0 | 2228039.3454 | 6119390.4088 | 7814613.5617 | 16162043.3159 | 4005400.3718 | 20167443.6877 | 0 | 2200773.1296 | 6044502.7639 | 7718980.179 | 15964256.0725 | 3956383.2344 | 19920639.307 | 0 | 2.2008 | 6.0445 | 7.719 | 15.9643 | 3.9564 | 19.9206

## Works Delivery Res Cost
CONFIDENTIAL
[Content removed from public version]

## WD Resource schedule
CONFIDENTIAL
[Content removed from public version]

## WD Labour Data (hidden)
Schedule Output | Schedule Output | Schedule Output | Schedule Output
Task Name | Remaining Cost | *Project Assignment | *Resource Name (Labour Assumption) | Resource Category | TG Resource Type | Construction Activities | time axis 2019-07-01 to 2023-08-01
zz000496 Project Energy Connect | 48721368.18 | [8 empty] | 156391.14 | 156391.14 | 156613.56 | 170630.64 | 384406.41 | 401097.02 | 401097.02 | 429069.23 | 429069.23 | 490166.91 | 509229.28 | 654659.25 | 700711.46 | 729382.96 | 796504.78 | 839435.22 | 938271.34 | 975032.07 | 973954.81 | 973954.81 | 1029004.47 | 1061013.35 | 1097274.08 | 1116310.5 | 1099086.2 | 1099086.2 | 1109667.19 | 1147000.74 | 1518251.51 | 1530297.78 | 1650995.25 | 1663541.52 | 1671185.41 | 1689364.02 | 1782689.93 | 1728137.22 | 1973249.22 | 973138.19 | 981625.78 | 994033.43 | 1057032.96 | 1446104.18 | 1446104.18 | 1507127.64 | 1636186.26 | 1430093.69 | 2017698.98
zz000496 Project Energy Connect | 30147675.48 | [8 empty] | 128579.42 | 128579.42 | 128579.42 | 128579.42 | 342355.19 | 359045.81 | 359045.81 | 387018.01 | 387018.01 | 433264.09 | 452326.46 | 532468.34 | 578520.55 | 607192.06 | 672187.86 | 689027.03 | 728296.5 | 728796.5 | 744943.54 | 744943.54 | 762051.42 | 777953.65 | 777953.65 | 777953.65 | 777953.65 | 777953.65 | 781439.31 | 781439.31 | 781439.31 | 781439.31 | 781439.31 | 781939.31 | 787837.28 | 804262.32 | 804262.32 | 804262.32 | 804762.32 | 761791.17 | 765381.4 | 765381.4 | 765381.4 | 765381.4 | 765381.4 | 765381.4 | 765381.4 | 710302.74 | 710802.74
Delivery Management | 8800550.07 | [8 empty] | 72635.02 | 72635.02 | 72635.02 | 72635.02 | 95099.51 | 111790.12 | 111790.12 | 111790.12 | 111790.12 | 137610.98 | 137610.98 | 154718.86 | 200771.06 | 200771.06 | 200771.06 | 200771.06 | 202039.96 | 202539.96 | 208950.18 | 208950.18 | 226058.06 | 231627.23 | 231627.23 | 231627.23 | 231627.23 | 231627.23 | 231627.23 | 231627.23 | 231627.23 | 231627.23 | 231627.23 | 232127.23 | 238025.19 | 243858.85 | 243858.85 | 243858.85 | 244358.85 | 201387.7 | 201387.7 | 201387.7 | 201387.7 | 201387.7 | 201387.7 | 201387.7 | 201387.7 | 156112.47 | 156612.47
Delivery Manager | 2763059.07 | [8 empty] | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 62386.6 | 62386.6
Sustenance Tier 2 Country Centre | 7267.95 | Project Wide Delivery Management |  | Susso | N/A | [20 empty] | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45
Outsource Material/Equipment | 12400 | Project Wide Delivery Management |  | Outsource Material/Equipment | N/A | [20 empty] | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
Senior Program Manager | 2743391.12 | Project Wide Delivery Management | Delivery Manager | Program Resource | Project Mgmt |  |  |  |  | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 61752.15 | 61752.15
Program & Subs Project Managers | 6037491 | [8 empty] | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 39155.1 | 55845.72 | 55845.72 | 55845.72 | 55845.72 | 80267.96 | 80267.96 | 97375.84 | 143428.05 | 143428.05 | 143428.05 | 143428.05 | 144062.5 | 144562.5 | 150972.71 | 150972.71 | 168080.59 | 172216.19 | 172216.19 | 172216.19 | 172216.19 | 172216.19 | 172216.19 | 172216.19 | 172216.19 | 172216.19 | 172216.19 | 172716.19 | 178614.16 | 182978.4 | 182978.4 | 182978.4 | 183478.4 | 140507.25 | 140507.25 | 140507.25 | 140507.25 | 140507.25 | 140507.25 | 140507.25 | 140507.25 | 93725.87 | 94225.87
Transmission Lines | 1703884.84 | [12 empty] | 11232.25 | 11232.25 | 11232.25 | 11232.25 | 11232.25 | 23026.1 | 23026.1 | 23026.1 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46686.66 | 46686.66 | 46686.66 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05
Sustenance Tier 2 Country Centre | 6330.15 | Project Wide Delivery Management |  | Susso | N/A |  | 2021-04-01: 234.45; 2021-05-01: 234.45; 2021-06-01: 234.45; 2021-07-01: 234.45; 2021-08-01: 234.45; 2021-09-01: 234.45; 2021-10-01: 234.45; 2021-11-01: 234.45; 2021-12-01: 234.45; 2022-01-01: 234.45; 2022-02-01: 234.45; 2022-03-01: 234.45; 2022-04-01: 234.45; 2022-05-01: 234.45; 2022-06-01: 234.45; 2022-07-01: 234.45; 2022-08-01: 234.45; 2022-09-01: 234.45; 2022-10-01: 234.45; 2022-11-01: 234.45; 2022-12-01: 234.45; 2023-01-01: 234.45; 2023-02-01: 234.45; 2023-03-01: 234.45; 2023-04-01: 234.45; 2023-05-01: 234.45; 2023-06-01: 234.45
Outsource Material/Equipment | 10800 | Project Wide Delivery Management |  | Outsource Material/Equipment | N/A |  | 2021-04-01: 400; 2021-05-01: 400; 2021-06-01: 400; 2021-07-01: 400; 2021-08-01: 400; 2021-09-01: 400; 2021-10-01: 400; 2021-11-01: 400; 2021-12-01: 400; 2022-01-01: 400; 2022-02-01: 400; 2022-03-01: 400; 2022-04-01: 400; 2022-05-01: 400; 2022-06-01: 400; 2022-07-01: 400; 2022-08-01: 400; 2022-09-01: 400; 2022-10-01: 400; 2022-11-01: 400; 2022-12-01: 400; 2023-01-01: 400; 2023-02-01: 400; 2023-03-01: 400; 2023-04-01: 400; 2023-05-01: 400; 2023-06-01: 400
Program Manager | 1686754.69 | Project Wide Delivery Management | Program Manager Tx Lines | Program Resource | Project Mgmt | [8 empty] | 11232.25 | 11232.25 | 11232.25 | 11232.25 | 11232.25 | 23026.1 | 23026.1 | 23026.1 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6
Substations | 1805609.01 | [12 empty] | 11232.25 | 11232.25 | 11232.25 | 11232.25 | 11232.25 | 23026.1 | 23026.1 | 23026.1 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46686.66 | 46686.66 | 46686.66 | 46686.66 | 46686.66 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 47837.96 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 49018.05 | 50227.64 | 50227.64
Sustenance Tier 2 Country Centre | 7267.95 | Project Wide Delivery Management |  | Susso | N/A | [20 empty] | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45
Outsource Material/Equipment | 12400 | Project Wide Delivery Management |  | Outsource Material/Equipment | N/A | [20 empty] | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
Program Manager | 1785941.06 | Project Wide Delivery Management | Program Manager Subs | Program Resource | Project Mgmt | [8 empty] | 11232.25 | 11232.25 | 11232.25 | 11232.25 | 11232.25 | 23026.1 | 23026.1 | 23026.1 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 46052.21 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 47203.51 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 48383.6 | 49593.19 | 49593.19
Substation Senior PM for Buronga and RC | 1213930.19 | [8 empty] | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 17107.88 | 17107.88 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 34715.76 | 40491.52 | 40491.52 | 40491.52 | 41469.12 | 41469.12 | 41469.12 | 41469.12 | 41469.12 | 41469.12 | 41469.12 | 41469.12 | 41469.12 | 41469.12 | 41469.12 | 41469.12 | 42471.15 | 42471.15 | 42471.15 | 42971.15
Senior Project Manager | 1091234.44 | Project Wide Delivery Management | Senior Project Manager | Program Resource | Project Mgmt |  |  |  |  | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 17107.88 | 17107.88 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 34215.76 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35947.93 | 35947.93 | 35947.93 | 35947.93
Senior Project Manager - Overtime | 95327.55 | Project Wide Delivery Management | Senior Project Manager - Overtime | Overtime | Project Mgmt |  | 2021-04-01: 4887.97; 2021-05-01: 4887.97; 2021-06-01: 4887.97; 2021-07-01: 5010.16; 2021-08-01: 5010.16; 2021-09-01: 5010.16; 2021-10-01: 5010.16; 2021-11-01: 5010.16; 2021-12-01: 5010.16; 2022-01-01: 5010.16; 2022-02-01: 5010.16; 2022-03-01: 5010.16; 2022-04-01: 5010.16; 2022-05-01: 5010.16; 2022-06-01: 5010.16; 2022-07-01: 5135.42; 2022-08-01: 5135.42; 2022-09-01: 5135.42; 2022-10-01: 5135.42
Sustenance Tier 2 Country Centre | 17818.2 | Project Wide Delivery Management |  | Susso | N/A |  | 2021-04-01: 937.8; 2021-05-01: 937.8; 2021-06-01: 937.8; 2021-07-01: 937.8; 2021-08-01: 937.8; 2021-09-01: 937.8; 2021-10-01: 937.8; 2021-11-01: 937.8; 2021-12-01: 937.8; 2022-01-01: 937.8; 2022-02-01: 937.8; 2022-03-01: 937.8; 2022-04-01: 937.8; 2022-05-01: 937.8; 2022-06-01: 937.8; 2022-07-01: 937.8; 2022-08-01: 937.8; 2022-09-01: 937.8; 2022-10-01: 937.8
Other Material | 9550 | Project Wide Delivery Management |  | Other Material | N/A |  | 2021-03-01: 500; 2021-04-01: 450; 2021-05-01: 450; 2021-06-01: 450; 2021-07-01: 450; 2021-08-01: 450; 2021-09-01: 450; 2021-10-01: 450; 2021-11-01: 450; 2021-12-01: 450; 2022-01-01: 450; 2022-02-01: 450; 2022-03-01: 450; 2022-04-01: 450; 2022-05-01: 450; 2022-06-01: 450; 2022-07-01: 450; 2022-08-01: 450; 2022-09-01: 450; 2022-10-01: 950
Substation Senior PM for DP and Wagga | 1314066.97 | [13 empty] | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 34215.76 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35571.15 | 41469.12 | 42471.15 | 42471.15 | 42471.15 | 42471.15 | 42471.15 | 42471.15 | 42471.15 | 42471.15 | 42471.15 | 42471.15 | 42471.15 | 42471.15 | 43498.23 | 43998.23
Senior Project Manager | 1215087.17 | Project Wide Delivery Management | Senior Project Manager | Program Resource | Project Mgmt | [9 empty] | 16690.61 | 16690.61 | 16690.61 | 16690.61 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 34215.76 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35071.15 | 35947.93 | 35947.93 | 35947.93 | 35947.93 | 35947.93 | 35947.93 | 35947.93 | 35947.93 | 35947.93 | 35947.93 | 35947.93 | 35947.93 | 36846.63 | 36846.63
Senior Project Manager - Overtime | 77162.8 | Project Wide Delivery Management | Senior Project Manager - Overtime | Overtime | Project Mgmt |  | 2022-06-01: 5010.16; 2022-07-01: 5135.42; 2022-08-01: 5135.42; 2022-09-01: 5135.42; 2022-10-01: 5135.42; 2022-11-01: 5135.42; 2022-12-01: 5135.42; 2023-01-01: 5135.42; 2023-02-01: 5135.42; 2023-03-01: 5135.42; 2023-04-01: 5135.42; 2023-05-01: 5135.42; 2023-06-01: 5135.42; 2023-07-01: 5263.8; 2023-08-01: 5263.8
Sustenance Tier 2 Country Centre | 14067 | Project Wide Delivery Management |  | Susso | N/A |  | 2022-06-01: 937.8; 2022-07-01: 937.8; 2022-08-01: 937.8; 2022-09-01: 937.8; 2022-10-01: 937.8; 2022-11-01: 937.8; 2022-12-01: 937.8; 2023-01-01: 937.8; 2023-02-01: 937.8; 2023-03-01: 937.8; 2023-04-01: 937.8; 2023-05-01: 937.8; 2023-06-01: 937.8; 2023-07-01: 937.8; 2023-08-01: 937.8
Other Material | 7750 | Project Wide Delivery Management |  | Other Material | N/A |  | 2022-05-01: 500; 2022-06-01: 450; 2022-07-01: 450; 2022-08-01: 450; 2022-09-01: 450; 2022-10-01: 450; 2022-11-01: 450; 2022-12-01: 450; 2023-01-01: 450; 2023-02-01: 450; 2023-03-01: 450; 2023-04-01: 450; 2023-05-01: 450; 2023-06-01: 450; 2023-07-01: 450; 2023-08-01: 950
Health, Safety and Environment Manager | 2214803.93 | [12 empty] | 13986.1 | 13986.1 | 13986.1 | 13986.1 | 13986.1 | 28671.51 | 28671.51 | 28671.51 | 28671.51 | 57343.01 | 57343.01 | 57343.01 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 62386.6 | 62386.6
Sustenance Tier 2 Country Centre | 7267.95 | Project Wide Delivery Management |  | Susso | N/A | [20 empty] | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45
Outsource Material/Equipment | 12400 | Project Wide Delivery Management |  | Outsource Material/Equipment | N/A | [20 empty] | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
Senior Program Manager | 2195135.98 | Project Wide Delivery Management | Health, Safety and Environment Manager | Program Resource | Project Mgmt | [8 empty] | 13986.1 | 13986.1 | 13986.1 | 13986.1 | 13986.1 | 28671.51 | 28671.51 | 28671.51 | 28671.51 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 61752.15 | 61752.15
Engineering Manager | 2356413.2 | [12 empty] | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 28671.51 | 43007.26 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 62386.6 | 62386.6
Sustenance Tier 2 Country Centre | 7267.95 | Project Wide Delivery Management |  | Susso | N/A | [20 empty] | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45
Outsource Material/Equipment | 12400 | Project Wide Delivery Management |  | Outsource Material/Equipment | N/A | [20 empty] | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
Senior Program Manager | 2336745.25 | Project Wide Delivery Management | Engineer Manager | Program Resource | Project Mgmt | [8 empty] | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 28671.51 | 43007.26 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 61752.15 | 61752.15
Contracts and Commercial Manager | 2435696.91 | [12 empty] | 27972.2 | 27972.2 | 27972.2 | 55944.4 | 55944.4 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 61752.15 | 61752.15
Senior Program Manager | 2435696.91 | Project Wide Delivery Management | Contracts and Commercial Manager | Program Resource | Project Mgmt | [8 empty] | 27972.2 | 27972.2 | 27972.2 | 55944.4 | 55944.4 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 61752.15 | 61752.15
System and Compliance | 2342077.45 | [12 empty] | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 28671.51 | 28671.51 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 62386.6 | 62386.6
Sustenance Tier 2 Country Centre | 7267.95 | Project Wide Delivery Management |  | Susso | N/A | [20 empty] | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45
Outsource Material/Equipment | 12400 | Project Wide Delivery Management |  | Outsource Material/Equipment | N/A | [20 empty] | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
Senior Program Manager | 2322409.5 | Project Wide Delivery Management | System and Compliance Manager | Program Resource | Project Mgmt | [8 empty] | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 28671.51 | 28671.51 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 61752.15 | 61752.15
Community & Stakeholder Engagment Manager | 2275730.88 | [12 empty] | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 28671.51 | 28671.51 | 28671.51 | 28671.51 | 28671.51 | 57343.01 | 57343.01 | 58611.91 | 58611.91 | 58611.91 | 58611.91 | 58611.91 | 60045.49 | 60045.49 | 60045.49 | 60045.49 | 60045.49 | 60045.49 | 60045.49 | 60045.49 | 60045.49 | 60045.49 | 60045.49 | 60045.49 | 61514.9 | 61514.9 | 61514.9 | 61514.9 | 61514.9 | 61514.9 | 61514.9 | 61514.9 | 61514.9 | 61514.9 | 61514.9 | 61514.9 | 63021.05 | 63021.05
Sustenance Tier 2 Country Centre | 14535.9 | Project Wide Delivery Management |  | Susso | N/A | [20 empty] | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9 | 468.9
Outsource Material/Equipment | 24800 | Project Wide Delivery Management |  | Outsource Material/Equipment | N/A | [20 empty] | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800
Senior Program Manager | 2236394.98 | Project Wide Delivery Management | Community Manager | Program Resource | Project Mgmt | [8 empty] | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 27972.2 | 28671.51 | 28671.51 | 28671.51 | 28671.51 | 28671.51 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 61752.15 | 61752.15
Easement Officer | 613134.5 |  |  | Program Resource | Support | [14 empty] | 4726.62 | 9453.23 | 9453.23 | 9453.23 | 9736.83 | 9736.83 | 9736.83 | 9736.83 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20659.6 | 20659.6 | 20659.6 | 20659.6 | 20659.6 | 20659.6 | 20659.6
Easement Officer | 613134.5 | Project Wide Delivery Management | Easement Officer | Program Resource | Support | [14 empty] | 4726.62 | 9453.23 | 9453.23 | 9453.23 | 9736.83 | 9736.83 | 9736.83 | 9736.83 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 19473.66 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20057.87 | 20659.6 | 20659.6 | 20659.6 | 20659.6 | 20659.6 | 20659.6 | 20659.6
Project Control | 9109268.54 | [8 empty] | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 121380.78 | 121380.78 | 121380.78 | 121380.78 | 121380.78 | 123624.08 | 123624.08 | 138924.21 | 138924.21 | 138924.21 | 174964.91 | 191804.08 | 226632.4 | 226632.4 | 226632.4 | 226632.4 | 226632.4 | 229797.58 | 229797.58 | 229797.58 | 229797.58 | 229797.58 | 232699.03 | 232699.03 | 232699.03 | 232699.03 | 232699.03 | 232699.03 | 232699.03 | 235943.35 | 235943.35 | 235943.35 | 235943.35 | 235943.35 | 238931.84 | 238931.84 | 238931.84 | 238931.84 | 238931.84 | 238931.84 | 238931.84 | 242257.26 | 242257.26
Project Control | 5057593.18 | [12 empty] | 49087.67 | 49087.67 | 49087.67 | 49087.67 | 49087.67 | 49932.36 | 49932.36 | 65232.49 | 65232.49 | 65232.49 | 100782.73 | 100782.73 | 134976.6 | 134976.6 | 134976.6 | 134976.6 | 134976.6 | 136708.21 | 136708.21 | 136708.21 | 136708.21 | 136708.21 | 138599.31 | 138599.31 | 138599.31 | 138599.31 | 138599.31 | 138599.31 | 138599.31 | 140374.21 | 140374.21 | 140374.21 | 140374.21 | 140374.21 | 142322.04 | 142322.04 | 142322.04 | 142322.04 | 142322.04 | 142322.04 | 142322.04 | 144141.31 | 144141.31
Sustenance Tier 2 Country Centre | 58143.6 | Project Wide Delivery Management |  | Susso | N/A | [20 empty] | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6 | 1875.6
Outsource Material/Equipment | 24800 | Project Wide Delivery Management |  | Outsource Material/Equipment | N/A | [20 empty] | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800
Contract Administrator | 2273314.39 | Project Wide Delivery Management | Project Coordinator | Program Resource | Project Mgmt | [8 empty] | 15300.13 | 15300.13 | 15300.13 | 15300.13 | 15300.13 | 15300.13 | 15300.13 | 30600.26 | 30600.26 | 30600.26 | 31518.27 | 31518.27 | 63036.54 | 63036.54 | 63036.54 | 63036.54 | 63036.54 | 63036.54 | 63036.54 | 63036.54 | 63036.54 | 63036.54 | 64927.63 | 64927.63 | 64927.63 | 64927.63 | 64927.63 | 64927.63 | 64927.63 | 64927.63 | 64927.63 | 64927.63 | 64927.63 | 64927.63 | 66875.46 | 66875.46 | 66875.46 | 66875.46 | 66875.46 | 66875.46 | 66875.46 | 66875.46 | 66875.46
Scheduler | 2701335.18 | Project Wide Delivery Management | Scheduler | Program Resource | Project Mgmt | [8 empty] | 33787.54 | 33787.54 | 33787.54 | 33787.54 | 33787.54 | 34632.23 | 34632.23 | 34632.23 | 34632.23 | 34632.23 | 69264.46 | 69264.46 | 69264.46 | 69264.46 | 69264.46 | 69264.46 | 69264.46 | 70996.07 | 70996.07 | 70996.07 | 70996.07 | 70996.07 | 70996.07 | 70996.07 | 70996.07 | 70996.07 | 70996.07 | 70996.07 | 70996.07 | 72770.98 | 72770.98 | 72770.98 | 72770.98 | 72770.98 | 72770.98 | 72770.98 | 72770.98 | 72770.98 | 72770.98 | 72770.98 | 72770.98 | 74590.25 | 74590.25
Project Controls Manager | 2763059.07 | [8 empty] | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 57977.46 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 59411.04 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 60880.45 | 62386.6 | 62386.6
Sustenance Tier 2 Country Centre | 7267.95 | Project Wide Delivery Management |  | Susso | N/A | [20 empty] | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45 | 234.45
Outsource Material/Equipment | 12400 | Project Wide Delivery Management |  | Outsource Material/Equipment | N/A | [20 empty] | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
Senior Program Manager | 2743391.12 | Project Wide Delivery Management | Program Control Manager | Program Resource | Project Mgmt |  |  |  |  | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 55944.4 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 57343.01 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 58776.59 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 60246 | 61752.15 | 61752.15
Project Accountant | 1288616.29 | [12 empty] | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16839.17 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35
Maintenance Support 30 - 35 | 1288616.29 | Project Wide Delivery Management | Project Accountant | Program Resource | Support | [8 empty] | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16348.71 | 16839.17 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 33678.34 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 34688.69 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35 | 35729.35
Transmission Line - Border to Buronga | 1219274.01 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 65052.45 | 47828.14 | 47828.14 | 47828.14 | 48255.84 | 48255.84 | 48255.84 | 48255.84 | 48255.84 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 50046.07
Development | 1219274.01 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 65052.45 | 47828.14 | 47828.14 | 47828.14 | 48255.84 | 48255.84 | 48255.84 | 48255.84 | 48255.84 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 50046.07
PROJECT APPROVAL | 0 | [5 empty] | 2019-10-01: 0
Project Approval and PADs | 0 | [5 empty] | 2019-10-01: 0
Development of Handover Package | 0 | [5 empty] | 2019-10-01: 0
WD Handover Document Approved | 0 | [5 empty] | 2019-10-01: 0
Project Approval Document (PAD) Issued | 0 | [5 empty] | 2019-10-01: 0
Risk Contingency | 0 | [5 empty] | 2019-10-01: 0
Project Contingency (P50) | 0 | [5 empty] | 2019-10-01: 0
WORKS DELIVERY MANAGEMENT | 1219274.01 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 65052.45 | 47828.14 | 47828.14 | 47828.14 | 48255.84 | 48255.84 | 48255.84 | 48255.84 | 48255.84 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 50046.07
Project Management | 878974.73 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 29291.72 | 30179.52 | 30179.52 | 30179.52 | 30607.21 | 30607.21 | 30607.21 | 30607.21 | 30607.21 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 31396.12 | 31896.12
Project Management | 878974.73 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 29291.72 | 30179.52 | 30179.52 | 30179.52 | 30607.21 | 30607.21 | 30607.21 | 30607.21 | 30607.21 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 31396.12 | 31896.12
Senior Project Manager | 509669.29 | TL Border to Buronga | Senior Project Manager | Program Resource | Project Mgmt |  |  |  |  | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8553.94 | 8553.94 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17973.97 | 17973.97
Senior Project Manager - Overtime | 0 | TL Border to Buronga | Senior Project Manager - Overtime | Overtime | Project Mgmt
Sustenance Tier 2 Country Centre | 15942.6 | TL Border to Buronga |  | Susso | N/A |  | 2021-04-01: 937.8; 2021-05-01: 937.8; 2021-06-01: 937.8; 2021-07-01: 937.8; 2021-08-01: 937.8; 2021-09-01: 937.8; 2021-10-01: 937.8; 2021-11-01: 937.8; 2021-12-01: 937.8; 2022-01-01: 937.8; 2022-02-01: 937.8; 2022-03-01: 937.8; 2022-04-01: 937.8; 2022-05-01: 937.8; 2022-06-01: 937.8; 2022-07-01: 937.8; 2022-08-01: 937.8
Other Material | 8650 | TL Border to Buronga |  | Other Material | N/A |  | 2021-03-01: 500; 2021-04-01: 450; 2021-05-01: 450; 2021-06-01: 450; 2021-07-01: 450; 2021-08-01: 450; 2021-09-01: 450; 2021-10-01: 450; 2021-11-01: 450; 2021-12-01: 450; 2022-01-01: 450; 2022-02-01: 450; 2022-03-01: 450; 2022-04-01: 450; 2022-05-01: 450; 2022-06-01: 450; 2022-07-01: 450; 2022-08-01: 950
Engineer 24 - 30 | 344712.84 | TL Border to Buronga | Engineer | Program Resource | Tech Fitter |  |  |  |  | 5560.56 | 5560.56 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 11343.53 | 11343.53 | 11343.53 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35
Project Documentation/Plan and Program | 0 | [5 empty] | 2019-10-01: 0
Site Management | 340299.28 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35760.73 | 17648.63 | 17648.63 | 17648.63 | 17648.63 | 17648.63 | 17648.63 | 17648.63 | 17648.63 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95
Site Management | 239840.71 | [5 empty] | 2021-03-01: 24065.33; 2021-04-01: 12501.56; 2021-05-01: 12501.56; 2021-06-01: 12501.56; 2021-07-01: 12501.56; 2021-08-01: 12501.56; 2021-09-01: 12501.56; 2021-10-01: 12501.56; 2021-11-01: 12501.56; 2021-12-01: 12862.54; 2022-01-01: 12862.54; 2022-02-01: 12862.54; 2022-03-01: 12862.54; 2022-04-01: 12862.54; 2022-05-01: 12862.54; 2022-06-01: 12862.54; 2022-07-01: 12862.54; 2022-08-01: 12862.54
Sustenance Tier 2 Country Centre | 7971.3 | TL Border to Buronga |  | Susso | N/A |  | 2021-04-01: 468.9; 2021-05-01: 468.9; 2021-06-01: 468.9; 2021-07-01: 468.9; 2021-08-01: 468.9; 2021-09-01: 468.9; 2021-10-01: 468.9; 2021-11-01: 468.9; 2021-12-01: 468.9; 2022-01-01: 468.9; 2022-02-01: 468.9; 2022-03-01: 468.9; 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9
Senior Site Manager Lines | 231869.41 | TL Border to Buronga | Senior Site Manager Lines | Program Resource | Site Mgmt |  | 2021-03-01: 24065.33; 2021-04-01: 12032.66; 2021-05-01: 12032.66; 2021-06-01: 12032.66; 2021-07-01: 12032.66; 2021-08-01: 12032.66; 2021-09-01: 12032.66; 2021-10-01: 12032.66; 2021-11-01: 12032.66; 2021-12-01: 12393.64; 2022-01-01: 12393.64; 2022-02-01: 12393.64; 2022-03-01: 12393.64; 2022-04-01: 12393.64; 2022-05-01: 12393.64; 2022-06-01: 12393.64; 2022-07-01: 12393.64; 2022-08-01: 12393.64
Senior Site Manager Lines - Overtime | 0 | TL Border to Buronga | Senior Site Manager Lines - Overtime | Overtime | Site Mgmt
Contract Administration | 0
Protection & Control | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other TG Resources | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety & Environment | 100458.57 | [5 empty] | 2021-03-01: 11695.41; 2021-04-01: 5147.06; 2021-05-01: 5147.06; 2021-06-01: 5147.06; 2021-07-01: 5147.06; 2021-08-01: 5147.06; 2021-09-01: 5147.06; 2021-10-01: 5147.06; 2021-11-01: 5147.06; 2021-12-01: 5287.41; 2022-01-01: 5287.41; 2022-02-01: 5287.41; 2022-03-01: 5287.41; 2022-04-01: 5287.41; 2022-05-01: 5287.41; 2022-06-01: 5287.41; 2022-07-01: 5287.41; 2022-08-01: 5287.41
Environmental Officer | 47218.26 | TL Border to Buronga | Environmental Officer | Program Resource | Support |  | 2021-03-01: 5970.95; 2021-04-01: 2388.38; 2021-05-01: 2388.38; 2021-06-01: 2388.38; 2021-07-01: 2388.38; 2021-08-01: 2388.38; 2021-09-01: 2388.38; 2021-10-01: 2388.38; 2021-11-01: 2388.38; 2021-12-01: 2460.03; 2022-01-01: 2460.03; 2022-02-01: 2460.03; 2022-03-01: 2460.03; 2022-04-01: 2460.03; 2022-05-01: 2460.03; 2022-06-01: 2460.03; 2022-07-01: 2460.03; 2022-08-01: 2460.03
Safety Officer | 45269.01 | TL Border to Buronga | Safety Officer | Program Resource | Support |  | 2021-03-01: 5724.46; 2021-04-01: 2289.78; 2021-05-01: 2289.78; 2021-06-01: 2289.78; 2021-07-01: 2289.78; 2021-08-01: 2289.78; 2021-09-01: 2289.78; 2021-10-01: 2289.78; 2021-11-01: 2289.78; 2021-12-01: 2358.48; 2022-01-01: 2358.48; 2022-02-01: 2358.48; 2022-03-01: 2358.48; 2022-04-01: 2358.48; 2022-05-01: 2358.48; 2022-06-01: 2358.48; 2022-07-01: 2358.48; 2022-08-01: 2358.48
Sustenance Tier 2 Country Centre | 7971.3 | TL Border to Buronga |  | Susso | N/A |  | 2021-04-01: 468.9; 2021-05-01: 468.9; 2021-06-01: 468.9; 2021-07-01: 468.9; 2021-08-01: 468.9; 2021-09-01: 468.9; 2021-10-01: 468.9; 2021-11-01: 468.9; 2021-12-01: 468.9; 2022-01-01: 468.9; 2022-02-01: 468.9; 2022-03-01: 468.9; 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9
Outage Plan in THEOS for Handover | 0 | [5 empty] | 2019-10-01: 0
Commissioning plan & program | 0 | [5 empty] | 2019-10-01: 0; 2019-11-01: 0
EARLY WORKS | 0 |  |  |  |  | Construction Activity | 2019-10-01: 0; 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Preliminary Studies & Planning | 0 |  |  |  |  | Construction Activity | 2019-10-01: 0; 2019-11-01: 0
Initial Concept Layouts & Surveys | 0 |  |  |  |  | Construction Activity | 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0; 2020-02-01: 0
ECI Award | 0 |  |  |  |  | Construction Activity
Early Contractor Involvement | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Initial Detailed Design | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0
Initial Civil & Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0
Transmission Line Design | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0
Initial Transmission Line Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0
Initial Procurement (LLE) | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Tower Sections | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Supplier Procurement - Tower Sections | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0
Initial Tower Sections Manufacture | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Tower Fittings | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Supplier Procurement - Tower Fittings | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0
Initial Tower Fittings Manufacture | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Conductors | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Supplier Procurement - Conductors | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0
Initial Conductors Manufacture | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
OHEW & OPGW | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Supplier Procurement - OHEW & OPGW | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0
OHEW & OPGW Procurement | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
OPGW Procurement | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Tender Specification | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Technical Specification Preparation | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0
Specification Finalisation | 0 |  |  |  |  | Construction Activity | 2020-04-01: 0
Procurement Review | 0 |  |  |  |  | Construction Activity | 2020-04-01: 0; 2020-05-01: 0
Tender Released to Market | 0 |  |  |  |  | Construction Activity
Tender and Site Visit | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0
Tender Period Closed | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0
Evaluation/ECI/Firm pricing | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0
Prepare and Issue Contract Award Documentation | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
EPC - Contract Award | 0 |  |  |  |  | Construction Activity
Delivery | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
TRANSMISSION LINE WORKS (CONTRACTOR) | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
DESIGN | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Civil Design | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Civil Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Civil Design Package IFC | 0 |  |  |  |  | Construction Activity
Transmission Line Design | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Line Schedule | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0
Structure & Fitting Designs | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0
Foundation Designs | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Stringing Charts | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0
PROCUREMENT & EQUIPMENT DELIVERY | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Tower Sections | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Tower Prototype Assembly | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0
Tower Test | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0
Tower Section Manufacture | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Tower Section Shipping | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Container de-stuffing & delivery to site | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0
Tower Fittings | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Tower Fittings manufacture | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Tower Fittings Delivery to site | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0
Conductors | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Conductors procurement | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Conductors Delivery | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0
OHEW & OPGW | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
OHEW & OPGW Procurement & Delivery | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
OPGW related equipment Procurement & Delivery | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
OHEW & OPGW Delivery | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0
CONTRACT & SITE ESTABLISHMENT | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Project Documentation | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Prepare WHSMP | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Detailed Outage Plan | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Prepare QMP, ITPs & Checklists | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Draft CEMP | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Review and Finalise CEMP | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0
Review and Finalise WHSQMP | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0
Pre-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0
Mobilisation | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Posession of Site (POS) | 0 |  |  |  |  | Construction Activity
Site Establishment | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0
Post-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0
Commencement of Site Work | 0 |  |  |  |  | Construction Activity
330kV TRANSMISSION LINE Construction | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Access and Clearing | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Mobilise (Fixed) | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0
Initial Survey | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0
Survey (10 per day) | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Initial Vegetation Clearing | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0
Initial Tower Pads & Benching | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0
Heavy Access Track (Required for Difficult Access) | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
Vegetation Clearing | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Tower Pads and Benching | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
Civil Works | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Direct Access | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Initial Earthworks, Boring (Direct Access) (Assume 12x Crews) | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0
Initial Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
Initial Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Earthworks, Boring (Direct Access) | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Difficult Access | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Initial Earthworks, Boring (Difficult Access) | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Initial Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0
Initial Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Earthworks, Boring (Difficult Access) | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Electrical Works | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Assembly and Erection | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Tower Construction | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Initial Tower Assembly (Assume 12x Crews) | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Assemble Tower Sections | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Initial Tower Erection | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0
Tower Erection required for Stringing | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0
Erect Towers | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Stringing | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Install/Tension Conductor and OPGW | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Tower Stringing (140km) (Assume 1 Crew) | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Testing and Commissioning | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0
Phase Out Testing (Substation required) | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0
PRACTICAL COMPLETION | 0 |  |  |  |  | Construction Activity
Transmission Line - Border to Buronga PC | 0 |  |  |  |  | Construction Activity
Transmission Line - Buronga to Red Cliffs | 1105055.46 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 29219.41 | 65480.15 | 48255.84 | 48255.84 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 50046.07
Development | 1105055.46 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 29219.41 | 65480.15 | 48255.84 | 48255.84 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 50046.07
PROJECT APPROVAL | 0 | [5 empty] | 2019-10-01: 0
Project Approval and PADs | 0 | [5 empty] | 2019-10-01: 0
Development of Handover Package | 0 | [5 empty] | 2019-10-01: 0
WD Handover Document Approved | 0 | [5 empty] | 2019-10-01: 0
Project Approval Document (PAD) Issued | 0 | [5 empty] | 2019-10-01: 0
Risk Contingency | 0 | [5 empty] | 2019-10-01: 0
Project Contingency (P50) | 0 | [5 empty] | 2019-10-01: 0
WORKS DELIVERY MANAGEMENT | 1105055.46 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 29219.41 | 65480.15 | 48255.84 | 48255.84 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 50046.07
Project Management | 870647.93 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 29219.41 | 29719.41 | 30607.21 | 30607.21 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 31396.12 | 31896.12
Project Management | 870647.93 | [8 empty] | 13905.86 | 13905.86 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 28451.41 | 28451.41 | 28451.41 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 29219.41 | 29719.41 | 30607.21 | 30607.21 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 31396.12 | 31896.12
Senior Project Manager | 509669.29 | TL Buronga to RC | Senior Project Manager | Program Resource | Project Mgmt |  |  |  |  | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8553.94 | 8553.94 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17973.97 | 17973.97
Senior Project Manager - Overtime | 0 | TL Buronga to RC | Senior Project Manager - Overtime | Overtime | Project Mgmt
Sustenance Tier 2 Country Centre | 10315.8 | TL Buronga to RC |  | Susso | N/A |  | 2021-10-01: 937.8; 2021-11-01: 937.8; 2021-12-01: 937.8; 2022-01-01: 937.8; 2022-02-01: 937.8; 2022-03-01: 937.8; 2022-04-01: 937.8; 2022-05-01: 937.8; 2022-06-01: 937.8; 2022-07-01: 937.8; 2022-08-01: 937.8
Other Material | 5950 | TL Buronga to RC |  | Other Material | N/A |  | 2021-09-01: 500; 2021-10-01: 450; 2021-11-01: 450; 2021-12-01: 450; 2022-01-01: 450; 2022-02-01: 450; 2022-03-01: 450; 2022-04-01: 450; 2022-05-01: 450; 2022-06-01: 450; 2022-07-01: 450; 2022-08-01: 950
Engineer 24 - 30 | 344712.84 | TL Buronga to RC | Engineer | Program Resource | Tech Fitter |  |  |  |  | 5560.56 | 5560.56 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 11343.53 | 11343.53 | 11343.53 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35
Project Documentation/Plan and Program | 0 | [5 empty] | 2019-10-01: 0
Site Management | 234407.53 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35760.73 | 17648.63 | 17648.63 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95
Site Management | 164831.33 | [5 empty] | 2021-09-01: 24065.33; 2021-10-01: 12501.56; 2021-11-01: 12501.56; 2021-12-01: 12862.54; 2022-01-01: 12862.54; 2022-02-01: 12862.54; 2022-03-01: 12862.54; 2022-04-01: 12862.54; 2022-05-01: 12862.54; 2022-06-01: 12862.54; 2022-07-01: 12862.54; 2022-08-01: 12862.54
Sustenance Tier 2 Country Centre | 5157.9 | TL Buronga to RC |  | Susso | N/A |  | 2021-10-01: 468.9; 2021-11-01: 468.9; 2021-12-01: 468.9; 2022-01-01: 468.9; 2022-02-01: 468.9; 2022-03-01: 468.9; 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9
Senior Site Manager Lines | 159673.43 | TL Buronga to RC | Senior Site Manager Lines | Program Resource | Site Mgmt |  | 2021-09-01: 24065.33; 2021-10-01: 12032.66; 2021-11-01: 12032.66; 2021-12-01: 12393.64; 2022-01-01: 12393.64; 2022-02-01: 12393.64; 2022-03-01: 12393.64; 2022-04-01: 12393.64; 2022-05-01: 12393.64; 2022-06-01: 12393.64; 2022-07-01: 12393.64; 2022-08-01: 12393.64
Senior Site Manager Lines - Overtime | 0 | TL Buronga to RC | Senior Site Manager Lines - Overtime | Overtime | Site Mgmt
Contract Administrator | 0 |  |  | Program Resource | Project Mgmt |  | 2019-10-01: 0
Protection & Control | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other TG Resources | 0
Linesperson | 0 | TL Buronga to RC | Linesperson | Program Resource | Tech Fitter
Linesperson - Overtime | 0 | TL Buronga to RC | Linesperson - Overtime | Overtime | Tech Fitter
Commissioning | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety & Environment | 69576.2 | [5 empty] | 2021-09-01: 11695.41; 2021-10-01: 5147.06; 2021-11-01: 5147.06; 2021-12-01: 5287.41; 2022-01-01: 5287.41; 2022-02-01: 5287.41; 2022-03-01: 5287.41; 2022-04-01: 5287.41; 2022-05-01: 5287.41; 2022-06-01: 5287.41; 2022-07-01: 5287.41; 2022-08-01: 5287.41
Environmental Officer | 32887.98 | TL Buronga to RC | Environmental Officer | Program Resource | Support |  | 2021-09-01: 5970.95; 2021-10-01: 2388.38; 2021-11-01: 2388.38; 2021-12-01: 2460.03; 2022-01-01: 2460.03; 2022-02-01: 2460.03; 2022-03-01: 2460.03; 2022-04-01: 2460.03; 2022-05-01: 2460.03; 2022-06-01: 2460.03; 2022-07-01: 2460.03; 2022-08-01: 2460.03
Safety Officer | 31530.31 | TL Buronga to RC | Safety Officer | Program Resource | Support |  | 2021-09-01: 5724.46; 2021-10-01: 2289.78; 2021-11-01: 2289.78; 2021-12-01: 2358.48; 2022-01-01: 2358.48; 2022-02-01: 2358.48; 2022-03-01: 2358.48; 2022-04-01: 2358.48; 2022-05-01: 2358.48; 2022-06-01: 2358.48; 2022-07-01: 2358.48; 2022-08-01: 2358.48
Sustenance Tier 2 Country Centre | 5157.9 | TL Buronga to RC |  | Susso | N/A |  | 2021-10-01: 468.9; 2021-11-01: 468.9; 2021-12-01: 468.9; 2022-01-01: 468.9; 2022-02-01: 468.9; 2022-03-01: 468.9; 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9
Outage Plan in THEOS for Handover | 0 | [5 empty] | 2019-10-01: 0
Commissioning plan & program | 0 | [5 empty] | 2019-10-01: 0; 2019-11-01: 0
EARLY WORKS | 0 |  |  |  |  | Construction Activity | 2019-10-01: 0; 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Preliminary Studies & Planning | 0 |  |  |  |  | Construction Activity | 2019-10-01: 0; 2019-11-01: 0
Initial Concept Layouts & Surveys | 0 |  |  |  |  | Construction Activity | 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0; 2020-02-01: 0
ECI Award | 0 |  |  |  |  | Construction Activity
Early Contractor Involvement | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Initial Detailed Design | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Initial Civil & Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Transmission Line Design | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Initial Transmission Line Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Tender Specification | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Technical Specification Preparation | 0 |  |  |  |  | Construction Activity | 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0
Specification Finalisation | 0 |  |  |  |  | Construction Activity | 2020-04-01: 0
Procurement Review | 0 |  |  |  |  | Construction Activity | 2020-04-01: 0; 2020-05-01: 0
Tender Released to Market | 0 |  |  |  |  | Construction Activity
Tender and Site Visit | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0
Tender Period Closed | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0
Evaluation/ECI/Firm pricing | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0
Prepare and Issue Contract Award Documentation | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
EPC - Contract Award | 0 |  |  |  |  | Construction Activity
Delivery | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
TRANSMISSION LINE WORKS (CONTRACTOR) | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
DESIGN | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Civil Design | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Civil Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Civil Design Package IFC | 0 |  |  |  |  | Construction Activity
Transmission Line Design | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Line Schedule | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0
Structure & Fitting Designs | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Foundation Designs | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Stringing Charts | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0
PROCUREMENT & EQUIPMENT DELIVERY | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Tower Sections | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Supplier Procurement - Tower Sections | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
Initial Tower Sections Manufacture | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Tower Prototype Assembly | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0
Tower Test | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0
Tower Section Manufacture | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Tower Section Shipping | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Container de-stuffing & delivery to site | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Tower Fittings | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Supplier Procurement - Tower Fittings | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
Tower Fittings manufacture | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Tower Fittings Delivery to site | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0
Conductors | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Supplier Procurement - Conductors | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
Conductors procurement | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Conductors Delivery | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0
OHEW & OPGW | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Supplier Procurement - OHEW & OPGW | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
OHEW & OPGW Procurement | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
OHEW & OPGW Delivery | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0
CONTRACT & SITE ESTABLISHMENT | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-10-01: 0
Project Documentation | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Prepare WHSMP | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Detailed Outage Plan | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Prepare QMP, ITPs & Checklists | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Draft CEMP | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Review and Finalise CEMP | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0
Review and Finalise WHSQMP | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0
Pre-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0
Mobilisation | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
Posession of Site (POS) | 0 |  |  |  |  | Construction Activity
Site Establishment | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Post-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Commencement of Site Work | 0 |  |  |  |  | Construction Activity
330kV TRANSMISSION LINE Construction | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Access and Clearing | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Mobilise (Fixed) | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0
Survey (10 per day) | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Initial Vegetation Clearing | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Vegetation Clearing | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0
Heavy Access Track (Required for Difficult Access) | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Tower Pads and Benching | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Civil Works | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Direct Access | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Initial Earthworks, Boring (Direct Access) (Assume 4x Crews) | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Initial Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0
Initial Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0
Earthworks, Boring (Direct Access) | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Difficult Access | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Initial Earthworks, Boring (Difficult Access) | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0
Initial Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0
Initial Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0
Earthworks, Boring (Difficult Access) | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0
Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Electrical Works | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Assembly and Erection | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Tower Construction | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Initial Tower Assembly (Assume 4x Crews) | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Assemble Tower Sections | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Initial Tower Erection | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0
Tower Erection required for Stringing | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Erect Towers | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0
Stringing | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Install/Tension Conductor and OPGW | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Tower Stringing (24km) Assume 1x Crew | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Testing and Commissioning | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0
Phase Out Testing (Substation required) | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0
PRACTICAL COMPLETION | 0 |  |  |  |  | Construction Activity
Transmission Line - Border to Red Cliffs PC | 0 |  |  |  |  | Construction Activity
Transmission Line - Buronga to Darlington Point | 1526792.57 | [8 empty] | 0 | 0 | 0 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 65480.15 | 48255.84 | 48255.84 | 48255.84 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50923.46 | 0
Development | 1526792.57 | [8 empty] | 0 | 0 | 0 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 65480.15 | 48255.84 | 48255.84 | 48255.84 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50923.46 | 0
PROJECT APPROVAL | 0 | [5 empty] | 2020-01-01: 0
Project Approval and PADs | 0 | [5 empty] | 2020-01-01: 0
Development of Handover Package | 0 | [5 empty] | 2020-01-01: 0
WD Handover Document Approved | 0 | [5 empty] | 2020-01-01: 0
Project Approval Document (PAD) Issued | 0 | [5 empty] | 2020-01-01: 0
Risk Contingency | 0 | [5 empty] | 2020-01-01: 0
Project Contingency (P50) | 0 | [5 empty] | 2020-01-01: 0
WORKS DELIVERY MANAGEMENT | 1526792.57 | [8 empty] | 0 | 0 | 0 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 65480.15 | 48255.84 | 48255.84 | 48255.84 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50923.46 | 0
Project Management | 1089622.36 | [11 empty] | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 29719.41 | 30607.21 | 30607.21 | 30607.21 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 31396.12 | 31396.12 | 31396.12 | 31396.12 | 31396.12 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 32257.15
Project Management | 1089622.36 | [11 empty] | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14017.07 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 28791.72 | 29219.41 | 29719.41 | 30607.21 | 30607.21 | 30607.21 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 31396.12 | 31396.12 | 31396.12 | 31396.12 | 31396.12 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 32257.15
Senior Project Manager | 630157.27 | TL Buronga to DP | Senior Project Manager | Program Resource | Project Mgmt | [7 empty] | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8345.31 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17107.88 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97
Senior Project Manager - Overtime | 0 | TL Buronga to DP | Senior Project Manager - Overtime | Overtime | Project Mgmt
Sustenance Tier 2 Country Centre | 20631.6 | TL Buronga to DP |  | Susso | N/A |  | 2021-09-01: 937.8; 2021-10-01: 937.8; 2021-11-01: 937.8; 2021-12-01: 937.8; 2022-01-01: 937.8; 2022-02-01: 937.8; 2022-03-01: 937.8; 2022-04-01: 937.8; 2022-05-01: 937.8; 2022-06-01: 937.8; 2022-07-01: 937.8; 2022-08-01: 937.8; 2022-09-01: 937.8; 2022-10-01: 937.8; 2022-11-01: 937.8; 2022-12-01: 937.8; 2023-01-01: 937.8; 2023-02-01: 937.8; 2023-03-01: 937.8; 2023-04-01: 937.8; 2023-05-01: 937.8; 2023-06-01: 937.8
Other Material | 10900 | TL Buronga to DP |  | Other Material | N/A |  | 2021-08-01: 500; 2021-09-01: 450; 2021-10-01: 450; 2021-11-01: 450; 2021-12-01: 450; 2022-01-01: 450; 2022-02-01: 450; 2022-03-01: 450; 2022-04-01: 450; 2022-05-01: 450; 2022-06-01: 450; 2022-07-01: 450; 2022-08-01: 450; 2022-09-01: 450; 2022-10-01: 450; 2022-11-01: 450; 2022-12-01: 450; 2023-01-01: 450; 2023-02-01: 450; 2023-03-01: 450; 2023-04-01: 450; 2023-05-01: 450; 2023-06-01: 950
Engineer 24 - 30 | 427933.49 | TL Buronga to DP | Engineer | Program Resource | Tech Fitter | [7 empty] | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5841.92 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12395.38 | 12395.38 | 12395.38 | 12395.38 | 12395.38 | 12395.38 | 12395.38
Project Documentation/Plan and Program | 0 | [5 empty] | 2020-01-01: 0
Site Management | 437170.21 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35760.73 | 17648.63 | 17648.63 | 17648.63 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18666.31 | 18666.31 | 18666.31 | 18666.31 | 18666.31 | 18666.31 | 18666.31 | 0
Site Management | 308560.98 | [5 empty] | 2021-08-01: 24065.33; 2021-09-01: 12501.56; 2021-10-01: 12501.56; 2021-11-01: 12501.56; 2021-12-01: 12862.54; 2022-01-01: 12862.54; 2022-02-01: 12862.54; 2022-03-01: 12862.54; 2022-04-01: 12862.54; 2022-05-01: 12862.54; 2022-06-01: 12862.54; 2022-07-01: 12862.54; 2022-08-01: 12862.54; 2022-09-01: 12862.54; 2022-10-01: 12862.54; 2022-11-01: 12862.54; 2022-12-01: 13234.35; 2023-01-01: 13234.35; 2023-02-01: 13234.35; 2023-03-01: 13234.35; 2023-04-01: 13234.35; 2023-05-01: 13234.35; 2023-06-01: 13234.35
Sustenance Tier 2 Country Centre | 10315.8 | TL Buronga to DP |  | Susso | N/A |  | 2021-09-01: 468.9; 2021-10-01: 468.9; 2021-11-01: 468.9; 2021-12-01: 468.9; 2022-01-01: 468.9; 2022-02-01: 468.9; 2022-03-01: 468.9; 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9; 2022-09-01: 468.9; 2022-10-01: 468.9; 2022-11-01: 468.9; 2022-12-01: 468.9; 2023-01-01: 468.9; 2023-02-01: 468.9; 2023-03-01: 468.9; 2023-04-01: 468.9; 2023-05-01: 468.9; 2023-06-01: 468.9
Senior Site Manager Lines | 298245.18 | TL Buronga to DP | Senior Site Manager Lines | Program Resource | Site Mgmt |  | 2021-08-01: 24065.33; 2021-09-01: 12032.66; 2021-10-01: 12032.66; 2021-11-01: 12032.66; 2021-12-01: 12393.64; 2022-01-01: 12393.64; 2022-02-01: 12393.64; 2022-03-01: 12393.64; 2022-04-01: 12393.64; 2022-05-01: 12393.64; 2022-06-01: 12393.64; 2022-07-01: 12393.64; 2022-08-01: 12393.64; 2022-09-01: 12393.64; 2022-10-01: 12393.64; 2022-11-01: 12393.64; 2022-12-01: 12765.45; 2023-01-01: 12765.45; 2023-02-01: 12765.45; 2023-03-01: 12765.45; 2023-04-01: 12765.45; 2023-05-01: 12765.45; 2023-06-01: 12765.45
Senior Site Manager Lines - Overtime | 0 | TL Buronga to DP | Senior Site Manager Lines - Overtime | Overtime | Site Mgmt
Contract Administration | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Protection & Control | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other TG Resources | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety & Environment | 128609.22 | [5 empty] | 2021-08-01: 11695.41; 2021-09-01: 5147.06; 2021-10-01: 5147.06; 2021-11-01: 5147.06; 2021-12-01: 5287.41; 2022-01-01: 5287.41; 2022-02-01: 5287.41; 2022-03-01: 5287.41; 2022-04-01: 5287.41; 2022-05-01: 5287.41; 2022-06-01: 5287.41; 2022-07-01: 5287.41; 2022-08-01: 5287.41; 2022-09-01: 5287.41; 2022-10-01: 5287.41; 2022-11-01: 5287.41; 2022-12-01: 5431.96; 2023-01-01: 5431.96; 2023-02-01: 5431.96; 2023-03-01: 5431.96; 2023-04-01: 5431.96; 2023-05-01: 5431.96; 2023-06-01: 5431.96
Environmental Officer | 60393.28 | TL Buronga to DP | Environmental Officer | Program Resource | Support |  | 2021-08-01: 5970.95; 2021-09-01: 2388.38; 2021-10-01: 2388.38; 2021-11-01: 2388.38; 2021-12-01: 2460.03; 2022-01-01: 2460.03; 2022-02-01: 2460.03; 2022-03-01: 2460.03; 2022-04-01: 2460.03; 2022-05-01: 2460.03; 2022-06-01: 2460.03; 2022-07-01: 2460.03; 2022-08-01: 2460.03; 2022-09-01: 2460.03; 2022-10-01: 2460.03; 2022-11-01: 2460.03; 2022-12-01: 2533.83; 2023-01-01: 2533.83; 2023-02-01: 2533.83; 2023-03-01: 2533.83; 2023-04-01: 2533.83; 2023-05-01: 2533.83; 2023-06-01: 2533.83
Safety Officer | 57900.14 | TL Buronga to DP | Safety Officer | Program Resource | Support |  | 2021-08-01: 5724.46; 2021-09-01: 2289.78; 2021-10-01: 2289.78; 2021-11-01: 2289.78; 2021-12-01: 2358.48; 2022-01-01: 2358.48; 2022-02-01: 2358.48; 2022-03-01: 2358.48; 2022-04-01: 2358.48; 2022-05-01: 2358.48; 2022-06-01: 2358.48; 2022-07-01: 2358.48; 2022-08-01: 2358.48; 2022-09-01: 2358.48; 2022-10-01: 2358.48; 2022-11-01: 2358.48; 2022-12-01: 2429.23; 2023-01-01: 2429.23; 2023-02-01: 2429.23; 2023-03-01: 2429.23; 2023-04-01: 2429.23; 2023-05-01: 2429.23; 2023-06-01: 2429.23
Sustenance Tier 2 Country Centre | 10315.8 | TL Buronga to DP |  | Susso | N/A |  | 2021-09-01: 468.9; 2021-10-01: 468.9; 2021-11-01: 468.9; 2021-12-01: 468.9; 2022-01-01: 468.9; 2022-02-01: 468.9; 2022-03-01: 468.9; 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9; 2022-09-01: 468.9; 2022-10-01: 468.9; 2022-11-01: 468.9; 2022-12-01: 468.9; 2023-01-01: 468.9; 2023-02-01: 468.9; 2023-03-01: 468.9; 2023-04-01: 468.9; 2023-05-01: 468.9; 2023-06-01: 468.9
Outage Plan in THEOS for Handover | 0
Commissioning plan & program | 0 | [5 empty] | 2020-01-01: 0; 2020-02-01: 0
EARLY WORKS | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0
Preliminary Studies & Planning | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0
Initial Concept Layouts & Surveys | 0 |  |  |  |  | Construction Activity | 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0
ECI Award | 0 |  |  |  |  | Construction Activity
Early Contractor Involvement | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0
Initial Detailed Design | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Initial Civil & Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Transmission Line Design | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Initial Transmission Line Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Tender Specification | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0
Technical Specification Preparation | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Specification Finalisation | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0
Procurement Review | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0
Tender Released to Market | 0 |  |  |  |  | Construction Activity
Tender and Site Visit | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
Tender Period Closed | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Evaluation/ECI/Firm pricing | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0
Prepare and Issue Contract Award Documentation | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
EPC - Contract Award | 0 |  |  |  |  | Construction Activity
Delivery | 0 |  |  |  |  | Construction Activity | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRANSMISSION LINE WORKS (CONTRACTOR) | 0 |  |  |  |  | Construction Activity | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DESIGN | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Civil Design | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Civil Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Civil Design Package IFC | 0 |  |  |  |  | Construction Activity
Transmission Line Design | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Line Schedule | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
Structure & Fitting Designs | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Foundation Designs | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0
Stringing Charts | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0
PROCUREMENT & EQUIPMENT DELIVERY | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Tower Sections | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Supplier Procurement - Tower Sections | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
Initial Tower Sections Manufacture | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Tower Prototype Assembly | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0
Tower Test | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0
Tower Section Manufacture | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Tower Section Shipping | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Container de-stuffing & delivery to site | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Tower Fittings | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Supplier Procurement - Tower Fittings | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
Tower Fittings manufacture | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Tower Fittings Delivery to site | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0
Conductors | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Supplier Procurement - Conductors | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
Conductors Procurement | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Conductors Delivery | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0
OHEW & OPGW | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Supplier Procurement - OHEW & OPGW | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
OHEW & OPGW Procurement | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
OHEW & OPGW Delivery | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0
CONTRACT & SITE ESTABLISHMENT | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Project Documentation | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Prepare WHSMP | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Detailed Outage Plan | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Prepare QMP, ITPs & Checklists | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Draft CEMP | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Review and Finalise CEMP | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0
Review and Finalise WHSQMP | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0
Pre-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0
Mobilisation | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Posession of Site (POS) | 0 |  |  |  |  | Construction Activity
Site Establishment | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0
Commencement of Site Work | 0 |  |  |  |  | Construction Activity
Post-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0
330kV TRANSMISSION LINE Construction | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Access and Clearing | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Mobilise (Fixed) | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Initial Survey | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Survey (10 per day) | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0
Initial Vegetation Clearing | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0
Initial Tower Pads & Benching | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Heavy Access Track (Required for Difficult Access) | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Vegetation Clearing | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Tower Pads and Benching | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Civil Works | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Direct Access | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Initial Earthworks, Boring (Direct Access) (Assume 24x Crews) | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0
Initial Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0
Initial Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
Earthworks, Boring (Direct Access) | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0
Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0
Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Difficult Access | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0
Initial Earthworks, Boring (Difficult Access) | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0
Initial Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0
Initial Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Earthworks, Boring (Difficult Access) | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0
Electrical Works | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Assembly and Erection | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Tower Construction | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Initial Tower Assembly (Assume 24x Crews) | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
Assemble Tower Sections | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0
Initial Tower Erection | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0
Tower Erection required for Stringing | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Erect Remaining Towers | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Stringing | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Install/Tension Conductor and OPGW | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Tower Stringing (400km) (Assume 3x Crews) | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Testing and Commissioning | 0 |  |  |  |  | Construction Activity | 2023-06-01: 0
Phase Out Testing (Substation required) | 0 |  |  |  |  | Construction Activity | 2023-06-01: 0
PRACTICAL COMPLETION | 0 |  |  |  |  | Construction Activity
Transmission Line - Border to Darlington Point PC | 0 |  |  |  |  | Construction Activity
Transmission Line - Darlington Point to Wagga | 1261203.02 | [17 empty] | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29569.93 | 66903.48 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50923.46
Development | 1261203.02 | [17 empty] | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29569.93 | 66903.48 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50923.46
PROJECT APPROVAL | 0 | [5 empty] | 2020-07-01: 0
Project Approval and PADs | 0 | [5 empty] | 2020-07-01: 0
Development of Handover Package | 0 | [5 empty] | 2020-07-01: 0
WD Handover Document Approved | 0 | [5 empty] | 2020-07-01: 0
Project Approval Document (PAD) Issued | 0 | [5 empty] | 2020-07-01: 0
Risk Contingency | 0 | [5 empty] | 2020-07-01: 0
Project Contingency (P50) | 0 | [5 empty] | 2020-07-01: 0
WORKS DELIVERY MANAGEMENT | 1261203.02 | [17 empty] | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29569.93 | 66903.48 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49107.68 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 49546.07 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50423.46 | 50923.46
Project Management | 912205.77 | [17 empty] | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29569.93 | 30069.93 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 31396.12 | 31396.12 | 31396.12 | 31396.12 | 31396.12 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 32257.15
Project Management | 912205.77 | [17 empty] | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14225.71 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 14395.86 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29219.41 | 29569.93 | 30069.93 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 30957.73 | 31396.12 | 31396.12 | 31396.12 | 31396.12 | 31396.12 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 31757.15 | 32257.15
Senior Project Manager | 528761.79 | TL DP to Wagga | Senior Project Manager | Program Resource | Project Mgmt | [13 empty] | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 8553.94 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17535.58 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97 | 17973.97
Senior Project Manager - Overtime | 0 | TL DP to Wagga | Senior Project Manager - Overtime | Overtime | Project Mgmt
Sustenance Tier 2 Country Centre | 15942.6 | TL DP to Wagga |  | Susso | N/A |  | 2022-02-01: 937.8; 2022-03-01: 937.8; 2022-04-01: 937.8; 2022-05-01: 937.8; 2022-06-01: 937.8; 2022-07-01: 937.8; 2022-08-01: 937.8; 2022-09-01: 937.8; 2022-10-01: 937.8; 2022-11-01: 937.8; 2022-12-01: 937.8; 2023-01-01: 937.8; 2023-02-01: 937.8; 2023-03-01: 937.8; 2023-04-01: 937.8; 2023-05-01: 937.8; 2023-06-01: 937.8
Other Material | 8650 | TL DP to Wagga |  | Other Material | N/A |  | 2022-01-01: 500; 2022-02-01: 450; 2022-03-01: 450; 2022-04-01: 450; 2022-05-01: 450; 2022-06-01: 450; 2022-07-01: 450; 2022-08-01: 450; 2022-09-01: 450; 2022-10-01: 450; 2022-11-01: 450; 2022-12-01: 450; 2023-01-01: 450; 2023-02-01: 450; 2023-03-01: 450; 2023-04-01: 450; 2023-05-01: 450; 2023-06-01: 950
Engineer 24 - 30 | 358851.38 | TL DP to Wagga | Engineer | Program Resource | Tech Fitter | [13 empty] | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5671.77 | 5841.92 | 5841.92 | 5841.92 | 5841.92 | 5841.92 | 5841.92 | 5841.92 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 11683.84 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12034.35 | 12395.38 | 12395.38 | 12395.38 | 12395.38 | 12395.38 | 12395.38 | 12395.38
Project Documentation/Plan and Program | 0 | [5 empty] | 2020-07-01: 0
Site Management | 348997.25 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36833.55 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18149.95 | 18666.31 | 18666.31 | 18666.31 | 18666.31 | 18666.31 | 18666.31 | 18666.31
Site Management | 246053.17 | [5 empty] | 2022-01-01: 24787.28; 2022-02-01: 12862.54; 2022-03-01: 12862.54; 2022-04-01: 12862.54; 2022-05-01: 12862.54; 2022-06-01: 12862.54; 2022-07-01: 12862.54; 2022-08-01: 12862.54; 2022-09-01: 12862.54; 2022-10-01: 12862.54; 2022-11-01: 12862.54; 2022-12-01: 13234.35; 2023-01-01: 13234.35; 2023-02-01: 13234.35; 2023-03-01: 13234.35; 2023-04-01: 13234.35; 2023-05-01: 13234.35; 2023-06-01: 13234.35
Sustenance Tier 2 Country Centre | 7971.3 | TL DP to Wagga |  | Susso | N/A |  | 2022-02-01: 468.9; 2022-03-01: 468.9; 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9; 2022-09-01: 468.9; 2022-10-01: 468.9; 2022-11-01: 468.9; 2022-12-01: 468.9; 2023-01-01: 468.9; 2023-02-01: 468.9; 2023-03-01: 468.9; 2023-04-01: 468.9; 2023-05-01: 468.9; 2023-06-01: 468.9
Senior Site Manager Lines | 238081.87 | TL DP to Wagga | Senior Site Manager Lines | Program Resource | Site Mgmt |  | 2022-01-01: 24787.28; 2022-02-01: 12393.64; 2022-03-01: 12393.64; 2022-04-01: 12393.64; 2022-05-01: 12393.64; 2022-06-01: 12393.64; 2022-07-01: 12393.64; 2022-08-01: 12393.64; 2022-09-01: 12393.64; 2022-10-01: 12393.64; 2022-11-01: 12393.64; 2022-12-01: 12765.45; 2023-01-01: 12765.45; 2023-02-01: 12765.45; 2023-03-01: 12765.45; 2023-04-01: 12765.45; 2023-05-01: 12765.45; 2023-06-01: 12765.45
Senior Site Manager Lines - Overtime | 0 | TL DP to Wagga | Senior Site Manager Lines - Overtime | Overtime | Site Mgmt
Contract Administration | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Protection & Control | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other TG Resources | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Safety & Environment | 102944.08 | [5 empty] | 2022-01-01: 12046.27; 2022-02-01: 5287.41; 2022-03-01: 5287.41; 2022-04-01: 5287.41; 2022-05-01: 5287.41; 2022-06-01: 5287.41; 2022-07-01: 5287.41; 2022-08-01: 5287.41; 2022-09-01: 5287.41; 2022-10-01: 5287.41; 2022-11-01: 5287.41; 2022-12-01: 5431.96; 2023-01-01: 5431.96; 2023-02-01: 5431.96; 2023-03-01: 5431.96; 2023-04-01: 5431.96; 2023-05-01: 5431.96; 2023-06-01: 5431.96
Environmental Officer | 48487.21 | TL DP to Wagga | Environmental Officer | Program Resource | Support |  | 2022-01-01: 6150.08; 2022-02-01: 2460.03; 2022-03-01: 2460.03; 2022-04-01: 2460.03; 2022-05-01: 2460.03; 2022-06-01: 2460.03; 2022-07-01: 2460.03; 2022-08-01: 2460.03; 2022-09-01: 2460.03; 2022-10-01: 2460.03; 2022-11-01: 2460.03; 2022-12-01: 2533.83; 2023-01-01: 2533.83; 2023-02-01: 2533.83; 2023-03-01: 2533.83; 2023-04-01: 2533.83; 2023-05-01: 2533.83; 2023-06-01: 2533.83
Safety Officer | 46485.57 | TL DP to Wagga | Safety Officer | Program Resource | Support |  | 2022-01-01: 5896.19; 2022-02-01: 2358.48; 2022-03-01: 2358.48; 2022-04-01: 2358.48; 2022-05-01: 2358.48; 2022-06-01: 2358.48; 2022-07-01: 2358.48; 2022-08-01: 2358.48; 2022-09-01: 2358.48; 2022-10-01: 2358.48; 2022-11-01: 2358.48; 2022-12-01: 2429.23; 2023-01-01: 2429.23; 2023-02-01: 2429.23; 2023-03-01: 2429.23; 2023-04-01: 2429.23; 2023-05-01: 2429.23; 2023-06-01: 2429.23
Sustenance Tier 2 Country Centre | 7971.3 | TL DP to Wagga |  | Susso | N/A |  | 2022-02-01: 468.9; 2022-03-01: 468.9; 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9; 2022-09-01: 468.9; 2022-10-01: 468.9; 2022-11-01: 468.9; 2022-12-01: 468.9; 2023-01-01: 468.9; 2023-02-01: 468.9; 2023-03-01: 468.9; 2023-04-01: 468.9; 2023-05-01: 468.9; 2023-06-01: 468.9
Outage Plan in THEOS for Handover | 0 | [5 empty] | 2020-07-01: 0
Commissioning plan & program | 0 | [5 empty] | 2020-07-01: 0; 2020-08-01: 0
EARLY WORKS | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Preliminary Studies & Planning | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0
Initial Concept Layouts & Surveys | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
ECI Award | 0 |  |  |  |  | Construction Activity
Early Contractor Involvement | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Initial Detailed Design | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Initial Civil & Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Transmission Line Design | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Initial Transmission Line Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Tender Specification | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Technical Specification Preparation | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0
Specification Finalisation | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0
Procurement Review | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0
Tender Released to Market | 0 |  |  |  |  | Construction Activity
Tender and Site Visit | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0
Tender Period Closed | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Evaluation/ECI/Firm pricing | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
Prepare and Issue Contract Award Documentation | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
EPC - Contract Award | 0 |  |  |  |  | Construction Activity
Delivery | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
TRANSMISSION LINE WORKS (CONTRACTOR) | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
DESIGN | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Civil Design | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Civil Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Civil Design Package IFC | 0 |  |  |  |  | Construction Activity
Transmission Line Design | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Line Schedule | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Structure & Fitting Designs | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0
Foundation Designs | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0
Stringing Charts | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
PROCUREMENT & EQUIPMENT DELIVERY | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Tower Sections | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Supplier Procurement - Tower Sections | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Initial Tower Sections Manufacture | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Tower Prototype Assembly | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Tower Test | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0
Tower Section Manufacture | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Tower Section Shipping | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Container de-stuffing & delivery to site | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0
Tower Fittings | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Supplier Procurement - Tower Fittings | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Tower Fittings manufacture | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Tower Fittings Delivery to site | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0
Conductors | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Supplier Procurement - Conductors | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Conductors procurement | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Conductors Delivery | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0
OHEW & OPGW | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
Supplier Procurement - OHEW & OPGW | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
OHEW & OPGW Procurement | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
OHEW & OPGW Delivery | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0
CONTRACT & SITE ESTABLISHMENT | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2022-01-01: 0; 2022-02-01: 0
Project Documentation | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Prepare WHSMP | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Detailed Outage Plan | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Prepare QMP, ITPs & Checklists | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Draft CEMP | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Review and Finalise CEMP | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0
Review and Finalise WHSQMP | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Pre-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Mobilisation | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0
Posession of Site (POS) | 0 |  |  |  |  | Construction Activity
Site Establishment | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0
Commencement of Site Work | 0 |  |  |  |  | Construction Activity
Post-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0
330kV TRANSMISSION LINE Construction | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Access and Clearing | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Mobilise (Fixed) | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0
Survey (10 per day) (2x Crew) | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0
Initial Vegetation Clearing | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0
Initial Tower Pads & Benching | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0
Heavy Access Track (Required for Difficult Access) | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0
Vegetation Clearing | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0
Tower Pads and Benching | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Civil Works | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0
Tower Foundations | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0
Direct Access | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0
Initial Earthworks, Boring (Direct Access) (12x Crew) | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0
Initial Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0
Initial Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0
Earthworks, Boring (Direct Access) | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0
Difficult Access | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0
Initial Earthworks, Boring (Difficult Access) (12x Crew) | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0
Initial Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0; 2022-08-01: 0
Initial Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0; 2022-09-01: 0
Earthworks, Boring (Difficult Access) | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0
Install Tower Foundations | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0
Curing & Backfill | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0
Electrical Works | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Assembly and Erection | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Tower Construction | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Initial Tower Assembly | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0
Assemble Tower Sections | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Initial Tower Erection | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0; 2022-08-01: 0
Tower Erection required for Stringing | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0
Erect Towers | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Stringing | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Install/Tension Conductor and OPGW | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Tower Stringing (152km) (Assume 2x Crews) | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0
Testing and Commissioning | 0 |  |  |  |  | Construction Activity | 2023-06-01: 0
Phase Out Testing (Substation required) | 0 |  |  |  |  | Construction Activity | 2023-06-01: 0
PRACTICAL COMPLETION | 0 |  |  |  |  | Construction Activity
Transmission Line - Darlington Point to Wagga PC | 0 |  |  |  |  | Construction Activity
Buronga Substation | 6820012.51 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36836.67 | 36836.67 | 36836.67 | 37941.77 | 49637.18 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 112254.88 | 112254.88 | 501301.45 | 501301.45 | 560684.11 | 560684.11 | 501301.45 | 501301.45 | 563936.04 | 610955.26 | 665544.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338365.87
Development | 6820012.51 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36836.67 | 36836.67 | 36836.67 | 37941.77 | 49637.18 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 112254.88 | 112254.88 | 501301.45 | 501301.45 | 560684.11 | 560684.11 | 501301.45 | 501301.45 | 563936.04 | 610955.26 | 665544.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338365.87
PROJECT APPROVAL | 0 | [5 empty] | 2019-10-01: 0
Project Approval and PADs | 0 | [5 empty] | 2019-10-01: 0
Development of Handover Package | 0 | [5 empty] | 2019-10-01: 0
WD Handover Document Approved | 0 | [5 empty] | 2019-10-01: 0
Project Approval Document (PAD) Issued | 0 | [5 empty] | 2019-10-01: 0
Risk Contingency | 0 | [5 empty] | 2019-10-01: 0
Project Contingency (P50) | 0 | [5 empty] | 2019-10-01: 0
WORKS DELIVERY MANAGEMENT | 6820012.51 | [8 empty] | 0 | 0 | [9 empty] | 36836.67 | 36836.67 | 36836.67 | 37941.77 | 49637.18 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 112254.88 | 112254.88 | 501301.45 | 501301.45 | 560684.11 | 560684.11 | 501301.45 | 501301.45 | 563936.04 | 610955.26 | 665544.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338365.87
Project Management | 32286.18 | [5 empty] | 2019-10-01: 0; 2023-08-01: 32286.18
Project Management | 32286.18 | [5 empty] | 2023-08-01: 32286.18
Senior Project Manager | 27634.97 | Buronga Sub | Senior Project Manager | Program Resource | Project Mgmt |  | 2023-08-01: 27634.97
Senior Project Manager - Overtime | 3947.85 | Buronga Sub | Senior Project Manager - Overtime | Overtime | Project Mgmt |  | 2023-08-01: 3947.85
Sustenance Tier 2 Country Centre | 703.35 | Buronga Sub |  | Susso | N/A |  | 2023-08-01: 703.35
Other Material | 0 | Buronga Sub |  | Other Material | N/A
Project Documentation/Plan and Program | 0 | [5 empty] | 2019-10-01: 0
Site Management | 6787726.33 | [8 empty] | 0 | 0 | [9 empty] | 36836.67 | 36836.67 | 36836.67 | 37941.77 | 49637.18 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 109203.84 | 112254.88 | 112254.88 | 501301.45 | 501301.45 | 560684.11 | 560684.11 | 501301.45 | 501301.45 | 563936.04 | 610955.26 | 665544.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306079.7
Site Management | 3478777.56 | [19 empty] | 36836.67 | 36836.67 | 36836.67 | 37941.77 | 37941.77 | 104056.77 | 104056.77 | 104056.77 | 104056.77 | 104056.77 | 104056.77 | 104056.77 | 104056.77 | 104056.77 | 104056.77 | 106967.47 | 106967.47 | 213934.94 | 213934.94 | 213934.94 | 213934.94 | 213934.94 | 213934.94 | 213934.94 | 213934.94 | 213934.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112466.82
Senior Site Manager Subs | 873770.96 | Buronga Sub | Senior Site Manager Subs | Program Resource | Site Mgmt | [15 empty] | 23364.39 | 23364.39 | 23364.39 | 24065.33 | 24065.33 | 24065.33 | 24065.33 | 24065.33 | 24065.33 | 24065.33 | 24065.33 | 24065.33 | 24065.33 | 24065.33 | 24065.33 | 24787.28 | 24787.28 | 49574.57 | 49574.57 | 49574.57 | 49574.57 | 49574.57 | 49574.57 | 49574.57 | 49574.57 | 49574.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19148.18
Senior Site Manager Subs - Overtime | 1176496.41 | Buronga Sub | Senior Site Manager Subs - Overtime | Overtime | Site Mgmt | [20 empty] | 37473.2 | 37473.2 | 37473.2 | 37473.2 | 37473.2 | 37473.2 | 37473.2 | 37473.2 | 37473.2 | 37473.2 | 38597.4 | 38597.4 | 77194.79 | 77194.79 | 77194.79 | 77194.79 | 77194.79 | 77194.79 | 77194.79 | 77194.79 | 77194.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29816.49
Sustenance Tier 2 Country Centre | 218038.5 | Buronga Sub |  | Susso | N/A | [20 empty] | 7033.5 | 7033.5 | 7033.5 | 7033.5 | 7033.5 | 7033.5 | 7033.5 | 7033.5 | 7033.5 | 7033.5 | 7033.5 | 7033.5 | 14067 | 14067 | 14067 | 14067 | 14067 | 14067 | 14067 | 14067 | 14067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033.5
Construction Manager | 514871.36 | Buronga Sub | Construction Manager | Program Resource | Site Mgmt | [15 empty] | 13472.28 | 13472.28 | 13472.28 | 13876.45 | 13876.45 | 13876.45 | 13876.45 | 13876.45 | 13876.45 | 13876.45 | 13876.45 | 13876.45 | 13876.45 | 13876.45 | 13876.45 | 14292.74 | 14292.74 | 28585.48 | 28585.48 | 28585.48 | 28585.48 | 28585.48 | 28585.48 | 28585.48 | 28585.48 | 28585.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22082.29
Construction Manager - Overtime | 695600.33 | Buronga Sub | Construction Manager - Overtime | Overtime | Site Mgmt | [20 empty] | 21608.3 | 21608.3 | 21608.3 | 21608.3 | 21608.3 | 21608.3 | 21608.3 | 21608.3 | 21608.3 | 21608.3 | 22256.55 | 22256.55 | 44513.1 | 44513.1 | 44513.1 | 44513.1 | 44513.1 | 44513.1 | 44513.1 | 44513.1 | 44513.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34386.37
Contract Administration | 0
Other TG Resources | 403068.62 | [5 empty] | 2022-02-01: 10556.38; 2022-03-01: 10556.38; 2022-04-01: 69939.03; 2022-05-01: 69939.03; 2022-06-01: 10556.38; 2022-07-01: 10556.38; 2022-08-01: 10556.38; 2022-09-01: 57575.6; 2022-10-01: 112164.55; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 40668.51
Substations Fitter | 110448.14 | Buronga Sub | Substations Fitter | Program Resource | Tech Fitter |  | 2022-02-01: 3761.54; 2022-03-01: 3761.54; 2022-04-01: 3761.54; 2022-05-01: 3761.54; 2022-06-01: 3761.54; 2022-07-01: 3761.54; 2022-08-01: 3761.54; 2022-09-01: 50780.75; 2022-10-01: 18807.69; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 14528.94
Substations Fitter - Overtime | 98764.36 | Buronga Sub | Substations Fitter - Overtime | Overtime | Tech Fitter |  | 2022-02-01: 5857.04; 2022-03-01: 5857.04; 2022-04-01: 5857.04; 2022-05-01: 5857.04; 2022-06-01: 5857.04; 2022-07-01: 5857.04; 2022-08-01: 5857.04; 2022-09-01: 5857.04; 2022-10-01: 29285.21; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 22622.82
Sustenance Tier 2 Country Centre | 29775.15 | Buronga Sub |  | Susso | N/A |  | 2022-02-01: 937.8; 2022-03-01: 937.8; 2022-04-01: 5626.8; 2022-05-01: 5626.8; 2022-06-01: 937.8; 2022-07-01: 937.8; 2022-08-01: 937.8; 2022-09-01: 937.8; 2022-10-01: 9378; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 3516.75
Telecommunications Technician | 64166.11 | Buronga Sub | Telecommunications Technician | Program Resource | Tech Mgmt |  | 2022-04-01: 21388.7; 2022-05-01: 21388.7; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 21388.7
Telecommunications Technician - Overtime | 99914.86 | Buronga Sub | Telecommunications Technician - Overtime | Overtime | Tech Mgmt |  | 2022-04-01: 33304.95; 2022-05-01: 33304.95; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 33304.95
Safety & Environment | 121327.51 | [5 empty] | 2021-01-01: 11695.41; 2021-02-01: 5147.06; 2021-03-01: 5147.06; 2021-04-01: 5147.06; 2021-05-01: 5147.06; 2021-06-01: 5147.06; 2021-07-01: 5147.06; 2021-08-01: 5147.06; 2021-09-01: 5147.06; 2021-10-01: 5147.06; 2021-11-01: 5147.06; 2021-12-01: 5287.41; 2022-01-01: 5287.41; 2022-02-01: 5287.41; 2022-03-01: 5287.41; 2022-04-01: 5287.41; 2022-05-01: 5287.41; 2022-06-01: 5287.41; 2022-07-01: 5287.41; 2022-08-01: 5287.41; 2022-09-01: 5287.41; 2022-10-01: 5287.41
Environmental Officer | 56915.08 | Buronga Sub | Environmental Officer | Program Resource | Support |  | 2021-01-01: 5970.95; 2021-02-01: 2388.38; 2021-03-01: 2388.38; 2021-04-01: 2388.38; 2021-05-01: 2388.38; 2021-06-01: 2388.38; 2021-07-01: 2388.38; 2021-08-01: 2388.38; 2021-09-01: 2388.38; 2021-10-01: 2388.38; 2021-11-01: 2388.38; 2021-12-01: 2460.03; 2022-01-01: 2460.03; 2022-02-01: 2460.03; 2022-03-01: 2460.03; 2022-04-01: 2460.03; 2022-05-01: 2460.03; 2022-06-01: 2460.03; 2022-07-01: 2460.03; 2022-08-01: 2460.03; 2022-09-01: 2460.03; 2022-10-01: 2460.03
Safety Officer | 54565.53 | Buronga Sub | Safety Officer | Program Resource | Support |  | 2021-01-01: 5724.46; 2021-02-01: 2289.78; 2021-03-01: 2289.78; 2021-04-01: 2289.78; 2021-05-01: 2289.78; 2021-06-01: 2289.78; 2021-07-01: 2289.78; 2021-08-01: 2289.78; 2021-09-01: 2289.78; 2021-10-01: 2289.78; 2021-11-01: 2289.78; 2021-12-01: 2358.48; 2022-01-01: 2358.48; 2022-02-01: 2358.48; 2022-03-01: 2358.48; 2022-04-01: 2358.48; 2022-05-01: 2358.48; 2022-06-01: 2358.48; 2022-07-01: 2358.48; 2022-08-01: 2358.48; 2022-09-01: 2358.48; 2022-10-01: 2358.48
Sustenance Tier 2 Country Centre | 9846.9 | Buronga Sub |  | Susso | N/A |  | 2021-02-01: 468.9; 2021-03-01: 468.9; 2021-04-01: 468.9; 2021-05-01: 468.9; 2021-06-01: 468.9; 2021-07-01: 468.9; 2021-08-01: 468.9; 2021-09-01: 468.9; 2021-10-01: 468.9; 2021-11-01: 468.9; 2021-12-01: 468.9; 2022-01-01: 468.9; 2022-02-01: 468.9; 2022-03-01: 468.9; 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9; 2022-09-01: 468.9; 2022-10-01: 468.9
Protection & Control | 2784552.64 | [5 empty] | 2022-02-01: 271522.72; 2022-03-01: 271522.72; 2022-04-01: 271522.72; 2022-05-01: 271522.72; 2022-06-01: 271522.72; 2022-07-01: 271522.72; 2022-08-01: 334157.31; 2022-09-01: 334157.31; 2022-10-01: 334157.31; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 152944.36
Control Technician | 502415.46 | Buronga Sub | Control Technician | Program Resource | Tech Mgmt |  | 2022-02-01: 53526.75; 2022-03-01: 53526.75; 2022-04-01: 53526.75; 2022-05-01: 53526.75; 2022-06-01: 53526.75; 2022-07-01: 53526.75; 2022-08-01: 53526.75; 2022-09-01: 53526.75; 2022-10-01: 53526.75; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 20674.71
Control Technician - Overtime | 782332.65 | Buronga Sub | Control Technician - Overtime | Overtime | Tech Mgmt |  | 2022-02-01: 83348.8; 2022-03-01: 83348.8; 2022-04-01: 83348.8; 2022-05-01: 83348.8; 2022-06-01: 83348.8; 2022-07-01: 83348.8; 2022-08-01: 83348.8; 2022-09-01: 83348.8; 2022-10-01: 83348.8; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 32193.47
Secondary Systems Technician | 510889.53 | Buronga Sub | Secondary Systems Technician | Program Resource | Tech Mgmt |  | 2022-02-01: 45321.76; 2022-03-01: 45321.76; 2022-04-01: 45321.76; 2022-05-01: 45321.76; 2022-06-01: 45321.76; 2022-07-01: 45321.76; 2022-08-01: 67982.64; 2022-09-01: 67982.64; 2022-10-01: 67982.64; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 35011.06
Secondary Systems Technician - Overtime | 795493.75 | Buronga Sub | Secondary Systems Technician - Overtime | Overtime | Tech Mgmt |  | 2022-02-01: 70569.42; 2022-03-01: 70569.42; 2022-04-01: 70569.42; 2022-05-01: 70569.42; 2022-06-01: 70569.42; 2022-07-01: 70569.42; 2022-08-01: 105854.12; 2022-09-01: 105854.12; 2022-10-01: 105854.12; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 54514.87
Sustenance Tier 2 Country Centre | 193421.25 | Buronga Sub |  | Susso | N/A |  | 2022-02-01: 18756; 2022-03-01: 18756; 2022-04-01: 18756; 2022-05-01: 18756; 2022-06-01: 18756; 2022-07-01: 18756; 2022-08-01: 23445; 2022-09-01: 23445; 2022-10-01: 23445; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 10550.25
Outage Plan in THEOS for Handover | 0 | [5 empty] | 2019-10-01: 0
Commissioning plan & program | 0 | [5 empty] | 2019-10-01: 0; 2019-11-01: 0
EARLY WORKS | 0 |  |  |  |  | Construction Activity | 2019-10-01: 0; 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Preliminary Studies & Planning | 0 |  |  |  |  | Construction Activity | 2019-10-01: 0; 2019-11-01: 0
Initial Concept Layouts & Surveys | 0 |  |  |  |  | Construction Activity | 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0
Commence Early Contractor Involvement (ECI) | 0 |  |  |  |  | Construction Activity
Early Contractor Involvement | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Initial Detailed Design | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Initial Civil & Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
High Voltage Design | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Initial HV Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Secondary System Design | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Initial Secondary System Designs | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
CONTRACT MANAGEMENT | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Contract Administration | 0 |  |  |  |  | Construction Activity
Tender Specification | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0
Technical Specification Preparation | 0 |  |  |  |  | Construction Activity | 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0
Specification Finalisation | 0 |  |  |  |  | Construction Activity | 2020-04-01: 0
Procurement Review | 0 |  |  |  |  | Construction Activity | 2020-04-01: 0
Tender Released to Market | 0 |  |  |  |  | Construction Activity
Tender and Site Visit | 0 |  |  |  |  | Construction Activity | 2020-04-01: 0; 2020-05-01: 0
Tender Period Closed | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0
Evaluation/ECI/Firm pricing | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0
Prepare and Issue Contract Award Documentation | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0
EPC - Contract Award | 0 |  |  |  |  | Construction Activity
Delivery | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2023-08-01: 0
330KV SUBSTATION CONTRACT WORKS | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0
DESIGN | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0
Civil Design | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Civil Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Civil Package IFC | 0 |  |  |  |  | Construction Activity
Structural Design | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0
Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Equipment, Gantry and Minor Foundations | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
Compounds and spill oil tank | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0
Miscellaneous | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0
Structural Package IFC | 0 |  |  |  |  | Construction Activity
High Voltage Design | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0
Structural Interface Document | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
SLD IFC | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0
Layouts | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0
Bay Elevations | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0
Conduits | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0
Earthing | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0
Building | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0
Miscellaneous | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0
HV Design Package Review | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
HV Design Package Ammendment | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0
HV Design IFC | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0
Secondary Design | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0
Protection Design | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Protection Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Protection Design Package IFC | 0 |  |  |  |  | Construction Activity
Automation Database | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Automation Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Automation Design Package IFC | 0 |  |  |  |  | Construction Activity
Communication Design | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0
Communication Design | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0
Prot Panel Layouts, schematics and label schedules | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0
Cables Schedules & connection diagrams | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0
CONSTRUCTION PROCUREMENT | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Procurement (LLE) | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Initial Procurement (LLE) | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Power Transformer (2x 400MVA) | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Power Transformer Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Initial Power Transformer Manufacture | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Finalise Trasformer Procurement | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Transformer Delivery | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Synchronous Condensers (2x 100MVAr) | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Synchronous Condensers Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Initial Sync Cond Manufacture | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Finalise Synchronous Condensers Procurement | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Synchronous Cond Delivery to Site | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Capacitor Banks (2x 330kV 50MVAr ) | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Capacitor Bank Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Initial Capacitor Bank Manufacture | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Finalise Capacitor Bank Procurement | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Capacitor Bank delivery to site | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Phase Shift Transformers (3x 330kV 400MVA) | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
PST Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Initial PST Manufacture | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Finalise PST Procurement | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
PST delivery to site | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Shunt Reactors (2x 330kV 60MVAr & 2x 330kV 50MVAr) | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Reactor Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Initial Shunt Reactor Manufacture | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
Finalise Reactor Procurement | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Reactor delivery to site | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
SSB (x 2) | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Finalise SSB Procurement | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0
SSB Manufacture and Deliver | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
SSB Manufacturer Design and Approval | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
SSB Manufacture | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0
SSB Fitout, FAT and Delivered | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Materials | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
HV Cables, Conductor and Fittings | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Secondary System Equipment | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Earthing Strap | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Steelwork | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Drainage materials | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0
LV Cables | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
DOCUMENTATION & SITE ESTABLISHMENT | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-02-01: 0
Project Documentation | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0
Prepare WHSMP | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
Detailed Outage Plan | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
Draft CEMP | 0 |  |  |  |  | Construction Activity | 2020-08-01: 0; 2020-09-01: 0
Review and Finalise WHSQMP | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0
Review and Finalise CEMP | 0 |  |  |  |  | Construction Activity | 2020-09-01: 0; 2020-10-01: 0
Pre-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0
Mobilisation | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Posession of Site (POS) | 0 |  |  |  |  | Construction Activity
Site Establishment | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0
Post-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0
Commencement of Site Works | 0 |  |  |  |  | Construction Activity
330kV SUBSTATION WORKS | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0
Civil Construction | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Earthworks, Bench and Drainage | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Security, Fencing and Lighting | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0
Trench and Conduit | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
HV Equipment and Support Structure Footings | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Initial HV Equipment and Support Structure Footings | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Initial Equipment Footing Curing | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
HV Equipment and Support Structure Footings | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
HV Equipment Foundation Curing | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Transformer Bunds | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
PST Bund 1,2,3 | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Tx 1 Bund | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Tx 2 Bund | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Reactor Bunds | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Reactor Bund 1 | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Reactor Bund 2,3,4 | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Synchronous Condenser Foundation | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Synchronous Condenser 1 Foundation | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Synchronous Condenser 2 Foundation | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Capacitor Bank Foundations | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Capacitor Bank 1 Foundation | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Capacitor Bank 2 Foundation | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Secondary Systems Buildings | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Building Foundations | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Site Earthworks | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0
Piling | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0
Formwork | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0
Tube in Electrical Conduits | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0
Pour Concrete | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Curing | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0
Miscellaneous Yard Foundations | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Excavate Foundations | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Curing | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0
Civil Construction Completion | 0 |  |  |  |  | Construction Activity
Steelwork Construction | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Initial HV Equipment Support Structures | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0
HV Equipment Support Structures | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Electrical Construction | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0
Earthgrid | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
Install Earthgrid | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
Switchyard Works | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Miscellaneous Equipment | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
Switchyard Cabling | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
Finalise Switchyard Cabling | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0
HV Equipment Installation | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Initial Installation of HV Equipment | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0
Installation of HV Equipment | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Install 220kV/330kV Connection Bus | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Secondary System | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
SSB Installation works | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0
Teminate SSB Cabling | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Installation of Capacitor Banks (2x 330kV 50MVAr) | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Capacitor Bank No.1 Installation | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
Capacitor Bank No.2 Installation | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Installation of Power Transformers (2x 400MVA) | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Installation of Tx 1 | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0
Installation of Tx 2 | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Installation of Synchronous Condensers (2x 100MVAr) | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Installation of Synchronous Condensor (No.1) | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Installation of Synchronous Condensor (No.2) | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Installation of Reactors (2x 330kV 60MVAr & 2x 330kV 50MVAr) | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Reactor No.1 Installation | 0 |  |  |  |  | Construction Activity | 2021-12-01: 0; 2022-01-01: 0
Reactor No.2 Installation | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0
Reactor No.3 Installation | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0
Reactor No.4 Installation | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Installation of PST (3x 330kV 400MVA) | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
Installation of PST 1 | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0
Installation of PST 2 and 3 | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
HV Equipment Installation Complete | 0 |  |  |  |  | Construction Activity
Testing & Pre-Commissioning | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0
Testing and Commissioning (All Assets) | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0
BBP and VT Balance | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0; 2022-09-01: 0
Substation Ready for Commissioning | 0 |  |  |  |  | Construction Activity
Demobilisation | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0
Demobilise from Site | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0
TESTING & COMMISSIONING (TG) | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2023-08-01: 0
Energise and Inservice Checks | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0
Energise and Inservice Checks (PST and Line Reactors) | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
PRACTICAL COMPLETION | 0 |  |  |  |  | Construction Activity
Practical Completion and Ready to Energise | 0 |  |  |  |  | Construction Activity
Red Cliffs Substation | 801711.33 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12046.27 | 73361.09 | 73361.09 | 73361.09 | 73361.09 | 103052.42 | 101572.62 | 291595.67
Development | 801711.33 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12046.27 | 73361.09 | 73361.09 | 73361.09 | 73361.09 | 103052.42 | 101572.62 | 291595.67
PROJECT APPROVAL | 0 | [5 empty] | 2020-05-01: 0
Project Approval and PADs | 0 | [5 empty] | 2020-05-01: 0
Development of Handover Package | 0 | [5 empty] | 2020-05-01: 0
WD Handover Document Approved | 0 | [5 empty] | 2020-05-01: 0
Project Approval Document (PAD) Issued | 0 | [5 empty] | 2020-05-01: 0
Risk Contingency | 0 | [5 empty] | 2020-05-01: 0
Project Contingency (P50) | 0 | [5 empty] | 2020-05-01: 0
WORKS DELIVERY MANAGEMENT | 801711.33 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12046.27 | 73361.09 | 73361.09 | 73361.09 | 73361.09 | 103052.42 | 101572.62 | 291595.67
Project Management | 0 | [5 empty] | 2020-05-01: 0
Project Management | 0
Senior Project Manager | 0 | RC Sub | Senior Project Manager | Program Resource | Project Mgmt
Senior Project Manager - Overtime | 0 | RC Sub | Senior Project Manager - Overtime | Overtime | Project Mgmt
Sustenance Tier 2 Country Centre | 0 | RC Sub |  | Susso | N/A
Other Material | 0 | RC Sub |  | Other Material | N/A
Project Documentation/Plan and Program | 0 | [5 empty] | 2020-05-01: 0
Site Management | 801711.33 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12046.27 | 73361.09 | 73361.09 | 73361.09 | 73361.09 | 103052.42 | 101572.62 | 291595.67
Site Management | 476515.77 | [5 empty] | 2022-04-01: 68073.68; 2022-05-01: 68073.68; 2022-06-01: 68073.68; 2022-07-01: 68073.68; 2022-08-01: 68073.68; 2022-09-01: 68073.68; 2022-10-01: 68073.68
Senior Site Manager Subs | 173510.99 | RC Sub | Senior Site Manager Subs | Program Resource | Site Mgmt |  | 2022-04-01: 24787.28; 2022-05-01: 24787.28; 2022-06-01: 24787.28; 2022-07-01: 24787.28; 2022-08-01: 24787.28; 2022-09-01: 24787.28; 2022-10-01: 24787.28
Senior Site Manager Subs - Overtime | 270181.77 | RC Sub | Senior Site Manager Subs - Overtime | Overtime | Site Mgmt |  | 2022-04-01: 38597.4; 2022-05-01: 38597.4; 2022-06-01: 38597.4; 2022-07-01: 38597.4; 2022-08-01: 38597.4; 2022-09-01: 38597.4; 2022-10-01: 38597.4
Sustenance Tier 2 Country Centre | 32823 | RC Sub |  | Susso | N/A |  | 2022-04-01: 4689; 2022-05-01: 4689; 2022-06-01: 4689; 2022-07-01: 4689; 2022-08-01: 4689; 2022-09-01: 4689; 2022-10-01: 4689
Contract Administration | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other TG Resources | 140376.08 | [5 empty] | 2022-08-01: 29691.33; 2022-09-01: 28211.53; 2022-10-01: 82473.22
Substations Fitter | 47019.22 | RC Sub | Substations Fitter | Program Resource | Tech Fitter |  | 2022-09-01: 28211.53; 2022-10-01: 18807.69
Substations Fitter - Overtime | 29285.21 | RC Sub | Substations Fitter - Overtime | Overtime | Tech Fitter |  | 2022-10-01: 29285.21
Sustenance Tier 2 Country Centre | 9378 | RC Sub |  | Susso | N/A |  | 2022-08-01: 2344.5; 2022-09-01: 0; 2022-10-01: 7033.5
Telecommunications Technician | 21388.7 | RC Sub | Telecommunications Technician | Program Resource | Tech Mgmt |  | 2022-08-01: 10694.35; 2022-09-01: 0; 2022-10-01: 10694.35
Telecommunications Technician - Overtime | 33304.95 | RC Sub | Telecommunications Technician - Overtime | Overtime | Tech Mgmt |  | 2022-08-01: 16652.48; 2022-09-01: 0; 2022-10-01: 16652.48
Safety & Environment | 49058.12 | [5 empty] | 2022-03-01: 12046.27; 2022-04-01: 5287.41; 2022-05-01: 5287.41; 2022-06-01: 5287.41; 2022-07-01: 5287.41; 2022-08-01: 5287.41; 2022-09-01: 5287.41; 2022-10-01: 5287.41
Environmental Officer | 23370.29 | RC Sub | Environmental Officer | Program Resource | Support |  | 2022-03-01: 6150.08; 2022-04-01: 2460.03; 2022-05-01: 2460.03; 2022-06-01: 2460.03; 2022-07-01: 2460.03; 2022-08-01: 2460.03; 2022-09-01: 2460.03; 2022-10-01: 2460.03
Safety Officer | 22405.53 | RC Sub | Safety Officer | Program Resource | Support |  | 2022-03-01: 5896.19; 2022-04-01: 2358.48; 2022-05-01: 2358.48; 2022-06-01: 2358.48; 2022-07-01: 2358.48; 2022-08-01: 2358.48; 2022-09-01: 2358.48; 2022-10-01: 2358.48
Sustenance Tier 2 Country Centre | 3282.3 | RC Sub |  | Susso | N/A |  | 2022-04-01: 468.9; 2022-05-01: 468.9; 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9; 2022-09-01: 468.9; 2022-10-01: 468.9
Protection & Control | 135761.36 | [5 empty] | 2022-10-01: 135761.36
Control Technician | 26763.38 | RC Sub | Control Technician | Program Resource | Tech Mgmt |  | 2022-10-01: 26763.38
Control Technician - Overtime | 41674.4 | RC Sub | Control Technician - Overtime | Overtime | Tech Mgmt |  | 2022-10-01: 41674.4
Secondary Systems Technician | 22660.88 | RC Sub | Secondary Systems Technician | Program Resource | Tech Mgmt |  | 2022-10-01: 22660.88
Secondary Systems Technician - Overtime | 35284.71 | RC Sub | Secondary Systems Technician - Overtime | Overtime | Tech Mgmt |  | 2022-10-01: 35284.71
Sustenance Tier 2 Country Centre | 9378 | RC Sub |  | Susso | N/A |  | 2022-10-01: 9378
Outage Plan in THEOS for Handover | 0 | [5 empty] | 2020-05-01: 0
Commissioning plan & program | 0 | [5 empty] | 2020-05-01: 0; 2020-06-01: 0
EARLY WORKS | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Preliminary Studies & Planning | 0 |  |  |  |  | Construction Activity | 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0
Initial Concept Layouts & Surveys | 0 |  |  |  |  | Construction Activity | 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0
Commence Early Contractor Involvement (ECI) | 0 |  |  |  |  | Construction Activity
Early Contractor Involvement | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Initial Detailed Design | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Initial Civil & Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
High Voltage Design | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
Initial HV Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0
CONTRACT MANAGEMENT | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Contract Administration | 0 |  |  |  |  | Construction Activity
Tender Specification | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Technical Specification Preparation | 0 |  |  |  |  | Construction Activity | 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0
Specification Finalisation | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0
Procurement Review | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0
Tender Released to Market | 0 |  |  |  |  | Construction Activity
Tender and Site Visit | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0
Tender Period Closed | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Evaluation/ECI/Firm pricing | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0
Prepare and Issue Contract Award Documentation | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
EPC - Contract Award | 0 |  |  |  |  | Construction Activity
Delivery | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0
330KV SUBSTATION CONTRACT WORKS | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0
DESIGN | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Civil Design | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Civil Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Civil Package IFC | 0 |  |  |  |  | Construction Activity
Structural Design | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Equipment, Gantry and Minor Foundations | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0
Compounds and spill oil tank | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Miscellaneous | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Structural Package IFC | 0 |  |  |  |  | Construction Activity
High Voltage Design | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Structural Interface Document | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0
SLD IFC | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0
Layouts | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0
Bay Elevations | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
Conduits | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0
Earthing | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0
Building | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Miscellaneous | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0
HV Design Package Review | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0
HV Design Package Ammendment | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0
HV Design IFC | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0
CONSTRUCTION PROCUREMENT | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Procurement (LLE) | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Switchbay Equipment (1x220kV) | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Switchbay Equipment Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2021-03-01: 0; 2021-04-01: 0
Initial Switchbay Equipment Manufacture | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Switchbay Equipment Delivery | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0
Materials | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
HV Cables, Conductor and Fittings | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Steelwork | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Drainage materials | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Earthing Strap | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
DOCUMENTATION & SITE ESTABLISHMENT | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Project Documentation | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Prepare WHSMP | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Detailed Outage Plan | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Draft CEMP | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Review and Finalise WHSQMP | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0
Review and Finalise CEMP | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0
Pre-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0
Mobilisation | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Posession of Site (POS) | 0 |  |  |  |  | Construction Activity
Site Establishment | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0
Post-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0
Commencement of Site Works | 0 |  |  |  |  | Construction Activity
330kV SUBSTATION WORKS | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0
Civil Construction | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0
Earthworks, Bench and Drainage | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0
Security, Fencing and Lighting | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0
Trench and Conduit | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0
HV Equipment and Support Structure Footings | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0
Curing | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0
Civil Construction Completion | 0 |  |  |  |  | Construction Activity
Steelwork Construction | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0
HV Equipment Support Structures | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0
Electrical Construction | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0
Earthgrid | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0
Install Earthgrid | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0
Switchyard/HV Equipment Installation | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0
Installation of HV Equipment | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0; 2022-08-01: 0
Switchyard Cabling | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0; 2022-09-01: 0
HV Equipment Installation Complete | 0 |  |  |  |  | Construction Activity
Testing & Pre-Commissioning | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0
Testing & Commissioning (Switchbay) | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0
BBP & VT Balance | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0
Substation Ready for Commissioning | 0 |  |  |  |  | Construction Activity
Demobilisation | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0
Demobilise from Site | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0
TESTING & COMMISSIONING (TG) | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0
Red Cliffs Substation Testing & Commissioning | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0
PRACTICAL COMPLETION | 0 |  |  |  |  | Construction Activity
Practical Completion and Ready to Energise | 0 |  |  |  |  | Construction Activity
Darlington Point Substation | 5026666.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37941.77 | 37941.77 | 37941.77 | 37941.77 | 37941.77 | 37941.77 | 39080.03 | 39080.03 | 39080.03 | 39080.03 | 39080.03 | 51126.3 | 112254.88 | 112254.88 | 112254.88 | 112254.88 | 112254.88 | 112254.88 | 115397.45 | 115397.45 | 115397.45 | 504468.67 | 504468.67 | 565492.13 | 678294.88 | 595953.97 | 684089.77
Development | 5026666.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37941.77 | 37941.77 | 37941.77 | 37941.77 | 37941.77 | 37941.77 | 39080.03 | 39080.03 | 39080.03 | 39080.03 | 39080.03 | 51126.3 | 112254.88 | 112254.88 | 112254.88 | 112254.88 | 112254.88 | 112254.88 | 115397.45 | 115397.45 | 115397.45 | 504468.67 | 504468.67 | 565492.13 | 678294.88 | 595953.97 | 684089.77
PROJECT APPROVAL | 0 | [5 empty] | 2020-03-01: 0
Project Approval and PADs | 0 | [5 empty] | 2020-03-01: 0
Development of Handover Package | 0 | [5 empty] | 2020-03-01: 0
WD Handover Document Approved | 0 | [5 empty] | 2020-03-01: 0
Project Approval Document (PAD) Issued | 0 | [5 empty] | 2020-03-01: 0
Risk Contingency | 0 | [5 empty] | 2020-03-01: 0
Project Contingency (P50) | 0 | [5 empty] | 2020-03-01: 0
WORKS DELIVERY MANAGEMENT | 5026666.8 | [5 empty] | 2020-03-01: 0; 2020-04-01: 0; 2021-06-01: 37941.77; 2021-07-01: 37941.77; 2021-08-01: 37941.77; 2021-09-01: 37941.77; 2021-10-01: 37941.77; 2021-11-01: 37941.77; 2021-12-01: 39080.03; 2022-01-01: 39080.03; 2022-02-01: 39080.03; 2022-03-01: 39080.03; 2022-04-01: 39080.03; 2022-05-01: 51126.3; 2022-06-01: 112254.88; 2022-07-01: 112254.88; 2022-08-01: 112254.88; 2022-09-01: 112254.88; 2022-10-01: 112254.88; 2022-11-01: 112254.88; 2022-12-01: 115397.45; 2023-01-01: 115397.45; 2023-02-01: 115397.45; 2023-03-01: 504468.67; 2023-04-01: 504468.67; 2023-05-01: 565492.13; 2023-06-01: 678294.88; 2023-07-01: 595953.97; 2023-08-01: 684089.77
Project Management | 0 | [5 empty] | 2020-03-01: 0
Project Management | 0
Senior Project Manager | 0 | DP Sub | Senior Project Manager | Program Resource | Project Mgmt
Senior Project Manager - Overtime | 0 | DP Sub | Senior Project Manager - Overtime | Overtime | Project Mgmt
Sustenance Tier 2 Country Centre | 0 | DP Sub |  | Susso | N/A
Other Material | 0 | DP Sub |  | Other Material | N/A
Project Documentation/Plan and Program | 0 | [5 empty] | 2020-03-01: 0
Site Management | 5026666.8 | [5 empty] | 2020-03-01: 0; 2020-04-01: 0; 2021-06-01: 37941.77; 2021-07-01: 37941.77; 2021-08-01: 37941.77; 2021-09-01: 37941.77; 2021-10-01: 37941.77; 2021-11-01: 37941.77; 2021-12-01: 39080.03; 2022-01-01: 39080.03; 2022-02-01: 39080.03; 2022-03-01: 39080.03; 2022-04-01: 39080.03; 2022-05-01: 51126.3; 2022-06-01: 112254.88; 2022-07-01: 112254.88; 2022-08-01: 112254.88; 2022-09-01: 112254.88; 2022-10-01: 112254.88; 2022-11-01: 112254.88; 2022-12-01: 115397.45; 2023-01-01: 115397.45; 2023-02-01: 115397.45; 2023-03-01: 504468.67; 2023-04-01: 504468.67; 2023-05-01: 565492.13; 2023-06-01: 678294.88; 2023-07-01: 595953.97; 2023-08-01: 684089.77
Site Management | 2753418 | [5 empty] | 2021-06-01: 37941.77; 2021-07-01: 37941.77; 2021-08-01: 37941.77; 2021-09-01: 37941.77; 2021-10-01: 37941.77; 2021-11-01: 37941.77; 2021-12-01: 39080.03; 2022-01-01: 39080.03; 2022-02-01: 39080.03; 2022-03-01: 39080.03; 2022-04-01: 39080.03; 2022-05-01: 39080.03; 2022-06-01: 106967.47; 2022-07-01: 106967.47; 2022-08-01: 106967.47; 2022-09-01: 106967.47; 2022-10-01: 106967.47; 2022-11-01: 106967.47; 2022-12-01: 109965.49; 2023-01-01: 109965.49; 2023-02-01: 109965.49; 2023-03-01: 219930.98; 2023-04-01: 219930.98; 2023-05-01: 219930.98; 2023-06-01: 219930.98; 2023-07-01: 219930.98; 2023-08-01: 219930.98
Senior Site Manager Subs | 824802.92 | DP Sub | Senior Site Manager Subs | Program Resource | Site Mgmt |  | 2021-06-01: 24065.33; 2021-07-01: 24065.33; 2021-08-01: 24065.33; 2021-09-01: 24065.33; 2021-10-01: 24065.33; 2021-11-01: 24065.33; 2021-12-01: 24787.28; 2022-01-01: 24787.28; 2022-02-01: 24787.28; 2022-03-01: 24787.28; 2022-04-01: 24787.28; 2022-05-01: 24787.28; 2022-06-01: 24787.28; 2022-07-01: 24787.28; 2022-08-01: 24787.28; 2022-09-01: 24787.28; 2022-10-01: 24787.28; 2022-11-01: 24787.28; 2022-12-01: 25530.9; 2023-01-01: 25530.9; 2023-02-01: 25530.9; 2023-03-01: 51061.81; 2023-04-01: 51061.81; 2023-05-01: 51061.81; 2023-06-01: 51061.81; 2023-07-01: 51061.81; 2023-08-01: 51061.81
Senior Site Manager Subs - Overtime | 827914.14 | DP Sub | Senior Site Manager Subs - Overtime | Overtime | Site Mgmt |  | 2022-06-01: 38597.4; 2022-07-01: 38597.4; 2022-08-01: 38597.4; 2022-09-01: 38597.4; 2022-10-01: 38597.4; 2022-11-01: 38597.4; 2022-12-01: 39755.32; 2023-01-01: 39755.32; 2023-02-01: 39755.32; 2023-03-01: 79510.64; 2023-04-01: 79510.64; 2023-05-01: 79510.64; 2023-06-01: 79510.64; 2023-07-01: 79510.64; 2023-08-01: 79510.64
Sustenance Tier 2 Country Centre | 147703.5 | DP Sub |  | Susso | N/A |  | 2022-06-01: 7033.5; 2022-07-01: 7033.5; 2022-08-01: 7033.5; 2022-09-01: 7033.5; 2022-10-01: 7033.5; 2022-11-01: 7033.5; 2022-12-01: 7033.5; 2023-01-01: 7033.5; 2023-02-01: 7033.5; 2023-03-01: 14067; 2023-04-01: 14067; 2023-05-01: 14067; 2023-06-01: 14067; 2023-07-01: 14067; 2023-08-01: 14067
Construction Manager | 475594.47 | DP Sub | Construction Manager | Program Resource | Site Mgmt |  | 2021-06-01: 13876.45; 2021-07-01: 13876.45; 2021-08-01: 13876.45; 2021-09-01: 13876.45; 2021-10-01: 13876.45; 2021-11-01: 13876.45; 2021-12-01: 14292.74; 2022-01-01: 14292.74; 2022-02-01: 14292.74; 2022-03-01: 14292.74; 2022-04-01: 14292.74; 2022-05-01: 14292.74; 2022-06-01: 14292.74; 2022-07-01: 14292.74; 2022-08-01: 14292.74; 2022-09-01: 14292.74; 2022-10-01: 14292.74; 2022-11-01: 14292.74; 2022-12-01: 14721.52; 2023-01-01: 14721.52; 2023-02-01: 14721.52; 2023-03-01: 29443.05; 2023-04-01: 29443.05; 2023-05-01: 29443.05; 2023-06-01: 29443.05; 2023-07-01: 29443.05; 2023-08-01: 29443.05
Construction Manager - Overtime | 477402.97 | DP Sub | Construction Manager - Overtime | Overtime | Site Mgmt |  | 2022-06-01: 22256.55; 2022-07-01: 22256.55; 2022-08-01: 22256.55; 2022-09-01: 22256.55; 2022-10-01: 22256.55; 2022-11-01: 22256.55; 2022-12-01: 22924.24; 2023-01-01: 22924.24; 2023-02-01: 22924.24; 2023-03-01: 45848.49; 2023-04-01: 45848.49; 2023-05-01: 45848.49; 2023-06-01: 45848.49; 2023-07-01: 45848.49; 2023-08-01: 45848.49
Contract Administration | 0
Other TG Resources | 312837.21 | [5 empty] | 2023-05-01: 61023.46; 2023-06-01: 109453.26; 2023-07-01: 27112.34; 2023-08-01: 115248.15
Substations Fitter | 77487.67 | DP Sub | Substations Fitter | Program Resource | Tech Fitter |  | 2023-06-01: 48429.79; 2023-07-01: 9685.96; 2023-08-01: 19371.92
Substations Fitter - Overtime | 45245.65 | DP Sub | Substations Fitter - Overtime | Overtime | Tech Fitter |  | 2023-07-01: 15081.88; 2023-08-01: 30163.76
Sustenance Tier 2 Country Centre | 21100.5 | DP Sub |  | Susso | N/A |  | 2023-05-01: 4689; 2023-06-01: 4689; 2023-07-01: 2344.5; 2023-08-01: 9378
Telecommunications Technician | 66091.09 | DP Sub | Telecommunications Technician | Program Resource | Tech Mgmt |  | 2023-05-01: 22030.36; 2023-06-01: 22030.36; 2023-07-01: 0; 2023-08-01: 22030.36
Telecommunications Technician - Overtime | 102912.3 | DP Sub | Telecommunications Technician - Overtime | Overtime | Tech Mgmt |  | 2023-05-01: 34304.1; 2023-06-01: 34304.1; 2023-07-01: 0; 2023-08-01: 34304.1
Safety & Environment | 92658.38 | [5 empty] | 2022-05-01: 12046.27; 2022-06-01: 5287.41; 2022-07-01: 5287.41; 2022-08-01: 5287.41; 2022-09-01: 5287.41; 2022-10-01: 5287.41; 2022-11-01: 5287.41; 2022-12-01: 5431.96; 2023-01-01: 5431.96; 2023-02-01: 5431.96; 2023-03-01: 5431.96; 2023-04-01: 5431.96; 2023-05-01: 5431.96; 2023-06-01: 5431.96; 2023-07-01: 5431.96; 2023-08-01: 5431.96
Environmental Officer | 43714.75 | DP Sub | Environmental Officer | Program Resource | Support |  | 2022-05-01: 6150.08; 2022-06-01: 2460.03; 2022-07-01: 2460.03; 2022-08-01: 2460.03; 2022-09-01: 2460.03; 2022-10-01: 2460.03; 2022-11-01: 2460.03; 2022-12-01: 2533.83; 2023-01-01: 2533.83; 2023-02-01: 2533.83; 2023-03-01: 2533.83; 2023-04-01: 2533.83; 2023-05-01: 2533.83; 2023-06-01: 2533.83; 2023-07-01: 2533.83; 2023-08-01: 2533.83
Safety Officer | 41910.13 | DP Sub | Safety Officer | Program Resource | Support |  | 2022-05-01: 5896.19; 2022-06-01: 2358.48; 2022-07-01: 2358.48; 2022-08-01: 2358.48; 2022-09-01: 2358.48; 2022-10-01: 2358.48; 2022-11-01: 2358.48; 2022-12-01: 2429.23; 2023-01-01: 2429.23; 2023-02-01: 2429.23; 2023-03-01: 2429.23; 2023-04-01: 2429.23; 2023-05-01: 2429.23; 2023-06-01: 2429.23; 2023-07-01: 2429.23; 2023-08-01: 2429.23
Sustenance Tier 2 Country Centre | 7033.5 | DP Sub |  | Susso | N/A |  | 2022-06-01: 468.9; 2022-07-01: 468.9; 2022-08-01: 468.9; 2022-09-01: 468.9; 2022-10-01: 468.9; 2022-11-01: 468.9; 2022-12-01: 468.9; 2023-01-01: 468.9; 2023-02-01: 468.9; 2023-03-01: 468.9; 2023-04-01: 468.9; 2023-05-01: 468.9; 2023-06-01: 468.9; 2023-07-01: 468.9; 2023-08-01: 468.9
Protection & Control | 1867753.22 | [5 empty] | 2023-03-01: 279105.73; 2023-04-01: 279105.73; 2023-05-01: 279105.73; 2023-06-01: 343478.68; 2023-07-01: 343478.68; 2023-08-01: 343478.68
Control Technician | 330795.32 | DP Sub | Control Technician | Program Resource | Tech Mgmt |  | 2023-03-01: 55132.55; 2023-04-01: 55132.55; 2023-05-01: 55132.55; 2023-06-01: 55132.55; 2023-07-01: 55132.55; 2023-08-01: 55132.55
Control Technician - Overtime | 515095.57 | DP Sub | Control Technician - Overtime | Overtime | Tech Mgmt |  | 2023-03-01: 85849.26; 2023-04-01: 85849.26; 2023-05-01: 85849.26; 2023-06-01: 85849.26; 2023-07-01: 85849.26; 2023-08-01: 85849.26
Secondary Systems Technician | 350110.59 | DP Sub | Secondary Systems Technician | Program Resource | Tech Mgmt |  | 2023-03-01: 46681.41; 2023-04-01: 46681.41; 2023-05-01: 46681.41; 2023-06-01: 70022.12; 2023-07-01: 70022.12; 2023-08-01: 70022.12
Secondary Systems Technician - Overtime | 545148.74 | DP Sub | Secondary Systems Technician - Overtime | Overtime | Tech Mgmt |  | 2023-03-01: 72686.5; 2023-04-01: 72686.5; 2023-05-01: 72686.5; 2023-06-01: 109029.75; 2023-07-01: 109029.75; 2023-08-01: 109029.75
Sustenance Tier 2 Country Centre | 126603 | DP Sub |  | Susso | N/A |  | 2023-03-01: 18756; 2023-04-01: 18756; 2023-05-01: 18756; 2023-06-01: 23445; 2023-07-01: 23445; 2023-08-01: 23445
Outage Plan in THEOS for Handover | 0 | [5 empty] | 2020-03-01: 0
Commissioning plan & program | 0 | [5 empty] | 2020-03-01: 0; 2020-04-01: 0
EARLY WORKS | 0 |  |  |  |  | Construction Activity | 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Preliminary Studies & Planning | 0 |  |  |  |  | Construction Activity | 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0
Initial Concept Layouts & Surveys | 0 |  |  |  |  | Construction Activity | 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0
Commence Early Contractor Involvement (ECI) | 0 |  |  |  |  | Construction Activity
Early Contractor Involvement | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Initial Detailed Design | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Initial Civil & Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
High Voltage Design | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Initial HV Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Secondary System Design | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Initial Secondary System Designs | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
CONTRACT MANAGEMENT | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Contract Administration | 0 |  |  |  |  | Construction Activity
Tender Specification | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0
Technical Specification Preparation | 0 |  |  |  |  | Construction Activity | 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0
Specification Finalisation | 0 |  |  |  |  | Construction Activity | 2020-12-01: 0; 2021-01-01: 0
Procurement Review | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0
Tender Released to Market | 0 |  |  |  |  | Construction Activity
Tender and Site Visit | 0 |  |  |  |  | Construction Activity | 2021-01-01: 0; 2021-02-01: 0
Tender Period Closed | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0
Evaluation/ECI/Firm pricing | 0 |  |  |  |  | Construction Activity | 2021-04-01: 0; 2021-05-01: 0
Prepare and Issue Contract Award Documentation | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
EPC - Contract Award | 0 |  |  |  |  | Construction Activity
Delivery | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
330KV SUBSTATION CONTRACT WORKS | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
DESIGN | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Civil Design | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Civil Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Civil Package IFC | 0 |  |  |  |  | Construction Activity
Structural Design | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Equipment, Gantry and Minor Foundations | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Compounds and spill oil tank | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Miscellaneous | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0
Structural Package IFC | 0 |  |  |  |  | Construction Activity
High Voltage Design | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0
Structural Interface Document | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
SLD IFC | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Layouts | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0
Bay Elevations | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0
Conduits | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0
Earthing | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0
Building | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0
Miscellaneous | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0
HV Design Package Review | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
HV Design Package Ammendment | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
HV Design IFC | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0
Secondary Design | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Protection Design | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Protection Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Protection Design Package IFC | 0 |  |  |  |  | Construction Activity
Automation Database | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Automation Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Automation Design Package IFC | 0 |  |  |  |  | Construction Activity
Communication Design | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Communication Design | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0
Prot Panel Layouts, schematics and label schedules | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0
Cables Schedules & connection diagrams | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0
CONSTRUCTION PROCUREMENT | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Procurement (LLE) | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Synchronous Condensers (2x 100MVAr) | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Synchronous Condensers Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
Initial Sync Cond Manufacture | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Finalise Synchronous Condensers Procurement | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Synchronous Cond Delivery to Site | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0
Capacitor Banks (2x 330kV 50MVAr ) | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Capacitor Bank Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
Initial Capacitor Bank Manufacture | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Finalise Capacitor Bank Procurement | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Capacitor Bank delivery to site | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0
Shunt Reactors (2x 330kV 100MVAr) | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Reactor Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0
Initial Shunt Reactor Manufacture | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Finalise Reactor Procurement | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Reactors delivery to site | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0
SSB | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Finalise SSB Procurement | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
SSB Manufacture & Deliver | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
SSB Manufacturer Design and Approval | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
SSB Manufacture | 0 |  |  |  |  | Construction Activity | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
SSB Fitout, FAT & Delievered | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Materials | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
HV Cables, Conductor and Fittings | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Secondary System Equipment | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Steelwork | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
Drainage materials | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0
Earthing Strap | 0 |  |  |  |  | Construction Activity | 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0
LV Cables | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0
DOCUMENTATION & SITE ESTABLISHMENT | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Project Documentation | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Prepare WHSMP | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Detailed Outage Plan | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Draft CEMP | 0 |  |  |  |  | Construction Activity | 2021-06-01: 0; 2021-07-01: 0
Review and Finalise WHSQMP | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0
Review and Finalise CEMP | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0
Pre-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0
Mobilisation | 0 |  |  |  |  | Construction Activity | 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Posession of Site (POS) | 0 |  |  |  |  | Construction Activity
Site Establishment | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0
Post-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0
Commencement of Site Works | 0 |  |  |  |  | Construction Activity
330kV SUBSTATION WORKS | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
Civil Construction | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Earthworks, Bench and Drainage | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0
Security, Fencing and Lighting | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0
Trench and Conduit | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0; 2022-11-01: 0
HV Equipment & Support Structure Footings | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Initial HV Equipment and Support Structure Footings | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0
Initial Equipment Footing Curing | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0
HV Equipment & Support Structure Footings | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0
Equipment Footing Curing | 0 |  |  |  |  | Construction Activity | 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
330kV 100MVAr Synchronous Condenser Foundation | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Synchronous Condenser 1 Foundation | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0
Synchronous Condenser 2 Foundation | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
330kV 60MVAr Shunt Reactor Bunds | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Reactor Bund 1 | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0
Reactor Bund 2 | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
330kV 50MVAr Capacitor Bank Foundations | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0
Capacitor Bank 1 Foundation | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0
Capacitor Bank 2 Foundation | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0
Secondary Systems Building | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0
Building Foundations | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0
Site Earthworks | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0
Piling | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0
Formwork | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0
Tube in Electrical Conduits | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0
Pour Concrete | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0; 2022-11-01: 0
SSB Foundations Curing | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0
Miscellaneous Yard Foundations | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0
Excavate Foundations | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0; 2022-11-01: 0
Curing | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0
Civil Construction Completion | 0 |  |  |  |  | Construction Activity
Steelwork Construction | 0 |  |  |  |  | Construction Activity | 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Initial HV Equpment Support Structures | 0 |  |  |  |  | Construction Activity | 2023-01-01: 0
HV Equipment Support Structures | 0 |  |  |  |  | Construction Activity | 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Electrical Construction | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
Earthgrid | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0
Install Earthgrid | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0
Switchyard Works | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Miscellaneous Equipment | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Switchyard Cabling | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Finalise Switchyard Cabling | 0 |  |  |  |  | Construction Activity | 2023-03-01: 0; 2023-04-01: 0
HV Equipment Installation | 0 |  |  |  |  | Construction Activity | 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Initial Installation of HV Equipment | 0 |  |  |  |  | Construction Activity | 2023-01-01: 0; 2023-02-01: 0
Installation of HV Equipment | 0 |  |  |  |  | Construction Activity | 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Install 132kV Connection Bus | 0 |  |  |  |  | Construction Activity | 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Secondary System | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
SSB Installation works | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0
Terminate SSB Cabling | 0 |  |  |  |  | Construction Activity | 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Synchronous Condensers (2x 100MVAr) | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0
Installation of Synchronous Condensor (No. 1) | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0
Installation of Synchronous Condensor (No. 2) | 0 |  |  |  |  | Construction Activity | 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0
330kV 60MVAr Shunt Reactor Bunds | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-04-01: 0; 2023-05-01: 0
Installation of Reactor No. 1 | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0
Installation of Reactor No. 2 | 0 |  |  |  |  | Construction Activity | 2023-04-01: 0; 2023-05-01: 0
330kV 50MVAr Capacitor Bank Foundations | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
Installation of Capacitor Bank No. 1 | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0
Installation of Capacitor Bank No. 2 | 0 |  |  |  |  | Construction Activity | 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0
HV Equipment Installation Complete | 0 |  |  |  |  | Construction Activity
Testing & Pre-Commissioning | 0 |  |  |  |  | Construction Activity | 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
Testing & Commissioning (All Assets) | 0 |  |  |  |  | Construction Activity | 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0
BBP & VT Testing | 0 |  |  |  |  | Construction Activity | 2023-07-01: 0; 2023-08-01: 0
Substation Ready for Commissioning | 0 |  |  |  |  | Construction Activity
Demobilisation | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
Demobilise from Site | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
TESTING & COMMISSIONING (TG) | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
Energise & Inservice Checks | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
PRACTICAL COMPLETION | 0 |  |  |  |  | Construction Activity
Practical Completion and Ready to Energise | 0 |  |  |  |  | Construction Activity
Wagga Substation | 812977.01 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12407.66 | 75407.18 | 75407.18 | 75407.18 | 75407.18 | 90663.05 | 123836.98 | 284440.59
Development | 812977.01 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12407.66 | 75407.18 | 75407.18 | 75407.18 | 75407.18 | 90663.05 | 123836.98 | 284440.59
PROJECT APPROVAL | 0 | [5 empty] | 2021-02-01: 0
Project Approval and PADs | 0 | [5 empty] | 2021-02-01: 0
Development of Handover Package | 0 | [5 empty] | 2021-02-01: 0
WD Handover Document Approved | 0 | [5 empty] | 2021-02-01: 0
Project Approval Document (PAD) Issued | 0 | [5 empty] | 2021-02-01: 0
Risk Contingency | 0 | [5 empty] | 2021-02-01: 0
Project Contingency (P50) | 0 | [5 empty] | 2021-02-01: 0
WORKS DELIVERY MANAGEMENT | 812977.01 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12407.66 | 75407.18 | 75407.18 | 75407.18 | 75407.18 | 90663.05 | 123836.98 | 284440.59
Project Management | 0 | [5 empty] | 2021-02-01: 0
Project Management | 0
Senior Project Manager | 0 | Wagga Sub | Senior Project Manager | Program Resource | Project Mgmt
Senior Project Manager - Overtime | 0 | Wagga Sub | Senior Project Manager - Overtime | Overtime | Project Mgmt
Sustenance Tier 2 Country Centre | 0 | Wagga Sub |  | Susso | N/A
Other Material | 0 | Wagga Sub |  | Other Material | N/A
Project Documentation/Plan and Program | 0 | [5 empty] | 2021-02-01: 0
Site Management | 812977.01 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12407.66 | 75407.18 | 75407.18 | 75407.18 | 75407.18 | 90663.05 | 123836.98 | 284440.59
Site Management | 489826.55 | [5 empty] | 2023-02-01: 69975.22; 2023-03-01: 69975.22; 2023-04-01: 69975.22; 2023-05-01: 69975.22; 2023-06-01: 69975.22; 2023-07-01: 69975.22; 2023-08-01: 69975.22
Senior Site Manager Subs | 178716.32 | Wagga Sub | Senior Site Manager Subs | Program Resource | Site Mgmt |  | 2023-02-01: 25530.9; 2023-03-01: 25530.9; 2023-04-01: 25530.9; 2023-05-01: 25530.9; 2023-06-01: 25530.9; 2023-07-01: 25530.9; 2023-08-01: 25530.9
Senior Site Manager Subs - Overtime | 278287.23 | Wagga Sub | Senior Site Manager Subs - Overtime | Overtime | Site Mgmt |  | 2023-02-01: 39755.32; 2023-03-01: 39755.32; 2023-04-01: 39755.32; 2023-05-01: 39755.32; 2023-06-01: 39755.32; 2023-07-01: 39755.32; 2023-08-01: 39755.32
Sustenance Tier 2 Country Centre | 32823 | Wagga Sub |  | Susso | N/A |  | 2023-02-01: 4689; 2023-03-01: 4689; 2023-04-01: 4689; 2023-05-01: 4689; 2023-06-01: 4689; 2023-07-01: 4689; 2023-08-01: 4689
Contract Administration | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other TG Resources | 133166.21 | [5 empty] | 2023-06-01: 15255.87; 2023-07-01: 48429.79; 2023-08-01: 69480.55
Substations Fitter | 67801.71 | Wagga Sub | Substations Fitter | Program Resource | Tech Fitter |  | 2023-07-01: 48429.79; 2023-08-01: 19371.92
Substations Fitter - Overtime | 30163.76 | Wagga Sub | Substations Fitter - Overtime | Overtime | Tech Fitter |  | 2023-08-01: 30163.76
Sustenance Tier 2 Country Centre | 7033.5 | Wagga Sub |  | Susso | N/A |  | 2023-06-01: 1172.25; 2023-07-01: 0; 2023-08-01: 5861.25
Telecommunications Technician | 11015.18 | Wagga Sub | Telecommunications Technician | Program Resource | Tech Mgmt |  | 2023-06-01: 5507.59; 2023-07-01: 0; 2023-08-01: 5507.59
Telecommunications Technician - Overtime | 17152.05 | Wagga Sub | Telecommunications Technician - Overtime | Overtime | Tech Mgmt |  | 2023-06-01: 8576.03; 2023-07-01: 0; 2023-08-01: 8576.03
Safety & Environment | 50431.39 | [5 empty] | 2023-01-01: 12407.66; 2023-02-01: 5431.96; 2023-03-01: 5431.96; 2023-04-01: 5431.96; 2023-05-01: 5431.96; 2023-06-01: 5431.96; 2023-07-01: 5431.96; 2023-08-01: 5431.96
Environmental Officer | 24071.4 | Wagga Sub | Environmental Officer | Program Resource | Support |  | 2023-01-01: 6334.58; 2023-02-01: 2533.83; 2023-03-01: 2533.83; 2023-04-01: 2533.83; 2023-05-01: 2533.83; 2023-06-01: 2533.83; 2023-07-01: 2533.83; 2023-08-01: 2533.83
Safety Officer | 23077.69 | Wagga Sub | Safety Officer | Program Resource | Support |  | 2023-01-01: 6073.08; 2023-02-01: 2429.23; 2023-03-01: 2429.23; 2023-04-01: 2429.23; 2023-05-01: 2429.23; 2023-06-01: 2429.23; 2023-07-01: 2429.23; 2023-08-01: 2429.23
Sustenance Tier 2 Country Centre | 3282.3 | Wagga Sub |  | Susso | N/A |  | 2023-02-01: 468.9; 2023-03-01: 468.9; 2023-04-01: 468.9; 2023-05-01: 468.9; 2023-06-01: 468.9; 2023-07-01: 468.9; 2023-08-01: 468.9
Protection & Control | 139552.86 | [5 empty] | 2023-08-01: 139552.86
Control Technician | 27566.28 | Wagga Sub | Control Technician | Program Resource | Tech Mgmt |  | 2023-08-01: 27566.28
Control Technician - Overtime | 42924.63 | Wagga Sub | Control Technician - Overtime | Overtime | Tech Mgmt |  | 2023-08-01: 42924.63
Secondary Systems Technician | 23340.71 | Wagga Sub | Secondary Systems Technician | Program Resource | Tech Mgmt |  | 2023-08-01: 23340.71
Secondary Systems Technician - Overtime | 36343.25 | Wagga Sub | Secondary Systems Technician - Overtime | Overtime | Tech Mgmt |  | 2023-08-01: 36343.25
Sustenance Tier 2 Country Centre | 9378 | Wagga Sub |  | Susso | N/A |  | 2023-08-01: 9378
Outage Plan in THEOS for Handover | 0 | [5 empty] | 2021-02-01: 0
Commissioning plan & program | 0 | [5 empty] | 2021-02-01: 0; 2021-03-01: 0
EARLY WORKS | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Preliminary Studies & Planning | 0 |  |  |  |  | Construction Activity | 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0
Initial Concept Layouts & Surveys | 0 |  |  |  |  | Construction Activity | 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0
Commence Early Contractor Involvement (ECI) | 0 |  |  |  |  | Construction Activity
Early Contractor Involvement | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Initial Detailed Design | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Initial Civil & Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
High Voltage Design | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
Initial HV Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0
CONTRACT MANAGEMENT | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Contract Administration | 0 |  |  |  |  | Construction Activity
Tender Specification | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0
Technical Specification Preparation | 0 |  |  |  |  | Construction Activity | 2021-09-01: 0; 2021-10-01: 0
Specification Finalisation | 0 |  |  |  |  | Construction Activity | 2021-10-01: 0; 2021-11-01: 0
Procurement Review | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Tender Released to Market | 0 |  |  |  |  | Construction Activity
Tender and Site Visit | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0
Tender Period Closed | 0 |  |  |  |  | Construction Activity | 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0
Evaluation/ECI/Firm pricing | 0 |  |  |  |  | Construction Activity | 2022-02-01: 0; 2022-03-01: 0
Prepare and Issue Contract Award Documentation | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0
EPC - Contract Award | 0 |  |  |  |  | Construction Activity
Delivery | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
330KV SUBSTATION CONTRACT WORKS | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
DESIGN | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0
Civil & Structural Design | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0
Civil Design | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0
Civil Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0
Civil Package IFC | 0 |  |  |  |  | Construction Activity
Structural Design | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0
Structural Detailed Design Development | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0
Equipment, Gantry and Minor Foundations | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0
Compounds and spill Oil Tank | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0; 2022-11-01: 0
Miscellaneous | 0 |  |  |  |  | Construction Activity | 2022-11-01: 0
Structural Package IFC | 0 |  |  |  |  | Construction Activity
High Voltage Design | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0
Structural Interface Document | 0 |  |  |  |  | Construction Activity | 2022-03-01: 0; 2022-04-01: 0
SLD IFC | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Layouts | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0
Bay Elevations | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0
Conduits | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0
Earthing | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0
Building | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0
Miscellaneous | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0
HV Design Package Review | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0; 2022-08-01: 0
HV Design Package Ammendment | 0 |  |  |  |  | Construction Activity | 2022-08-01: 0; 2022-09-01: 0
HV Design IFC | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0
CONSTRUCTION PROCUREMENT | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0
Procurement (LLE) | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0
Switchbay Equipment (1x330kV) | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0
Switchbay Equipment Supplier Procurement | 0 |  |  |  |  | Construction Activity | 2022-09-01: 0; 2022-10-01: 0
Switchbay Equipment Manufacture | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0
Switchbay Equipment Delivery | 0 |  |  |  |  | Construction Activity | 2023-01-01: 0; 2023-02-01: 0
Materials | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0
HV Cables, Conductor and Fittings | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0
Steelwork | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0
Drainage materials | 0 |  |  |  |  | Construction Activity | 2022-10-01: 0; 2022-11-01: 0
Earthing Strap | 0 |  |  |  |  | Construction Activity | 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0
DOCUMENTATION & SITE ESTABLISHMENT | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0
Project Documentation | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0
Prepare WHSMP | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0
Detailed Outage Plan | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0
Draft CEMP | 0 |  |  |  |  | Construction Activity | 2022-04-01: 0; 2022-05-01: 0
Review and Finalise WHSQMP | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0
Review and Finalise CEMP | 0 |  |  |  |  | Construction Activity | 2022-05-01: 0; 2022-06-01: 0
Pre-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0
Mobilisation | 0 |  |  |  |  | Construction Activity | 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0
Posession of Site (POS) | 0 |  |  |  |  | Construction Activity
Site Establishment | 0 |  |  |  |  | Construction Activity | 2023-01-01: 0; 2023-02-01: 0
Post-POS HSE Audit | 0 |  |  |  |  | Construction Activity | 2023-02-01: 0
Commencement of Site Works | 0 |  |  |  |  | Construction Activity
330kV SUBSTATION WORKS | 0 |  |  |  |  | Construction Activity | 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
Civil Construction | 0 |  |  |  |  | Construction Activity | 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0
Earthworks, Bench and Drainage | 0 |  |  |  |  | Construction Activity | 2023-02-01: 0
Security, Fencing and Lighting | 0 |  |  |  |  | Construction Activity | 2023-02-01: 0
Trench and Conduit | 0 |  |  |  |  | Construction Activity | 2023-02-01: 0; 2023-03-01: 0
HV Equipment & Support Structure Footings | 0 |  |  |  |  | Construction Activity | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0
HV Equipment and Support Structure Footings | 0 |  |  |  |  | Construction Activity | 2023-03-01: 0
Curing | 0 |  |  |  |  | Construction Activity | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0
Civil Construction Completion | 0 |  |  |  |  | Construction Activity
Steelwork Construction | 0 |  |  |  |  | Construction Activity | 2023-05-01: 0
HV Equipment Support Structures | 0 |  |  |  |  | Construction Activity | 2023-05-01: 0
Electrical Construction | 0 |  |  |  |  | Construction Activity | 2023-03-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
Earthgrid | 0 |  |  |  |  | Construction Activity | 2023-03-01: 0
Install Earthgrid | 0 |  |  |  |  | Construction Activity | 2023-03-01: 0
Switchyard Works | 0 |  |  |  |  | Construction Activity | 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
Installation Miscellaneous Equipment | 0 |  |  |  |  | Construction Activity | 2023-05-01: 0; 2023-06-01: 0
Switchyard Cabling | 0 |  |  |  |  | Construction Activity | 2023-05-01: 0; 2023-06-01: 0
Finalise Switchyard Cabling | 0 |  |  |  |  | Construction Activity | 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0
HV Equipment Installation | 0 |  |  |  |  | Construction Activity | 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0
Installation of HV Equipment | 0 |  |  |  |  | Construction Activity | 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0
HV Equipment Installation Complete | 0 |  |  |  |  | Construction Activity
Testing & Pre-Commissioning | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
Testing & Commissioning | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
BBP & VT Balance | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
Substation Ready for Commissioning | 0 |  |  |  |  | Construction Activity
Demobilisation | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
Demobilise from Site | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
TESTING & COMMISSIONING (TG) | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
Energise & Inservice Checks | 0 |  |  |  |  | Construction Activity | 2023-08-01: 0
PRACTICAL COMPLETION | 0 |  |  |  |  | Construction Activity
Practical Completion and Ready to Energise | 0 |  |  |  |  | Construction Activity

## s5. Project Development
|  |  |  | Current / Nominal values (2018/9) | [6 empty] | Restatement to 2017-18 LABOUR rates | [6 empty] | Restatement to 2017/8 $ | [6 empty] | Rounded ($M)
s5. Project Development | Nominal / Current Rates | Labour adjusted | Restated estimates | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-24) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-24) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-24) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-4) | TOTAL
Labour / People costs
PEC Project Management Team
Project Management team | 18836781.8562 | 18685225.601 | 18456560.2528 | 0 | 5778592.9458 | 5297367.7684 | 5349697.7684 | 16425658.4827 | 2411123.3735 | 18836781.8562 | 0 | 5732099.7649 | 5254746.4105 | 5306655.3758 | 16293501.5512 | 2391724.0498 | 18685225.601 | 0 | 5661951.6908 | 5190440.0733 | 5241713.7891 | 16094105.5532 | 2362454.6995 | 18456560.2528 | 0 | 5.662 | 5.1904 | 5.2417 | 16.0941 | 2.3625 | 18.4566
PEC Project Management Team | 18836781.8562 | 18685225.601 | 18456560.2528 | 0 | 5778592.9458 | 5297367.7684 | 5349697.7684 | 16425658.4827 | 2411123.3735 | 18836781.8562 | 0 | 5732099.7649 | 5254746.4105 | 5306655.3758 | 16293501.5512 | 2391724.0498 | 18685225.601 | 0 | 5661951.6908 | 5190440.0733 | 5241713.7891 | 16094105.5532 | 2362454.6995 | 18456560.2528 | 0 | 5.662 | 5.1904 | 5.2417 | 16.0941 | 2.3625 | 18.4566
Major Projects Team
Major Projects team | 3634750 | 3605505.6682 | 3561382.3471 | 0 | 975176.8293 | 1063829.2683 | 1063829.2683 | 3102835.3659 | 531914.6341 | 3634750 | 0 | 967330.789 | 1055269.9517 | 1055269.9517 | 3077870.6924 | 527634.9758 | 3605505.6682 | 0 | 955492.8248 | 1042355.8089 | 1042355.8089 | 3040204.4426 | 521177.9045 | 3561382.3471 | 0 | 0.95549 | 1.0424 | 1.0424 | 3.0402 | 0.52118 | 3.5614
Major Projects Team | 3634750 | 3605505.6682 | 3561382.3471 | 0 | 975176.8293 | 1063829.2683 | 1063829.2683 | 3102835.3659 | 531914.6341 | 3634750 | 0 | 967330.789 | 1055269.9517 | 1055269.9517 | 3077870.6924 | 527634.9758 | 3605505.6682 | 0 | 955492.8248 | 1042355.8089 | 1042355.8089 | 3040204.4426 | 521177.9045 | 3561382.3471 | 0 | 0.95549 | 1.0424 | 1.0424 | 3.0402 | 0.52118 | 3.5614
Other incremental resources required for PEC
Other incremental resources required for PEC | 6787656.25 | 6733044.3863 | 6650646.99 | 0 | 1821078.5061 | 1986631.0976 | 1986631.0976 | 5794340.7012 | 993315.5488 | 6787656.25 | 0 | 1806426.5427 | 1970647.1375 | 1970647.1375 | 5747720.8176 | 985323.5687 | 6733044.3863 | 0 | 1784319.9241 | 1946530.8263 | 1946530.8263 | 5677381.5768 | 973265.4132 | 6650646.99 | 0 | 1.7843 | 1.9465 | 1.9465 | 5.6774 | 0.97327 | 6.6506
Subtotal - Other incremental resources | 6787656.25 | 6733044.3863 | 6650646.99 | 0 | 1821078.5061 | 1986631.0976 | 1986631.0976 | 5794340.7012 | 993315.5488 | 6787656.25 | 0 | 1806426.5427 | 1970647.1375 | 1970647.1375 | 5747720.8176 | 985323.5687 | 6733044.3863 | 0 | 1784319.9241 | 1946530.8263 | 1946530.8263 | 5677381.5768 | 973265.4132 | 6650646.99 | 0 | 1.7843 | 1.9465 | 1.9465 | 5.6774 | 0.97327 | 6.6506
Total Labour costs | 29259188.1062 | 29023775.6556 | 28668589.5899 | 0 | 8574848.2812 | 8347828.1343 | 8400158.1343 | 25322834.5498 | 3936353.5564 | 29259188.1062 | 0 | 8505857.0966 | 8280663.4997 | 8332572.465 | 25119093.0612 | 3904682.5944 | 29023775.6556 | 0 | 8401764.4398 | 8179326.7086 | 8230600.4243 | 24811691.5727 | 3856898.0172 | 28668589.5899 | 0 | 8.4018 | 8.1793 | 8.2306 | 24.8117 | 3.8569 | 28.6686
Labour Related costs
Recruitment | 607275.7622 | 602389.7663 | 595017.8635 | 0 | 607275.7622 | 0 | 0 | 607275.7622 | 0 | 607275.7622 | 0 | 602389.7663 | 0 | 0 | 602389.7663 | 0 | 602389.7663 | 0 | 595017.8635 | 0 | 0 | 595017.8635 | 0 | 595017.8635 | 0 | 0.59502 | 0 | 0 | 0.59502 | 0 | 0.59502
Training | 114724.8476 | 114724.8476 | 113320.8722 | 0 | 50841.4634 | 48963.4146 | 13205.0305 | 113009.9085 | 1714.939 | 114724.8476 | 0 | 50841.4634 | 48963.4146 | 13205.0305 | 113009.9085 | 1714.939 | 114724.8476 | 0 | 50219.2777 | 48364.212 | 13043.4305 | 111626.9201 | 1693.952 | 113320.8722 | 0 | 0.050219 | 0.048364 | 0.013043 | 0.11163 | 0.001694 | 0.11332
Office Lease costs | 1311356.7073 | 1311356.7073 | 1295308.6357 | 0 | 396722.561 | 342987.8049 | 342987.8049 | 1082698.1707 | 228658.5366 | 1311356.7073 | 0 | 396722.561 | 342987.8049 | 342987.8049 | 1082698.1707 | 228658.5366 | 1311356.7073 | 0 | 391867.5646 | 338790.4017 | 338790.4017 | 1069448.3679 | 225860.2678 | 1295308.6357 | 0 | 0.39187 | 0.33879 | 0.33879 | 1.0694 | 0.22586 | 1.2953
Travel & Expenses | 3558757.4 | 3558757.4 | 3515206.1731 | 0 | 910379.8 | 993141.6 | 993141.6 | 2896663 | 662094.4 | 3558757.4 | 0 | 910379.8 | 993141.6 | 993141.6 | 2896663 | 662094.4 | 3558757.4 | 0 | 899238.7885 | 980987.7692 | 980987.7692 | 2861214.3269 | 653991.8462 | 3515206.1731 | 0 | 0.89924 | 0.98099 | 0.98099 | 2.8612 | 0.65399 | 3.5152
Labour Related costs | 5592114.7171 | 5587228.7211 | 5518853.5445 | 0 | 1965219.5866 | 1385092.8195 | 1349334.4354 | 4699646.8415 | 892467.8756 | 5592114.7171 | 0 | 1960333.5907 | 1385092.8195 | 1349334.4354 | 4694760.8455 | 892467.8756 | 5587228.7211 | 0 | 1936343.4943 | 1368142.3829 | 1332821.6014 | 4637307.4785 | 881546.0659 | 5518853.5445 | 0 | 1.9363 | 1.3681 | 1.3328 | 4.6373 | 0.88155 | 5.5189
Non-Labour costs
Geo Technical Studies | 635150 | 635150 | 625191.2021 | 0 | 635150 | 0 | 0 | 635150 | 0 | 635150 | 0 | 635150 | 0 | 0 | 635150 | 0 | 635150 | 0 | 625191.2021 | 0 | 0 | 625191.2021 | 0 | 625191.2021 | 0 | 0.62519 | 0 | 0 | 0.62519 | 0 | 0.62519
Legal Costs | 4650000 | 4650000 | 4577090.5923 | 0 | 1770000 | 1380000 | 900000 | 4050000 | 600000 | 4650000 | 0 | 1770000 | 1380000 | 900000 | 4050000 | 600000 | 4650000 | 0 | 1742247.3868 | 1358362.3693 | 885888.5017 | 3986498.2578 | 590592.3345 | 4577090.5923 | 0 | 1.7422 | 1.3584 | 0.88589 | 3.9865 | 0.59059 | 4.5771
Consultant costs | 1230454.4 | 1230454.4 | 1211161.561 | 0 | 1230454.4 | 0 | 0 | 1230454.4 | 0 | 1230454.4 | 0 | 1230454.4 | 0 | 0 | 1230454.4 | 0 | 1230454.4 | 0 | 1211161.561 | 0 | 0 | 1211161.561 | 0 | 1211161.561 | 0 | 1.2112 | 0 | 0 | 1.2112 | 0 | 1.2112
Non-Labour costs | 6515604.4 | 6515604.4 | 6413443.3554 | 0 | 3635604.4 | 1380000 | 900000 | 5915604.4 | 600000 | 6515604.4 | 0 | 3635604.4 | 1380000 | 900000 | 5915604.4 | 600000 | 6515604.4 | 0 | 3578600.1498 | 1358362.3693 | 885888.5017 | 5822851.0209 | 590592.3345 | 6413443.3554 | 0 | 3.5786 | 1.3584 | 0.88589 | 5.8229 | 0.59059 | 6.4134
TOTAL PROJECT DEVELOPMENT | 41366907.2233 | 41126608.7767 | 40600886.4898 | 0 | 14175672.2678 | 11112920.9538 | 10649492.5697 | 35938085.7913 | 5428821.4321 | 41366907.2233 | 0 | 14101795.0872 | 11045756.3192 | 10581906.9003 | 35729458.3068 | 5397150.47 | 41126608.7767 | 0 | 13916708.0839 | 10905831.4608 | 10449310.5274 | 35271850.0722 | 5329036.4176 | 40600886.4898 | 0 | 13.9167 | 10.9058 | 10.4493 | 35.2719 | 5.329 | 40.6009

## PD-Labour(&related)
CONFIDENTIAL
[Content removed from public version]

## PD-NonLabour
CONFIDENTIAL
#REF!
[Content removed from public version]

## s6 Land & Environment
|  |  |  | Current / Nominal values (2018/9) | [6 empty] | Restatement to 2017-18 LABOUR rates | [6 empty] | Restatement to 2017/8 $
s6.1 Land and Environment | Nominal / Current Rates | Labour adjusted | Restated estimates | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-24) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-24) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-24) | TOTAL
Category
Labour | 5370392.6368 | 5327183.7382 | 5261990.9302 | 0 | 2173152.2733 | 1501480.8435 | 1197006.72 | 4871639.8368 | 498752.8 | 5370392.6368 | 0 | 2155667.6083 | 1489400.2867 | 1187375.8894 | 4832443.7843 | 494739.9539 | 5327183.7382 | 0 | 2129287.0606 | 1471173.3601 | 1172845.0655 | 4773305.4863 | 488685.444 | 5261990.9302
Labour related
Recruitment | 95592.5376 | 94823.4228 | 93662.9963 | 0 | 95592.5376 | 0 | 0 | 95592.5376 | 0 | 95592.5376 | 0 | 94823.4228 | 0 | 0 | 94823.4228 | 0 | 94823.4228 | 0 | 93662.9963 | 0 | 0 | 93662.9963 | 0 | 93662.9963
Training | 26125 | 26125 | 25805.2885 | 0 | 15125 | 11000 | 0 | 26125 | 0 | 26125 | 0 | 15125 | 11000 | 0 | 26125 | 0 | 26125 | 0 | 14939.9038 | 10865.3846 | 0 | 25805.2885 | 0 | 25805.2885
Travel | 451428 | 451428 | 445903.5315 | 0 | 248285.4 | 203142.6 | 0 | 451428 | 0 | 451428 | 0 | 248285.4 | 203142.6 | 0 | 451428 | 0 | 451428 | 0 | 245246.9423 | 200656.5892 | 0 | 445903.5315 | 0 | 445903.5315
Labour related | 573145.5376 | 572376.4228 | 565371.8163 | 0 | 359002.9376 | 214142.6 | 0 | 573145.5376 | 0 | 573145.5376 | 0 | 358233.8228 | 214142.6 | 0 | 572376.4228 | 0 | 572376.4228 | 0 | 353849.8425 | 211521.9738 | 0 | 565371.8163 | 0 | 565371.8163
Non-Labour
EIS | 6480604.2 | 6480604.2 | 6378991.939 | 0 | 4581428.2 | 1899176 | 0 | 6480604.2 | 0 | 6480604.2 | 0 | 4581428.2 | 1899176 | 0 | 6480604.2 | 0 | 6480604.2 | 0 | 4509593.9599 | 1869397.9791 | 0 | 6378991.939 | 0 | 6378991.939
Property Consulting Fees | 3268470 | 3268470 | 3217222.2125 | 0 | 2151082 | 1117388 | 0 | 3268470 | 0 | 3268470 | 0 | 2151082 | 1117388 | 0 | 3268470 | 0 | 3268470 | 0 | 2117354.2334 | 1099867.9791 | 0 | 3217222.2125 | 0 | 3217222.2125
Surveys, Legal and Misc Fees | 3000000 | 3000000 | 2952961.6725 | 0 | 1910200 | 1089800 | 0 | 3000000 | 0 | 3000000 | 0 | 1910200 | 1089800 | 0 | 3000000 | 0 | 3000000 | 0 | 1880249.1289 | 1072712.5436 | 0 | 2952961.6725 | 0 | 2952961.6725
Non-Labour | 12749074.2 | 12749074.2 | 12549175.824 | 0 | 8642710.2 | 4106364 | 0 | 12749074.2 | 0 | 12749074.2 | 0 | 8642710.2 | 4106364 | 0 | 12749074.2 | 0 | 12749074.2 | 0 | 8507197.3223 | 4041978.5017 | 0 | 12549175.824 | 0 | 12549175.824
Total | 18692612.3744 | 18648634.3611 | 18376538.5705 | 0 | 11174865.4109 | 5821987.4435 | 1197006.72 | 18193859.5744 | 498752.8 | 18692612.3744 | 0 | 11156611.6311 | 5809906.8867 | 1187375.8894 | 18153894.4072 | 494739.9539 | 18648634.3611 | 0 | 10990334.2254 | 5724673.8356 | 1172845.0655 | 17887853.1266 | 488685.444 | 18376538.5705

## L&E-Labour(&related)
CONFIDENTIAL
[Content removed from public version]

## L&E-NonLabour
CONFIDENTIAL
[Content removed from public version]

## s7 Stakeholder & Comm Egmt
|  |  |  | Current / Nominal values (2018/9) | [6 empty] | Restatement to 2017-18 LABOUR rates | [6 empty] | Restatement to 2017/8 $
s7 Stakeholder & Community Engagement | Current Rates | Labour adjusted | Restated estimates | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-24) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-24) | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Subtotal | Post Commissioning costs (2023-24) | TOTAL
Labour costs
Labour costs - Major Projects | 0 | 412507.7992 | 407459.6268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113439.6448 | 123752.3397 | 123752.3397 | 360944.3243 | 51563.4749 | 412507.7992 | 0 | 112051.3974 | 122237.888 | 122237.888 | 356527.1734 | 50932.4533 | 407459.6268
Labour costs - Stakeholder & Communications Project Team | 2511465.992 | 2491259.3355 | 2460771.8961 | 0 | 877396.2736 | 698467.7952 | 569121.9072 | 2144985.976 | 366480.016 | 2511465.992 | 0 | 870336.9524 | 692848.0899 | 564542.888 | 2127727.9303 | 363531.4052 | 2491259.3355 | 0 | 859685.9757 | 684369.1797 | 557634.1464 | 2101689.3018 | 359082.5943 | 2460771.8961
Labour | 2511465.992 | 2903767.1346 | 2868231.5229 | 0 | 877396.2736 | 698467.7952 | 569121.9072 | 2144985.976 | 366480.016 | 2511465.992 | 0 | 983776.5972 | 816600.4296 | 688295.2278 | 2488672.2546 | 415094.8801 | 2903767.1346 | 0 | 971737.3731 | 806607.0677 | 679872.0344 | 2458216.4752 | 410015.0476 | 2868231.5229
Labour Related costs
Travel | 616951.6 | 616951.6 | 609401.493 | 0 | 165523.6 | 180571.2 | 180571.2 | 526666 | 90285.6 | 616951.6 | 0 | 165523.6 | 180571.2 | 180571.2 | 526666 | 90285.6 | 616951.6 | 0 | 163497.9615 | 178361.4126 | 178361.4126 | 520220.7867 | 89180.7063 | 609401.493
Labour Related costs | 616951.6 | 616951.6 | 609401.493 | 0 | 165523.6 | 180571.2 | 180571.2 | 526666 | 90285.6 | 616951.6 | 0 | 165523.6 | 180571.2 | 180571.2 | 526666 | 90285.6 | 616951.6 | 0 | 163497.9615 | 178361.4126 | 178361.4126 | 520220.7867 | 89180.7063 | 609401.493
Non-Labour
Community improvement | 300000 | 300000 | 295296.1672 | 0 | 100000 | 100000 | 100000 | 300000 | 0 | 300000 | 0 | 100000 | 100000 | 100000 | 300000 | 0 | 300000 | 0 | 98432.0557 | 98432.0557 | 98432.0557 | 295296.1672 | 0 | 295296.1672
Community Engagement - External support | 3103750 | 3103750 | 3055084.9303 | 0 | 2427458 | 676292 | 0 | 3103750 | 0 | 3103750 | 0 | 2427458 | 676292 | 0 | 3103750 | 0 | 3103750 | 0 | 2389396.8118 | 665688.1185 | 0 | 3055084.9303 | 0 | 3055084.9303
Design / Communications costs | 1375000 | 1375000 | 1353440.7666 | 0 | 275000 | 450000 | 600000 | 1325000 | 50000 | 1375000 | 0 | 275000 | 450000 | 600000 | 1325000 | 50000 | 1375000 | 0 | 270688.1533 | 442944.2509 | 590592.3345 | 1304224.7387 | 49216.0279 | 1353440.7666
Non-Labour | 4778750 | 4778750 | 4703821.8641 | 0 | 2802458 | 1226292 | 700000 | 4728750 | 50000 | 4778750 | 0 | 2802458 | 1226292 | 700000 | 4728750 | 50000 | 4778750 | 0 | 2758517.0209 | 1207064.4251 | 689024.3902 | 4654605.8362 | 49216.0279 | 4703821.8641
Total | 7907167.592 | 8299468.7346 | 8181454.88 | 0 | 3845377.8736 | 2105330.9952 | 1449693.1072 | 7400401.976 | 506765.616 | 7907167.592 | 0 | 3951758.1972 | 2223463.6296 | 1568866.4278 | 7744088.2546 | 555380.4801 | 8299468.7346 | 0 | 3893752.3555 | 2192032.9054 | 1547257.8373 | 7633043.0982 | 548411.7818 | 8181454.88

## SHC-Labour(&related)
CONFIDENTIAL
[Content removed from public version]

## SHC-NonLabour
CONFIDENTIAL
[Content removed from public version]

## s8 Insurance
Cost estimate by month>
[16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | Current / Nominal values (2018/9) | [5 empty] | Restatement to 2017/8 rates
s8 Insurance | Cost Type | Description | Supplier | Assumption / evidence source | Assumption provided by | Total - One off (FY20) | Total Cost to be phased | Recurring? | Start Month | End Month | Duration (Months) | Allocate across Major Projects? | PEC allocation - one off | PEC allocation - Annual cost | Monthly equivalent | [51 empty] | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | TOTAL | time axis 2020-04-01 to 2024-06-01
Insurance | Insurance | Insurance required during construction phase | [Removed] | [Removed] | Head of Risk - TransGrid |  | 8727006 | y | 6 | 39 | 34 | n | 0 |  | 256676.6471 |  |  |  |  | 0 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2566766.4706 | 3080119.7647 | 3080119.7647 | 0 | 8727006 | 0 | 2526521.0033 | 3031825.2039 | 3031825.2039 | 0 | 8590171.4111
[13 empty] | 0 | 0 | 256676.6471 | 0 | 0 | 0 | 0 | 0 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 256676.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2566766.4706 | 3080119.7647 | 3080119.7647 | 0 | 8727006 | 0 | 2526521.0033 | 3031825.2039 | 3031825.2039 | 0 | 8590171.4111

## s9 BidderPmts
Cost estimate by month>
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
s9 Bidder Payments | Cost Type | Report Reference | Description | Supplier | Assumption / evidence source | Assumption provided by | [51 empty] | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | TOTAL | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | TOTAL | time axis 2020-04-01 to 2024-06-01
Bidder - Data | Bidder Payments |  | Data | [Removed] |  | Project Director |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bidder - Data | Bidder Payments |  | Bidder Expenses | [Removed] |  | Project Director |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bidder Payment 1 | Bidder Payments |  | Bidder Payment 1 |  |  | Project Director |  |  |  |  | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000 | 0 | 492160.2787 | 0 | 0 | 0 | 492160.2787
Bidder Payment 2 | Bidder Payments |  | Bidder Payment 2 |  |  | Project Director |  |  |  |  | 0 |  | 0 | 0 | 8000000 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 0 | 12000000 | 0 | 11811846.6899 | 0 | 0 | 0 | 11811846.6899
[7 empty] | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 8000000 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500000 | 0 | 0 | 0 | 12500000 | 0 | 12304006.9686 | 0 | 0 | 0 | 12304006.9686
SUBTOTAL | Bidder Payments | [5 empty] | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 8000000 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500000 | 0 | 0 | 0 | 12500000 | 0 | 12304006.9686 | 0 | 0 | 0 | 12304006.9686
[7 empty] | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 8000000 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500000 | 0 | 0 | 0 | 12500000 | 0 | 12304006.9686 | 0 | 0 | 0 | 12304006.9686